Cycle 2
ASEAN ECONOMIC REFORM PROGRAMME EVALUATION REPORT
Cover image designed by Evening Tao/ Freepik

June 2020
Version History
D08_04	ASEAN Economic Reform Cycle 2 Programme Evaluation Report
Revision	Written By	Checked By	Approved By
Revision 1	Neil Pogorelsky	Valerie McDonnell-Lenoach
Revision 2	Neil Pogorelsky	Dulce Pedroso	Rachel Linn

Table of Acronyms
Abbreviation
AER	ASEAN Economic Reform
ASEAN	Association of Southeast Asian Nations
BEIS	Department for Business, Energy & Industrial Strategy
CoST	Construction Sector Transparency Initiative
CSO	Civil society organisation
DIT	Department for International Trade
EL	Evaluation and Learning
ER	Economic reform (pillar)
EQ	Evaluation question
Fair Biz	Promoting a Fair Business Environment in ASEAN
FCO	Foreign and Commonwealth Office
Fintech	Financial services technology
FSIP	Financial Services and Intellectual Property
G&I	Gender and inclusion
GAC	Global Anti-Corruption
GESI	Gender and Social Inclusion
GIACC	National Centre for Governance, Integrity and Anti-Corruption (Malaysia)
IF	Islamic Finance
INCEIF	International Centre for Education in Islamic Finance
IO	Intermediate outcome
IP	Intellectual Property
IPO	Intellectual Property Office
IPOPHL	Philippines Intellectual Property Office
JFU	Joint Funds Unit
KII	Key informant interview
MSME	Micro-, small- and medium-sized enterprise
MREL	Monitoring, reporting, evaluation and learning
ODA	Official Development Assistance
OECD	Organisation for Economic Co-operation and Development
PEQ	Programme evaluation question
PF or ‘Fund’	Prosperity Fund
PF-6	Indonesia, the Philippines, Malaysia, Myanmar, Thailand and Vietnam
PDFU	Prosperity Fund Delivery Unit
PM	Programme Manager
PMT	Programme management team
PwC	PricewaterhouseCoopers
QPR	Quarterly progress reporting
RAG	Red-amber-green
RD	Regulatory Delivery
SB	Secondary benefit
SDG	UN Sustainable Development Goals
SRO	Senior Responsible Owner
ToC	Theory of Change
TORs	Terms of reference
UNDP	United Nations Development Programme
VfM	Value for money

Contents

ANNEXES

TABLES
Table 1: Evaluation sample	v
Table 2: Cycle 2 sampling plan	2
Table 3: Programme structure, delivery approach, budget and expenditure through May 2020	8
Table 4: Prosperity Fund programme overlaps	10
Table 5 : Data quality assessment measurement criteria	15
Table 6: Cycle 2 evaluation data-quality assessment scores	16
Table 7: Data Triangulation by programme evaluation question	17
Table 8: Summary of ASEAN Economic Reform Programme Cycle 2 gender and inclusion scorecard findings	27
Table 9: Summary of the ASEAN Economic Reform Programme value for money scorecard for Cycle 2	32
Table 10: ASEAN Economic Reform Programme Cycle 2 key findings	37
Table 11: ASEAN Economic Reform Programme Cycle 2 evaluation recommendations	39
Table 12: Lessons	40
Table 13: ASEAN Economic Reform Programme gender and inclusion scorecard (Cycle 2)	41
Table 14: Gender and inclusion-related progress made and results achieved during the past year	50
Table 15: Gender and inclusion-related lessons	53
Table 16: Gender and inclusion recommendations	55
Table 17: ASEAN Economic Reform Programme value for money scorecard (Cycle 2)	57
Table 18: ASEAN Economic Reform Programme evaluation themes for Cycle 2	69
Table 19: Evaluation matrix for Cycle 2	70
Table 20: Sampling plan for Cycle 2	75
Table 21: Assessment of preliminary stakeholder inventory	76
Table 22: Preliminary assessment of sufficiency of likely evidence by programme evaluation question	79
Table 23: Draft Cycle 2 workplan	81
Table 24: Cycle 2 evaluation delivery milestones	82
Table 25: Programme Evaluation and Learning team members	86
Table 26: Cycle 2 ASEAN Economic Reform Programme provisional evaluation budget	88
Table 27: Risks and mitigation measures	89
Table 28: Evaluation Options Analysis	91
Table 29: Programme evaluation questions mapped to report sections	99

FIGURES
Figure 1: ASEAN Economic Reform Programme Theory of Change	7
Figure 2: ASEAN Economic Reform Programme budget allocation and spend (GBP million) by pillar to May 2020. Source: Prospero	9
Figure 3: ASEAN Economic Reform Programme management structure	9
Figure 4: Progress on delivery of outputs and some intermediate outcomes	23
Figure 5: Learning through the evaluation process	83

BOXES
Box 1: Cycle 2 programme evaluation questions	12
Box 2: Summary of Cycle 2 evaluation findings	19
Box 3: The Prosperity Fund’s secondary benefits	25
# Executive summary
Brief overview / The Association of Southeast Asian Nations Economic Reform Programme supports inclusive economic growth and helps reduce poverty while creating opportunities for UK businesses in Southeast Asia. / Intended results cover intellectual property, reform of regulations, competition policy, anti-corruption measures and financial services. / The programme is on track and is generating results, but there is an increased risk that some higher-level results may not be achieved during the life of the programme. / The programme has surpassed its anti-corruption and government transparency targets. / The programme’s approach to secondary benefits has improved. / The programme has increased its focus on gender and inclusions to ensure that it is integral to the programme design. It should now concentrate on delivering results. / Value for money is good and improving, partly through added support in the programme management team. / Governance structures are sound, and the steering board has become more effective. / Delays because of COVID-19 are likely to continue for the next six months. Revised workplans take this into account.

What does the Prosperity Fund aim to achieve through the ASEAN Economic Reform Programme and how?
The programme promotes inclusive economic growth and poverty reduction. It does this by helping to create a fairer business environment and develop financial markets across Southeast Asia. It seeks to embed UK expertise, standards and regulations, and to create opportunities for businesses in the region, including UK business.
The programme operates in Indonesia, Malaysia, Myanmar, the Philippines, Thailand and Vietnam. It runs from 2018 to 2022 and will spend GBP 19 million.
The three pillars of the programme are:
- Business environment
- Transparency
- Financial markets.
What did the evaluation look at?
The evaluation was completed in June 2020 and covers activities between June 2019 and May 2020. It focused on:
- How is the programme progressing?
- How does the programme use learning?
- How does the programme demonstrate value, gender and social inclusion and sustainability?
The evaluation looked at activities in Malaysia, the Philippines and Thailand and followed up on the recommendations of the last evaluation and the Annual Review in the other countries (see Table 1). The evaluation also identified relevant lessons for the Prosperity Fund more broadly.
Table 1: Evaluation sample
Sampled countries			Follow-up countries		Light-touch country
Philippines	Malaysia	Thailand	Vietnam	Myanmar	Indonesia
Business environment	Transparency / Finance	Transparency	Review of learning and changes to design and context in countries covered by last evaluation.		Review of implementation and changes in context.

The evaluation and learning team reviewed over 100 documents and interviewed 46 stakeholders (26 women and 20 men). Because of the COVID-19 pandemic, there were no interviews with government counterparts due to the programme team’s concern that the evaluation would distract partners during a time of crisis. This approach was approved by the Joint Funds Unit. The evaluation team worked with the programme team using scorecards to assess value for money and gender and inclusion.
What did the evaluation find?
Progress: All programme strands are under way. Previous concerns regarding the delivery of the Financial Services and Intellectual Property component of the programme have been resolved. This component is now also more relevant to the needs of each country.
However, delays because of COVID-19 are likely to continue for at least the next six months. Revised workplans take this into account.
Performance: The programme is meeting milestones and producing results across all three pillars, but there is an increased risk of some higher-level results not being achieved. For example, the Islamic finance activities support the overall aim of the Prosperity Fund to protect poor people from financial shocks. However, they are not creating new opportunities for poor people to access financial products or services. The programme should assess new proposals against their ability to help address inclusive finance goals.
The approach to secondary benefits has improved. There are Secondary Benefits Advisers in five of the six countries. The Prosperity Fund’s approach to generating commercial opportunities, including for UK firms, is now better understood. The programme’s secondary benefits include the UK’s ability to influence regulation and policy development.
Results achieved: Results cover intellectual property, regulatory reform, competition policy, anti-corruption measures and financial services. Examples include:
- A manual to help enforce intellectual property rights and recommendations for national regulations in the Philippines, Indonesia and Myanmar (intellectual property).
- Training in how to reform regulation and adopt the UK’s approach to reform in Vietnam (regulatory reform).
- Reports on competition policy in the Philippines, Thailand and Brunei (competition policy).
- Surpassing targets for initiatives for responsible business, disclosure of procurement data and measures to decrease corrupt practices and follow international standards (anti-corruption and transparency).
- Paper on the regulation of financial technology, reports on tackling money laundering and on Islamic finance, and a financial innovation learning visit (financial services).
Further results under the Financial Services and Intellectual Property component of the programme may be possible. However, new proposals should be assessed against their contribution to financial inclusion. They should also be scrutinised for how they help promote partner country goals, access to finance by women and minorities and value for money.
Design: The programme design remains sound but could be communicated better. The assumptions and risks, and the way the programme expects change to happen should be clearer and more detailed.
Improved monitoring would show whether knowledge and skills are improving and whether they are put into practice. The programme delivers a lot of training. Whether this has been successful depends on knowing whether participants are using the training to work more effectively. Counting how many people have participated will not demonstrate success.
Gender and inclusion: The programme has improved its approach to gender and inclusion and should now concentrate on delivering results and meeting more than minimum standards. The current focus is mostly on whether men and women are equally involved in project activities. Beyond this, there is variation in how much different parts of the programme pay attention to understanding and overcoming social and political obstacles faced by women and other marginalised groups. The anti-corruption and government transparency work shows the most ambition in this area and is beginning to show promising results.
Primary purpose and secondary benefits: The programme supports policy changes which will contribute to both primary purpose and secondary benefits. The reforms help enterprises, including those headed by women, to access markets. They will also reduce barriers to capital markets, both promoting inclusive growth and improving access to markets for UK and international firms.
Value for money: Value for money is good and improving, partly through increased capacity in the programme management team. When the programme was being designed and contracted the focus was on cost. This has now shifted towards efficiency, effectiveness and equity. Financial management has also improved with additional staff capable of enacting effective oversight of spend and supplier performance.
Governance and management: Management structures work and the steering board has become more effective. The board has been focusing on both efficiency and results.
The approach to deliver the programme brings some complexities. The programme has five implementers, including international organisations, other UK government departments and commercial partners. The Foreign and Commonwealth Office also delivers some components. This brings challenges, particularly for commercial providers who have to cover a range of themes in a single project. It remains to be seen whether this approach is more effective than focusing on fewer areas with fewer partners.
The programme has responded to the recommendations of the previous Annual Review and evaluation on staffing, contract management and the results framework. Further work is necessary to finalise indicators that track implementers’ progress.
Learning: The programme has expanded its approach to learning over the past year. Quarterly reporting includes lessons learned; responses to recommendations from the Southeast Asia Prosperity Fund forum and to the Annual Review and evaluation; and reflections on training. Learning is on the steering board’s agenda, which highlights the overall commitment to learning. The programme’s quarterly reports include lessons on programme management and technical delivery. The PFLearning platform is used more – Foreign and Commonwealth Office staff say the platform helps share knowledge. However, last year’s evaluation was not widely disseminated, as the JFU publication policy was not in place at the time.
Monitoring varies in quality and may not produce evidence of change. Some implementers have not yet finished revising their progress indicators as recommended by the Annual Review. The programme should also keep observing whether change is actually happening.
What are the lessons from the ASEAN Economic Reform Programme for the Prosperity Fund as a whole?
- It is challenging to integrate gender equality and inclusion into programme strands unless this is done meaningfully from the outset. This entails consulting people who are able to provide insights on gender and inclusion related barriers and opportunities in specific sectors or issues.
- It is important to assess the individual projects underneath the regional programme. Annual evaluations can supplement but not replace the need to monitor the effectiveness of activities. To ensure accountability and transparency, a management response to all evaluation recommendations, publication of the findings and monitoring of implementation of any resulting actions are crucial.
# Introduction
This report documents the findings of the Cycle 2 evaluation of the Association of Southeast Asian Nations (ASEAN) Economic Reform (AER) Programme, based on work conducted between 15 April and 1 June 2020 by the Prosperity Fund (PF) Evaluation and Learning (EL) service. While the programme EL team is independent of the Foreign Commonwealth Office (FCO) and the PF, the findings have been validated with the programme management team (PMT) with whom the associated recommendations have been co-created.[1] The PF EL approach includes an annual cycle of evaluations at the programme and Fund levels. The Cycle 1 evaluation was formative, assessing the design of the programme and anticipating its potential effects. The current evaluation is process-based, examining how it is being implemented and progress against outcome expectations. The Cycle 3 evaluation will be summative, assessing what has been achieved.
[1] Validation and co-creation of recommendations occurred, first, through a facilitated sense-making workshop (29 May) and, subsequently, through an iterative review and comments on drafts of this report by the PMT.
## Report structure
The body of this report presents the key findings of the evaluation, drawing on both a programme-wide records review and interviews, and also on four case studies undertaken this cycle.[2] This report presents the findings on design, progress to date, governance and management, primary purpose, secondary benefits, gender and inclusion, value for money, sustainability and learning, rather than by themes or evaluation questions, reflecting changes to the structure of all evaluation reports requested by the Joint Funds Unit (JFU) in April 2020. Annex 6 maps this report’s sub-headings against the evaluation questions.
[2] See Section 3 for a more comprehensive discussion of the approach.
## Purpose and scope of the evaluation
This cycle’s evaluation focused on two themes of particular interest to the AER Programme: progress toward results and application of learning. The PMT hopes to use the results of the evaluation to “inform the ongoing oversight and management of the programme”. The findings will also “help to prioritise and manage any new budget capacity realised in Year 2”.[3] The evaluation addresses 15 programme evaluation questions (PEQs). These are described in Box 1. As described in the Cycle 2 Approach Paper in Annex 3, this evaluation is process-based, examining how the programme is implementing, what that means in terms of the likelihood of achieving results and where the programme should focus its efforts in addressing any performance risks.
[3] EL, “ASEAN Economic Reform Programme Cycle 2 Approach Paper,” Programme Manager’s statement for cycle 2, 2020.
The evaluation sampled data broadly across the programme to meet two needs: the needs of the programme and the need to look at the performance of the PF as a whole. The evaluation assessed overall AER Programme performance, with more in-depth analysis of the performance of targeted strands in Malaysia, the Philippines and Thailand (Table 2). The evaluation also followed up on actions following the Cycle 1 evaluation and Annual Review recommendations. This approach allowed the evaluation to explore all of the programme’s technical areas and consider constraints posed by the local context. It also meant the evaluation could contribute to the Fund evaluation and to PF thematic and sector (Financial Services and Ease of Doing Business) evaluations.

Table 2: Cycle 2 sampling plan
SAMPLED			FOLLOW-UP		LIGHT-TOUCH
Philippines	Malaysia	Thailand	Vietnam	Myanmar	Indonesia
ER 1:[4] Strengthening the business environment	ER 2: Improving business and government transparency, anti-corruption / ER 3: Broadening and deepening financial markets	ER 2: Improving business and government transparency, anti-corruption	Follow-up on learning, design adjustment and context change in Cycle 1 sample countries		Update on implementation and changes in context
[4] The AER Programme consists of three pillars: Economic Reform (ER) 1 on strengthening the business environment, ER 2 on advancing business and government transparency and compliance and ER 3 on broadening and deepening financial markets.

The evaluation was originally intended to lead directly into the second programme Annual Review, with planned joint sampling and a strong link between the two efforts to help guide the programme into the second half of implementation. Due to knock-on effects of the COVID-19 crisis, however, the Annual Review has been delayed and no new official date had been set at the time of writing. However, this evaluation will feed into the Annual Review, as originally planned, once the new date is set. [5] The evaluation will be followed by a cooperative dissemination planning effort between the PMT and EL, and potentially a launch event.[6] This will be followed by a joint after-action review in preparation for revising the evaluation approach for Cycle 3 in 2021. The case studies (see Table 2) on ER 1 in the Philippines, ER 2 in Malaysia, ER 2 in Thailand and ER 3 in Malaysia will be developed as learning products for programme use as learning tools.
[5] The evaluation will support the Annual Review by providing an evidence base. EL team members will also be available to Annual Review team to provide direct information. The PMT have indicated that they expect to include an EL team member on the Annual Review team.
[6] No timing, contents or participation in an event has yet been discussed – this will be a topic of the dissemination planning effort.
## Audience and stakeholders
The audience for this report includes the PMT, the AER Programme steering board, the JFU and other PF programmes that may want to learn from the AER Programme’s experience as one of the earlier starting PF programmes. The general public may also find this report of interest, including recipient governments, researchers and development workers and taxpayers. The AER Programme’s delivery partners have also expressed interest in the evaluation findings. The EL team, including thematic, sector and Fund-level EL teams are also key audiences and users of this and all programme-level evaluations. These audiences are also stakeholders in the programme.
The evaluation engaged continuously with the PMT from the evaluation design process through to the development of findings and recommendations. The PMT has also been engaged in reviewing and commenting on this report. This engagement included four workshops: an evaluation design workshop, a kick-off workshop, a value for money (VfM) assessment workshop and a sense-making workshop. All AER Programme Managers (PMs), the Singapore-based PMT members, several steering board members and the Senior Responsible Owner (SRO) were also interviewed as a part of the evaluation fieldwork. The EL team also engaged with the JFU via comment and approval on the approach and through monthly meetings with the FCO Monitoring, Reporting, Evaluation and Learning (MREL) Lead for the AER Programme. The EL team did not engage with recipient governments, beyond the review of secondary sources, at the direction of the programme team and in agreement with the JFU.[7] Data was collected by reviewing more than 110 documents and conducting 47 interviews (26 women and 20 men) representing the steering board, the PMT, all PMs, all delivery partners, delivery partner national teams in sampled countries and some private sector and civil society organisations (CSOs).
[7] As discussed in Section 3, this was a decision taken in response to the COVID-19 crisis and the need of the recipient governments to focus on crisis response, as well as the unavailability of the AER PMs to facilitate government introductions.

# Context update
The Cycle 1 evaluation described the programme context. The context and design of the programme are covered in the AER business case.[8] Additional contextual detail specific to Malaysia, the Philippines and Thailand can be found in the case study annexes. Since the Cycle 1 evaluation (July 2019), several key changes in context have occurred, which are impacting the course of the AER Programme. The foremost of these is, of course, the COVID-19 global pandemic. While the majority of the six AER partner countries, the ‘PF-6’,[9] have had relative success battling the pandemic, the crisis and required response have significantly impacted the programme. Due to travel restrictions, a refocusing of resources and less attention by both the FCO and the partner governments, and an inability to re-design some aspects of the planned work, the programme is likely facing three to six months’ delay. Some delivery partners indicate that they have or will request no-cost or low-cost extensions. The long-term implications of the COVID-19 crisis are still unclear, but are likely to exacerbate poverty, making programmes focused on poverty alleviation even more relevant. The Programme team reports that government counterparts are expressing continued commitment to and interest in the AER Programme as a result.[10]
[8] FCO, “ASEAN Economic Reform Programme (renamed from Southeast Asia Economic Reform Programme) Business Case,” 2018.
[9] Indonesia, Malaysia, Myanmar, the Philippines, Thailand and Vietnam.
[10] KIIs.
There also has been an election in one PF-6 country and a change of government in another in the past year. The first, the election in Thailand, caused a minor shift in focus, as the existing government was re-elected in a contentious and divisive contest, but ultimately the AER Programme in Thailand stayed on track. The second, a change in the ruling coalition in Malaysia, was more significant, as a new government was installed and AER champions and other stakeholders in the previous government left office. As is common, the new government is still finding its feet and it is not yet clear if priorities will shift away from the planned areas of AER work. [11]
[11] Two significant political events affected Malaysian society with varying effects on the programme. The first was the historic general election in 2018 that toppled the previous government of 61 years and led to a new ruling government. Then, in February 2020, the Malaysian government led by the multi-ethnic Pakatan Harapan, the Alliance of Hope, collapsed. The new coalition government called Perikatan Nasional, the National Alliance, was formed following the resignation of Prime Minister Mahathir Mohamad due to policy differences in the previous Pakatan Harapan coalition. The current political situation is likely to lead to possible changes in certain key national priorities.
Further, presidential elections are planned in the Philippines for May 2022. The current administration, led by Rodrigo Duterte, has a strong parliamentary position and broad public support. However, Duterte is ineligible for re-election under the Philippines single six-year term for presidents. Local media have reported that manoeuvring for the 2022 elections has already started[12] and the 2022 election could negatively impact the government’s appetite for, and ability to, progress reforms during 2021.[13]
[12] See, for example, https://www.manilatimes.net/2020/03/05/opinion/columnists/the-maneuvering-for-the-2022-elections-has-begun/700318/.
[13] KIIs.
There is also a planned general election in Myanmar, expected in November 2020. After the election, the FCO expects a change of ministers and other senior government officials, which may occur up to 2021.
A significant diplomatic issue emerged in the Philippines when the Duterte administration issued a temporary suspension of bilateral cooperation activities with countries that signed the resolution of the UN Human Rights Council on 11 July 2019. The Office of the President issued an order barring government ministries from working with the UK. While this caused some temporary delay in the AER Programme, it was able to proceed with programme delivery through multilateral organisations. Those implemented by other delivery partners were re-organised, in close coordination with Post, and with sound stakeholder and risk management. [14] This issue was largely resolved by March 2020, at which point the exigencies of the COVID-19 crisis removed all remaining barriers to cooperation.[15]
[14] FCO Philippines developed a structured risk management plan, with senior-level lobbying carried out by FCO across PF programmes, and especially AER, that was discussed and reviewed weekly to assess viability of deliverables and overall engagement as a tool for continued delivery. There have been no substantial unresolved delays within the fiscal year.
[15] See Asian development Bank (2020). Economic Indicators for the Philippines, for a post-COVID-19 outlook.
Lastly, the UK exit from the European Union has not so much changed the context of work in Southeast Asia, as hastened developments that were already underway and emphasised the strategic importance of strengthening ties with the region. The UK has appointed an ambassador specifically to ASEAN, which has supported the regional goals of the AER Programme.[16] The UK sees ASEAN as a strategic partner in strengthening trade ties with the region,[17] and the PF programmes active in the region, including AER, are pursuing secondary benefits within this context.
[16] KIIs
[17] See https://thediplomat.com/2020/01/what-does-the-uks-new-asean-mission-say-about-its-southeast-asia-engagement-post-brexit/
## ASEAN Economic Reform Programme design review
As described in the Cycle 1 Evaluation Report, the AER Programme is a GBP 19 million programme promoting inclusive economic growth in Southeast Asia (and designed to increase global prosperity, including for the UK). Its goal, aligned with the PF’s primary purpose, is to lift people out of poverty on a sustainable basis by stimulating growth and creating jobs. It targets three outcomes:
- Strengthened (and harmonised) business environment frameworks for domestic and foreign firms, including UK Companies (programme outcome 1)
- Improved business practices adopted and corruption risk minimised to create a fairer business environment in ASEAN (programme outcome 2)
- More inclusive, efficient and diversified financial markets to create new financing opportunities for businesses and individuals (programme outcome 3).
These feed into two intermediate outcomes (IOs) in the PF’s Theory of Change (ToC) (see Figure 1):
- Trade; Financial and Economic Reform: PF countries have better financial and economic systems, which support business growth (IO4)
- Ease of Doing Business: PF countries are on paper and in practice easier places to do business. Positive experiences of investors and other private sector actors become well known (IO5).
The programme has three primary pillars of investment, with three strands under the first pillar and five components under the third. The three pillars are:
ER 1 – Strengthening business environment, with the following strands:
- ER 1.1 – Intellectual property (IP) enforcement
- ER 1.2 – Strengthening regulatory frameworks and processes
- ER 1.3 – Competition policy
- ER 2 – Advancing business and government transparency and compliance
- ER 3 – Broadening and deepening financial markets, with the following components:
- Capital markets development
- Financial services technology (fintech)
- Islamic finance (IF)
- Anti-money laundering
- Accounting standards.
The Financial Services and Intellectual Property (FSIP) Programme is the commercially procured portion of the AER Programme. It includes part of ER 1.1 and all of ER 3.
The AER Programme ToC has not been altered since the Cycle 1 evaluation, though the logframe is being revised in response to Annual Review and Cycle 1 evaluation recommendations.[18] These revisions focus on the indicators of change and not the underlying theory or links between ToC elements.
[18] See discussion of utilisation of the cycle 1 evaluation in Section 4.4.1
Figure 1 presents the programme ToC. Table 3 describes the delivery approach, budget and spend through May 2020 for each of the programme pillars. Table 3 describes the budget and spend to date by pillar.
Figure 1: ASEAN Economic Reform Programme Theory of Change[19]
[19] AER Revised Theory of Change, Draft, January 2019. Under the current ToC all activities support all three outcomes.

Table 3: Programme structure, delivery approach, budget and expenditure through May 2020
AER DELIVERY APPROACH
Strand/Component	Delivery Partner	Budget (GBP)	Expenditure to May 2020 (GBP)
ER 1.1 IP enforcement	PriceWaterhouseCoopers (PwC)/ Intellectual Property Office (IPO)	IPO: GBP 750,000 / PwC: included with ER 3, below	IPO: GBP 350,772[20] / PwC: included with ER 3, below
ER 1.2 Regulatory reform	Regulatory Delivery (RD)/ Department for Business, Energy & Industrial Strategy (BEIS)	GBP 800,000	GBP 428,458[21]
ER 1.3 Competition	Organisation for Economic Co-operation and Development (OECD)	GBP 2,400,000	GBP 1,995,881
ER 2 Anti-corruption and government transparency	United Nations Development Programme (UNDP)	GBP 5,302,000	GBP 4,295,957
ER 3 Financial services – Capital markets	PwC	GBP 7,897,857, inclusive of PwC portion of ER 1.1[22]	GBP 2,724,116, inclusive of PwC portion of ER 1.1
ER 3 Financial services – Fintech	PwC
ER 3 Financial services – Accounting standards	PwC
ER 3 Financial services – Anti-money laundering	PwC
ER 3 Financial services – Islamic finance	PwC
[20] Total doesn’t give the best representation of IP in-house and RD/BEIS as the total allocation includes attaché salaries and platform charges, which have fluctuated. Programme allocation of spend is (costs) GBP 390,000 and (to date) GBP 173,393.
[21] Programme allocation of spend is (costs) GBP 667,865 and (to date) GBP 328,295.
[22] A financial breakdown according to the Financial services and Intellectual Property Programme is not available on Prospero or in the programme quarterly reporting.

Source: Prospero
Figure 2: ASEAN Economic Reform Programme budget allocation and spend (GBP million) by pillar to May 2020. Source: Prospero
## Governance
The governance structures in place are both comprehensive and fairly effective. The budget for the AER Programme is held by the FCO and delegated to the British High Commission in Singapore, along with the responsibility for compliance with the International Development Act. The programme is governed by a steering board headed by the SRO, who is the High Commissioner in Singapore, and composed of the ambassadors for each PF-6 mission along with a senior representative from the FCO, the Department for International Trade (DIT), the JFU and the Prosperity Fund Delivery Unit (PFDU). The board meets every three months.[23]
[23] AER Programme Business Case, KIIs.
Figure 3 illustrates the AER Programme management structure.
Figure 3: ASEAN Economic Reform Programme management structure

The PMT is led from Singapore, by the Head of AER, who reports to the Head of Economics and Trade. It also includes a 0.5 full-time equivalent PM in each PF-6 country. In addition, there is support provided by DIT, the economist network and the Head of Prosperity in (most) PF-6 countries. The PMT is responsible for monitoring and managing delivery, finances, inter-pillar coordination, risk management and monitoring and evaluation.[24]
[24] ibid.
All delivery partners submit quarterly progress reports. On an informal basis, all delivery partners also report to the PMT in each posting on an ongoing basis as work is delivered and respond to informal requests for information from Post and from Singapore.
## Links to other Prosperity Fund programmes
The AER Programme is only one of several PF programmes operating in ASEAN on issues of business environment reform and financial services. Other programmes are set out in Table 4 below.
Table 4: Prosperity Fund programme overlaps
LINKS TO OTHER PF PROGRAMMES
AER Programme strand/component	Overlap programme	Description of mutual support and/or overlap[25]
ER 2 – Anti-corruption and government transparency	Global Anti-Corruption (GAC) Programme	The ASEAN Business Integrity Platform delivered under ER 2 by UNDP is also being undertaken under the GAC Programme by the OECD.
ER 1.3 – Competition policy	Global Business Environment Programme	Indonesian competition assessments under the Global Business Environment Programme overlap with the competition assessment work undertaken by the OECD under ER 1.3., The Global Business Environment Programme’s competition strand focuses on competition assessment capacity building, strengthening institutional capacity to identify and sanction anti-competitive regulations/practices. The AER Programme’s competition policy strand focuses on assessing challenges in competition policy in the logistics sector. There are also possible overlaps in the Philippines and Vietnam, though these are not yet confirmed.
ER 3 – Fintech	Global Trade Programme	A Fintech project in Vietnam is currently under development. The project concept focuses on supporting the state to establish two fintech management mechanisms: a ‘regulatory sandbox’ (a framework set up by a financial sector regulator to allow private companies to test new, innovative business models in a controlled environment) and an innovation hub (an organisation and place that provides facilities and support to create and nurture start-ups). It is not yet clear if this will overlap with the AER Programme’s fintech project.
ER 1.1 – IP	The Global Trade Programme	The Global Trade Programme has proposed projects in Indonesia and Vietnam, but delayed development of these to wait and see how AER work develops.
ER 3 – Capital Markets	ASEAN Low Carbon Energy Programme	The ASEAN Low Carbon Energy Programme has a green finance component – as a result, ASEAN Capital Markets Forum engagement is required from both programmes. FCO Singapore is coordinating to avoid conflicting approaches.
[25] The Programme team notes that the AER Programme was the first designed and with delivery started in ASEAN. Once other programmes identified business environment reform and financial spaces in ASEAN as target areas of PF work, the AER Programme was asked to re-justify its objectives and purpose in these spaces.

These overlaps have required PMT attention and additional communication work over the past year, to explain to newer programmes what the AER Programme is already doing and where the points of overlap might be. In particular, the GAC Programme’s decision to include anti-corruption work on the ASEAN business integrity platform, which is very similar to the work being delivered by UNDP in ASEAN under the AER Programme, required extensive coordination facilitation by the AER PMT to successfully reduce overlap between of the two efforts.
The programme is part of the Financial and Economic Reform and Ease of Doing Business PF sectors.

# Approach
The AER Cycle 2 evaluation was conducted using virtual primary data collection methods and largely followed the approach used for Cycle 1 evaluation. The evaluation approach continues to be a process analysis, with a focus on assessing how the programme is progressing, and on collecting and validating evidence that demonstrates how, where and why the linkages in the programme-level ToC and the ToCs of its pillars are valid or not. To that end, this evaluation addresses 15 PEQs (as listed in Box 1).[26] In addition, two scorecards, one on gender and inclusion (G&I) and one on VfM, have been completed.
[26] Also see the evaluation matrix in Annex 3.
The entirety of the programme has been evaluated through reviews of reporting data and interviews with Programme team staff, some steering board members and representatives of all delivery partners to address 15 evaluation questions (see Box 1). In addition, in-depth data collection through documentation review[27] and interviews[28] have been conducted for four samples:[29]
[27] See the bibliography in Annex 5.
[28] See a list of interviewees in Annex 4.
[29] See selection criteria, as described in the AER Programme Cycle 2 Approach Paper in Annex 3.
- all three strands of ER 1 activity in the Philippines, including IPO work and FSIP Programme work delivered by Rouse (a PwC contractor) on IP, RD/BEIS work on regulatory reform and OECD work on competition assessments
- ER 2 work on anti-corruption delivered by UNDP in Malaysia
- ER 2 work on government procurement transparency delivered by Construction Sector Transparency Initiative (CoST) (a UNDP contractor) in Thailand
- ER 3 work on Islamic finance delivered by PwC in Malaysia.
These samples reached more interviewees,[30] including CSOs and private sector organisations where possible, and in-country delivery teams, and reviewed more documentation, including deliverables, planning documents and external documentation, than the broader programme-level work. This approach allowed for triangulation across countries and delivery partners. As in Cycle 1, this approach is intended to build the evidence base upon which the evaluation findings are made, while maintaining the VfM of the evaluative approach. The virtual approach, born of necessity, did make addressing issues of country ownership and management, use of country systems, harmonisation with other donors and building capacity in partner countries more challenging. However, these have been considered by documenting the country samples as additional learning products, which can be used and shared by the FCO at the national level, and by including national consultants based in the sampled countries in the EL team. The approach was developed with and approved by the PMT via workshops and iterative approach paper reviews, and was also approved by the JFU after a quality control process.
[30] The sample sizes were: Philippines – 16 interviews and 42 documents; Malaysia – 20 interviews and 45 documents; Thailand – 11 interviews and 22 documents. Note that the total sample was 46 interviews, as some stakeholders were interviewed for multiple country samples.
Box 1: Cycle 2 programme evaluation questions
PEQ 1.1. What progress against IO indicators can be observed? / PEQ 1.2. To what extent have there been unexpected or unintended effects? (Limitations apply.) / PEQ 2.1. To what extent has primary purpose been achieved, and if so, what and where (country, sector, intervention)? / PEQ 2.2. How does the primary purpose achieved compare to what was expected? / PEQ 5.1 What factors have contributed to the achievement of the primary purpose and secondary benefits (SBs)? / PEQ 7.1 To what extent has the programme adjusted ToCs or programme design in response to changing context or understanding of causal pathways? What has it changed and why? / PEQ 7.2 Which assumptions (implicit or explicit) and causal pathways in the programme/project have been valid and which have not and why? (Limitations apply.) / PEQ 7.3 Since Cycle 1, is there new evidence that shows projects are more or less likely to contribute to financial inclusion or a better understanding of risk? If so, what? / PEQ 8.1 How is the AER Programme meeting regional priorities? To what extent is it focused on national priorities and is this helping, inhibiting or not affecting its regional focus? (Limitations apply.) / PEQ 9.1 How is evidence on VfM being used to guide programming? What effect is this having, if any, on the achievement of VfM? / PEQ 9.2 How does the programme management structure support the achievement of regional objectives? / PEQ 10.1 In what ways has the programme design or implementation changed in relation to gender responsiveness/inclusion at programme and project levels? / PEQ 11.1 What actions and/or progress has the programme made in response to the Cycle 1 Evaluation and Annual Review findings and recommendations? / PEQ 11.2 What learning activities have been undertaken during the year? Who was involved? What has resulted from these activities? / PEQ 11.3 In what ways have the delivery pathways been responsive to changing context?

The decision not to interview government counterparts was taken at the request of the FCO (due to governments’ need to focus on crisis response and the expected limits on the availability of FCO PMs, who were on or were supporting crisis teams, to facilitate introductions). This decision was validated and approved by the JFU. In the Cycle 2 Approach Paper, it is noted that:
“The design of the evaluation approach is informed by lessons learned by the EL team during the Cycle 1 evaluation. As in Cycle 1, the entirety of the programme will be evaluated via interviews with PMT members and implementing partners and review of programme documentation. In addition, for Cycle 2, indicator data uploaded to Prospero will now be available and included in the cross-programme evaluation. Due to current limitations on travel and in-person contact arising from the COVID-19 health crisis, this work will not be supplemented by interviews of government partners or key stakeholders as planned. Collection of additional data for select strands in the sampled countries for Cycle 2 – the Philippines, Thailand and Malaysia – will be limited to interviews with FCO, implementing partner and partner team members, as well as documentary evidence.”
This decision has, as expected, limited the ability of the evaluation to triangulate evidence on some issues, particularly the continuing relevance of the programme and the potential for sustaining the programme effects. The EL team is aware of the potential bias that focusing on programme implementers in its interviews may bring and this is reflected in the data-quality assessment scores.[31] The EL team has attempted, where possible, to mitigate this risk by relying on public statements of recipient governments, though the risk of bias remains.
[31] Bias is one of four equally-weighted criteria in the data quality assessment report.
All interviewees for this evaluation were promised confidentiality, and therefore all references to evidence collected via interview is listed as key informant interviews (KIIs).
The primary evaluation tool is the evaluation matrix found in Annex 3, which was reviewed and approved by the PMT and the JFU. Additional tools used were:
- Interview scripts, designed per stakeholder type with specific questions relevant to each case study, tested, validated and revised throughout the evaluation process
- The G&I scorecard, standard across the PF, completed as part of the evaluation by the EL team (see 8)
- The PF standard VfM scorecard, completed by the PMT, with EL support via a workshop and an iterative process of reviewing and incorporating feedback (see Annex 2)
- A facilitated sense-making workshop with the PMT, the EL team, EL thematic representatives and an external facilitator, used to support co-creation of the evaluation recommendations
- A data-quality assessment approach based on the EL Data Quality Assessment Guidance.
Indicator data is not yet available for the AER Programme on the Prospero monitoring portal, and, as such, most indicators used for this evaluation were collected from quarterly reporting at the programme and project levels, as developed by the FCO and the delivery partners.
Consortium values have been adhered to throughout the delivery of this evaluation. This includes a code of ethics, which aligns with the UK Evaluation Society guidelines for good practice. The evaluation has sought to adhere to the principle of ‘do no harm’ and to maintain a cross-cutting focus on G&I. Concerning safeguarding, a policy and accompanying processes to guard against the possibility of sexual exploitation and abuse by EL members is in place. All team members were required to declare any actual or potential conflicts of interest with their work in delivering EL services. No relevant conflicts were identified. In addition, the EL team was able to:
- Work independently and without interference in its assessment, beyond the limitations to access to government counterparts as discussed above
- Use independently verifiable evidence as discussed
- Protect beneficiaries and other stakeholders by ensuring they had the opportunity to withhold or disassociate their names from any published accounts of their opinions (in some cases, the EL team was unable to collect sufficient feedback from a wide enough cross-section to anonymise collected opinions, and elected not to report opinion or quote informants or, otherwise, to make feedback generic in order to protect anonymity, even where not specifically requested)
- Follow a broad-based participatory approach by engaging with a range of stakeholders – public and private sectors, men and women, etc. – in the consultation processes. The outreach to stakeholders included 26 women and 20 men.
## Assessment of evaluation data quality
In line with the PF data-quality assessment approach,[32] the evaluation data’s quality was assessed for each case study as well as for the overall programme evaluation. The assessment approach measures quality, by programme evaluation question, against five, equality-weighted criteria using scores of one to five, with one indicating ‘weak’ and five ‘strong’, see Table 5. These are validity, reliability (assessed at programme level only), completeness, precision and bias.
[32] See the EL guidance on data quality.

Table 5 : Data quality assessment measurement criteria
Table 6, below sets out the assessment of data in the Cycle 2 Evaluation against the topic areas and the quality criteria. The scores reflect aggregated scores across the programme-wide evaluation work, inclusive of the scoring for each sample. In general, bias scores have tended to be middling to low, not due to deliberate attempts to mislead the EL team, but because the revised evaluation approach limited ability to reach external stakeholders, such that, while multiple viewpoints were used to triangulate findings, these tended to come from within the same organisations (FCO, delivery partner or both). This is not an ideal scenario and the Cycle 3 Evaluation should aim to improve on this where possible. However, the overall quality of evidence reflects a wide range of evidence sources and the overall conclusions are considered to have an adequate evidence base, Moderate to Good in aggregate for all topics, and can be considered with some confidence, particularly in terms of Design and Learning.
Table 6: Cycle 2 evaluation data-quality assessment scores
TOPIC AREA	VALIDITY	RELIABILITY	COMPLETENESS	PRECISION	BIAS	AGGREGATE SCORE
Design	Good	Good	Good	Moderate	Moderate	Good
Progress toward results	Moderate	Moderate	Weak–moderate	Moderate	Weak–moderate	Moderate
Gender and Inclusion	Good	Good	Moderate	Moderate	Weak–moderate	Moderate
Governance and Management	Good	Moderate	Good	Moderate	Weak–moderate	Moderate
Sustainability	Moderate	Moderate	Good	Moderate	Weak–moderate	Moderate
Learning	Good	Good	Good	Moderate	Moderate	Good
Overall	Good	Moderate	Good	Moderate	Weak–moderate	Moderate

### Triangulation of data to support findings
As has been described, due to the pandemic and FCO’s concern about burdening partner governments during a time of crisis, the evaluation team was unable to interview most planned external stakeholders. Nonetheless, the evaluation did triangulate data in order to reach its findings and no reported finding is supported by just a single data point, though many are supported by data triangulated from multiple implementing partner or FCO data sources.

Table 7: Data Triangulation by programme evaluation question
PEQS FOR CYCLE 1	DATA POINTS BY TYPE[33]
	FCO	IMPLEMENTING PARTNER	OTHER
PEQ 1.1 What progress against IO indicators can be observed?	17	20	4
PEQ 1.2 To what extent have there been unexpected or unintended effects?	10	13	2
PEQ 2.1 To what extent has primary purpose been achieved, and if so, what and where (country, sector or intervention)?	8	6	0
PEQ 2.2 How does the achieved primary purpose compare to what was expected?	9	16	3
PEQ 5.1 What factors have contributed to the achievement of primary purpose and SBs?	9	24	3
PEQ 7.1 To what extent has the programme adjusted ToCs or programme design in response to changing context or understanding of causal pathways? What and why?	8	4	0

PEQ 7.2 Which assumptions (implicit or explicit) and causal pathways in the programme/project have been valid and which have not and why?	3	19	0
PEQ 7.3 Since Cycle 1, is there new evidence that shows projects are more or less likely to contribute to financial inclusion or a better understanding of risk? If so, what?	6	13	3
PEQ 8.1 How is the AER Programme meeting regional priorities? To what extent is it focused on national priorities and is this helping, inhibiting or not affecting its regional focus?	6	8	0
PEQ 9.1 How is evidence on VfM being used to guide programming? What effect is this having, if any, on the achievement of VfM?	8	9	1
PEQ 9.2 How does the programme management structure support the achievement of regional objectives?	11	17	0
PEQ 10.1 In what ways has the programme design or implementation changed in relation to gender responsiveness/inclusion at programme and project levels?	6	14	4
PEQ 11.1 What actions and/or progress has the programme made in response to the Cycle 1 Evaluation and Annual Review findings and recommendations?	15	10	0
PEQ 11.2 What learning activities have been undertaken during the year? Who was involved? What has resulted from these activities?	6	5	0
PEQ 11.3 In what ways have the delivery pathways been responsive to changing context?	7	10	3
[33] Data source count indicates a unique document or interview of a key informant, but does not indicate the quality or relevance of each data point.

# Findings
Box 2: Summary of Cycle 2 evaluation findings
Delivery is on track with the FSIP Programme’s delayed inception now complete. / Risk of achievement of regional objectives has grown as the programme has increasingly focused on bilateral relevance. / Islamic finance work, which focuses on the poor’s economic resilience, does not support the programme’s inclusive finance objectives well, though it does align with the Fund’s objectives. / The programme has prioritised learning in both delivery and management, but missed an opportunity to capitalise on the Cycle 1 evaluation. / Programme management has significantly improved with added staffing and a transition of the programme’s commercial partner to a payment-by-results footing. / The SB approach and plan are now better defined and integrated across the programme team.

Most of the AER Programme is now in delivery, including delivery across all pillars and strands.
- The FSIP Programme – a commercially delivered sub-programme comprising part of the ER 1.1 strand and the ER 3 pillar – experienced significant delays to inception approval and then significant re-design. It is now delivering, albeit delayed relative to original expectations.
- ER 1.2 is on track, seen as effective and valued by partners.
- ER 1.3 is mostly on track, though the relevance to all PF-6 partners remains unclear and how the work will result in changed policy is not yet proven.
- ER 2 is performing well and is largely seen as the most successful programme element so far. There have been country-specific delays and changes of direction to which the programme has successfully adapted.
Delivery risks have grown over the past year. Despite finalisation of the PwC negotiations and completion of inception, the delay to the start of FSIP work, delays to some Philippines projects and the impact of the COVID-19 crisis have increased the risk that the AER Programme will not be able to deliver on some IOs and outcomes during its current lifecycle. COVID-19 has delayed the programme, resulted in adjustments to delivery approach,[34] and, crucially, delayed the launch of some work products, which may reduce their relevance. There is mixed evidence of the continued commitment of government to some programme elements in some countries. The PMT has been pleased overall at the commitment of its counterpart governments to many aspects of the programme, but new government priorities for the anti-money laundering work in Myanmar and potential changes in priority around anti-corruption work in Malaysia due to political changes[35] stand out as major shifts. These risks may be balanced out by the impacts of changes in approach in response to COVID-19. Re-casting training and workshops as virtual products, for example, is reported to be more sustainable and can reach wider audiences. The FSIP re-scoping has also increased the relevance of that portion of the programme to national governments. As observed in the Cycle 1 Evaluation Report, however, the programme has trended overall to a more country-specific project design. This is not necessarily problematic, but there is a risk that some of the regional objectives articulated in the business case may therefore not be achieved.
[34] Note that delivery partners believe they can successfully adjust the delivery approach to compensate for the exigencies of COVID-19. This is explored in Section 4.1.
[35] The current political situation in Malaysia is uncertain, with no sitting of parliament since the appointment of the new prime minister, who was sworn in as the eighth prime minister by the King. See news reports from CNBC and MalayMail, for more detail.
Among delivery risks, while the Islamic finance work in Malaysia aligns well with PF objectives, it is not well-aligned with the AER ToC. Due to revisions in the workplan, elimination of most of the originally scoped work, and development of three new work areas, now reduced to one, there is a weak link between the Islamic finance work and the inclusive finance outcome in the AER ToC. This work does however, link strongly to overall PF goals on resilience and poverty alleviation. While this is not necessarily representative of the whole of the FSIP Programme, it does suggest that the demand-led approach to re-scoping FSIP has not focused on alignment with the AER Programme’s objectives.
The AER Programme has engaged in more effective, cross-programme learning as compared to last year. However, opportunities to use the Annual Review and Cycle 1 evaluation as learning touchpoints, particularly with delivery partners, were not fully capitalised upon. The PMT has successfully increased engagement with learning, including effective regional activities on G&I, programme management and SBs, among others. Whereas last year’s evaluation noted that learning was largely seen as a delivery activity (where it was effective), the programme has more fully engaged in learning as a management strategy. Dissemination of the lessons arising from the Annual Review and Cycle 1 evaluation was largely limited to within the PMT, and not all PMs reported perceiving these lessons to be relevant to their work.[36]
[36] Reasons for this include very stretched programme management resources and also the lack of a dissemination policy across the PF at the time of the Cycle 1 evaluation.
Several Annual Review and evaluation recommendations were successfully implemented. In particular, the addition of new regional staff has been positively impactful, and the commercial contract has been successfully transitioned towards payment by results. The growth of Singapore-based programme management staff from 0.5 FTE to 2 FTE is seen across the PMT and delivery partners as one of the most helpful changes made over the past year, enabling the programme to work closely with the commercial partner to facilitate the transition from programme inception to implementation and delivery. However, some recommendations in the Cycle 1 evaluation remain unaddressed, including one that is repeated this year.[37]
[37] See further discussion on use of the Cycle 1 evaluation recommendations in Section 4.4.1.
The PMT has made considerable efforts to improve approaches to G&I at strand level over the past year, with a focus on FSIP and capacity building of project teams on PF G&I policy. The realities of delivery have driven a minimum standards approach to G&I, centring on gender-equitable participation, across most of the programme. However, the evaluation observed significant differences across suppliers in terms of ambition and success. The evaluation also noted that the AER Programme is disadvantaged by being one of the earlier PF programmes to start – lacking access to tools and templates other programmes that commenced later have used, such as G&I action plans.
The programme has made clear strides in developing and communicating an SB plan. The Cycle 1 evaluation noted a lack of SB approach penetration to the PMs and that the programme is disadvantaged by its multilateral delivery partners’ inability to directly pursue SBs. While the limitations in delivery partners’ ability to pursue SBs cannot be changed, the programme has continued to pursue SBs, with DIT support, by clarifying and disseminating the SB plan focused on FCO, BEIS and the commercial partner’s capacities to pursue SBs. The original SB focus, as articulated in the business case, was on soft power and exports. There are signs that soft power gains are being made; exports are less clear. The SB approach has benefited over the past year from having SB Advisers in five of the PF-6 countries.
## Design
The programme has made substantial progress ensuring the commercial provider effectively re-scoped the FSIP work in order to move through inception and into delivery. Final inception documents were submitted in December 2019 and subsequently approved. This followed a contract variation in November 2019 in support of the re-scoping and a strengthening of the delivery model.
The programme has also re-designed several delivery elements to effectively accommodate COVID-19 distancing requirements, though not all activities can be shifted into virtual delivery. Given the focus on delivering training and capacity-enhancement support via workshops and learning platforms across much of the programme, the COVID-19 pandemic has had an understandable impact on ability to deliver and on delivery approach. Recipient governments were distracted from most concerns beyond crisis response and therefore delivery had to be shifted to virtual modes. FSIP and the UNDP-implemented Promoting a Fair Business Environment in ASEAN (Fair Biz) programme reported that most planned activities could be transitioned to virtual delivery, though some had to be delayed.[38] Some PMs and delivery partner national teams, however, reported concerns that national culture may inhibit uptake of virtual meetings, in particular where a foundation of trust was not yet established.[39] The OECD has had to delay the launch of some competition reports and transition others to a virtual launch, which some stakeholders felt limited their impact. [40] UNDP reported[41] that the shift to virtual delivery has also had benefits, including capturing re-usable training materials and reaching a wider audience, generating more participation and at a lower cost to participants (including women and disadvantaged groups), than prior in-person events had. The OECD also expect to have wider and more senior participation in their Philippine Competition Assessment launch.[42]
[38] FSIP, Q4 Quarterly Report; UNDP, Q4 Quarterly Report.
[39] KIIs.
[40] Competition reports for the Philippines and Thailand are delayed, along with fact-finding missions for Cambodia and Laos.
[41] KIIs, UNDP Q4 Quarterly Report.
[42] KIIs.
A payment-by-results approach, as part of the FSIP contract variation, has raised the ambition of the programme and resulted in monitoring metrics which are more focused on results than activities. As part of the move out of inception and re-scoping, a contract variation was concluded that, among other things, shifted PwC away from an activity-based payment schedule and onto a results-based schedule for the FSIP Programme. [43] Each FSIP work package has a number of milestones with payments attached, and the PMT reports[44] that this has improved FSIP focus on outputs. Contract management, further discussed in Section 4.4, is consequently consuming a disproportionate amount of PMT staff time.[45] However, the steering board and PMs and national teams in many of the PF-6 countries have been more satisfied with PwC’s delivery as a result, though this is not unanimous and there are still residual frustrations. Some FSIP delivery elements, such as the Thai fintech project, remain unapproved.[46]
[43] Stakeholders indicated that the original contract was poorly drafted, which lacked suitable clauses to enact a results-based payment system.
[44] KIIs.
[45] The AER Programme Q3 Quarterly Report notes: a key lesson has been “The importance of specifying ‘payment by results’ in the initial Statement of Requirements. This was not built in for this contract, and it has been a long negotiation to try and agree terms retrospectively.”
[46] AER Programme Q3 Quarterly Report; KIIs.
Observations from the Islamic finance case study suggest that some re-design work may not align well with the overall AER ToC. Some Islamic finance implementing stakeholders discuss financial inclusion as a priority while others only position financial inclusion as one of many possible outcomes. This difference may be one reason there is an observed misalignment between the FSIP and AER ToCs. Although the AER ToC need not reflect every workstream, each workstream should be able to use the AER ToC to guide its interventions and contribute to AER outcomes.[47]
[47] With exception of the ‘Country Report & Master Plan on Islamic MSME Financing Sector’ where the objective is to increase access to finance for MSMEs, the ToRs and concept note for the other work packages do not mention financial inclusion. See FSIP - ToR IF_MYS_01 V4.F (approved), FSIP - ToR IF_MYS_02 V4.F (approved) and Concepts for Work package 4_07042020.
UNDP’s revised ToC and logframe have improved delivery focus, while revisions to the other strands are ongoing, but promising. The Cycle 1 evaluation recommended that AER seek revisions to the delivery partner/strand logframes. The AER PMT have pursued this over the past year and reported on progress via the quarterly reports[48] and in monthly status calls with the monitoring and reporting team, the EL team and with the JFU’s MREL support staff. This is explored further in Section 4.4.1. The revisions have improved focus on outputs and IOs,[49] observed anecdotally via KIIs and in quarterly reporting where more delivery partners are reporting against logframe indicators. However, strand logframes do not sufficiently integrate gender-disaggregated data, with the exception of the logframe for ER 2.[50]
[48] See AER Programme, Q3 Quarterly Report, 2019, ‘Actions taken, new recommendations and recommendation owner(s)’, Page 5.
[49] See, for example, UNDP, Project Steering Board Meeting Y2 Minutes, 2019.
[50] See Table 8 in Section 4.3.

## Progress toward results
### Primary purpose
The programme has made progress toward delivering a number of planned outputs across all pillars and some IOs can be observed. Outputs and IOs observed, to date, are attributable to the programme. Future outcomes are expected to be on a contribution basis, with programme activities unlikely to be the only cause of the expected results.
Figure 4: Progress on delivery of outputs and some intermediate outcomes

With an incomplete logframe, measuring specific progress is challenging and tends to focus on activities and strand-level outputs. As discussed further in Section 4.4.1, the PMT has focused on revising strand-level logframes, with an intention of revising the programme logframe once these are complete. To date, only UNDP is regularly reporting against their logframe.[51] However, FSIP has started to report select indicators, with the draft Q4 quarterly report including some indicators.[52] However, programme reporting does predominately focus on activities and outputs, in part due to the lack of indicator reporting in delivery partner (other than UNDP) reports.[53], [54]
[51] See for example UNDP, Prosperity Fund Quarterly Report for Q4.
[52] FCO, Draft Year 2 Q4 Quarterly Report.
[53] KIIs.
[54] It should be noted that one reason for the lack of IO and outcome indicator reporting is that the types of activities undertaken (policy advice, capacity development support) may take time to produce, and therefore report on, outcomes.
Despite these issues, the programme has made promising progress in key areas. These include observed progress on government transparency and anti-corruption across all countries of activity, strong engagement on IP at the regional level and in the Philippines and encouraging interest in regulatory reform in Vietnam.[55] These early wins suggest the programme’s continued traction at national and regional levels and the relevance of the implementation approach.
[55] FCO, Draft Year 2 Q4 Quarterly Report.
Ability to measure and test the “embeddedness” of delivered capacity improvements will be challenging at best, without added qualitative monitoring. Much of the programme involves delivering capacity at the output, IO or even outcome level and many activities are focused on training, learning platform engagement, direct agency-level support and workshops. This is true of:
- all of the in-house IP work
- some of the FSIP IP work[56]
  [56] The FSIP IP work also includes a significant element of delivering capacity through the development of reports.
- most of the regulatory reform work
- some of the competition assessment work, which has IOs focused on competition authority engagement and requests of support around recommendations
- many of the ER 2 work strands focus on learning and engagement
- some of the ER 3 pillar work, which includes capacity enhancement on anti-money laundering and financial crimes, capital markets development and fintech regulation, among others.
Several of the strand logframes have outcomes that include measures of uptake, but programme-wide these tend to focus on numbers of trainings delivered or numbers of participants. In some cases, measures of recommendations or policies implemented are included. But there is a missing link that remains unmeasured: the extent to which the systems, skills, knowledge and other capacities delivered penetrate into the participants’ home organisations. Understanding this penetration, or ‘embeddedness’, of new capacities would support the programme in active management of progress and establishing evidence of impact.[57] This was also observed in the Cycle 1 evaluation.
[57] Recommendations on how to address this are included in Section 7.
### Secondary benefits
The programme has made significant progress on SBs through the completion of an SB plan, improved plan dissemination and much-improved coordination across government in the PF-6 countries. As observed in the Cycle 1 evaluation, the AER Programme is somewhat disadvantaged by the inability of its multilateral delivery partners (ER 1.3 and ER 2) to directly pursue SBs.[58] The programme has sought to manage this issue by:
[58] Stakeholders noted that different types of delivery partners are expected to bring different types of benefits. The FCO chose multi-lateral institutions as delivery partners for some benefits they come with (networks, relationships in region etc), but the consequence is a limited ability to directly pursue SBs. Whereas, PwC doesn’t generally have the needed relationships in-country because their offices are generally not doing development activities with counterpart government agencies; but they can pursue the SBs that the multi-laterals cannot. The overall approach then, is a portfolio, where different delivery partners are used to maximise their relative advantages.
- approaching SBs from a regional, rather than programmatic perspective by developing plans, approaches and tools that capitalise on all of the cross-PF work in Southeast Asia[59]
  [59] FCO, Southeast Asia Draft Secondary Benefit Plan, 2018
- taking responsibility for production of SBs within the FCO where needed, and supporting this through a strong network of SB Advisers, currently in five of the six PF-6 countries[60], [61]
  [60] A proposal for the one outstanding PF-6 country without a SB Adviser, Malaysia, has been submitted, but no funding decision had yet been made as of writing.
  [61] FCO, AER PF Non-ODA Bid Form, 2020-21 Cycle, 2020.
- ensuring delivery partners that can pursue SBs have comprehensive, actionable and measurable SB plans in place and incorporating these into monitoring and contract management tools.[62]
  [62] KIIs.
Of the SBs envisaged in the programme business case, there is evidence of soft power effects emerging; the case is less clear for exports, thus far. The AER Programme Business Case identified UK export opportunities and soft power as the primary opportunities for SBs.[63] Across the strands, stakeholders are able to identify ways in which the programme activities have created opportunities for UK influence with recipient governments, by supporting key strategic reforms and through output visibility.[64], [65] However, no stakeholders were able to point to new exports for UK or other international business opportunities that had yet arisen from programme activities, though there is hope for work that is just starting on the FSIP Programme, particularly in fintech, where the UK has a strategic advantage.[66], [67]
[63] SE Asia Economic Reform Business Case, FCO, 2018.
[64] KIIs.
[65] Note that the AER Business Case preceded the PF SB typology developed by the JFU, and therefore any limitations in planned SBs relative to the JFU SB concept are understandable.
[66] KIIs.
[67] Stakeholders noted that ‘enabling environment’ programmes will not be able to see a direct export outcome they are targeted at supporting all (domestic and international) business. This is indicated in the AER Business Case and it has also been acknowledged by the JFU.
The programme has used its non-ODA resources effectively. Non-ODA funds have been used to support the SB Adviser network, in region, and to pursue commercial SBs. Planned commercial SB development activities include researching Southeast Asia’s markets and promoting the findings to UK companies, encouraging the reduction and removal of trade barriers, promoting UK exports, and supporting the creation of business-to-business and government-to-UK business links.[68] In the past year, the network has engaged in improved coordination via workshops and regular teleconferences, and in identifying opportunities arising from PF implementation in the region.[69]
[68] AER PF Non-ODA Bid Form, 2020–21.
[69] KIIs.
Box 3: The Prosperity Fund’s secondary benefits
Exports: Increased export opportunities can arise from new markets in the partner country (market creation), a widening of the market (more of the same and more innovative goods and services in the same sector) or a deepening of the market (supplying the supply chain in the partner country). / Foreign direct investment: Foreign direct investment from partner countries increases economic activity in the UK, competition and productivity, and can lead to learning within sectors and along the supply chain. / Outward direct investment: UK companies benefiting from being able to outsource production into the partner country. Repatriation of profits and improvements to the supply chain as well as upskilling (i.e., the focus on the higher skill end of the production process) in the UK benefit the UK economy (applies to manufacturing and private and public services). / Soft power: Creating good will – an enabling SB. Soft power describes a nation’s ability to attract and persuade, rather than coerce or buy the outcomes it wants. Soft power is a country’s culture, political ideals and policies. / Market access (including imports) for UK firms: Improved market access (including imports) for British companies can have a number of benefits by reducing import costs: consumers may benefit directly, UK producers get better access to raw materials, intermediate goods and skilled labour. / Network effects: UK businesses building partnerships and working successfully with companies from other third countries, gaining new opportunities in markets of third countries.

## Gender and inclusion
The PMT has made considerable efforts to improve approaches to G&I at strand level over the past year. These efforts have focused mainly on the development of an FSIP Gender and Social Inclusion (GESI) Plan and building the capacity of project teams on PF G&I requirements during the PF Regional Forum.
In terms of level of ambition, the realities of delivery have driven a minimum standards approach to G&I, centring on gender-equitable participation, across most of the programme. Delivery partners appear to be strongly incentivised by targets on ensuring, at least numerical, gender-equitable participation in activities.[70] However, several G&I-relevant analyses conducted in inception have not translated into delivery, while post-inception there appears to be a lack of analysis of G&I-related barriers and opportunities as they relate to specific interventions and country contexts, which could be used to inform activities, notable work on gender by UNDP notwithstanding. Further work could be done to increase the ambition on G&I, to review women's participation to analyse gendered dynamics, wider social inclusion or indeed intersectionality, which might inform interventions and outcomes for the most marginalised.
[70] KIIs.
There is large variation across programme strands and suppliers on G&I in terms of levels of engagement, capacity, ambition and results, with UNDP the most successful. G&I is integrated most meaningfully into the ER 2 strand at regional level, through targeted interventions and mainstreaming of gender considerations in other project components. With regard to ER 1 and ER 3, high turnover of staff and consultants with G&I expertise appears to be a challenge for delivery partners, in spite of internal efforts to build capacity across project teams under the FSIP Programme. (The RAG[71] ratings presented in the scorecard table below would differ, were programme strands to be assessed individually, with ER 2 exceeding minimum standards, and therefore scoring ‘green’, for all relevant dimensions.)[72]
[71] Red, amber, green.
[72] Those dimensions not related solely to the programme level; namely, ‘design’, ‘accountability’, ‘delivery partners’ and ‘results’.
The AER Programme has been disadvantaged by being one of the earlier PF programmes to start, with more guidance now available than there was during design. As a result, the AER Programme has not employed design tools that are now commonly used across the PF, including G&I action plans (with the exception of FSIP, which has developed a GESI plan in the past year), but should make efforts to ensure that, as a minimum, benefits flow to all members of target groups (e.g. businesses, including women-owned businesses) and that women and other marginalised groups are not further disadvantaged by programme activities.[73]
[73] KIIs.
Table 8 provides a summary of G&I scorecard findings for Cycle 2. The completed scorecard and full analysis can be found in 8.

Table 8: Summary of ASEAN Economic Reform Programme Cycle 2 gender and inclusion scorecard findings
SCORECARD DIMENSION	RAG RATING	FINDINGS
Design		The primary focus of G&I-related efforts across the programme is limited to gender-equitable participation in activities. Several analyses of gender-specific barriers and opportunities conducted in inception have not translated into delivery (nor refreshed in relation to specific interventions planned). / ER 1 interventions have focused on gender-equitable participation rather than substantive consideration of G&I-related issues. RD International attempted to identify gender-specific regulatory barriers, but the G&I-related findings of consultations were too general to inform activities.[74] / G&I is integrated most meaningfully into design of the ER 2 strand, through targeted interventions and mainstreaming of gender considerations in other project components. G&I-related work under ER 2 is foregrounded primarily in regional-level interventions led by the UNDP gender team in Bangkok. / The PMT has made considerable efforts to support improvements to FSIP by developing a gender plan.[75] However, the plan remains relatively low ambition, dealing only with minimum standards. There is the option to pursue more ’empowering and transformational activities’ should further budget become available. This is a disappointing outcome.[76]
Internal capability and incentives		Both the Head of the AER Programme and the Head of the PF (FCO Singapore) are active members of the G&I champions network, and have presented to the network on their experience of supporting the development of the FSIP GESI Plan.[77] / The PF Regional Forum held in November 2019 included a training session on G&I, which explored PF G&I requirements and practical examples of best practice. All FCO PMs and delivery partners were present. / There is evidence that the PMT has regularly drawn on government expertise at strategic points since the addition of the two new team members – having, for example, received support and advice from the centre on the development of the FSIP GESI Plan – but observe that more sector-specific advice would be beneficial.[78]
Accountability		To meet minimum standards, the programme must ensure strand logframes disaggregate data consistently and expand quarterly progress reporting (QPR) to include progress against indicators. There has been resistance from some delivery partners to integrating targeted G&I or disaggregated indicators. Only the ER 2 strand logframe mainstreams G&I effectively, through targeted G&I and sex-disaggregated indicators.[79] / Evidence on engagement with end beneficiaries is more limited (and challenging given the programme’s focus on policy ‘tweaks’ rather than root and branch reform), but the evaluation has identified positive examples of engagement with civil society under ER 2. At regional level, UNDP is engaging relevant stakeholders through targeted G&I-related activities and, in Malaysia, through the development of a national CSO network.[80]
Financial resources		The AER Programme does not have a programme-wide VfM strategy. However, the PMT has invested considerable effort in supporting the FSIP Programme to develop a VfM plan, which integrates three equity indicators, two of them process-oriented (e.g., ‘percent of outputs applying minimum GESI requirements’) and one on generating evidence that the approach to G&I has evolved as a result of lessons learned.[81] Budget considerations have thus far limited the extent to which the FSIP Programme is planning to pursue equity opportunities beyond the minimum standard.
Delivery Partners		There is large variation between delivery partners in terms of levels of understanding and engagement on G&I. / At regional level, UNDP is very well-placed in terms of in-house G&I expertise, but G&I capacity at country level may be more uneven.[82] The Gender Audit conducted by CoST Thailand represents a major milestone in its development of G&I-related capacity.[83] / Under ER 1 and ER 3, there have been efforts to build G&I-related capacity across the project team. At the same time, however, this may have been undermined by high turnover of team members with G&I expertise.[84]
Results		For both ER 1 & ER 3 G&I-related results are not being regularly reported, making it challenging to assess results achieved over the past year. G&I-related risks are not included in risk monitoring and mitigation set out in QPR for either workstream. / However, the ER 2 workstream has had considerable success in delivering G&I-related results, primarily at regional level where interventions focus on gender diversity in leadership and support for young entrepreneurs.[85]
[74] Ibid
[75] FSIP, DRAFT Gender Equality and Social Inclusion Plan, April 2020. More detail on the GESI Plan and the process for developing it, are included in Section 1: 8.
[76] FSIP, DRAFT Gender Equality and Social Inclusion Plan; KIIs
[77] Evaluation sensemaking workshop, 29 May 2020
[78] KIIs
[79] UNDP / ER 2 pillar logframe
[80] KIIs
[81] FSIP DRAFT VfM Plan
[82] KIIs
[83] CoST Thailand, Gender Audit, finalised December 2019.
[84] KIIs
[85] UNDP quarterly progress reporting, Qs 1-4 19/20

## Governance and management
The addition of two new regional staff members has positively impacted the programme’s management and delivery. Two additional full-time-equivalent staff were recruited in September 2019, replacing a 0.5 FTE position that was vacated in March 2019.[86] In the interim, the Head of Economics and Trade and the Head of Prosperity Fund in Southeast Asia, both Singapore-based, were back filling the responsibilities of the vacant position, which was unsustainable.[87] Recruiting additional management staff was the highest priority recommendation in the Cycle 1 Evaluation Report. Across the programme, stakeholders report that, after an acclimatisation period, the additional programme support has had a significant, positive impact on programme management. [88] The new Head of Programme is seen as critical for getting the FSIP Programme out of inception and through contract variation in a way satisfactory to the steering board. Because of the complexity of the FSIP Programme, and its numerous low-value work packages, the added financial management support has been crucial, not only for keeping the programme running, but also for allowing the Head and the PMs to focus on activity management and other areas of governance.[89]
[86] FCO, AER Year 2 Q2 Quarterly Report, 2019
[87] Stakeholders note, however that even prior to the staffing vacancy, the time demands of the programme on these leadership positions was high, suggesting that PF oversight requirements can be a burden.
[88] Note that the programme is still within the 5% cap on administrative expense.
[89] KIIs
The complexity of ensuring FSIP is delivered to PF requirements, and managing PwC as the sole commercial delivery partner, has far exceeded original expectations and dominated regional staff time. The PMT estimates that managing the FSIP Programme and its implementing delivery partner PwC has consumed about 80 per cent of the new Head of Programme’s time. This exceeds expectations and is disproportionate to the relative financial cost of the FSIP Programme, but it has been necessary to get the programme running. The FSIP Programme has also taken up most of the steering board’s attention.[90]
[90] Ibid
The steering board is widely seen as more strategically focused and therefore more effective over the past year. The SRO is credited with a focus on high-level policy and decision making, and improving how the board functions by actively managing the agenda, distributing materials early and pushing the PMT to deliver improved management products. These include improved programme reporting and a recently developed dashboard of key indicators, currently being trialled. As a result, the board has seen strong participation by its members and is taking a more active role in programme direction and decision making. The relationship between the PMT and the board continues to be positive and effective. The board is also actively engaged in the risk management process which elevates key risks identified by the PMT in the quarterly reports for the steering board’s attention. Substantial attention was given to risks around the commercial contract for FSIP delivery and delays resulting from its extended inception period over the past year. [91]
[91] FCO, Draft Year 2 Q4 Quarterly Report
Across several of the strands, long management chains limit the ability of the programme to communicate or coordinate cross-cutting issues with the on the ground, point of delivery teams. At country level, there is a lack of awareness or penetration of programme approaches and goals, particularly in cross-cutting areas like G&I and SBs into the delivery teams on the ground.[92] The apparent cause is long management chains that stretch from delivery teams to regional management teams on the delivery partner side, to regional PMs, to the PMT. While these do not appear to be hampering implementation effectiveness, they are creating communication complexities.
[92] Ibid
### Using the Cycle 1 evaluation
Some of the recommendations arising from the 2019 evaluation and Annual Review of the AER Programme have been addressed:
- Vacancies have been filled in the PMT and overall staffing resources have been increased by 1.5 FTEs. Overall, these changes were seen as positive by interviewees and enabled clearer guidance to be provided to PMs (with strategic management and day-to-day management being divided across PMT members), working mechanisms (such as developing a decision tree to clarify who can make what types of decisions) and dealing with delivery partners. One interviewee noted that while not all problems were resolved, colleagues were working to make improvements. Another felt more improvements may materialise over time as new staff become more familiar with the programme. However, changes at the PMT level do not overcome resource constraints in Myanmar where the Head of Prosperity position has been disbanded.
- The PMT has invested a lot of time in managing PwC and the FSIP Programme, and some improvements have been reported. These include more (and better) engagement of senior PwC staff in meetings, particularly those with senior government officials (which has also been well received by counterparts), greater clarity around the role of the FSIP Country Coordinator, and PwC’s flexibility toward changing work packages.
- Delivery partners were invited to the regional PF forum last November where discussions were held on communication challenges and how to improve them. Some small improvements were reported, although given that the forum happened shortly before the start of the end-of-year holiday period, plus the advent of COVID-19, more time is likely needed to see notable improvements. The forum also featured a centrally-placed and well-attended opening session on G&I that attendees reported as usefully prioritising G&I in delivery.
- More SB Advisers have been recruited and are now in place in five of the PF-6 countries, supporting the AER Programme to map and identify opportunities for SBs. The support has been welcomed by some interviewees, since it has resulted in more time being given to considering SBs, liaising with DIT while also ensuring there is no conflict of interest around using ODA funding to support UK businesses. Non-commercial benefits (soft power) are perceived to be more relevant to the AER Programme, while there remain some mixed perceptions about whether commercial benefits are applicable and what delivery partners are expected to do to achieve them.
- Project- and country-level ToCs have not been developed further,[93] although project-level logframes are being devised or updated, which will then inform revisions to the AER Programme logframe. PMs are not actively involved in revisions to logframes.[94] Project logframes cover multiple countries and therefore are generalised. While project logframes are likely to be useful for accountability purposes and improve transparency of progress in reporting (something PMs still feel is needed), the logframes do not yet meet the intentions behind the recommendations made in the Cycle 1 evaluation that the programme should work on “building up critical thinking on the ToC [which] along with more strategic, outcome-focused management of delivery partners, would help the programme get ahead of changing context and how changes may impact programme delivery”. Projects remain underpinned with assumptions that are unlikely to hold true (e.g., staff turnover will not hinder embedding changes in knowledge and skills in practice to improve the business environment).
  [93] An exception to this is the UNDP-led ER 2 pillar, which did adopt a revise theory of change at its annual steering board meeting following completion of the annual review and cycle 1 evaluation, but not in direct response to the recommendations therein.
  [94] KIIs
- Gender and social inclusion is still seen as one of the greatest challenges for the AER Programme and individual projects, despite significant effort on the FSIP GESI plan. Some interviewees report that the AER Programme’s G&I approach has not substantively improved and specialist expertise is required to understand the direct impact of G&I on issues such as business integrity and IP. Situational analysis needs to be refreshed and intervention-specific to inform activities. Largely, across interviewees, G&I is read as specifically “women”, and other inclusion aspects (such as poverty, ethnicity, age and persons living with disabilities) have not been properly considered.
- Delivery partners were not aware of the recommendations of last year’s evaluation, but all expressed strong support for learning from them and how to improve their work. One interviewee felt the 2019 recommendations were relevant only for the regional PMT or the sampled countries, rather than the broader AER Programme.
- The programme is tracking uptake and implementation of many, but not all, of the recommendations in quarterly reports.[95]
  [95] FCO, Year 2 Q3 Quarterly Report
### Value for money
The PMT, and particularly the two new regional staff members, have made considerable efforts to ensure that the programme represents good VfM. Changes made during the past year include: requiring and supporting the development of a robust VfM plan for the FSIP Programme; a transition from payment by milestone to payment by results; the ringfencing of PM time for financial management and development of a system for scrutinising commercial invoices; monitoring proposed budget changes in light of reprogramming due to COVID-19; and an ongoing re-stress test of programme risks (see Table 17 in Annex 2 for details).
However, differences in the type of agreement, and differences in the trust placed in the commercial partner by multi-national and cross-government partners, have resulted in different levels of scrutiny of different partners on VfM. The FCO has introduced closer management of PwC over the last year. FCO approval is required to make even minor amendments to work packages, a highly administrative process which, while arising from legitimate concerns around performance, risks flexibility to adapt to changing contexts. In contrast, and similar to findings in Cycle 1, less time is spent on the financial management of other delivery partners. One interviewee perceived that they do not receive the same level of scrutiny on VfM as other delivery partners.[96]
[96] KIIs
At strand level:
- Under ER 1, delivery partners understand VfM mainly in terms of cost control. While there is some awareness of VfM by programme staff, there was no specific evidence to show that VfM is being used to guide programming. Evidence provided by interviewees of good VfM included savings related to hotels, flights and meeting rooms and providing government-to-government assistance, which was perceived to be cheaper than using commercial providers.
- ER 2 has demonstrated good VfM across all four dimensions: economy, efficiency, effectiveness and equity. For UNDP, flexibility and autonomy in running the project is reported to have promoted ownership and commitment.[97] UNDP’s experience and capability as a delivery partner has ensured the successful delivery of planned activities and outputs. Close consultation with stakeholders has ensured the project meets stakeholder needs. Resources were well budgeted and spent, with no unexpected delays and excess funds carried forward and repurposed. Suggestions from interviewees on improving VfM centred on economy – holding workshops in less exclusive venues, for instance. As regards CoST Thailand, which also represents good VfM across all four dimensions, the effectiveness and efficiency cases are the most compelling, with clear results to show for the programme and cost sharing with the government driving efficiencies.
  [97] Ibid.
- Under ER 3, the FSIP Programme Manual provides detail on the programme’s VfM ambition, covering all four ‘Es’. Each of the ‘Es’ is also considered in the work package selection criteria, alongside ‘proposed impact’ and ‘level of demand by beneficiaries’.[98] PwC gives a RAG rating and score for each work package against VfM assessment criteria and shares this with the FCO for approval. The decision not to move ahead with two of the three work packages for Islamic finance adheres to principles of effectiveness and efficiency: proposed outputs for Phase 2 of the Waqf land development fell outside overall PF goals as stated in the original statement of requirements; while primary research carried out to inform the master plan on the Islamic MSME Financing Sector showed the original hypothesis that finance was a key binding constraint to be inaccurate.[99]
  [98] FSIP Programme, IF Year 2 Work Package and Budget Review 24042020, Page 2.
  [99] KIIs.
Table 9 below provides a summary of the VfM scorecard ratings and commentary for Cycle 2. The completed scorecard can be found in 8. Additional findings on ‘equity’ are presented in Section 4.3.
Table 9: Summary of the ASEAN Economic Reform Programme value for money scorecard for Cycle 2
SCORECARD ELEMENT	VfM SCORECARD YEAR 1	QUALITY OF VfM EVIDENCE CYCLE 2	PROGRESS CYCLE 2 (DIRECTION OF TRAVEL)
1. Relevance and robustness of VfM measures in place	Adequate	Good	Good
2. Approach to procurement and cost containment	Good	Good	Good
3. Efficient use of resources and inputs by PF interventions	Good	Good	Good
4. Validation of PF ToC causal pathways (for primary purpose and SBs)	Adequate	Good	Good
5. Sustainability of programme activities	Adequate	Good	Good
6. Ability of leadership management and oversight structures to support programme delivery	Adequate	Good	Good
7. Strategies and measures adopted to enhance delivery and mitigate risk	Good	Good	Good
8. Equity of programme design and approach	Adequate	Adequate	Adequate
OVERALL VfM ASSESSMENT	Adequate	Good	Good

## Sustainability
Some elements of the programme are better set up for sustainable effect than others, with self-financing and a continuation of impacts as the predominant sustainability goals. Given the relatively short programme lifecycle, and the small scopes and budgets of some programme elements, the sustainability of programme effects is a challenge. Delivery partners noted, in particular, that short projects make embedding change difficult.[100] For example, under ER 2, the programme has had success in promoting sustainability in Thailand by integrating disclosure policy into national law.[101] The OECD’s work on competition and RD/BEIS’s work on regulatory policy seek similar approaches by integrating policies and practices into counterpart agencies. [102] The IPO’s approach to embedding change is focused on developing skills in select participants that can be transitioned to host agencies, a train-the-trainer approach. However, as noted in the Cycle 1 evaluation, the small sizes of FSIP work packages make implementing lasting change a major challenge, even where they build on each other over time.
[100] Ibid.
[101] The ER 2 eighth quarterly report notes: “Revision to the 2016 public procurement law to include infrastructure procurement transparency requirements has greatly increased the “embeddedness” of CoST TH. Passed October 2019.” Also see comments on anti-corruption efforts in corruption to SDG attainment.
[102] KIIs.
Tie-in with Sustainable Development Goals has become clearer, with UNDP making the most visible contribution among the delivery partners. One approach to moving the sustainability goal forward in the programme is the conscious and explicit tying of programme objectives to Sustainable Development Goals (SDGs) to which the counterpart governments have already committed. This approach can be effective, because it links intervention areas that the counterparts are interested in with commitments they would like to be seen to make progress on, reinforcing commitment to and interest in the AER Programme. Most delivery partners can articulate the SDGs their work aligns with,[103] but, perhaps unsurprisingly, UNDP (ER 2) makes this explicit in their work products more often than the others.
[103] Ibid.
The programme is not designed to address environmental sustainability. The Fund-level ToC describes how a “three pillared understanding of sustainability runs through programming design – green, self-financing and people centred, supporting women’s economic empowerment and excluded groups.” Environmental sustainability has not been an explicit objective of the AER Programme.[104] However, it is addressed in the design via resiliency support efforts,[105] and all delivery partners have public environmental safeguarding policies.[106] There are no environmental sustainability indicators in the current draft programme logframe.[107] However, the PMT has expressed interest[108] in the momentum to “build back ‘better’ – greener and more inclusive,” in response to COVID-19 as a way to explore further possibilities for incorporating environmental sustainability into the programme.
[104] AER Programme Business Case.
[105] FSIP Programme workplan, Revised, April 2020. The Islamic finance project, for example, includes building resiliency to economic and environmental shocks as a primary project goal. For example, the Pre-Emergency Fund based on Islamic social finance interim report assesses the financial impact of disaster in all 3 stages of pre, during and post disaster, the future potential costs of these disasters and a preliminary identification of Islamic social finance model for the emergency fund.
[106] See for example PwC, UNDP, the OECD and BEIS.
[107] Draft AER Programme logframe, 2020
[108] FCO, Draft Year 2 Q4 Quarterly Report
## Learning
The programme has expanded its approach to learning over the past year with an added focus on capturing learning in regular reports and through several programme learning events, which have resulted in design and delivery improvements. The programme has embedded its focus on learning by reporting quarterly on lessons learned and in response to recommendations arising from the annual Southeast Asia PF forum, training received and the Annual Review and evaluation.[109] This is a positive step, which keeps learning within the strategic focus of the steering board and, by extension, clarifies the PMT’s commitment to learning as a management approach. This has led to evidence that the programme is using learning to promote improvements in delivery.[110] In the past year, the PMT has also instituted a monthly ‘check-in’ call with FCO MREL, PF monitoring and reporting and EL, also serving to emphasise focus on and commitment to learning. Through these methods, the programme has maintained focus on logframe revisions at the strand and programme levels. At the same time, the programme has engaged more in direct learning events.[111] Uptake and use of PFLearning has increased and stakeholders report finding it increasingly useful for knowledge sharing.[112]
[109] See Year 2 Q3 and Q4 Quarterly reports.
[110] See, for example, improvements in approach to gender programme-wide and particularly in getting the FSIP gender plan complete, which arose, in part, from evaluation and annual review recommendations.
[111] The SEA PF forum, SB workshop and trainings were mentioned by key informants.
[112] KIIs
The learning opportunities arising from the Annual Review and Cycle 1 evaluation were not well-disseminated within the programme or to the delivery partners, which was a missed opportunity. This is explored in detail in Section 4.4.1.[113]
[113] See recommendations for discussion of avoidance of future occurrence.
Learning continues to be a focus of delivery activities, which suggests that upskilling the AER Programme and delivery partners in learning approaches, particularly learning across strands on remote learning, will have relevant value. The Cycle 1 evaluation observed: “Learning as a technical delivery activity is fairly well-considered – with sufficient thought given on how to best deliver and sustain learning.[114] In-house IP and Fair Business have developed learning programming that attempts to build knowledge across multiple events, engaging with consistent partners and using a reinforcing curriculum. For other strands, such as those implemented by the OECD and RD/BEIS, learning as an output is primarily focused on generating and distributing reports.”[115] This continues to be true, with, perhaps, even more emphasis on learning approaches as many programme learning activities are taken online in response to COVID-19.[116] Stakeholders noted UNDP’s success in widening engagement through online forums.[117] There would likely be value in identifying successful approaches and sharing them across delivery partners, and the PMT indicates this process has already started.
[114] See for example 3rd UK IP Enforcement Programme Report, 13-14 November 2018 or UNDP, Promoting a Fair Business Environment in ASEAN, Baseline Study, 30th May 2019.
[115] Prosperity fund evaluation and learning, ASEAN Economic Reform Programme Evaluation Report, Cycle 1, 2019
[116] The Q4 Quarterly report notes delays due to COVID-19 as the primary programme risk and the mitigation plan includes, “to work closely with our delivery partners to deliver the programme remotely where possible.”
[117] FCO, Draft Year 2 Q4 Quarterly Report, KIIs
# Risks
While the progress is positive, the risk to the ability to deliver and evidence all IOs during the programme lifecycle has grown over the last year. The Programme team actively monitors and reports on delivery risks in quarterly reporting. Some, but not all, of the risks noted in this evaluation have been reported by the programme team.[118]
[118] Among risks presented here that have been tracked by the Programme team are: risks about the commitment of the new Government of Malaysia and potential risks resulting from delayed and virtual launches of OECD assessment reports.
- In-house IP (ER 1.1): There is still no strong evidence that the assumptions underpinning the ToC are holding true. For example, The IPO aims for participants to attend two seminars. However, only 20 per cent of this year’s participants had participated in both the IP enforcement seminar in 2018 and the one in 2019. Data collection efforts have not yet been sufficient to produce evidence of change.
- The OECD (ER 1.3): Some of the OECD’s IOs relate to increased knowledge and skills in competition assessments. However, activities to develop capacity are not central to the project, making it difficult to see how capacity development will be supported. Additionally, there are several other initiatives taking place around competition policy assessment that may frustrate ability to attribute change. The OECD do intend, however, to conduct a survey asking persons consulted how much their knowledge and skills have changed. This may result in evidence. However, the COVID-19 mitigation approach of having a virtual launch in the Philippines means there is a risk of low response rates, similar to the survey problems experienced by the IPO. This would further the risk of lack of evidence.
- UNDP (ER 2): There is mixed evidence on the continued commitment of the Malaysian government to some programme aspects. As a result, Fair Business IO A (improved transparency and integrity policies and practices by government and business) is at risk as the new Malaysian government’s interest has become less clear.
- FSIP Islamic finance (ER 3): Implementation of the Zakat Blockchain platform (the third phase of the Zakat Blockchain work package) will not be possible before programme end date and would exceed existing funding under the FSIP Programme. As a result, it was decided that only phases 1 and 2 of the programme would be implemented. The FSIP Programme will therefore explore the potential approaches for new technologies, specifically blockchain technology, and the application of smart contracts in enhancing zakat collection, management and disbursement, but stop short of developing and testing the prototype platform.[119] This means the ability of the programme to achieve the outcome as set out in the ToC (new Islamic finance services provide new financing sources), will depend on external factors such as existing state zakat platforms. This increases the risk that outcomes may not be realised (without additional PF support).
  [119] FSIP Programme, IF Year2 WP and Budget Review 24042020, Page 2.
The programme has generally handled emerging contextual risks effectively. Undoubtedly the most significant risk, and the one that dominates the latest programme quarterly report, is COVID-19. The programme reports that, “COVID-19 has had a big impact on the delivery of the programme in quarter 4. Some activities were able to take place in January and February 2020 but then all delivery partners had to postpone planned travel and activities and re-design their programmes, either using alternative delivery methods or postponing activities until later in the year. This has been an intensive and time-consuming process, not least because everyone is working within extraordinary circumstances and the future remains uncertain.” Despite this uncertainty, the programme has effectively and actively managed the associated risk by supporting delivery partner reprogramming to move to remote delivery and supporting no-cost[120] or low-cost[121] extensions. Other contextual risks, such as the change of government in Malaysia and the temporary suspension of bilateral cooperation activities issued by the current administration in the Philippines following the resolution of the UN Human Rights Council on 11 July 2019, have also been effectively managed, through reliance on the PMs at each posting and also through the networks of the delivery partners, particularly multilateral partners.[122]
[120] UNDP, FSIP.
[121] RD/BEIS.
[122] KIIs.

# Summary of key findings
Findings arising from this cycle’s evaluation have been validated with the PMT. Each finding is presented with a discussion of its implications. Where a finding has a related recommendation, this is noted. Table 10 describes the key findings arising from this evaluation that are relevant at programme level, and are in priority order of the related recommendation, where one is made (see Section 7).
Table 10: ASEAN Economic Reform Programme Cycle 2 key findings
#	FINDING	Discussion
1	The risk that the programme will not deliver all IOs during its lifecycle has grown. In part, this is due to weakening of links between the design of some workstreams and the ToC during the FSIP re-scoping. Likewise, the linkages between ER 1.2 outputs and outcomes remain uncertain. The PMT lacks internal subject matter expertise on inclusive finance, and the time available to apply the financial markets subject matter expertise within the programme team, to support the management of FSIP re-design proposals and to ensure alignment with programme goals.	The PMT has tended to use ToC as a compliance document, rather than a management tool. In part this is due to the number of management and reporting tools and systems the programme team is juggling. This is also partly due to the ToC being a relatively novel approach for many in the FCO (as compared to DFID, where use is common). Added support for PMTs in inclusive finance and in designing and using the ToC may support better, active design and management toward outcome level results. / See recommendation 1
2	The PMT has made considerable efforts to improve approaches to G&I at strand level over the past year, with a focus on the FSIP Programme. In terms of level of ambition, the realities of delivery have driven a minimum standards approach to G&I, centring on gender-equitable participation, across most of the programme. There is large variation across programme strands and suppliers on G&I in terms of levels of engagement, capacity, ambition and results, with UNDP the most successful. The AER Programme has been disadvantaged by being one of the earlier PF programmes to start, with more guidance and tools available now than there was during inception.	Given the programme was disadvantaged by not having access to the now standard G&I tools, a minimum standards approach is reasonable. However, this approach could be combined with measures to further incentivise programme components to seek and take opportunities to exceed minimum standards, and increase impact. Access to and use of G&I tools at inception should be pursued in the event of an additional round of funding. It could also be beneficial to contract specialist external support on G&I in the specific sectors in which the programme is working, to inform the design of a subsequent phase of programming. Other relevant resources are planned EL products, including a sector report on financial inclusion and G&I case studies. / Future procurement exercises would benefit from integrating careful assessment of the G&I expertise of potential deliver partners into the evaluation of bids. Integrating G&I-related requirements and expectations into contracting mechanisms and budgets from the outset could help set clear expectations for DPs and provide the PMT with leverage when requirements are not met. / See recommendation 2
3	Awareness of the lessons and recommendations among delivery partners was low, with some noting changes that likely arose from recommendations, but not the associated learning. This is particularly true for the delivery partner country teams who sit at the point of service delivery. Some AER PMs felt the Cycle 1 evaluation lacked relevance because the sampling had not occurred in their countries.	A deliberate evaluation dissemination plan would better support cross-programme learning and penetration into delivery partners, in order to capitalise on the learning and reflection opportunities an evaluation and/or review process brings. This would be most effective if it includes delivery partners in some way, such as through dissemination of case study learning products. / See recommendation 3
4	While the logframe revisions at strand and programme level are not yet complete, review of the drafts and completed ones suggest that the programme will struggle to evidence how delivered capacity enhancement is being “embedded”[123] in the recipient organisations.	Despite the number and diversity of monitoring tools used, the programme currently lacks a way to develop qualitative evidence of how change is becoming embedded that would be useful for making a case for future funding. Addressing this shortfall will also support the needed evidence base to manage for results. / See recommendation 4
5	Having completed a troubled inception period and re-scoping process, PwC is now delivering a much-improved FSIP Programme. This has been greatly aided by the disproportionate focus of programme management, whose capacity has been increased.	Management of commercial partners, either due to mis-aligned incentives or due to complexity of contractive processes, has meant the resources needed to oversee and manage the delivery are higher than for other types of delivery partners (cross-government, multilateral), and programmes should plan and budget for this requirement. / FCO Singapore should also consider whether a more simplified delivery approach, with fewer delivery partners, would be more effective in the event of an additional round of PF funding.
6	While many Cycle 1 evaluation recommendations were implemented, some were not taken up by the PMT. All Annual Review recommendations were acted upon. In part this was due to staff turnover around the time of the evaluation, and in part due to the existence of a management response for the Annual Review but not the evaluation, as the PF management response template was not yet in place at the time of the Cycle 1 evaluation. Uptake of evaluation recommendations improved as the programme began reporting on progress in quarterly reports.	Inclusion of a management response process greatly improves the likelihood of recommendation uptake and integration into regular reporting helps support completion.
[123] The meaning here is: passed on to other staff members and becoming part of regular practice.

# Recommendations
The evaluation approach included co-creation of recommendations with the PMT in a virtual workshop setting.[124] The PMT has also had a chance to reflect, review and comment on the recommendations. The recommendations are presented in Table 11 in order of priority, as discussed with the PMT. Recommendations that are connected to the evidence collected, productive in terms of making a positive impact on the remainder of the delivery cycle and reasonably actionable for the PMT have been prioritised. The individual case study learning products also include recommendations that the PMT should consider. However, only those recommendations elevated to this evaluation report require a management response, in alignment with the JFU’s publication policy.
[124] See Section 3 for further discussion of the tools and approach used.
Table 11: ASEAN Economic Reform Programme Cycle 2 evaluation recommendations
FINDING	RECOMMENDATION	LEAD	TIMEFRAME
1. Use of the ToC as an active design and management tool and need for added support to manage increased delivery risk	Consider adding sense-check of new FSIP proposals to confirm alignment with the AER Programme ToC as a routine element in the approval process. / Consider engaging support via the EL service, or elsewhere, in shoring up inclusive finance aspects of the FSIP Programme and developing a better understanding of the change pathways.	Head of Programme	Prior to Q3 2020-21
2. G&I and the need to combine ensuring minimum standards are met with taking opportunities to exceed minimums when presented.	Ensure that PF minimum standards (as set out in the G&I scorecard) are met across the programme. / Reconnect with the allocated UK government Social Development Adviser for support with implementing minimum standards as needed. / Document lessons learned from strands and activities that are seeking to exceed minimum standards through targeted work on G&I-related issues to inform a subsequent phase of programming. / Support via added learning support on financial inclusion and sharing of best practice on how to implement successfully. (see also recommendation 3, below).	Head of Programme	Immediate and through the programme delivery lifecycle
3-Need for evaluation dissemination and maximising the usefulness of evaluation and other learning products.	Plan and execute an evaluation dissemination plan in coordination with EL, based on the evaluation findings and AER management response. Consider including delivery partners in the dissemination and using the case studies to support strand-level learning.	EL and Head of Programme jointly	Within 2 months of final evaluation approval
4-Need for qualitative evidence of change to support adaptive management, learning across strands and making a solid, evidence-based case for future funding.	To better track effectiveness, consider ensuring delivery partners’ monitoring systems extend beyond the quantitative logframe indicators to also determining whether new practices and capacities are becoming embedded and resulting in the desired outcomes. Note that this was also a Cycle 1 recommendation and remains relevant.	Head of Programme and delivery partners	Prior to Cycle 3 evaluation

# Lessons
In addition to evaluation findings and recommendations specific to the programme, the evaluation process also identified select lessons of relevance to the programme, the Fund, the FCO and the development community more broadly. These are detailed in Table 12 below.
Table 12: Lessons
#	Lessons
1	G&I-related analysis conducted during design phases will not necessarily translate into implementation, unless G&I is made visible in programme management processes, including quarterly reporting. / For global or regional programmes, there may be more entry points to address G&I-related barriers and opportunities substantively at the national level. Consultations to inform programme design should include informants who are positioned to provide insights on G&I-related barriers and opportunities in specific sectors or issues. / Procurement exercises benefit from integrating careful assessment of the level of G&I expertise, and not just the level of ambition, committed to programmes by delivery partners into the evaluation of bids.
2	Systematic quantitative and qualitative evidence is necessary to assess the effectiveness of individual projects underneath the AER Programme. The quality of annual evaluations relies on the quality, quantity and completeness of evidence collected and analysed by implementers. Annual evaluations can supplement but cannot replace the ongoing monitoring by implementers. Logframes are not an adequate tool for this. Programmes should therefore seek support from their implementing partners in longer-term observation of participants, particularly in capacity-enhancement activities.
3	To ensure accountability and transparency, a management response to all evaluation recommendations, publication of the findings and monitoring of implementation of any resulting actions are crucial. As such, it is useful to include these as metrics in the Annual Review and/or subsequent evaluation processes. The PF publication policy does require management response and publication, but as observed in this evaluation, the policy only took effect after the Cycle 1 evaluation. It is natural for the Fund to have evolving practices, but reinforcing the policy through inclusion in review and evaluation practices will help programmes maximise the value of evaluations, even if policies shift over time.

: Gender and inclusion approach and analysis
Introduction to the gender and inclusion approach and analysis
In Cycle 2 the AER Programme evaluation has sought to understand what progress has taken place on integrating G&I considerations into programme design and delivery. Specifically, it answers programme evaluation question 10.1:
“In what ways has the programme design or implementation changed in relation to gender responsiveness/inclusion at programme and project levels?”
The primary tool used to inform data collection and analysis is the G&I scorecard (revised version developed by the JFU in May 2020), which measures whether programmes are meeting PF minimum standards on G&I and provides a framework for interrogating key dimensions of programmes – design, government capability and incentives, accountability, financial resources, delivery partners and results.
However, the analysis presented below extends beyond the scorecard requirements in order to answer programme evaluation question 10.1 fully, with a focus on changes made in Year 2 which relate to gender responsiveness and inclusion, and the expected results of those changes (including examples of good practice, challenges and learning generated and/or applied since the Cycle 1 evaluation).
This annex provides a brief overall assessment of G&I-related issues in the design and implementation of the AER Programme, before presenting the completed G&I scorecard for Cycle 2.
Scorecard
Table 13 below provides an overview of AER G&I scorecard ratings for Cycle 2. A RAG rating of ‘green’ indicates that the programme meets PF G&I minimum standards for the dimension in question; ‘amber’ means it is either not clearly aligned with PF G&I policy minimum standards, with areas for development, or is unable to provide evidence; and ‘red’ means it fails to meet PF G&I minimum standards.
Table 13: ASEAN Economic Reform Programme gender and inclusion scorecard (Cycle 2)
Design	Internal capability and incentives	Accountability	Financial resources	Delivery Partners	Results	OVERALL SCORE

### Design
The primary focus of G&I-related efforts across the programme is gender-equitable participation in activities. Several of the G&I-relevant analyses conducted in inception have not translated into delivery. Post-inception there appears to be a lack of analysis of gender-specific barriers and opportunities, as they relate to specific interventions and country contexts, which could be used to inform activities. Where there have been attempts to move beyond participation to identify and address G&I-related barriers and opportunities, these have had limited success (see sub-sections on ER 1 and ER 3 below). UNDP is the exception, implementing both targeted interventions and mainstreaming gender considerations across project components.
The programme has been somewhat disadvantaged by being one of the earlier PF programmes to start in that more limited guidance was available at the time of inception. As a result, the AER Programme has not employed design tools that are now commonly used, including programme-level G&I action plans. With most strands now nearing the mid-point of implementation, it may be too late in the programme to derive significant value from developing a programme-level G&I action plan. Nevertheless, it is important that the programme seeks to meet other minimum standards in Year 3 (see the ‘Recommendations’ section)
### Economic reform 1
The implementation of ER 1.1 has focused on gender-equitable participation rather than substantive consideration of G&I-related issues. Delivery partners appear to be strongly incentivised by targets on ensuring at least numerical equality of participation of women and men in, for example, meetings and workshops.[125] In-house IP has also interrogated the causes of unequal participation where this has occurred; for instance, enquiring about possible barriers to women’s attendance following regional workshops where women from some countries were better represented than others.[126] In-house IP has also sought to include senior female speakers (although mostly from the UK) in events as visible role models.[127] There has, however, been some resistance to gender-equitable participation where this is not perceived to get the right people in the room, i.e. secure the attendance of those needed to facilitate effective discussion of the topic on the agenda.[128] This highlights the limitation, in isolation, of participation-focused approaches which do not address problems in the wider enabling environment.
[125] KIIs.
[126] Ibid.
[127] Ibid.
[128] Ibid.
It is worth noting that there may be relatively limited scope to move beyond participation to the integration of G&I-related issues, given the nature and regional focus of interventions being pursued under ER 1.1. Milestone reporting for the FSIP work package to develop an IP enforcement manual notes that the “risk mitigation activity for this work package includes discussions and consultations with ASEAN to align on GESI priorities” but that following discussion with ASEAN the project concluded that there is no scope to integrate G&I-related issues into manuals, which set out only countries’ laws and procedures on IP enforcement. The delivery partners instead propose to “add a section on G&I-related issues to manuals for Indonesia, Vietnam and Philippines, which include additional commentary in addition to the laws,” suggesting that there may be more scope to integrate G&I-related issues at country level.[129]
[129] FSIP, Milestone report: IP enforcement manual.
Under ER 1.2, RD International and the Office for Product Safety and Standards have developed a high-level gender strategy for PF projects, which focuses on gender mainstreaming in MREL activities, as well as a review of key issues, evidence of what works and measurement tools for G&I in standards and regulatory reform.[130] However, there have been challenges in drawing on this evidence to inform more granular project-level analysis, which might inform design of activities. RD International intended this year to identify gender-specific regulatory barriers through consultation, but the G&I-related findings of those consultations were too general (for example, issues relating to women’s labour force participation and access to finance) to inform ER 1 activities.[131] It is possible that this exercise could have been more productive had the project identified stakeholders and CSOs with specific relevant expertise and/or invested more time in developing participants’ capacity to respond on the kinds of issues of interest to the project.
[130] RD International Gender Strategy.
[131] KIIs.
Similarly, under ER 1.3, there does not appear to be any coverage of G&I-related issues in the OECD competition assessments produced by the project.
### Economic reform 2
G&I is integrated most meaningfully into design of the ER 2 strand, through both targeted interventions and mainstreaming of gender considerations in other project components. G&I-related work under ER 2 is foregrounded primarily in regional-level interventions led by the UNDP gender team in Bangkok.
Targeted interventions focus on gender diversity in leadership and support for young entrepreneurs, and include development of learning platforms for government, private sector and civil society dialogue and related knowledge products. G&I-related issues have also been mainstreamed in project components on business integrity and responsible business conduct. This includes a study on gender mainstreaming across five dimensions of business integrity, the development of a ‘FairBiz’ hub for companies to exchange best practices in business integrity project management, which includes thematic platforms on ‘Youth & Entrepreneurship’ and ‘Diversity & Inclusion’, and plans for a session on sexual harassment and ‘sextortion’ as part of a series of webinars for the newly-developed ASEAN Judicial Integrity Network.[132]
[132] UNDP QPR, Qs 1–4 2019/20.
This work is informed by an inception phase baseline study on gender diversity in boards and senior management positions in PF-6 countries, although this evaluation was not able to determine whether this assessment is regularly revisited.
At country level the focus is mainly on gender-equitable participation. UNDP country teams did not point to in-country activities with a specific G&I lens or objectives, or earmarked funding.[133] There are two exceptions: in Vietnam, a FairBiz grant integrating business integrity into training for young entrepreneurs, and in Myanmar, advocacy campaigns on business integrity targeting women and young people.[134] ER 2 G&I-related activities and results are outlined more fully in the ‘Results’ section.
[133] KIIs.
[134] UNDP QPR, Qs 1–4 2019/20.
It is worth noting that focusing G&I efforts at regional level presents some drawbacks in terms of limitations on scope. The focus on leadership stands to benefit a relatively small group of women professionals who are unlikely to be the poorest or most vulnerable. And participants in the regional dialogue on gender-equal leadership noted in their feedback that the absence of more than a few male participants may have represented a missed opportunity to build a constituency of male support for change.[135]
[135] KIIs.
For the elements of ER 2 being implemented by CoST Thailand, the focus is primarily on mainstreaming gender, in monitoring efforts for instance (see the ‘Accountability’ section). Targeted activities on G&I focus on building internal capacity (and are examined in detail in ‘Internal capability and incentives’ section).[136] In Year 3, the CoST Thailand workplan includes a gender strategy, regardless of PF funding.[137] There is an argument that assurance activities stand to benefit marginalised groups through the resolution of community-based problems such as dust, traffic and noise (some of which may disproportionately affect women due to their domestic and caregiving roles) although this argument was not advanced by CoST staff themselves. An impact study carried out by CoST Thailand has shown that the geographical distribution of projects includes poorer areas (although this is not an explicit intention of the programme and the study does not include a counterfactual).[138]
[136] CoST Thailand, Gender Audit, finalised December 2019.
[137] KIIs.
[138] CosT Thailand, Impact Study, finalised December 2019.
Importantly, UNDP is capturing G&I-related lessons learned from experience of implementation, and adaptations made, in quarterly reporting for ER 2. On business integrity and sustainable practices, for example, the project has shifted its approach from promoting anti-corruption compliance to building collaborative and innovative ecosystems. G&I-related issues are integral to examples cited of this new approach, including the launch of a network of companies and stakeholders promoting gender-equal leadership and the training of young entrepreneurs on business integrity. Lessons are also being generated by relevant multi-country research on gender-equal leadership in the workplace.[139]
[139] UNDP QPR, Qs 1–4 2019/20.
### Economic reform 3:
The PMT has made considerable efforts to support improvements to the FSIP Programme over the past year, primarily through the development of a gender plan, one of several documents the PMT requested that PwC develop to support the close of the inception phase.
The July 2019 Annual Review assessed that the FSIP approach to G&I “remains conceptual rather than integrated within the design of interventions for a higher impact. The robust country gender scoping assessments do not seem to have shaped nor informed the FSIP Programme strategy intervention focus or the proposed workstreams for implementation…despite having dedicated sections on gender and inclusion for each programme strand (IP, fintech, etc.) in the strategy”. Accordingly, the Annual Review recommended that the PMT oversee recovery plans for the FSIP workstrands, including the meaningful integration of practical G&I dimensions.[140]
[140] Annual Review of the AER Programme, 2018/19.
PwC conducted a ‘rapid assessment process’ to formulate a GESI plan which was intended to assess potential risks to ‘do no harm’ and develop risk-mitigation strategies, as well as identify strategic opportunities aligned with the current work packages to advance gender equality and social inclusion. In December, PwC recommended six G&I focus areas to be integrated into the programme’s delivery (although it is possible that the plan overestimated the level of ambition i.e. scope for transformation, offered by those opportunities).[141]
[141] FSIP, DRAFT Gender Equality and Social Inclusion Plan, April 2020.
However, recovery efforts have taken longer than expected, with five iterations of the plan developed over a period of six months.[142] There has also been a reduction in the level of ambition during this process (i.e. since the December version), with the most recent (April 2020) version dealing only with minimum standards, as the programme lacks the budget to pursue the strategic opportunities identified.[143] Minimum standard activities identified focus mainly on ensuring gender-equitable participation in, for example, consultations, workshops and committees. For some work packages, planned minimum standard activities go beyond gender-equitable participation by seeking to address G&I-related issues – for instance, under the capital markets component, steps to improve the collection of relevant data to inform risk-monitoring decision making, and, under the fintech component, consideration of challenges faced by marginalised groups in the drafting of responsible regulatory policies and regulations for peer-to-peer lending and crowdfunding.[144]
[142] KIIs.
[143] FSIP, DRAFT Gender Equality and Social Inclusion Plan, April 2020; KIIs.
[144] FSIP, DRAFT Gender Equality and Social Inclusion Plan, April 2020.
The Islamic finance component is the set of work packages for which minimum standard activities appear to have been most thoroughly thought through in the GESI plan. It is also the only set of work packages to refer to groups other than women in relation to specific activities, including people with disabilities, those with poor mental health and the elderly.[145] However, in practice, implementers appeared to assume that the work package that will move forward to implementation – a pre-emergency fund – will inherently provide benefits to the most vulnerable and marginalised due to the nature of the intervention. The fund would benefit, for example, those with the lowest incomes, female-headed households, people with disabilities, etc. owing to norms around the distribution of funds through Islamic financing instruments.[146] However, the evaluation did not identify how implementers intend to ensure G&I-sensitivity in delivery, for example through selection criteria and/or identifying specific needs, vulnerabilities and barriers to access.
[145] Ibid.
[146] KIIs.
Challenges encountered during the development of the FSIP Programme gender plan (particularly budgetary constraints) result, at least partly, from a lack of practical integration of G&I issues into programme design and contracting from the outset. The fragmentation of the FSIP Programme structure, workstreams and budgets also poses a challenge in this context. At the time of writing, the gender plan has not yet been formally approved.[147]
[147] KIIs.
### Internal capability and incentives
Both the Head of the AER Programme and Head of the Prosperity Fund (FCO Singapore) are G&I champions, who attend network meetings regularly and have presented to the network on their experience of supporting the development of the FSIP GESI plan. They also plan to engage delivery partners in the network (having previously invited UNDP to present, although this did not take place due to staff illness).[148]
[148] Evaluation sensemaking workshop, 29 May 2020.
In terms of PMT efforts to build capacity across the programme, the PF Regional Forum held in November 2019 included a training session on G&I, which explored PF G&I requirements and practical examples of best practice. All FCO PMs and delivery partners were present during the workshop. The PMT point to the decision to make G&I the opening session of the forum as evidence that the programme has worked to centre G&I in its design and delivery. The PMT has since discussed G&I with delivery partners during monthly calls, encouraging them to view all activities “through a G&I lens”.[149] According to the PMT, the improvement of the FSIP GESI plan provides some evidence that G&I was being taken more seriously. There is also evidence of FCO PMs (at Post) proactively addressing G&I when opportunity arises – with the PM in Thailand, for example, asking how FSIP will integrate G&I into the re-design of terms of reference (ToRs) on electronic ‘know your customer’ checks and cyber-security.[150]
[149] VfM scorecard, AER Programme Cycle 2 evaluation.
[150] Ibid.
There is some evidence that the PMT has drawn on government expertise at strategic points, having, for example, received support and advice from the centre on the development of the FSIP GESI plan.[151] As noted under ‘design’, the programme has been somewhat disadvantaged by being one of the earlier PF programmes to start, with the PMT noting that the guidance and support now available was not on offer at the time of programme design. One implication of this is that there has been ‘push back’ to the PMT on the part of some delivery partners on, what they see as, the impracticality of building in and mainstreaming G&I-related issues retroactively. While G&I was integrated effectively into programme statements of requirements, it is not referenced in contracting mechanisms, which the PMT reflects has left them without contractual levers with which to respond to resistance.[152]
[151] KIIs.
[152] Ibid.
The PMT acknowledge that they could do more to incorporate G&I-related issues into the programme, but note that “this will need support, and some good strong examples of ways in which financial services and intellectual property programmes can practically incorporate G&I into their programme planning”.[153] Indeed, this evaluation has found that a key challenge for the PMT has been capacity to provide tailored, sector-specific advice on suggestions to delivery partners on G&I. The PMT did draw heavily on the technical advice and support provided by the Prosperity Fund Department, with the Social Development Adviser playing a key role in advising on the FSIP Gender Plan. However, more tailored advice could be accessed to help going forward. The evaluation recommends that the PMT review a sector report on financial services which is due to be produced by the PF EL team in June and will include a G&I section. The PF EL team will also be producing two G&I case studies this year (subject matter yet to be selected) to support cross-PF learning, which will explore G&I-related challenges experienced by programmes and how programmes have responded to them. A future PF programme could include a call-down contract for specialist external support on G&I in the specific sectors in which the programme is working.
[153] VfM scorecard, AER Programme Cycle 2 evaluation.
### Accountability
The AER Programme is in the process of finalising some strand-level (i.e. delivery partner) logframes and therefore the programme-level logframe. Until logframes are finalised, it is difficult to state definitively that the programme is disaggregating its data reporting sufficiently (by sex as a minimum) and consistently across workstreams. The PMT noted that there has been resistance on the part of some delivery partners to integrating targeted G&I or disaggregated indicators. To meet PF minimum standards, and progress to a green RAG rating over the coming year, the programme must also improve reporting templates to include reporting against logframe indicators and milestones (both quantitative and qualitative). Evidence on stakeholder engagement is more limited, although the evaluation has identified positive examples of engagement with civil society under ER 2 (discussed below).
### Economic reform 1
The RD BEIS logframe indicates that all output level indicators (e.g., on numbers of officials trained) are sex and age disaggregated[154] but these numbers (disaggregated or otherwise) do not appear to be reported in QPR to the FCO.[155] The OECD logframe disaggregates by sex the number of stakeholders met during fact-finding missions but not the proportion of relevant stakeholders with whom an interaction has occurred.[156] Again, the OECD does not appear to report on these indicators in QPR. Neither the RD/BEOS nor the OECD logframes include G&I targeted indicators.[157]
[154] RD/BEIS/ER 1.2 strand logframe.
[155] RD/BEIS QPR Qs 1-4 2019/20.
[156] OECD/ER 1.3 strand logframe.
[157] OCED QPR Qs 1-4 2019/20.
### Economic reform 2
ER 2 is the only strand with a logframe that mainstreams G&I throughout. It does this through:
- an output statement that refers directly to engagement with women and under-represented groups (Output 1: Partnerships fostered between public and private sectors, and civil society including women and under-represented groups)
- targeted G&I indicators (3.1: “[number] of companies engaged in dialogue on gender and inclusion through participation in project platforms” and 3.3 “[number of] knowledge products developed to inform multi-stakeholder dialogue [to include…gender]”)
- mainstreaming of sex-disaggregated indicators on participation and, importantly, results for participants (1.3 “[number of] stakeholders engaged through the regional platforms” and 1.2 “[percentage] of involved stakeholders reporting feeling more comfortable on dialogue on integrity and transparency with counterparts following participation in the platforms”).[158]
  [158] UNDP/ER 2 strand logframe.
Under output 2 – that is, work delivered by CoST Thailand – output indicators are likewise sex-disaggregated (2.3 “[number] of stakeholders involved in procurement monitoring of infrastructure projects’) or refer to targeted G&I-related activities (2.4 “[number of] interventions conducted to analyse and promote women’s inclusion in transparent public procurement processes” with milestones including a gender audit in Year 2 and the development of two related pieces of guidance in Year 3). In addition, in March 2020 a new intermediate-outcome-level indicator for CoST related to output 2.4 was added to build on progress achieved in Year 2 (“CoST West Lombok and CoST Thailand uses the guidance developed by the CoST International Secretariat to promote and increase the participation of women by the end of Year 3”).[159] This represents an increased level of ambition on G&I for this part of the programme.
[159] Ibid.
Unlike other delivery partners, UNDP is reporting on these indicators in its QPR to the FCO.[160]
[160] UNDP QPR, Qs 1–4 2019/20.
UNDP is necessarily engaging with relevant stakeholders through targeted G&I-related activities at regional level (see the ‘Design’ section and the ‘Results’ section). At country level, the evaluation identified an important intangible outcome not captured in regular reporting: engagement with Malaysian CSOs championing gender issues through the development of a national network of CSOs affected by governance issues.[161]
[161] KIIs.
### Economic reform 3
The FSIP Programme ToC includes “gender-equality and socially inclusive (GESI) work package designs” as a cross-cutting activity.[162] The logframe therefore does not require sufficient data to be collected to create, evidence and test G&I-related pathways from outputs to impact. At the time of writing, the PMT is in discussions with PwC about strengthening logframe indicators relating to G&I.
[162] FSIP Theory of Change.
### Financial resources
The VfM scorecard assesses quality of evidence on equity of programme design and approach to be ‘good’ and progress/direction of travel in Cycle 2 as ‘adequate’. The content of the VfM scorecard on equity speaks primarily to the section of this G&I scorecard on internal capability and incentives and so has been included above.[163]
[163] VfM scorecard, AER Programme Cycle 2 evaluation.
The AER Programme does not have a programme-wide VfM strategy. The PMT has, however, invested considerable effort in supporting the FSIP Programme to develop a VfM plan, as one of the set of documents requested by the PMT to close FSIP’s inception phase (as described under ‘design’ above). Although still in draft form, this plan integrates three equity indicators. The first two are process-oriented: “[percentage] of outputs applying minimum GESI requirements” as set out in the GESI plan (with a target of 100%) and “[percentage] of relevant workstreams that complete their respective strategic opportunities outputs” (again with a target of 100%). (As noted in the ‘Design’ section above, in practice FSIP lacks the budget to pursue strategic opportunities identified.) The third indicator usefully commits the project to generating “evidence GESI process has evolved as a result of lessons learned or programme adaptations”.[164] Lesson learning could be facilitated by expanding quarterly reporting templates (which are apparently currently being reviewed by the PMT) to include reporting of G&I-related lessons, and drawn upon to inform a subsequent phase of programming.
[164] FSIP DRAFT VfM Plan.
It is worth noting that some of the issues noted under ‘design’ above may limit the VfM offered by the programme on G&I. These limitations include ineffective consultation on G&I issues related to regulatory reforms under ER 1 and inadequate budgets to pursue G&I-related opportunities under the FSIP Programme (ER 1.1 and ER 3)
There is large variation between delivery partners in terms of levels of understanding and engagement on G&I. In spite of the limitations noted in the ‘Design’ section above, UNDP is the standout, with the ER 2 workstream appearing to draw on quality in-house expertise to integrate both targeted activities and effective mainstreaming (again, as indicated in the ‘Design’ section above). The high turnover of staff and consultants with G&I expertise appears to have been a challenge this year for delivery partners implementing the ER 1 and ER 2 workstreams. A lesson for any future procurement is that careful assessment of the G&I expertise of potential delivery partners should be integrated into bid evaluation.
### Economic reform 1
In the past year RD/BEIS brought in a staff member with relevant expertise from their London team to provide support on G&I-related issues. However, this individual has since moved on and RD/BEIS are now considering whether to bring in someone independent to support them.[165]
[165] KIIs.
### Economic reform 2
UNDP regional is very well-placed in terms of in-house G&I expertise, resulting in the mainstreaming of a comprehensive approach to gender throughout their work (see the ‘Design’, ‘Accountability’ and ‘Results’ sections). From the limited sample, there is some evidence that capacity on G&I at country level may be more uneven, with national staff or partners not always able to comment on outcomes of their engagement with relevant regional activities.[166]
[166] KIIs.
The gender audit conducted by CoST Thailand represents a major milestone in the organisation’s development of G&I-related capacity. Carried out to a high standard in-house by the CoST Policy and Advocacy Adviser, the audit assessed levels of gender equality in CoST Thailand’s staffing as well as gender mainstreaming in implementation. Finalised in December 2019, the audit’s main findings are as follows:[167]
[167] CoST Thailand, Gender Audit, finalised December 2019.
- Women’s representation is high, with an average of 50 per cent female participation across CoST Thailand bodies. In qualitative terms, women professionals reported an equal level of participation and weight in decision making within the programme.
- The staff responsible for CoST Thailand perceived both the Comptroller General Department within the Thai Ministry of Finance and the Anti-Corruption Organisation of Thailand (the two organisations responsible for employing staff who deliver the programme) to offer gender-equal access and opportunities. According to interviewees, decisions relating to hiring, retention, promotion and training of professionals involved in CoST work, as well as allocation of workload, are not influenced by gender.
- The level of gender awareness identified amongst those involved in the CoST Thailand programme was high (i.e., staff and consultants interviewed shared a common perception that men and women have equal roles in society and the workplace).
- Gender obstacles and ‘glass ceilings’ were not reported by interviewees, although a minority cited difficulties managing work and family responsibilities.
- A point of concern was identified in relation to low female representation and engagement in public hearings which form part of the assurance process. An impact study carried out in parallel also found that: “a potential drawback … relates to the lack of gender diversity in the public forum sessions led by CoST assurance team, which can reinforce old gender stereotypes already ingrained in the sector.”
The audit recommended that CoST Thailand develop a gender strategy as well as a system capturing gender representation across all CoST bodies, re-design public hearings to improve women’s participation and conduct annual gender reviews.[168] As no assurance activities have been held since the completion of the audit, there is no evidence as yet of the implementation of public-facing recommendations, but the Year 3 workplan includes the development of a guidance note on gender for CoST members and a new logframe indicator has been added to monitor improvements in women’s participation.
[168] Ibid.
The gender audit has also had important spill-over effects (i.e., unintended positive outcomes), as the first of its kind not only within CoST Thailand but across the entire CoST programme. The audit provides recommendations at the global level to inform the next business plan of the CoST International Secretariat and improve the delivery of gender-inclusive infrastructure (by, for example, identifying gender-focused organisations that could provide strategic advice to CoST).[169] As UNDP’s QPR observes, it is a “great achievement to see that a gender audit commissioned by UNDP in Thailand may have ripple effects throughout the countries where CoST projects are implemented”.[170]
[169] Ibid; KIIs.
[170] UNDP QPR, Qs 1-4 2019/20.
### Economic reform 3
The 2019 Annual Review reported that, under FSIP, “a new delivery team is now in place with a commitment to improve quality of design work and embedding gender and inclusion as a golden thread in their delivery approach”.[171] However, there have also been staffing changes during the past year, with the onboarding in Q4 of two new Gender Experts, suggesting that turnover of staff focused on or with expertise in G&I is high.[172]
[171] Annual Review of the AER Programme, 18/19.
[172] FSIP QPR, Q4 2019/20.
In November 2019, the FSIP GESI Lead led training introducing the GESI Framework and Rapid Assessment Process to project teams. Training had the immediate objective of providing a common language and approach for evaluating G&I risks and opportunities, and longer-term aim of equipping the team with a deeper understanding of G&I issues as they relate to their work.[173] This evaluation has not, however, been able to seek feedback from project teams on the quality, usefulness and application of learning from this training.
[173] KIIs; FSIP QPR, Qs 1–4 2019/20.
The evaluation identified evidence that some project teams have also sought and received support from PwC London on G&I, but that support provided was not always sufficiently informed about and sensitive to local context and G&I dynamics.[174]
[174] KIIs.
### Results
### Economic reform 1 and 3
For both ER 1 and ER 3, G&I-related results are not being regularly reported given the content of logframes and QPR, making it challenging to assess results achieved over the past year (other than process-related progress already outlined in the ‘Design’ section). Risks related to G&I and ‘doing no harm’ have not been included in risk monitoring and mitigation set out in QPR for either workstream.
### Economic reform 2
The ER 2 workstream has had considerable, and by far the most, success in delivering G&I-related results over the past year, primarily at regional level where interventions focus (as discussed in the ‘Design’ section) on gender diversity in leadership and support for young entrepreneurs, but also, albeit to a more limited extent, at country level – through, in Vietnam, a FairBiz grant integrating business integrity into training for young entrepreneurs and, in Myanmar, advocacy campaigns on business integrity targeting women and youth.[175] The ‘green’ RAG rating given for ‘results’ in the G&I scorecard reflects results achieved under ER 2. Table 14 outlines progress made and results achieved under ER 2 to the end of Year 2, as well as relevant plans for implementation in Year 3.
[175] UNDP QPR, Qs 1–4 2019/20.
Table 14: Gender and inclusion-related progress made and results achieved during the past year[176]
[176] Ibid.
OUTPUT	RESULTS AGAINST G&I-RELEVANT INDICATORS	OTHER G&I-RELATED ACTIVITIES AND PROGRESS
1: Partnerships fostered between public and private sectors, and civil society including women and under-represented groups	Output Indicator 1.1 – Number of learning and knowledge platforms for Government –private sector and civil society policy dialogue. / Year 2 target surpassed. 8 cumulative from Year 1, including young social entrepreneurs (21–23 August 2019) and gender-equal leadership dialogue (29–30 August 2019). / Output Indicator 1.2 – percentage of involved stakeholders reporting feeling more comfortable on dialogue on integrity and transparency with counterparts following participation in the platforms (disaggregated by gender). / Year 2 target surpassed. 88.3% of questionnaire respondents participating in the regional dialogues reported this. / Note: This data will be disaggregated by sex from Q1 2020/21. / Output indicator 1.3 (introduced in March 2020) – number of stakeholders engaged through the regional platforms (sex-disaggregated and sector-disaggregated). / Year 2 target surpassed. 602 stakeholders engaged in regional dialogues (of which 48 per cent are women).	FairBiz engaged companies in ASEAN on issues related to women’s leadership and participation in boards and at senior management level. Priorities identified by countries for the coming year include, in Indonesia, training of suppliers with a focus on small and medium-sized enterprises and women-owned business. / Advocacy and communications: In Myanmar, in response to the Anti-Corruption Commission’s request, UNDP is developing a national multi-media campaign to increase public awareness on anti-corruption and business integrity with emphasis on participation of women, youth and other vulnerable groups, to be produced and aired between April and September 2020. In Thailand, UNDP launched a campaign to raise awareness among young entrepreneurs on business integrity under the theme “2020 New Year’s Resolution for Responsible Business”.
2: Public procurement systems strengthened through transparency and open contracting tools	Output Indicator 2.3 – number of stakeholders involved in procurement monitoring of infrastructure projects (disaggregated by gender). / Year 2 target surpassed. In Thailand in Years 1 and 2, 408 stakeholders were engaged in workshops and events, including the ‘Train the Trainers for Comptroller General’s Department officers’ in nine regions, across all of which an estimated 80 per cent of attendees were women. In Indonesia in Years 1 and 2, 116 stakeholders were engaged in CoST activities, with nearly 40 per cent of attendees being women. / Output Indicator: 2.4 (revised in March 2020) – number of interventions conducted to analyse and promote women’s inclusion in transparent public procurement processes. / Year 2 target achieved. The first intervention consisted of a gender audit of the CoST programme in Thailand, which provided recommendations that can be applied at a global level.	N/A
3: Business integrity and sustainable practices promoted for private companies and state-owned	Output Indicator 3.1 (revised in March 2020) – number of companies engaged in dialogue on G&I through participation in project platforms. / (Previously: Regional network of companies established promoting G&I) / Year 2 targets surpassed. / A regional dialogue on gender-equal leadership was held on 29 –30 August 2019, with 20 participating companies and business associations from ASEAN countries. / Output Indicator 3.3 – number of knowledge products developed to inform multi-stakeholder dialogue / Year 2 target surpassed. Six (two regional + four country). Regional knowledge products developed to inform multi-stakeholder dialogue included ‘Good Corporate Governance and Gender Diversity in ASEAN’. Country-level studies included ‘Engendering Business Integrity’ (in Indonesia).	Through the Regional Dialogue, UNDP launched a network of companies interested in championing gender equality in leadership positions. / Business integrity and responsible business conduct initiatives at the country level are progressing including, in Indonesia, completion of a study on gender mainstreaming in the five dimensions of business integrity, titled “Engendering of Business Integrity”. / In January 2020, implementation of the FairBiz Grants awarded at the end of 2019 began including, in Vietnam, contracting with partners for integration of business integrity training into business development/incubator programmes for young entrepreneurs. / 33 young social entrepreneurs who participated in the workshop “Business Integrity and Responsible Business Practices in the Start-up Ecosystem in ASEAN” (21–23 August 2019) co-created a Business Integrity Toolkit to guide young entrepreneurs in managing risks and opportunities, keeping their business in order and working collectively for business integrity. / A strategy on private sector engagement through FairBiz has been developed, which envisaged the creation of a Business Integrity Hub for the exchange of learning and best practices in business integrity project management, structured in “thematic platforms” to include: Youth & Entrepreneurship and Diversity and Inclusion (which expands a gender platform launched in 2019). / A multi-country research project has been launched to develop an advocacy report on factors that promotes gender-equal leadership at the workplace, including good practices and enabling factors in Indonesia, Malaysia, the Philippines, Thailand and Vietnam.
4: Anti-corruption policies and redress mechanisms improved in target countries	None	Plans for a series of webinars for members of the Judicial Integrity Network in ASEAN to be held between May 2020 and September 2021, including a webinar on “addressing sexual harassment and sextortion in the broader context of gender equality in the judiciary”.

UNDP documentation demonstrates effective mainstreaming of G&I-related issues in programme management, including risk monitoring and management. A social and environmental screening – including ‘do no harm’ considerations, high-level identification of G&I-related issues (for example, corruption and ‘sextortion’) and a commitment to engage with grassroots women’s organisations – was signed off in October 2019.[177] CoST has a safeguarding policy in place to ensure that the programme “do[es] no harm”, which, referencing gender and marital status, includes steps to ensure non-discrimination in public outreach activities and a grievance procedure for participants.[178] (The gender audit recommends that a webinar on this policy be delivered to CoST member secretariats.[179])
[177] UNDP Social and Environmental Screening, finalised October 2019.
[178] CoST Thailand, Gender Audit, finalised December 2019.
[179] Ibid.
The two most recent quarterly reports for ER 2 identify as a programme risk, “keeping the momentum generated by the Fair Business Lab and Gender Equal Leadership Lab to support dialogue with business sector on sustainable business practices and business integrity,’ as well as appropriate mitigation measures: “Working with champions and with young entrepreneurs has been identified as the best solution to generate tangible impact and create long-lasting partnerships with selected business sector representatives”.[180]
[180] UNDP QPR, Qs 1–4 2019/20.
Lessons
The table below summarises the main evaluation findings on G&I and related lessons.
Table 15: Gender and inclusion-related lessons
FINDING	LESSON	RELEVANT AUDIENCE
The PMT has made considerable efforts to improve approaches to G&I at strand level over the past year, with a focus on the FSIP Programme.	G&I-related analysis conducted during design phases will not necessarily translate into implementation, unless G&I is made visible in programme management processes, including quarterly reporting.	PMT, delivery partners
In terms of level of ambition, the realities of delivery have driven a minimum standards approach to G&I, centring on gender-equitable participation, across most of the programme.	A minimum standards approach is acceptable under the PF. When combined with seeking and taking opportunities to exceed minimum standards, as they arise, a minimum standards approach can still be impactful. With this in mind, the programme could focus in year 3 on (i) ensuring minimum standards are met across all programme strands and (ii) on gathering G&I-related evidence and lessons from strands and interventions which exceed minimum standards by pursuing targeted G&I-related results (through more detailed quarterly reporting, for instance). / There may be more entry points to address G&I-related barriers and opportunities substantively at country level rather than regional level. This should be borne in mind in the design of any subsequent phase of programming. Consultations to inform programme design need to include informants who are positioned to provide insights on G&I-related barriers and opportunities in specific sectors or issues.	PMT, delivery partners
There is large variation across programme strands and suppliers on G&I in terms of levels of engagement, capacity, ambition and results, with UNDP the most successful.	Future procurement exercises would benefit from integrating careful assessment of the G&I expertise of potential delivery partners into the evaluation of bids. Integrating G&I-related requirements and expectations into contracting mechanisms (including the level of G&I expertise committed to the programme) and budgets from the outset could help set clear expectations for delivery partners and provide the PMT with leverage when requirements are not met.	PMT
The AER Programme has been disadvantaged by being one of the earlier PF programmes to start, with more guidance and tools now available than was the case during inception.	As noted above, a minimum standards approach is reasonable, particularly given the programme’s disadvantaging lack of access to now standard G&I tools. Each PF programme is allocated one of two central Social Development Advisers from whom it can call down G&I-related advice; this could be a source of support on implementing minimum standards as needed. / Access to and use of G&I tools at inception should be pursued in the event of an additional round of PF funding. It could also be beneficial to contract specialist external support on G&I in the specific sectors in which the programme is working or to draw on any Helpdesk support that might be available at that point, to inform the design of a subsequent phase of programming. Other relevant resources are planned EL products, including a sector report on financial inclusion and G&I case studies. A future programme with a higher level of ambition on G&I could also benefit from sharing learning across programme strands or at portfolio level (sectorally).	PMT

Recommendations
The evaluation recommendation on G&I focuses on ensuring that PF minimum standards are met in Year 3 and gathering evidence and lessons to inform any subsequent phase of programming, potentially with a higher level of ambition on G&I.
Table 16: Gender and inclusion recommendations
LESSON	RECOMMENDATION	TARGET AUDIENCE (ASSIGNED TO)	TIMEFRAME
A minimum standards approach is acceptable under the PF. When combined with seeking and taking opportunities to exceed minimum standards, as they arise, a minimum standards approach can still be impactful. With this in mind, the programme could focus in Year 3 on (i) ensuring minimum standards are met across all programme strands and (ii) on gathering G&I-related evidence and lessons from strands and interventions which exceed minimum standards by pursuing targeted G&I-related results.	(1) Ensure that PF minimum standards (as set out in the G&I scorecard) are met across the programme. These are: / Social impact assessment undertaken, applied and refreshed (Design) / Realistic level of ambition identified and G&I action plan in place (Design) / Good use of UK government’s social development expertise, along with active capability building on part of programme team (Internal capability and incentives) / Active G&I champion (Internal capability and incentives) / G&I integrated into monitoring, reporting & evaluation, with disaggregated data & indicators (Accountability) / Active stakeholder & beneficiary engagement (including women & excluded groups) (Accountability) / VfM strategy with G&I mainstreamed & clear equity indicators (Financial resources) / Procurement of high-quality, relevant and sufficient G&I expertise (Delivery partners) / Good G&I results (Results) / Active G&I / ‘Do No Harm’ risk monitoring & mitigation (Results) / To support implementation of, and hold suppliers to account for delivering, minimum standards: ensure G&I is visible in quarterly reporting; create opportunities for regular lesson learning across programme strands; reflect G&I risks and mitigation in the programme risk register; and integrate consideration of G&I into country-level oversight. / Reconnect with allocated government Social Development Adviser for support on implementing minimum standards as needed. / (2) Share and capture lessons learned across strands, suppliers and activities, particularly those that are seeking to exceed minimum standards through targeted work on G&I-related issues, to inform a subsequent phase of programming. Identify opportunities to share learning with PF programmes working in the same sectors at portfolio level.	Head of Programme	Immediate and through the programme delivery lifecycle

: Value for money approach and analysis
Value for money methods note
The VfM scorecard interrogates eight elements across two vectors: attainment (what one sees today) and direction (what is likely in the future). The eight elements seek to clarify what is often referred to as “the four Es”: economy, efficiency, effectiveness and equity.
In Cycle 2 the focus has been on ‘direction of travel’, assessing how VfM considerations have been integrated throughout the programme, reviewing actions following from the baseline VfM assessment in Cycle 1, and addressing issues identified in evaluation or Annual Review.
The scorecard has been completed through a four-step process, informed by the PF VfM Scorecard Guidance:
- Step 1: The evaluators led a workshop with the PMT to outline the scorecard process and provide an opportunity to discuss queries around its completion.
- Step 2: The PMT provided initial ratings on the eight elements and identified evidence to support this.
- Step 3: The evaluators validated ratings and commentary through interviews with the PMT, reviewing documentary evidence and incorporating assessment of equity through evidence collected and G&I scorecard ratings.
- Step 4: The evaluators and Programme team discussed the results to agree and finalise scorecard ratings and commentary.
ASEAN Economic Reform Programme scorecard for Cycle 2
Table 17: ASEAN Economic Reform Programme value for money scorecard (Cycle 2)
SCORECARD ELEMENT	VFM SCORECARD YEAR 1 (2019/20)	QUALITY OF VFM EVIDENCE CYCLE 2 (2020/21)	PROGRESS CYCLE 2 (DIRECTION OF TRAVEL)	COMMENTARY ON QUALITY OF VFM EVIDENCE AND ‘DIRECTION OF TRAVEL’ SCORES
1. Relevance and robustness of VfM measures in place	Adequate	Good evidence	Good	VfM indicators have been included in the programme-level logframe. There has been a recent review of all strand-level logframes and the portfolio-level logframe, which is in the process of being finalised. VfM indicators sit mainly at output and outcome levels. / The majority of procurement took place in Year 1. However, where procurement has been necessary this has been done in line with the necessary procedures. For example, procurement of the ASEAN Financial Regulators Visit to the UK in January 2020 was done using a single source justification as this approach represented the best VfM. / The VfM plan, required as part of the contract with PwC, is nearly finalised following consultation with PwC UK and VfM technical expert (the JFU). The JFU noted that the VfM is robust and compares well with VfM plans from other commercial partners. For example, key performance indicators in the VfM plan include as a measure of economy, the percentage spend on expenses as a proportion of fees, and under efficiency, the percentage of outputs successfully completed within the allocated time and budget. There are also a number of qualitative indicators which are perhaps more difficult to assess without specific metrics, but they cite ‘evidence’ in addition to quantitative indicators. For example, under ‘equity’, and the implementation of the G&I plan, they cite the indicator as provision of evidence that the G&I process has evolved as a result of lessons learned or programme adaptations. / In addition, considerable time and effort has been invested by the programme team and Commercial Dept to agree a system of KPIs which ensures VfM across the portfolio. This has involved a transition from payment by milestone, which is a process, activity-focused incentive system, to payment by results, which incentivises the delivery partner to focus on effectiveness of delivery. Success criteria for attainment of milestones has been built into the ToRs for each work package, as well as an agreed ‘milestone management process’ which includes generic success criteria, and requires FCO sign-off for each of these. To move to strong evidence the programme will need to track PwC IO performance relative to invoicing to demonstrate that this approach is indeed delivering effectiveness and efficiency. A service-level agreement is also being completed with PwC, which defines eight different criteria PwC are reporting against (for example, timely reporting, MREL, financial management, etc). Up to five per cent of the quarterly management fee is at risk for failure to satisfy the agreed service levels. / Progress towards ‘strong evidence’ next year will be illustrated by evidence of how far the programme have been able to use VfM measures put in place to effectively manage and monitor the programme.
2. Approach to procurement and cost containment	Good	Good evidence	Good	The commercial contract is designed on the basis of payment by results which allows for cost containment. Managing this relationship remains challenging and demanding on PT time. There have been several examples where the PT have challenged expenditure and a further example where the PT have followed up on where costs needed to be reimbursed (e.g. as a result of an internal PwC programme audit).. The programme is highly complex, so the Programme Manager has devised a robust system for checking invoices, cross-checking against milestone completion records and flagging any questionable spend. An example is where this process seemed to reveal that some of the anti-money laundering milestones in Myanmar had been billed twice, but it transpired that some expenses had been separated and included in a later invoice. / Where PwC have been required to re-design delivery models, VfM has been central to the review of the new plans. In Thailand, the PT have rejected a request to increase the daily fee for consultants agreed in the framework contract. In Vietnam, the suggestion to include a senior level partner has been rejected due to the high costs this would entail. / For other delivery partners, it is more difficult to closely monitor spend. The agreements with the OECD and UNDP limits detailed oversight, and the evaluation relies on the strength of multilateral agreements to ensure accountability. There are similar limitations with RD/BEIS and the UK IPO as other government departments. Financial management is at the level of the compliance with activity-based budgets. / Expenditure is still monitored and challenged at this level. Ernst & Young, the delivery partner for the ASEAN financial regulators visit to the UK in January 2020, were followed up to explain some missing receipts from their invoice. There was a query for RD/BEIS regarding an additional expert, translation costs and the class of air travel used. The OECD had to be called out on an unexpected overspend at the end of the 2019/20 financial year which the programme team was not informed about. All these queries were successfully resolved (emails attached for information). / The Programme team have fully utilised the support provided by the PFDU, the Commercial Dept and the project management office in terms of financial advice, contracts and VfM, ensuring that the approach is in line with PF rules and expectations. (Evidence: PwC contract variation x 2; SSJ for ASEAN Financial Regulators Visit; inputs into PwC KPIs, VfM and G&I plans; UNDP MoU extension) / There has been a need for particular vigilance at the end of this financial year as a result of the necessary re-forecasting of activities and budgets due to the COVID-19 pandemic, ensuring transparency with the adaption to remote delivery models and the associated change in costs. / Through co-location with the in-house IP Programme Manager, the EL team was able to observe the mitigation measures he took to reduce the financial impact of COVID-19 on event cancellation, dedicating a concerted effort towards cost recovery which proved relatively successful (flights, accommodation, venue costs).
3. Efficient use of resources and inputs by PF interventions	Good	Good evidence	Good	The new Programme Manager has ring-fenced time for financial management which has enabled close monitoring of programme spend. This was in response to the implementation of robust VfM measures, such a payment by milestone delivery, which requires considerable capacity to manage properly. The PMT hold weekly meetings with the commercial contractor, and a joint workshop was held in (January 2020) to discuss financial management. However, there remain challenges the programme team are working closely with PwC to address, ensuring more real time information on spend through regular meetings and financial reports. / The Programme team are using leverage provided by the framework contract and contract variation to drive agreement on the G&I plan, KPIs and the Thailand delivery model. Funding was withheld as part of the contract variation for this purpose). As above, the framework contract is also being used to manage budget thresholds, e.g., in terms of enforcing top daily rates for consultants. A further example is provided by programme adaption in the light of COVID-19, and the agreement that these changes have to be governed by a contract variation, to ensure proper oversight, transparency and accountability. / Evidence of close oversight in-country is provided by a recent issue raised by the Programme Manager in Bangkok, regarding proposed UNDP spend on a project in Southern Thailand which was tenuous in its link to AER Programme objectives. Subsequent meetings between SG, Post and UNDP resolved this matter and the project was withdrawn. / The Programme team are closely monitoring proposed budget changes in the light of reprogramming due to COVID-19, ensuring that adjustments are recorded and any re-budgeting represents VfM – for example, appropriate re-allocation of cost-saving as a result of virtual delivery (rather than face-to-face). This scrutiny is particularly relevant to new workplans for the FSIP Programme and the Fair Biz Project in the 2020/21 financial year. Evidence of this scrutiny being effective will help a move towards ‘strong evidence’ in the coming year.
4. Validation of PF ToC causal pathways (for primary purpose & SBs)	Adequate	Good evidence	Good	Evidence for the validation of this scorecard can be found in the 2nd chapter of the business case. / The overall approach of the programme remains consistent in terms of aiming to refine policy rather than to promote root and branch reform. Following recommendations from last year’s evaluation, the programme team have been working closely with the MREL team to review both the ToC and strand-level logframes. Further technical assistance was provided by the EL consultant to then review the portfolio-level logframe. The Programme team have taken on board the advice of the EL team to reduce the number of indicators to make them more relevant and refined, based on data-quality awareness. Log frames are also being closely assessed in terms of integrating G&I indicators into delivery partner logframes, and particularly into the output and IO levels of the logframes. The two larger programmes, PwC and UNDP, have now been finalised and are in the process of onboarding onto Prospero. Work on the other three (RD/BEIS, in-house IP and OECD) are near completion. This process will allow for the finalisation of all logframes and a bedding-in period before the Annual Review later this year (2020). / The evaluation also recommended alignment of management tools to IO expectations. Work has been undertaken to directly map outputs outlined in Q4 reports to outcomes and IOs in the ToC. In addition, efforts have been made to capture this information in a summary dashboard for the steering board, which was presented as a draft to the steering board meeting in May (evidence in board papers and preparatory documents). This management process has already started through the development of an indicator dashboard connected to KPIs and will be refined over the coming months, with the intention to be able to fully validate ToC causal pathways by next year, and to demonstrate if there are pathways which are compromised and why. Work on SBs has been ongoing, with a round of funding applications for non-ODA funds put forward by the region. To date, one non-ODA proposal has been approved for the development of a ‘fintech bridge’ (one-day events in the region bringing together a group of UK fintech firms to pitch their products and services – proposing themes of environmental, social (inclusion) and combating financial crime). Plans are in place to review programmes ToC to map out where SBs will emerge; the PwC SB plan will be reviewed and a video workshop held with the programme team. There is a JFU Steering Group considering SB attribution and working with SB Advisers in the region which will help inform the development of SB indicators.
5. Sustainability of programme activities	Adequate	Good evidence	Good	The programme has been demand-led with the key stakeholders across the programme being mainly government partners, maximising the potential for sustainability beyond the life of the programme. Through implementation in Year 2, the programme has continued this approach, flexing and adapting to changing priorities. Examples of this are under the FSIP Programme, Accounting Standards in Thailand, where PwC have had to change activities to ensure a fit with government priorities, and in Myanmar, where the priorities of the Myanmar Financial Intelligence Unit have changed due to recent Financial Action Task Force outcomes. / The fintech team in Vietnam submitted the final fintech ecosystem catalogue report to the State Bank of Vietnam, providing an assessment of fintech companies, opportunities and gaps in the market. SBV noted that this guide would help them to direct ways forward for financial innovation and inclusion in Vietnam. In Myanmar, through GovRisk, the FSIP Programme has supported the development of a key actions matrix to support the government anti-money laundering working committee with post-MER follow up. / RD/BEIS work on regulatory reform provides evidence of sustainability – as a result of training provided under the programme the Vietnamese Govt is looking to adopt the same UK model of ‘x’ in 2 ’y’ out to support regulatory reform. The Vietnamese government signed Resolution 68 on 12 May which aims to tackle the red tape challenge in Vietnam and is modelled on the UK government’s successful Administrative Burdens Reduction programme. This is a huge success for the programme the Philippines government are also showing interest in incorporating UK best practice into government policy. / Under the FairBiz programme in Indonesia, UNDP worked in partnership with the UK Government Digital Service to conduct a workshop with the West Java Provincial Government and Bandung City Government (March 2020) on improving public procurement through digitisation. Outputs included joint recommendations for making the current procurement system more open and transparent, at provincial and city level. In Thailand, the Government Digital Service delivered a virtual seminar on digitalisation of public services to the Comptroller General’s Department officials. / In the Philippines, key government agencies (Government Procurement Policy Board Technical Support Office, Department of Budget and Management, Department of Education, Department of Health, and Department of Local Governance) have learned to identify and prioritise procurement data to help make better analysis and timely decisions using a procurement dashboard. Some staff and the pilot agencies have been training on the use of the dashboard which they hope will be adopted more widely within the Philippine government. / All these initiatives speak to sustainability in the sense that they are building government capacity, using UK systems, policies and best practice to inform the process. Close monitoring will be necessary to assess how many of these initiatives are actually implemented in the longer term, and whether they achieve the intended objectives. / It was noted in the evaluation last year that in order to better track the programme’s effectiveness, delivery partners’ monitoring systems should be extended beyond the quantitative logframe indicators to also determine whether new practices are continuing and resulting in the desired outcomes. This issue is currently being considered in the context of the quality of delivery partner reporting. Current quarterly reports still focus mainly at the output level, making it difficult to report against IOs or outcomes. The PMT are currently reviewing the reporting template to make it more directive in this regard, and can include support on providing qualitative statements supported by evidence regarding progress towards outcomes. / Efforts have also been made working with delivery partners to develop evidence of impact in the form of ‘good news stories’. Further evidence of this will be presented next year.
6. Ability of leadership, management and oversight structures to support programme delivery	Adequate	Good evidence	Good	The programme is highly complex, working across six PF countries, with five delivery partners and a programme team dispersed across the region. This requires an efficient and effective governance structure, and progress has been made to put this in place. / Oversight is provided by the steering board, made up of Heads of Mission of all PF countries, the Ambassador to ASEAN, the Deputy Trade Commissioner and representatives from the JFU, the PFDU and the Asia Pacific Directorate. The SRO is the High Commissioner in Singapore. The board heads up both the AER Programme and the Low Carbon Energy Programme. The board has a critical oversight role. The ground work before these meetings is undertaken by the Singapore Programme team to prepare the board members for any decisions. Attendance has improved but further work could be done to ensure full engagement, for example a focus on strategic high-level issues facilitating the board to take effective decisions. / There are PMs based in all PF countries, managing the programme on the ground. Following recommendations from the evaluation last year, the programme team in Singapore has been strengthened with the recruitment of a Head of Programme and Programme Manager who are solely dedicated to managing the Economic Reform Programme. The Programme Working Group meets monthly and has a good attendance – there is a standing agenda, but also a slot to discuss broader strategic issues (for example, a recent discussion around whether COVID-19 had changed stakeholder priorities, and whether the objectives of the programme were still relevant in a post-COVID-19 world). The Programme team in Singapore is able to provide a coordinating role, as well as being a conduit for information to and from the PFDU and the JFU in London. / The Cycle 1 evaluation suggested more clarity regarding roles and responsibilities between the regional and Post Programme teams. The recruitment of two dedicated programme staff has gone a long way to providing this clarity, along with regular and structured Programme Working Group meetings. An organogram has been produced for the region, and organisational structure and communications were further discussed at a face-to-face meeting of the Programme Working Group in the margins of the November PF regional meeting. Clear and regular communication between the PMT across the region ensures that the risk of task duplication is limited. An example is the agreement of a milestone management process with PwC, which clearly indicates the role of the PMs and the regional team in Singapore, and who is responsible for approving what and in what timeframe. / The Programme team in Singapore have regular monthly meetings with delivery partners to pick up any issues/risks/challenges/success stories and to report back on issues raised by the PMs to do with contract management. For example, problems with the PwC milestone approval process. The evaluation recommended training to enhance the programme team’s understanding of different types of delivery partners, their operating models and strengths and weaknesses. While there has not been focused training on this, stakeholder and contract management was an integral part of the contract management training delivered to all PMs in November 2019. / In order to move this element to ‘strong’, it would be helpful if there could be increased buy in to the regional objectives of the programme, rather than it being perceived as a collection of country programmes. In addition, further training could be undertaken around the different types of delivery partners, what to look out for, what makes them different and the advantages and disadvantages. Consideration of delivery partners and more broadly, of programme delivery models, will become increasingly relevant as the programme moves towards designing a new phase of the programme. / It is worth considering if the complexity of the delivery structure, and all of the VfM measures put in place are, paradoxically, creating some inefficiencies. There is considerable programme resource invested in managing the programme which is time consuming and challenging. However, once all programme documentation is finalised (workplans, G&I reports, VfM reports, management processes etc.) it should be possible for the programme team to use their time more efficiently. The programme has moved beyond the tipping point to roll back on the investment to date, and now needs to capitalise on that investment in terms of achieving primary purpose and SBs to the best degree possible.
7. Strategies and measures adopted to enhance delivery and mitigate risk	Good	Good evidence	Good	Risk is managed with the programme risk register. This is a live document and is kept under constant review by the programme team. / Each of the programme strands has a risk register, and they report on these risks every quarter as part of the quarterly report. For the commercial contract, PwC are required to treat red risks as a higher priority, and have particular requirement on this detailed in the service-level agreement. / There is a portfolio-level risk register which captures the key high-level risks, which is adjusted on a quarterly basis according to inputs from the quarterly reports. / In parallel, the top 15 risks are reported on Prospero. This promotes transparency and increases the potential for adoption of risk trends across the PF portfolio. / In addition, PMs report of changing risks and if they are trending upwards or downward. Risks can be reported both through the Programme Working Group meetings, and on an ad hoc basis if necessary. In this way the risk register can be adjusted between quarterly reports (e.g., Presidential decree in the Philippines was reported in real time, problems of engagement with stakeholders in Indonesia). / Risk trends have informed delivery. For example, when the Presidential Decree in the Philippines made official engagement very difficult, the programme team, informed by Post, adapted their ways of working with government stakeholders to allow the work to continue. / High-level risks and risks trending upwards are reported to the PF steering board which sits every quarter, and signs off on the risk register. / The programme is currently undergoing a re-stress test, to ensure that the identified risks are the right ones, and are sign-posted at the right level. / The programme quarterly reports evidence active tracking and management of risks, with risks reported and tracked over time, with a fuller discussion of the most significant risks included in the narrative.
8. Equity of programme design and approach	Adequate	Adequate	Adequate	The evaluation last year recommended developing a broader and more explicit definition of vulnerability and inclusion in the programme context and considerable progress has been made in this regard. The Programme team have drawn on the PF G&I policy and technical support offered by the Social Development Adviser from the JFU/PFDU. Both the Head of PF for Southeast Asia, and the Head of the AER Programme are members of the G&I Champions Network and have presented to this group to share lessons learned from the programme. / The UNDP programme promoting a fair business environment has been noted as taking very positive steps in terms of incorporating gender and social inclusion into their core programming. / PwC presented a good G&I scoping report. Unfortunately, the G&I plan submitted at the end of the inception phase was not up to the same standard. Following critical feedback, PwC re-wrote the report to take into account the initial scoping findings and presented an exciting and ambitious plan to take forward. Unfortunately, the new plan required extensive additional funding. In the absence of this funding, work has been ongoing with PwC to produce a G&I plan which meets PF minimum requirements, but which can be funded within the current PwC budget. This has been a very challenging process which remains unresolved at the end of this FY. The current strategy is to reach an agreement that satisfies PF minimum requirements, which PwC agree to fund within the existing contract. Ideas put forward for activities which would be more ‘empowering and transformative’ (as defined by the PF G&I framework) will be put on hold pending the availability of funding either within, or outside of the PwC contract. / During monthly calls with delivery partners, gender and social inclusion has been discussed and partners encouraged to view all activities through the G&I lens. Due to the nature of the programme, there is some push back on this, in terms of the practicalities of building in/mainstreaming G&I activities retroactively. As one of the first PF programmes, there was neither the guidance nor support that is available now. The Programme team could do more to try and incorporate G&I activities, but this will need support, and some good strong examples of ways in which all programme strands can practically incorporate G&I into their programme planning. In this way, the move from amber to green in the G&I scorecard can be achieved over the coming year. / The PF Regional Forum in November 2019 included a training session on GESI, which looked at both the PF GESI requirements and some practical examples of best practice. It is notable that this training was the opening session of the forum, illustrating how the programme has worked to centre G&I in its design and delivery. All PMs and delivery partners were present during the workshop. The improvement of the PwC G&I plan provides some evidence that G&I was being taken more seriously as a result. Evidence of PMs proactively addressing G&I when opportunity arises – the Programme Manager in Thailand asking how PwC will integrate G&I into re-design of ToRs on electronic ‘know your customer’ checks and cyber-security. / Overall, the programme has made significant progress in addressing the equity concerns identified in the Cycle 1 VfM scorecard, but as the work is not yet complete, the equity score remains ‘adequate’, with the expectation that once the work on integrating G&I into delivery partner logframes is complete, the score should improve to ‘good’ or better.
OVERALL VfM ASSESSMENT	Adequate	Good	Good

: Cycle 2 Evaluation Approach Paper
Cycle 2 Approach Paper cover note
Since the drafting of the initial approach paper, significant changes in safety and security have occurred that have affected the ability to deliver the Cycle 2 evaluation as planned. In the initial draft, we noted the following risk:
“Deterioration in safety/security environment in the region or one of the sampled countries inhibits the ability to complete the planned sample.”
The planned mitigation, however, did not anticipate the severity of the current COVID-19 crisis and resulting restrictions on all travel and likely restrictions on any in-person meetings.
In response to these considerations, and in consultation with the PMT and the JFU, we have revised the scope of the Cycle 2 evaluation. This document describes the updated scope and approach, while also addressing all questions posed by the JFU and arising from the EQuALS review of the draft approach paper.
Executive summary
This programme evaluation Approach Paper for programme Cycle 2 is an update to the approved Approach Paper for the AER Programme Cycle 1 evaluation (2019). The updates reflect key themes and evaluation questions for 2020 and lessons from Cycle 1. Overall, the Cycle 1 Approach Paper continues to govern the planned approach to the AER Programme evaluation, except where updated in this document.
The Cycle 2 Approach Paper has been developed in full cooperation with the PMT including PMs in the countries which will be sampled. The PMT identified two themes of interest for the Cycle 2 evaluation. These are: (1) progress toward results and (2) application of learning. To assess these themes, the PMT has identified 15 PEQs to prioritise for this evaluation cycle, listed in the box below.[181]
[181] PEQ numbering corresponds to the Fund-level questions and is therefore non-linear.
PEQ 1.1. What progress against IO indicators can be observed? / PEQ 1.2. To what extent have there been unexpected or unintended effects? (Limitations apply.) / PEQ 2.1. To what extent has primary purpose been achieved, and if so, what and where (country, sector, intervention)? / PEQ 2.2. How does primary purpose achieved compare to the expectations? / PEQ 5.1 What factors have contributed to the achievement of primary purpose and SBs? / PEQ 7.1 To what extent has the programme adjusted ToCs or programme design in response to changing context or understanding of causal pathways? What has it changed and why? / PEQ 7.2 Which assumptions (implicit or explicit) and causal pathways in the programme/project have been valid and which have not and why? (Limitations apply.) / PEQ 7.3 Since Cycle 1, is there new evidence that shows projects are more or less likely to contribute to financial inclusion or a better understanding of risk? If so, what? / PEQ 8.1 How is the AER Programme meeting regional priorities? To what extent is it focused on national priorities and is this helping, inhibiting or not affecting its regional focus? (Limitations apply.) / PEQ 9.1 How is evidence on VfM being used to guide programming? What effect is this having, if any, on the achievement of VfM? / PEQ 9.2 How does the programme management structure support the achievement of regional objectives? / PEQ 10.1 In what ways has the programme design or implementation changed in relation to gender responsiveness/inclusion at programme and project levels? / PEQ 11.1 What actions and/or progress has the programme made in response to the Cycle 1 Evaluation and Annual Review findings and recommendations? / PEQ 11.2 What learning activities have been undertaken during the year? Who was involved? What has resulted from these activities? / PEQ 11.3 In what ways have the delivery pathways been responsive to changing context?

Due to limitations in outreach to external stakeholders arising from COVID-19 considerations, the ability to triangulate data to answer some PEQs is reduced. The PEQs which are affected are noted in the box above.
As a part of, and in addition to, addressing the PEQs, the Cycle 2 evaluation will address the three cross-fund thematic areas: G&I, VfM and SBs. As in Cycle 1, scorecards for G&I and VfM will be completed.
The design of the evaluation approach is informed by lessons learned by the EL team during the Cycle 1 evaluation. As in Cycle 1, the entirety of the programme will be evaluated via interviews with PMT members and implementing partners and review of programme documentation. In addition, for Cycle 2, indicator data uploaded to Prospero will now be available and included in the cross-programme evaluation. Due to current limitations on travel and in-person contact arising from the COVID-19 health crisis, this work will not be supplemented by interviews of government partners or key stakeholders as planned. Collection of additional data for select strands in the sampled countries for Cycle 2 – the Philippines, Thailand and Malaysia – will be limited to interviews with FCO, implementing partner and partner team members, as well as documentary evidence. The sampling plan was developed in cooperation with the PMT and the PMs in each affected post. In addition, the EL team has held dialogue with the FCO MREL team to support coordination of sampling with the Annual Review.
The evaluation will start on 25 March, one week earlier than initially planned, to accommodate the additional time teleconference scheduling is likely to take. Data collection, interviews and assessment will conclude by 12 May with sense-making conference calls with the programme team in Singapore and other posts, as selected by the PMT. A draft of the evaluation report will be made available to the programme team for review and comment by 22 May and the draft report will be submitted to the JFU by 11 June. The final report should be approved by JFU by 10 July, prior to the Annual Review.
The programme EL team is largely the same as the team utilised for the Cycle 1 evaluation so as to carry forward the knowledge and experience gained in the last cycle. An additional EL team member has been added with specific expertise in inclusive finance to better support evaluation and recommendation development in this area of particular interest to the programme. A second new team member has been added in Malaysia to support data collection and document interpretation there.
Purpose of this document
This programme evaluation approach paper for programme Cycle 2 is an update to the approved approach paper for the AER Programme Cycle 1 evaluation (2019). The updates reflect the key themes and evaluation questions for 2020 and lessons from Cycle 1. Overall, the Cycle 1 Approach Paper continues to govern the planned approach to the AER Programme evaluation, except where updated in this covering document.
The design of the Cycle 2 evaluation is informed, in part, by lessons learned during the Cycle 1 evaluation, identified during a formal after-action process. Key lessons were:
- The evaluation attempted to answer too many evaluation questions, diluting the key areas of interest to the PMT.
- Engagement with the sampled country posts was complicated by the attempt to reach all programme aspects in each country, over-burdening the PMs.
- The level of detail in the evaluation report was appreciated by the PMT, but also made it difficult to focus in on key findings and recommendations.
Programme status update
The FCO PMT described the programme status in the latest quarterly report:[182]
[182] Quarter 2, 2019 Quarterly Report, FCO, 8 November 2019.
“The majority of the programme strands (five of six) continue with implementation. These are progressing well against their workplans, with some delays to the UNDP programme due to recruitment of expert leads. The FSIP strand being delivered by PwC received steering board approval to move from inception to the implementation phase on 1 October 2019. This is subject to the agreement of a contract amendment (currently being drafted) that will include a number of qualifications to give greater certainty of delivery: agreeing quality metrics to facilitate payment by results; the completion and agreement of the programme gender plan; and agreement on the delivery model in Thailand.
Considering some significant programme delays, particularly in relation to ensuring quality delivery of the PwC element (which is about 40 per cent of total programme allocation), the expected spend to December 2019 is reasonable. The Programme team is confident that the forecast can be delivered by the end of the calendar year. There are two notable risks around spend for both UNDP and PwC, but with the increase in programme staff, these risks can be closely managed and mitigated as the year progresses.”
Since that report, the FCO and PwC have negotiated performance metrics, revised some delivery plans and replaced the PwC lead on the contract with a new staff member acceptable to the PMT. The PwC logframe is in revision and should be finalised prior to the start of the Cycle 2 evaluation.
The programme logframe is also being revised based on the work conducted over the past six months on delivery partner logframes. This should also be complete and final selected indicators uploaded to Prospero prior to the Cycle 2 evaluation start.
Since the drafting of the quarter 2 report, significant changes, not the least of which include the national and near-global shut downs of travel, meetings, and in-person activities resulting from the COVID-19 crisis, are likely to have an effect on the scope and schedule of the programme. The FCO is still evaluating the potential impacts on the programme at this time and we cannot make any specific statement on what the overall effect is likely to be.
Development of Cycle 2 Approach Paper
The process to develop this approach paper update began on 1 January. A staffing budget of 10 days was allocated across three EL team members to undertake the update work.
This time was used to:
- develop proposed themes, sampling plan, schedule and EL team composition
- develop a proposed evaluation matrix
- conduct interviews with the PMs in each post where sampling was proposed, with the PMT, and update the EL thematic teams on the thematic assessment needs for Cycle 2
- teleconference with the FCO MREL team to discuss coordination needs between the evaluation and Annual Review and coordinate within EL on the proposed sampling and any conflicts or overlaps with evaluation sampling on other programmes
- meet with the PMT to review and revise all proposals, produce the draft approach paper, respond to any requested edits of the draft approach paper arising from PMT review, and respond to any edits arising from the JFU review of the approach paper.
Consultations with the Programme team occurred by email and phone prior to the formal kick-off and in person at the Southeast Asia PF forum in Singapore in November 2019. Drafts of the proposed themes, schedule and evaluation matrix were shared by email with the PMT and then discussed in person in late January at an approach paper review workshop in Singapore. The evaluation matrix was also shared with the FCO MREL team in order to facilitate coordination on sampling with the Annual Review. Several calls were also held with the FCO MREL team to further the goal of coordinating on sampling. Calls and correspondence were utilised to coordinate with the PMs in the three sampled countries to identify any sampling and coordination risk, any timing issues and any other concerns about the proposed sampling plan. The PMT reviewed and commented on the draft of this approach paper, prior to submission to JFU for review and approval.
The draft approach paper was submitted to the JFU on 26 February. On 17 March, the JFU returned comments, including comments from a passing EQuALS review of the draft. One of the JFU’s central concerns was how the evaluation plan would need to be adjusted to address the limitations in delivery arising from the COVID-19 crisis. In response, the EL team developed two options:[183] a revised scope, on-schedule option and a full-scope, delayed option. In consultation with the PMT, we recommended the first option. This final approach paper documents the revised scope agreed upon with the PMT.
[183] The EL team developed an “Options Analysis” memo, delivered to the JFU on 18 March and included as an annex to this paper.
The key changes for the Cycle 2 Approach Paper are:
- Cycle 2 evaluation themes and matrix
- Cycle 2 sampling plan
- Cycle 2 schedule
- Adjustments to the approach to thematic assessments, including VfM, G&I and SBs
- Adjustments to EL team composition
- Programme manager’s statement for Cycle 2
- Update on risks and mitigations.
Cycle 2 evaluation themes
Based on PMT interests and needs, the Cycle 2 evaluation focuses on two themes which then guide the PEQs discussed in the next section. These themes are outlined below.
Table 18: ASEAN Economic Reform Programme evaluation themes for Cycle 2
#	THEME	DISCUSSION
1	Progress toward results	The programme seeks to understand what progress it has made toward achieving its planned IOs and outcomes, including both primary purpose and SBs and thematic results.
2	Application of learning	The programme would like to evaluate what it has learned in the past year, how this learning has been applied, including responses to the Annual Review and Cycle 1 evaluation recommendations, and where there are possibilities for improvement in the application of learning going forward.

Cycle 2 evaluation matrix
The evaluation matrix has been revised to prioritise select PEQs that reflect the programme needs and interests as well as PF evaluation needs and thematic evaluation needs. It has been further annotated to indicate where the revision of the scope of the evaluation suggests that full triangulation of data may no longer be possible.
The evaluation matrix, below, is organised first by the Fund-level questions then by the PEQs. The PEQ numbering is not linear, reflecting the fact that some evaluation questions (EQs) are not covered by the Cycle 2 evaluation. This is done intentionally to enable later aggregation for Fund-level evaluation reporting.
Table 19: Evaluation matrix for Cycle 2
FUND-LEVEL EQS / (ITALICS INDICATES NON-PRIORITISED EQ)	PRIORITY FOR CYCLE 2	PEQS FOR CYCLE 1	DATA SOURCE (WHO, WHAT?)	DATA COLLECTION METHOD	TRIANGULATION RISK
EQ1. What evidence is there that the PF is likely to contribute to the intended outputs and IOs in the ToC, as well as any unintended or unexpected effects?	X	PEQ 1.1 What progress against IO indicators can be observed?	Indicator data	Review Prospero, quarterly reports
		PEQ 1.2 To what extent have there been unexpected or unintended effects?	Stakeholder input[184]	KIIs	X
EQ2. Which types of interventions, sectors and country settings have been more and less successful in contributing to the achievement of primary purpose?	X	PEQ 2.1 To what extent has the primary purpose been achieved, and if so, what and where (country, sector, intervention)?	Indicator data	Review Prospero, quarterly reports; KIIs with implementing partners and the FCO
		PEQ 2.2 How does primary purpose achieved compare to the expectations?	Stakeholder input	Review Prospero, quarterly reports; KIIs with implementing partners and the FCO
EQ3. Which types of interventions, sectors and country settings have been more and less successful in contributing to the achievement of SBs?	Not prioritised in Cycle 2
EQ4. What evidence is there that the changes supported by the PF interventions will be sustainable and ensure environmental sustainability, will be self-financing and lead to inclusive growth that reduces inequality?	Not prioritised in Cycle 2
EQ5. What factors have contributed to the achievement of primary and SBs?	X	PEQ 5.1 What factors have contributed to the achievement of primary and SBs?	Stakeholder input	KIIs; Review Prospero
EQ6. How has the balance and relationship between primary and SBs across the portfolio influenced the achievement of results?	Not prioritised in Cycle 2
EQ7. Which assumptions and causal pathways outlined in the ToC remain valid, which have been adapted and what refinements need to be made?	X	PEQ 7.1 To what extent has the programme adjusted TOCs or programme design in response to changing context or understanding of causal pathways? What and why?	Programme information, indicator data, project information, stakeholder input, VfM scorecard	Desk review of programme documentation / Prospero / KIIs / Programme team self-assessment
		PEQ 7.2 Which assumptions (implicit or explicit) and causal pathways in the programme/project have been valid and which have not and why?			X
		PEQ 7.3 Since Cycle 1, is there new evidence that shows projects are more or less likely to contribute to financial inclusion or a better understanding of risk? If so, what?	Indicator data, stakeholder input	Desk review of programme documentation / Prospero / KIIs
EQ8. To what extent is the institutional governance set-up of the PF more or less effective in achieving i) primary purpose; ii) SB; iii) other results?	X	PEQ 8.1 How is the AER Programme meeting regional priorities? To what extent is it focused on national priorities and is this helping, inhibiting or not affecting its regional focus?	Stakeholder input / Programme documentation	KIIs / quarterly reports, annual reviews	X
EQ9. What types of programmes, approaches, and governance and management arrangements have been more or less effective for achieving results and demonstrate good approaches to supporting inclusive growth and VfM?	X	PEQ 9.1 How is evidence on VfM being used to guide programming? What effect is this having, if any, on the achievement of VfM?	Stakeholder input / VfM scorecard / Stakeholder input	KIIs / Programme team self-assessment / Thematic team assessment
		PEQ 9.2 How does the programme management structure support the achievement of regional objectives?		KIIs, quarterly reports, annual reviews, steering board minutes
EQ10. To what extent have the PF interventions contributed to results that support gender equality, women's economic empowerment and social inclusion?	X	PEQ 10.1 In what ways has the programme design or implementation changed in relation to gender responsiveness/inclusion at programme and project levels?	Stakeholder input / Programme documentation	G&I scorecard / KIIs
EQ11. How is the PF learning and why is action on this learning happening more and less successfully?	X	PEQ 11.1 What actions and/or progress has the programme made in response to the Cycle 1 Evaluation and Annual Review findings and recommendations?	Stakeholder input / Programme documentation	Desk review of programme documentation / KIIs
		PEQ 11.2 What learning activities have been undertaken during the year? Who was involved? What has resulted from these activities?
		PEQ 11.3 In what ways have the delivery pathways been responsive to changing context?
EQ12. Which PF lessons in translating outputs into IOs are sufficiently robust for wider learning?	Not prioritised in Cycle 2
[184] Stakeholders can include the PMT, PMs in PF-6 country posts, implementing partners, recipient agencies, private sector organisations, other bi- and multi-lateral donors and other development actors.

The PMT will complete the VfM scorecard, which the EL team will review as part of PEQ 9.1 and the thematic team will review and moderate against the evidence provided by the PMT. The EL thematic team will complete the G&I scorecard. SBs will be assessed in terms of progress toward anticipated results under PEQs 1.1 and 5.1.
Cycle 2 sampling plan
As described in the Cycle 1 Approach Paper, all PF-6 countries and all activities will be evaluated. Cycle 2 will collect primary data on select programme strands in three different countries. Sampled countries and activities are evaluated at a greater level of detail than those not sampled.
The Cycle 2 sampling plan is informed by the selected themes, PEQs, the status of programme implementation, the PMT’s needs and interests, the need to coordinate sampling across programmes and with the Annual Review team, and the lessons learned from the Cycle 1 evaluation. To design the sampling plan, the evaluation:
- de-prioritised countries where sampling had occurred in Cycle 1 (Vietnam and Myanmar)
- canvased PMT interests
- de-prioritised countries where sampling for other PF programmes was occurring or was likely to occur in the first half of 2020 (Indonesia)
- developed the concept of reduced sampling per country, across more countries to reduce the administrative burden on PMs, while covering all programme strands/components
- reviewed the status of implementation of each stand/component in each potential sample country to ensure that the mix of countries and activities would allow the evaluation to reach active, in-process programme components in the potential sample
- reviewed these with each programme manager to confirm the likely availability of stakeholders and the existence of implementation activities to evaluate
- presented the proposed mix to the PMT for further validation and approval
- updated the evaluation matrix to reflect the proposed sample and confirm that data from the broader (non-country sampling) data collection approach would likely allow the evaluation to triangulate evidence to confirm or contradict information collected in the country-level sampling.
This sampling approach, of looking at select strands within each sampled country, allows the EL team to: sample more broadly across the programme within the budget available, reduce the administrative burden on individual PMs, focus more clearly on progress against goals, identify how the programme is responding to changing context and derive a more informed regional view of performance and response to learning. At the same time, the approach to collecting documentary and limited key informant interview data across the whole programme allows for triangulation of fact.

Table 20: Sampling plan for Cycle 2
PF-6 COUNTRY	PILLAR	IMPLEMENTING PARTNER	PROGRAMME STRAND
Republic of the Philippines	ER 1.1	Rouse under PwC	IP enforcement component of the FSIP Programme implemented in cooperation with the Intellectual Property Office
	ER 1.2	Regulatory Delivery/Department for Business, Energy and Industrial Strategy	Regulatory strengthening programme implemented in cooperation with the Anti-Red Tape Authority
	ER 1.3	OECD	Logistics sector competition assessment implemented in cooperation with the competition authority
Kingdom of Thailand	ER 2	COST under UNDP	Government transparency in procurement programme implemented across multiple agencies
Federation of Malaysia	ER 2	UNDP	Government transparency and private sector anti-corruption programme components
	ER 3	PwC	Capital markets development FSIP component focused on Islamic finance development in cooperation with the Ministry of Economic Development (public sector), the Red Crescent Society (non-profit) and May Bank (private sector)

The sampling plan was developed in cooperation with the PMT. The EL team developed an initial proposal, interviewed each programme manager, identified risks to the evaluation and to the programme, discussed Annual Review coordination needs with the FCO MREL team and finalised a proposal based on the information collected. This proposal was presented to the PMT for validation and approval. The proposal was then revised, adjusting the methods of collection to a virtual approach to adopt to existing and likely COVID-19 response restrictions. This revision was validated with the PMT, documented in a separate memo to the JFU,[185] and used to update this approach paper.
[185] See a reproduction of the memo in the annex to this approach paper.
Given the limitations in travel and in-person meetings imposed by national governments and EL policy in response to the COVID-19 crisis, interviews and focus group meetings will be held virtually – primarily by phone, but also potentially by video conferencing. The EL team believes that the effectiveness of such an approach is limited and will be most successful with people and organisations that the EL team has a prior relationship with. While the EL team is committed to attempting to reach all stakeholders, the evaluation matrix and PEQ triangulation limitation assessment is based on the assumption that the team will only reach FCO and implementing partner teams in each sampled country.
The sample will be complemented with data collected more broadly across the whole of the programme and across all PF-6 countries. This includes monitoring data stored in Prospero, programme reporting, implementing partner-produced documentation and interviews with the PMs in each relevant post and with the central implementing partner teams. In this way, the evaluation will collect comparison and triangulation points for the strands/components sampled in Malaysia, Philippines and Thailand.
Cycle 2 methods and availability of data
Given the revision to the scope of the Cycle 2 evaluation in response to COVID-19–associated limitations, the EL team has re-assessed its approach to data collection and assessment and the likely availability of the data to meet analytic needs. This has included assessing the preliminary stakeholder inventory to determine where there are likely to be gaps, reviewing the documentary evidence assembled to date, and determining where there may be shortfalls in information to complete the planned evaluation approach. As notated above, this work has allowed the EL team to identify which of the selected PEQs are likely and less likely to be fully answerable given the data likely to be collected.
These PEQs come with clear links to the Fund-level EQs and the sector assessment approaches. As described in the Cycle 1 Approach Paper, the evaluation will triangulate the collected evidence to assess progress toward results and contribution to any results in progress observed. Finally, the evaluation will be augmented and supported through the application of scorecard and other assessment tools addressing the Fund’s cross-cutting themes: G&I, VfM and SBs.
Further, through data collection, the evaluation will focus on testing the causal pathways within the programme ToC, particularly the links between outputs and IOs.
This triangulated approach to data collection and sampling will help to mitigate some of the main limitations to data collection, including the availability of stakeholders given the planned ‘virtual’ approach and the reliability of data. The tables below review the original planned sources of information for Cycle 2 and the updated assessment of availability resulting from the re-scoping.
Table 21: Assessment of preliminary stakeholder inventory
PROGRAMME/ PILLAR	IMPLEMENTING PARTNER	ORIGINALLY IDENTIFIED STAKEHOLDER	ASSESSED LIKELIHOOD OF PARTICIPATION UNDER REVISED SCOPE (HIGH, MID, LOW, N/A)
Singapore
Programme		PMT members	High
		Head of Prosperity Programme, SEA	High
		SRO	Mid
		UNDP	High
		OECD	High
		PwC	High
ER 1.1	IPO	IPO team members supporting regional intellectual property efforts	High
The Philippines
Programme		Programme Manager	High
		Head of Prosperity	High
		Steering board member	Mid
ER 1.1	Rouse under PwC	PwC central team	High
		Rouse team	High
		PwC country team	High
		Intellectual Property Office of the Philippines	Mid
		Philippine Department of Information and Communication Technology	Low
		BSP – Bangko Sentral ng Pilipinas	Low
		National Telecommunications Commission	Low
		National Committee on IP Rights	Low
		Philippines Chamber of Commerce & Industry	Mid
		Intellectual Property Association of the Philippines	Mid
		Brticham	Mid
		Other international organisations: World Intellectual Property Organization, Japanese External Trade Organization, etc	N/A
ER 1.2	RD/BEIS	Implementation Lead, RD/BEIS	High
		Anti-Red Tape Authority Departments: 1) Compliance, Monitoring and Evaluation Office team; 2) Regulatory Management and Training Division; 3) the Better Regulation Office	Mid
		Philippine Women’s Business Council	Low
		World Bank	High
		USAID	Mid
		Philippine Department of Information and Communication Technology	Low
ER 1.3	OECD	OECD	High
		OECD national expert	High
		Competition authority	Mid
		Awaiting OECD reporting to further identify stakeholders	N/A
Thailand
Programme		Programme manager	High
		DIT representative	High
		Steering board member	Mid
ER 2	COST under UNDP	UNDP multi-stakeholder group representatives	High
		Comptroller General's Department, Ministry of Finance	Mid
		1–2 COST participating agencies	Low
		COST National Secretariat	High
		Anti-Corruption Organisation of Thailand	Mid
		1–2 anti-corruption non-governmental organisations	Mid
Malaysia
Programme		Programme manager	High
		Head of Prosperity	High
		Steering board members	Mid
ER 2	UNDP	UNDP country officer	High
		UNDP programme office	High
		Governance, Integrity and Anti-Corruption Centre	Mid
		Pilot Ministries (not yet selected by UNDP)	N/A
		Civil society organisation (not yet selected by UNDP)	N/A
ER 3	PwC	PwC FSIP team	High
		International Centre for Education in Islamic Finance (INCEIF)	Mid
		Maybank	Low
		Ministry of Entrepreneurial Development	Low
		Red Crescent Society	Low
		Association of Islamic Banking and Financial Institutions	Low
		Alliance for Financial Inclusion	Mid
		FinTech Association of Malaysia	Mid
		World Bank	Mid
		Securities Commission	Low

Table 22: Preliminary assessment of sufficiency of likely evidence by programme evaluation question
DATA SOURCE	CURRENTLY AVAILABLE	LIKELY TO SUPPORT TRIANGULATION FOR PEQ:
		1.1	1.2	2.1	2.2	5.1	7.1	7.2	7.3	8.1	9.1	9.2	10.1	11.1	11.2	11.3
KIIs with “high” likelihood of occurring			X	X	X	X	X	X	X	X	X	X	X	X	X	X
KIIs with “mid” likelihood of occurring	Moderate risk		X	X	X	X		X	X	X		X	X	X	X	X
KIIs with “low” likelihood of occurring	High risk		X	X	X	X		X	X	X		X	X	X	X	X
Logframe indicators (Prospero)	X	X		X	X	X			X		X	X	X	X
Programme Annual Review	X	X	X	X	X	X	X	X	X	X	X	X	X	X	X	X
Programme quarterly reports	X	X	X	X	X	X	X	X	X	X	X	X	X	X	X	X
Implementing partner quarterly reports (Regulatory reform, IPO, OECD, UNDP, FSIP)	X	X	X	X	X	X	X	X	X	X			X	X
IPO participant survey results			X		X					X
OECD PH Competition Assessment	X	X					X
OECD PH SOE study	X	X					X
UNDP Malaysia workplan	X						X					X
UNDP Malaysia Corporate Governance Review	X	X					X
COST workplan Y1, Y2	X						X			X			X	X
CoST Thailand Impact Study	X	X		X					X
CoST Thailand Assurance Report	X	X		X					X
RD / BEIS work products, PH		X		X					X
FSIP workplan	X	X					X			X			X	X
FSIP IP work products, PH		X		X					X
FSIP reports and other work products, MA	X	X		X					X
VfM self-assessment		X	X	X		X					X			X		X
G&I scorecard							X	X			X

These will be supplemented with collection of external documents, including national plans and priority documents, sustainable development goal plans and priority documents, and external studies and reports, which can begin once the evaluation starts.
Cycle 2 evaluation products and schedule
### Deliverables and other products
The primary deliverable for the evaluation will be the evaluation report. In addition, the evaluation will result in a:
- G&I scorecard, completed by the EL thematic team
- VfM scorecard, completed by the programme team
- sense-making workshop as part of delivery of learning touchpoints
- stakeholder engagement/targeted dissemination plan
- summary presentation of key findings, learning, issues for consideration by the Annual Review, issues for consideration in subsequent evaluations and any recommendations.
The primary audience for the report is the programme team and the SRO, and it is expected to be oriented toward findings and recommendations, with analysis and data reserved for the report annexes. Based on feedback from both JFU and the PMT, this approach will better support PMT use of the evaluation report and ensure a focus on the recommendations. The executive summary of the report will conform to the standard recently agreed by EL and JFU. A summary presentation will support the evaluation report.
The quality assurance approach will mirror that utilised for the Cycle 1 evaluation, documented in the Cycle 1 Approach Paper.
### Evaluation schedule
As anticipated in the Cycle 1 Approach Paper, the evaluation schedule has been moved earlier in the calendar this year to ensure the final evaluation report is available to the Annual Review team. To that end, pending JFU approval of this approach paper update, evaluation activities will begin on 1 April 2020 and conclude in July, with fieldwork and workshops taking place from late April to May. According to this schedule, it is expected that the approved report will be available to the Annual Review team in mid-July in time for the Annual Review delivery date.
The second year’s Annual Review is due to be delivered at the end of July 2020.[186] It was agreed with the PMT that the Annual Review and EL teams would meet to coordinate their sampling approach and minimise the burden on programme stakeholders of information requests and support the information needs of the Annual Review, as far as possible.[187] Subject to budget availability in the finalised budget, the EL team will further support this coordination by making a team member available to join the Annual Review team.[188]
[186] The Annual Review team has not yet been appointed. The estimated dates are based on not-yet-complete terms of reference and are therefore subject to change.
[187] Coordination with the EL team will be set out in the Annual Review terms of reference to be drafted by the PMT.
[188] Note that there are limits to participation, as outlined by JFU. For example, evaluation service members cannot participate in scoring Annual Review categories.
The draft Cycle 2 workplan is presented in Table 23 below. The workplan will be revisited and finalised at the evaluation kick-off.
Table 23: Draft Cycle 2 workplan[189]
[189] To be confirmed at evaluation kick-off.
MONTH	COORDINATING ACTIVITY	DATA COLLECTION ACTIVITY				LEARNING TOUCHPOINT	DELIVERABLE	NOTE
2020
Jan	Approach paper planning workshop	ToC and indicator review for EQ data source development				TP1		Approach paper kick-off meeting and EQ validation completed
Feb	PMT approach paper review and comment						Draft approach paper delivery	Approach paper delivery to the JFU on 26 February
Mar	Coordination call						Final approach paper delivery	Final approach paper submitted to the JFU 25 March
Apr	Kick-off/ VfM online workshop	Programme documentation requests. Programme and delivery partner interviews	Report drafting					Kick-off/ VfM online workshop, 8 Apr

May	Coordination call	Sampling via teleconferencing and evidence compiling				TP2		Sense-making workshop, 12 May, online
Jun	Coordination call/Annual Review coordination meeting			Report revision		TP3	Draft evaluation report / Draft summary presentation	11 June: draft report to the JFU / Management response planning
Jul	Coordination call						Final revision evaluation report submission	10 July: report submission. / Monitoring and reporting coordination and revision meeting date TBC
Aug	Monthly MREL coordination call					TP4		Dissemination planning
Sep	Monthly MREL coordination call
Oct	Monthly MREL coordination call					TP5		After-action review
Nov	Monthly MREL coordination call
Dec	Monthly MREL coordination call	ToC and indicator updates. / Programme activity update collection.
2021
Jan	Year 3 approach paper kick-off meeting
Key: / TP1 – Evaluation plan / TP2 – Validate findings and develop recommendations / TP3 – Sense-making and action planning / TP4 – Wider learning and enquiry / TP5 – After-action review

Table 24 below summarises key Cycle 2 evaluation delivery milestones and dates. Included are two milestones for programme manager/programme team actions – VfM scorecard and draft evaluation review deadlines – and proposed event dates for the sense-making workshop. Milestones in italics indicate programme team responsibilities/activities.
Table 24: Cycle 2 evaluation delivery milestones
DATE	MILESTONE
1 April	Evaluation kick-off, programme team and delivery partner remote interviews begin
8 April	File programme document requests with FCO/delivery partners, proposed stakeholder list to FCO at Post (Malaysia, Thailand, Philippines)
8 April	VfM online workshop
17 April	Sampling planning complete. FCO comment on stakeholder plan and counterpart meeting requests complete
16 April	VfM scorecard draft completed by PMT
20 April – 1 May	Remote sampling via phone/video conferencing
7 May	Interviews and data collection complete
12 May	Teleconferenced sense-making call(s)
13–21 May	Evidence compiling, scoring, report drafting
22–28 May	PMT review and comment on draft evaluation report
11 June	Submission to EQuALS/JFU
15 June TBC	Annual Review coordination meetings/calls
1 month from submission (10 July)	Final draft report and summary presentation

### Learning touchpoints in Cycle 2
One of the main objectives of programme evaluations in the PF is to promote learning. The annual evaluation cycle takes place throughout implementation, meaning that lessons and evidence are generated on an ongoing basis. Through this process programme teams can understand what is working well and what areas could be strengthened. This can then inform decision making and lead to improvements and adaptation throughout the life of the programme.
Learning is facilitated through close engagement between the evaluation and programme team throughout the evaluation cycle. The diagram below shows how learning is enabled through the evaluation process. In Cycle 1, the evaluation applied seven learning touchpoints. This approach has been simplified, based on learning from Cycle 1. The five learning touchpoints have been included in the workplan.
Figure 5: Learning through the evaluation process

The process outlined above ensures that the evaluation meets the needs of the Programme team and that learning is applied and feeds into adaptation. It also generates learning that can be disseminated across the PF and used to communicate the work of the Fund externally.
Adjustments to thematic assessments for Cycle 2
In coordination with the JFU, the EL team has updated and revised the approach to assessment of VfM, G&I and SBs for Cycle 2.
### Value for money
 VfM will be assessed again through the VfM scorecard, which encompasses the ‘four Es’.[190] In Cycle 2 the focus will be on ‘direction of travel’, assessing how VfM considerations have been integrated throughout the programme, reviewing actions following from the baseline VfM assessment in Cycle 1, and addressing issues identified in evaluation or Annual Review. This will allow both good practice and progress/intent to be assessed. The scorecard will be completed through a three-step process.
[190] The four Es are Economy, Efficiency and Effectiveness and Equity. The VfM assessment draws on broader principles set out, for instance, in National Audit Office guidance on VfM or HM Treasury’s Managing Public Money.
- Step 1: The PMT provides initial ratings on the eight elements[191] and identifies documentary evidence (e.g. risk registers) to support this. (April 2020)
  [191] Some of these will be addressed by looking exclusively at programme-level arrangements; others from reviewing individual strands. Guidance on what to consider will be provided with the scorecard at the start of the process.
- Step 2: The evaluators validate ratings and commentary through interviews with the Programme Team, reviewing the documentary evidence and incorporating assessment of equity through evidence collected and G&I scorecard ratings. (May 2020)
- Step 3: The evaluators and Programme team discuss the results to agree on ratings, complete the scorecard and identify any necessary actions. (May 2020)
The completed scorecard will inform the draft of the evaluation report where relevant and will be added in an annex. Separate recommendations may be provided to improve VfM if the evidence collection and scorecard lead to any.
### Secondary benefits
The SB analysis for Cycle 2 will focus on:
Assessing whether the mechanisms to deliver SBs are effective:
- Focusing on plans since the Programme Team’s SB workshop held in September 2019;
- Assessing governance and management processes to support SBs, including cooperation with delivery partners, local and UK-based organisations;
- Reviewing baselines and identifying remaining barriers or unfulfilled conditions.
Testing whether the delivery of SBs is as planned:
- Are the expected SBs likely to be delivered?
- Are any unexpected SBs emerging and likely to be delivered?
Identifying SBs that have already occurred – both expected and unexpected – including assessing:
- The actions taken to achieve these SBs;
- The relative contribution of the programme with a focus on selected examples, through discussions with the Programme Team, delivery partners and companies benefiting (if identifiable at this stage);
- Trade-offs, if any, between SBs and primary purpose (e.g. are SBs actually facilitating further inclusive growth, or are they achieved at the expense of it?);
- Possible case studies for future cycles.
Documenting learning on SB achievement:
- Describing causal pathways and how specific barriers were or were not overcome;
- Identifying and describing the conditions identified as necessary to achieve specific SBs;
- Assessing what might be improved and what other programmes might learn.
The SB analysis will be produced as a separate section in the evaluation report and will also inform the VfM scorecard analysis.
### Gender and inclusion
In Cycle 2 of the evaluation, the evaluation will seek to understand what progress has taken place on integrating G&I considerations into programme design and delivery, including good practice and challenges and the learning that has been generated and applied since the Cycle 1 evaluation. Specifically, the Cycle 2 evaluation seeks to answer the following questions:
PEQ 10.1 In what ways has the programme design or implementation changed in relation to gender responsiveness/inclusion at programme and project levels?
This will focus on what has changed and how. What impact does this have on 1) alignment with PF Gender Policy and Guidance; 2) expected impact on G&I and distributional impacts of projects?
In the case of the AER this means, in particular, how has the programme revised and actioned its definition of G&I? How has G&I been integrated into the ToC, logframe and strand theories of change? Is the approach taken likely to result in meaningful outcomes?
The broad approach to evaluating G&I across the PF is outlined in the Early Thematic G&I Evaluation Approach Paper.[192] The primary tool used by the EL team is the G&I scorecard that provides a broad framework to guide the focus and development of interview questions and the document review. The scorecard will be used to interrogate key areas of the programme according to different dimensions – programme design, internal capability, financial resources, accountability mechanisms and partnerships. A summary of the scorecard is available in Section 2.5 of the Cycle 1 Approach Paper.
[192] Available at: https://www.pflearning.co.uk/x/5oOn
The G&I Scorecard will guide the document review and interviews with the PMT, implementing partners and external stakeholders. The completed scorecard will be added as an annex to the evaluation report.
ASEAN Economic Reform Programme Cycle 2 EL team
The Cycle 2 EL team differs little from the Cycle 1 team. The Programme Evaluation Lead, both Principal Evaluators, one of the senior Evaluators, the Evaluator, the VfM and SB Thematic Lead and the G&I Lead are the same. One Senior Evaluator left the team during Cycle 1 due to other commitments. The EL team has added one senior evaluator with specific experience in inclusive finance to better support evaluating programme performance in designing for and achieving inclusivity in the capital markets development and fintech strands of the ER 3 pillar. The Cycle 1 national consultants for Myanmar and Vietnam will not be re-engaged as the Cycle 2 sample focuses on other countries. A national consultant for Thailand is deemed unnecessary as both the Programme Evaluation Lead and the proposed senior evaluator live and work in Thailand. A national consultant for the Philippines is deemed unnecessary as the Programme Evaluation Lead previously lived and worked in the Philippines. A national consultant for Malaysia is deemed likely to be necessary and recruitment will begin once the JFU and EL have agreed on a budget for the current cycle.[193]
[193] See note on the status of the Cycle 2 evaluation budget, below.
The programme EL team for Cycle 2 is set out in Table 25 below:

Table 25: Programme Evaluation and Learning team members
ROLE	LOCATION/NOTE
Programme Evaluation Lead	Bangkok, Thailand
Principal Evaluator	Melbourne, Australia
Principal Evaluator & Client Relationship Manager	Jakarta, Indonesia
Senior Evaluator, Inclusive Finance	Bangkok, Thailand
Evaluator (UK)	London, UK
Thematic Team Lead (VfM and SBs)	London, UK
G&I Lead	London, UK
National Consultant (Malaysia)	Awaiting JFU approval of candidate

Programme manager’s statement for Cycle 2
### How the findings will be used
The findings of the evaluation and key learning points will inform the ongoing oversight and management of the programme. The findings will also help to prioritise and manage any new budget capacity realised in Year 2.
The evaluation and the Annual Review processes are on course to be better aligned this cycle. We have strongly encouraged the EL team to support coordination on sampling with the Annual Review and, where possible, to sample jointly. This is intended to minimise disruption to programme implementation and avoid confusion between the processes for the stakeholders.
### How we participated in the evaluation design
The design of the second evaluation and overall approach have been discussed extensively and take account of advice from the programme on issues including:
- potential areas for learning, the opportunity to focus on managing multiple delivery pathways, and adapting to change and challenges within that delivery structure
- the opportunities for successful sampling, where the programme is more mature and where stakeholders are engaged or likely to be participative with the evaluation process
- focusing and prioritising the PEQs in areas where we see the most opportunity to learn and improve and where we hope to generate recommendations for the coming year.
### Communication and coordination are agreed and useful
As in the past cycle, the programme and EL teams have had good and regular communication, with the Programme Evaluation Lead understanding and taking on board the concerns of the programme team and conducting regular in-person and electronic communication. Communication will occur in the region with the FCO at post.
### Clarity around roles, responsibilities and ownership of evaluation products
While both ownership of the evaluation product by the FCO and the need for an independent process are clearly understood, there is a need to coordinate effectively with the Annual Review team on sampling and engagement with stakeholders, particularly external stakeholders. The Annual Review has not yet been planned or commissioned for this year and we will seek to ensure that the EL team is fully informed of the process so that they can effectively engage and coordinate sampling activities. Further, we support the addition of an EL team member to the Annual Review team, if the budget to do so is available.
We have also asked the EL team to be clear in its communication with external stakeholders and ensure that these stakeholders understand that the evaluation is of the PF, the AER Programme and of FCO planning and execution, and not an evaluation of the stakeholders or their operations.
### Adjustments to approach in response to COVID-19 restrictions
We have been consulted by the EL team regarding options to complete the evaluation without in-person meetings or in-person field work. Of the options presented, we prefer to maintain the current schedule, even if the limitations impact the ability of the EL team to triangulate data in answer to some of the PEQs and remote sense-making limits the ability to participate broadly in the development of findings and recommendations. The current planned approach of ‘virtual field work’, with outreach primarily to FCO and implementing partner staff and leadership, with some effort to reach external stakeholders, best meets the FCO’s needs, given the current situation.
We believe that the alternative, delaying the evaluation for 4 to 6 months, is less viable, as there are likely to be few programme activities in the intervening period and stakeholders would then be asked to discuss programme activities from 6 to 18 months prior.

Status of the Cycle 2 evaluation budget
The JFU and EL have not yet finalised a budget agreement post-March. This means that all plans – including schedule, workplan and staffing plan – presented herein are provisional, until an overall budget agreement is reached.
Table 26: Cycle 2 ASEAN Economic Reform Programme provisional evaluation budget
ROLE	PROVISIONAL DAYS
Programme Evaluation Lead	30
Principal Evaluator	35
Principal Evaluator and Client Relationship Manager	7
Senior Evaluator (Southeast Asia)	20
Evaluator (UK)	15
Thematic Team Lead (VfM and SBs)	7
G&I Lead	2.5
National Consultant (Malaysia)	21

Sector alignment
The JFU has recently determined that EL will no longer develop ‘family’ evaluations or use ‘families’ in the organisation of programme or fund evaluations. EL will instead organise evaluation data by sectors, which align with the five Fund-level IOs. The AER Programme aligns with both the Ease of Doing Business and Financial and Economic Reform sectors.
The current plan, still awaiting JFU acceptance, is that the AER Programme’s strand/component findings will feed into two sector reports:
Ease of Doing Business, covering sub-sectors:
- Business Environment (strand/component – Strengthening Business Environment)
- Anti-Corruption (strand/component – Advancing Business and Government Transparency and Compliance)
Financial and Economic Reform, covering sub-sector:
Financial Services (strand/component – Broadening and deepening financial markets)
Update on risks and mitigations
Table 27: Risks and mitigation measures
RISK	LIKELIHOOD (1-5)	IMPACT (1-5)	RISK SCORE	MITIGATION MEASURES	AFTER MITIGATION
					LIKELIHOOD (1-5)	IMPACT (1-5)	RISK SCORE
Lack of engagement of FCO staff at post and their counterparts and of delivery partners with the EL team impacts negatively on the capacity of the EL team to generate findings.	3	4	12	Following on from Cycle 1, the EL team has built good relations with the programme team. Further, the EL team consulted with the PMs at each post in the sampled countries to pre-clear the sampling plan which has helped to build consensus on the approach. Likewise, the EL team has communicated with all delivery partners in advance of the evaluation to set participation expectations. Sampling plans will be communicated well in advance of the evaluation.	2	3	6
Complexity of delivery pathways and multiplicity of government counterparts may inhibit the ability of the EL team to collect complete and accurate stakeholder opinion.	3	3	9	The EL team will work with FCO at post in each sampled country, each year during the approach paper development and from day one of evaluation kick-off to identify stakeholders and request participation. Sufficient time has been built into the schedule to request meetings in advance of fieldwork. This approach successfully mitigated this risk in Cycle 1.	1	3	3
Delivery partners and FCO programme team do not upload monitoring data onto Prospero.	2	4	8	The EL team works very closely with the Monitoring & Reporting team to keep abreast of the programme team’s compliance with data reporting requirements on Prospero. The programme is behind in uploading to Prospero and the evaluation data collection plan relies more heavily this cycle on access to indicators. Fortunately, the programme team has been tracking their progress against indicators offline so that there is a fall-back option.	2	2	4
Turnover in programme staff leads to loss of institutional knowledge.	2	3	6	This is beyond the EL team’s control. The team will check with FCO what knowledge management system is in place to capture and store important information and knowledge that would otherwise be gone when staff leaves. Moreover, all EL products developed with the programme will remain available and accessible through PFLearning for new onboarding team members.	2	2	4
Deterioration in bilateral relations with one or more of the sampled countries inhibits the ability to complete the planned sample.	2	4	8	This scenario will be treated as a finding in itself that must be investigated and reported by the EL team. Mitigation will occur via ongoing MREL coordination calls and back-up sampling plans focused on extended collection in the other sampled countries.	2	2	4
Deterioration in safety/security environment in the region or one of the sampled countries inhibits the ability to complete the planned sample.	5	4	20	This is a potential risk in all evaluations, but the risk is currently elevated due to the global COVID-19 crisis. Mitigation has been considered and agreed: the sampling approach has been revised to conduct all interviews, focus groups, workshops and/or other meetings using teleconferencing tools, with no in-person meetings planned.	2	3	6
Use of remote – telephone and teleconferencing – interviews will limit the ability of the EL team to engage with external and government counterpart stakeholders.	4	4	16	The scope has been revised to reduce reliance on external stakeholders and counterparts. The EL team will continue to attempt to reach out to such stakeholders and request FCO assistance in making introductions.	3	3	9
The EL team does not have the requisite capacity and/or skill composition to complete Year 1 evaluation cycle report.	2	3	6	Recruitment is already underway to fill a vacant post and we expect to find an appropriate team member before we start to prepare for the Cycle 2 evaluation report. The Programme Evaluation Lead and other EL colleagues will carry out in-depth inductions to ensure the new team is rapidly up to speed.	1	2	2

Cycle 2 Approach Paper Annex A: Options analysis memo
On 26 February, EL submitted a draft approach paper to the JFU for the Cycle 2 AER Programme, commencing 1 April. The evaluation plan included in-person sampling in Malaysia, the Philippines and Thailand. Since that time, due to the COVID-19 outbreak, travel has become highly restricted, first by EL policy and later by FCO and national policies of the governments in the planned sample countries. The latest restrictions and anticipation of future restrictions are such that it is highly unlikely that the Cycle 2 EL team will be able to:
- travel to any sampled country
- meet with any FCO, implementing partner, government, or external stakeholder in the countries where the EL team is already located (Malaysia and Thailand)
- deliver any in-person workshop or meeting to the PMT in Singapore or utilise embassy resources in the EL team’s countries of residence to deliver an effective virtual workshop.
In consideration of these restrictions, the AER Programme EL team developed two options for moving forward with the Cycle 2 evaluation in Year 3:
1. Implement a ‘revised scope’ evaluation approach, relying on reduced, limited KIIs and revising the ‘sense-making workshop’ deliverable to a limited teleconference for this cycle, but delivering the evaluation on schedule.
2. Delay the Cycle 2 evaluation until September or October 2020, and delivering the full evaluation plan.
We have considered the pros, cons and risks of each option as presented below.
Table 28: Evaluation Options Analysis
Option	Pros	Cons	Risks
Revised scope, on-schedule approach	Continues to support the AER Programme Annual Review schedule / Meets AER PMT stated preferences / Delivers sufficient learning and programme feedback to support year 3 implementation	Does not sufficiently improve contextual understanding in newly sampled countries / Removes government counterparts, other donors, programme activity participants, and external stakeholders from sampling plan, reducing ability to triangulate evidence / Reduced stakeholder outreach and little or no face-to-face interviews reduces the quality of evidence	Reduced stakeholder outreach and little or no face-to-face interviews may limit the ability to adequately answer PEQ 1.2 (unintended consequences) and PEQ 5.1 (factors contributing to benefit achievement) / Reduced sense-making participation reduces effectiveness of learning and recommendation development
Full evaluation plan with four- to five-month delay	Delivers the full, robust, EQuALS-validated evaluation plan / Delivers outreach to external stakeholders and improves contextual understanding	Does not support the Annual Review / Does not meet PMT preferences / Creates down-stream crowding of evaluation activities for Cycle 3	Insufficient evidence to support the planned Annual Review / Slow return to normalisation requires further delay, interfering with the cycle 3 evaluation / Reduced time until next evaluation frustrates PMT and FCO and reduces ability to deliver an effective Cycle 3 evaluation

We have twice consulted the PMT to understand their needs and preferences and they have confirmed that they prefer option 1. Despite the cons and risks enumerated, we also agree that option 1 is the preferable approach.

If accepted by the JFU, then, we would:
1. Revise the evaluation matrix to specify which stakeholders we expect to reach for each PEQ;
2. Revise the deliverable plan for a teleconferenced sense-making process;
3. Notate which PEQs may not be answerable;
4. Add additional planning on modes and methods of communication with the PMT;
5. Kick off the evaluation a week early to accommodate the additional interview scheduling requirements in anticipation that outreach may be delayed under the current situation;
6. Document these changes in the final approach paper submission.

: List of key informants
ORGANISATION/LOCATION	ROLE
UNDP Malaysia	Programme Assistant
FCO Thailand	Economic & Prosperity Counsellor, Thailand, and UK Permanent Representative to United Nations Economic and Social Commission for Asia and the Pacific (delegated from the Ambassador)
UNDP Thailand	Programme Manager
FCO Singapore	ASEAN ER Programme Officer
FCO Malaysia	High Commissioner & Steering Board Member
FCO, Thailand	Programme Manager
CoST International	Asia Regional Manager
FCO - Vietnam	AER Programme Manager
UNDP Malaysia	Consultant
UNDP - Regional Hub	Project Manager (TAAC)
INCEIF	Leading on Waqf Work Package
CoST Thailand	Programme Head
PwC - with INCEIF	Islamic Financial Workstream Lead
Baranda and Associates, Part of the Rouse Network, Philippines	Managing Partner
FCO Malaysia	Programme Manager
Baranda and Associates, Part of the Rouse Network, Philippines	Junior Associate
PwC	Country Coordinator
FCO - Myanmar	AER Programme Manager
FCO Singapore	Head of Prosperity Fund, SEA
CSO - PJ Residence	President
PFDU	SEA Regional Director, Economic and Trade Policy, Steering Board Member
FCO - Philippines	AER Programme Manager
FCO Singapore	High Commissioner & SRO
PwC - Philippines	FSIP Philippines Coordinator
PwC - Singapore	FSIP Programme Director
FCO - Indonesia	AER Programme Manager
FCO - Philippines	Head of Prosperity
UNDP - Regional Hub	Project Specialist
Barcenas & Partners Law Offices	Consultant, OECD Competition Assessment
CoST Assurance Team	Team Leader
UNDP Malaysia/ Myanmar	Team Leader (Former)
RD/BEIS	Regulatory Attaché
FCO Vietnam	Head of Prosperity, VN and delegated Steering Board Attendee
Rouse	Deputy CEO
CSO- Women's Centre for Change	Liaison Officer
PwC - Singapore	FSIP Programme Coordinator
INCEIF	President of INCEIF
FCO - Singapore	SE Asia Intellectual Property Projects Manager
OECD	Senior Competition Expert
PwC - UK	FSIP M&E Manager
CSO-Penang Heritage	Vice President
FCO Singapore	Head of ASEAN ER Programme
RD/BEIS	Programme Manager
PwC - Singapore	FSIP Programme Manager
UNDP Thailand	Team Leader
OECD	Competition Expert

: Bibliography

AER, Theory of Change, 2018
APEC, Comprehensive Review of Potentially Anti-Competitive Laws and Regulations. APEC Economic Committee, 2020 https://www.apec.org/Publications/2020/03/Comprehensive-Review-of-Potentially-Anti-Competitive-Laws-and-Regulations
APEC, EC 04 2018A - Comprehensive Review of Potentially Anti-Competitive Laws and Regulations, 2019 https://www.apeccp.org.tw/htdocs/doc/Workshop/w2019/19_cplg_002.pdf
Asian Development Bank, Economic Indicators for the Philippines, 2020, available at https://www.adb.org/countries/philippines/economy
Bank Negara, Value based intermediation: strengthening the roles and impacts of Islamic Finance, 2018
Congrave, J. Shaw and Thomas, M, A review of the key issues, evidence of what works and measurement tools. Work and Opportunities for London programme help desk, 2020
Congrave, J, Shaw, A and Thomas, M, Women’s Economic Empowerment and Standards and Regulatory Reform, 2020
CoST International, "Transparent procurement systems: good for the public, the private sector and the SDGs," 2019
CoST Thailand, CoST Impact Study, 2019
CoST Thailand, Gender Audit, 2019
Darani Vachanavuttivong, Sriwan Puapondh, Kasma Visitkitjakarn, Michael Ramirez and Tilleke & Gibbins, "Doing business in Thailand: overview," Thompson and Reuters, 2020
Evaluation and Learning, ASEAN Economic Reform Programme Cycle 1 Evaluation Report, 2019
Evaluation and Learning, ASEAN Economic Reform Programme Cycle 2 Approach Paper, 2020
FCO, “ASEAN Economic Reform programme (renamed from Southeast Asia Economic Reform Programme) Business Case,” 2018
FCO, AER PF Non-ODA Bid Form, 2020-21 Cycle, 2020
FCO, AER Programme Quarterly Reports, Year 2, Qs 1-4, 2019-20
FCO, Annual Review of the AER Programme, 18/19, 2019
FCO, FSIP Year 1, Q4 Quarterly Report, SRO Narrative, 2019
FCO, Global Trade Programme, Vietnam Country Plan, 2019
FCO, SE Asia Economic Reform Business Case, 2018
FCO, SE Asia Economic Reform Business Case, FCO, 2018
FCO, Southeast Asia Draft Secondary Benefit Plan, 2018
FSIP, A FinTech-enabled, Waqf financial product suite Interim Report, 2020
FSIP, DRAFT Gender Equality and Social Inclusion Plan, April 2020
FSIP, FSIP - Annex 2.15 Capital Markets Report, 2020
FSIP, FSIP - Concepts for Work package 4_07042020, 2020
FSIP, FSIP - Programme workplan revision, Apr 2020
FSIP, FSIP – Secondary Benefits Plan, 2019
FSIP, FSIP - ToR IF_MYS_01 V4.F (approved), 2020
FSIP, FSIP - ToR IF_MYS_02 V4.F (approved), 2020
FSIP, FSIP - ToR IF_MYS_03 V4.F (approved), 2020
FSIP, FSIP COVID-19 report update, 2020
FSIP, FSIP DRAFT VFM Plan, 2019
FSIP, FSIP GESI Plan Minimum Compliance, 2020
FSIP, FSIP GESI Plan, 2019
FSIP, FSIP Implementation and Workplan Budget Summary, 2019
FSIP, FSIP Inception Report, 2019
FSIP, FSIP logframe, May 2019
FSIP, FSIP Monthly Report, March 2020
FSIP, FSIP Programme Manual v2, 2020
FSIP, FSIP Programme_IF Year2 WP and Budget Review 24/04/2020, 2020
FSIP, FSIP Quarterly Progress Reports, Qs 1-4, 2019-20
FSIP, FSIP Secondary Benefits Plan
FSIP, FSIP Theory of Change, 2019
FSIP, FSIP TOR Intellectual Property Philippines 01, 2020
FSIP, FSIP TOR Intellectual Property Philippines 05, 2020
FSIP, FSIP TOR Intellectual Property Philippines 06, 2020
FSIP, Interim Report – WP 1- Pre-Emergency Fund based on Islamic Social Finance Interim Report, 2020
FSIP, Interim Report – WP 3- Country Report and Masterplan on the Islamic MSME Financing Sector Interim Report, 2020
FSIP, Milestone report: IP enforcement manual, 2020
FSIP, Philippines IP diagnostic report, 2019
FSIP, Work package milestone reports: IP 01 – M02, 03, 04; 05 – M03; 06 – M03, 04, 2020
GIACC (National Centre for Governance, Integrity and Anti-Corruption (Malaysia)), Monitoring Dashboard, 2020
Global Innovation Policy Centre, Art of the Possible – US Chamber International IP Index, 2020, https://www.theglobalipcenter.com/wp-content/uploads/2020/01/Philippines.pdf
ICD-Thomas Reuters, Islamic Finance Development Report: Towards Sustainability, 2017
IFN FinTech, ‘IFN Islamic FinTech Landscape recognises three more start-ups’, 21 December 2017
IMF, Philippines policy responses to COVID-19, 2020, available at https://www.imf.org/en/Topics/imf-and-covid19/Policy-Responses-to-COVID-19#P
IPO, Inhouse IP draft logframe, May 2020
IPO, Inhouse IP Enforcement Seminar Report, 2018
IPO, Inhouse IP Innovation and Valuation Seminar, 2019
IPO, Inhouse IP Quarterly Reports, Qs 1-4, 2019-20
IPO, Inhouse IP Enforcement Seminar Report, November 2019
IPO, UK-Indonesia IP Seminar Report, 2019
Kasetsart University, CoST TH Assurance Report, 2019
Maurice Burke, “Geckos, crocodiles and paper tigers – anti-corruption enforcement in South East Asia,” Global Investigations Review, 22 September 2015
OCED, Quarterly Progress Reports Qs 1-4, 2019-20
OCED, The Competition Assessment Report, 2020
OECD Draft Revised Logframe, May 2020
OECD, ‘The Impact on Competition of State-Owned Enterprises in Logistics – A Focus on Small-Package Delivery Services’, 2020
OECD, ER 1.3 strand logframe, 2019
PwC, Mail - MYS FSIP - Progress Update Meeting 7th April
PwC, Mail - Re_ FSIP MYS_ Islamic Finance Y2 WP Discussion _27 April 2020
RD BEIS, ER 1.2 strand logframe, 2020
RD BEIS, Quarterly Progress Reports, Qs 1-4, 2019-20
RD International, Gender Strategy, n.d.
RDI, Draft Logframe, May 2020
RDI, Implementation Plan, March 2019
RDI, Philippines Mission Report, March 2019
RDI, Philippines Mission Report, October 2019
RDI, South East Asia Regulatory Reform Programme Implementation Plan, 2019
RDI, Work Calendar Plan Daft, April 2020
The City UK, Global Trends in Islamic Finance and the UK Market, 2018
The Philippines Star, ‘IPOPHL seeks amendment to Intellectual Property Code’, 15 April 2019, available at, https://www.philstar.com/business/2019/04/15/1910053/ipophl-seeks-amendment-intellectual-property-code
UNDP, "High-Level Seminar on Increasing transparency and integrity in Public Procurement in the context of the SDGs, a summary," 2019
UNDP, “Regional Project on Promoting a Fair Business Environment in ASEAN, 2018-21”, 2018
UNDP, “Support to the effective implementation of public procurement reform in Thailand,” 2019
UNDP, ER 2 logframe, 2020
UNDP, Fair Biz Anti-Bribery Management System Pilot Programme Draft, 2019
UNDP, Fair Biz Draft Gender Report, 28 August 2019
UNDP, Fair Biz in ASEAN Project 2nd Steering Board Meeting Report, 2019
UNDP, Fair Biz Malaysia GIACC ToR_2019
UNDP, Fair Biz Malaysia integrity & training module_2019
UNDP, Fair Biz Malaysia Year 2 Work Plan, 2019
UNDP, Fair Biz Malaysia Year 3 Work Plan, 2020
UNDP, Fair Biz Mid Term Review (Aug 2018 – Apr 2019), 2019
UNDP, Fair Biz Project Log Frame (Updated Version), 2019
UNDP, Fair Biz Project Theory of Change (Version 1), 2018
UNDP, Fair Biz Project Theory of Change (Version 2), 2019
UNDP, Fair Biz Social &Environmental Screening Report, 2019
UNDP, Fair Biz Strategy Report, 10 Feb 2020
UNDP, Fair Biz Summary Report_ Future of Leadership is Gender Equal, 2019
UNDP, Fair Biz ToR for Fair Biz Advisory Group, 2020
UNDP, Fair Business Programme 1st Annual Report, 2019
UNDP, Fair Business Programme Logframe, Revision July 2019
UNDP, Fair Business Programme Logframe, Revision March 2020
UNDP, Fair Business Project Document, 2018
UNDP, Matrix on possible activities, actors, beneficiaries, in addressing gender & anti-corruption issues in the business environment. 2020
UNDP, Prosperity Fund Quarterly Reports, Year 2, Qs 1-4, 2019-20
UNDP, Review and mapping of regulatory, statutory body & oversight landscape in Corporate Malaysia, 15 Dec 2019
UNDP, Social and Environmental Screening, finalised October 2019
UNDP, Workplan for Thailand, 2018
United States Trade Representative, Special 301 Report, 2019, available at https://ustr.gov/sites/default/files/2019_Special_301_Report.pdf
World Bank, Philippines Economic Update, October 2019. https://www.worldbank.org/en/country/philippines/publication/philippines-economic-update-october-2019-edition
: Map of programme evaluation questions to report sections
Table 29 below maps the PEQs to sections of this report. Note that the PEQ numbering is aligned to the Fund EQs and therefore is not sequential.
Table 29: Programme evaluation questions mapped to report sections
SECTION	PEQS
4.1 Design	7.1, 8.1, 11.3
4.2 Progress toward results
4.2.1 Primary purpose	1.1, 1,2, 2.1, 2.2, 5.1
4.2.2 Secondary benefits	1,1, 1,2, 5.1
4.3 Gender and inclusion	7.3, 10.1
4.4 Governance and management
4.4.1 Using the Cycle 1 evaluation	11.1
4.4.2 Value for money	9.1, 9.2
4.5 Sustainability	7.3
4.6 Learning	7.2, 11.2