Annual Review - Summary Sheet

Title: ASEAN Economic Reform Programme
Programme Value: £19 million		Review Date: November 2020
Programme Code:	Start Date: April 2018	End Date: March 2022

Summary of Programme Performance
Year	04/2018-08/2019	08/2019- 10/2020
Programme Score	B	A
Risk Rating	Moderate/Major	Moderate

Summary of progress and lessons learnt since last review
This is the second annual review of the ASEAN Economic Reform (AER) Programme, covering the period August 2019 to October 2020. The review team held a number of bilateral interviews with key FCDO officials including the SRO and AER programme leadership and team. Consultations took place with all the delivery partners, some posts and in-country beneficiaries. These consultations were supplemented with desk assessments of progress reports, evaluations reports and analysis of data/information provided by the AER programme management team and delivery partners.

The review team has looked across the whole programme, against the outputs, outcomes, and impacts set out in the Business Case and in the updated logframe and Theory of Change. The review team has also considered progress made against the results framework while considering whether the outputs are still the right ones in order to achieve the outcomes and impact and if the indicators are monitoring progress.

From these assessments it is clear that the programme is relevant to inclusive economic growth and poverty reduction in the PF6 countries - Indonesia, Malaysia, Myanmar, the Philippines, Thailand and Vietnam, with some additional work across ASEAN - by enabling a fairer business environment and broadening and deepening financial markets. The gender and inclusion objectives of the programme have a potential to contribute to the economic empowerment of women and girls, and other excluded groups, through wider accessibility to business opportunities and financial systems. Gains are being made, but there is still work to be done to ensure that G&I is effectively embedded, monitored and responding to the voices, needs and capacities of excluded groups. It remains important to target effectively and draw out the qualitative gains to demonstrate and deliver on primary purpose.

Year 2 of programme implementation has seen significant progress, with all programme strands now up and running and starting to deliver outputs. Overall, the programme embeds UK standards in a region where UK expertise is highly regarded, and has been well-received by our country partners.

Delivery from January 2020 has been dominated by the global pandemic of Covid-19 (C-19) as the Programme Team and Delivery Partners work through the implications for the programme. This has been challenging, particularly as the situation remains uncertain. The PF6 countries have had some success battling the pandemic, but the crisis and required response have significantly impacted the programme. Travel restrictions, the refocusing of resources to attend to the crisis both on the part of the FCO and partner governments and the need for programme re-design to accommodate new time frames has led to delays in programme implementation for some strands by approximately 3 to 6 months.

Despite the pandemic, the AER programme objectives remain highly relevant and important. A strategic decision was taken to maintain the focus on the current programme rather than trying to pivot to address new C-19 priorities. Indeed, the programme objectives as they stand will support economic recovery and leave room to integrate an increasing focus on ‘building back better, and stronger’. In addition, the alternative delivery models adopted have produced some unexpected benefits with accessibility and reach.

The review team assesses that although the AER has made a good progress in a number of areas since the previous Annual Review; significant challenges around measuring the achievement of outcomes and impacts of the programme need to be addressed to ensure the programme is effective and represents good value for money (VfM).

Achievements

Specific achievements by strands over the last 15 months, include:

The strand delivered by RDI BEIS has made significant progress. For example:

  - The Prime Minister of Vietnam signed Resolution 68 that aims to tackle the red tape challenge in Vietnam and is modelled on the UK Governments successful Administrative Burden Reduction Programme
  - In the Philippines, RDI have signed an MoU with the Anti-Red Tape Authority and are currently developing a programme of work to include training, and developing a ‘whole of government approach guideline’.

OECD have made significant progress finalising the Competition Assessment Reports and conducted a successful launch of the reports in Thailand. Using the OECD Competition Assessment Toolkit to develop the reports, the resulting recommendations will promote more pro-competition regulation and a level playing field for businesses in the region.

The UNDPs FairBiz Programme has delivered progress and made significant contributions related to gender and inclusion. Public officials in Indonesia and Thailand have been introduced to UK government standards and trained on using tools to verify supplier quality and compliance. The UNDP’s partner CoST (the Infrastructure Transparency Initiative), helped the Thai government substantially reduce its procurement costs (estimated to be in the region of US$360) by introducing higher standards of transparency and integrity into the procurement system. In addition, in Myanmar, the FairBiz Programme is working with the government to reduce corruption through the recently established Corruption Prevention Units (CPUs). Targeted technical support has been provided to CPUs on how to apply a Corruption Risk Assessment (CRA) when creating legislation. At the time of the review, participants from over 20 Ministries and Union organisation’s CPUs had been trained including the Ministry of Health and Sports, the Ministry of Education and the Ministry of Agriculture, Livestock and Irrigation..

The FSIP strand delivered by PwC has generated a number of outputs. For example:

  - The FSIP IP work-stream has successfully developed and published IP Enforcement Manuals on how the IP enforcement system works in Indonesia, Vietnam and the Philippines. In addition, the IP work-stream also developed the ASEAN IP Manual which compiles IP laws and procedures in 10 ASEAN member countries.
  - The FSIP programme hosted a FinTech Roundtable as part of the Singapore FinTech Festival (November 2019), attending by the ASEAN regulators and representatives of the Financial Conduct Authority (FCA) and the Bank of England (BoE). The roundtable facilitated an exchange on regulations for FinTechs and lessons learned by the UK.
  - FSIP refined the regulatory Code of Conduct for Peer-to-Peer (P2P)/IT lending in Indonesia with the FinTech Lending Association (APFI). This will help to increase the speed and transparency of new digital technologies in the financial sector.
  - FSIP has identified opportunities, trends, and gaps in the Vietnamese FinTech landscape, detailed in the FinTech Ecosystem Catalogue report. The report identifies a number of recommendations to improve the Fin Tech landscape.
  - In Myanmar, under the FSIP Accounting Standards work stream, training was provided to build the capacity of Myanmar financial regulators on IFRS9 implementation and regarding update of prudential return templates.

Complimenting this activity, the In-House IP strand has delivered three IP capacity building seminars to over 400 officials from all ten ASEAN member states, covering topics on IP enforcement and IP innovation. These seminars helped officials to learn best practice and devise more effective IP enforcement strategies and methods to commercialise IP assets.

With the aim of promoting more inclusive, efficient and diversified markets to create new financing opportunities, Economic Reform Programme, in collaboration with the PF Low Carbon Energy Programme, arranged a visit to the UK for financial services regulators from all 10 ASEAN countries, representing the two key ASEAN working committees responsible for developing the region’s sustainable finance market – the Working Committee on Capital Market Development and the ASEAN Capital Markets Forum .The visit enabled them to learn about the UK’s approach to sustainable finance, financial innovation and how to facilitate the participation of sophisticated investors in cross border capital market activity. This practical support from the UK for a key pillar of the ASEAN Economic Community blueprint provides a tangible demonstration of the UK commitment to ASEAN as we continue to develop our relationship.

Specific management achievements over the last 15 months, include:

The programme has recruited Head of Programme and Programme Manager. Both of these roles commenced in September 2019 and are based in Singapore.

The programme has worked with PwC to improve the implementation plans/ work packages resulting in the Steering Board agreeing to move into implementation with PwC (a contract variation was signed in November 2019). The programme team also signed a second contract variation for the PwC FSIP programme to accommodate changes in the schedule, budget and delivery mechanism as a result of C-19. This variation also incorporates changes to financial management as well as defining penalties for late delivery and the service levels that PwC are held accountable to.

Working with MREL partners and 5 delivery partners on strand level logframes and the programme log frame to ensure that they can accurately capture and measure results, and that they are all aligned with the programme. The Theory of Change Data have been uploaded onto Prospero.

The programme has improved its quarterly reporting. The programme team are working closely with delivery partners to ensure evidenced reporting at both output and outcome level. Effort has been invested to increase the quality of good news stories as a tool to demonstrate results/impact. Learning and actions taken to address annual review and evaluation recommendations are now presented in the reporting.

A merger has been negotiated to integrate the PF Indonesia Regulatory Reform Programme into the RDI BEIS strand of ER. Programme teams are currently working on operationalising the merger.

Challenges and Risks
C-19 pandemic had been a complex challenge for the programme which has in the last 6 months substantially impacted the ability of delivery partners to implement activities. While travel restrictions continue, strict Standard Operating Procedures are in place (e.g. to ensure adherence to physical distancing). These consequently affected engagement levels with government, private sector and other programme stakeholders. In order to mitigate these risks, the programme team have worked very closely with all delivery partners to revise work plans and budgets, taking into account re-scheduling and changing delivery models where appropriate and necessary. This work is on-going with the continuing uncertainties around C-19 and its impact on the region.

The balance between primary purpose (inclusive economic growth for poverty reduction) and secondary benefits, and the extent to which this programme can evidence that it is delivering outcomes and impact is a key risk. The programme has a theory of change and logframes in place, but there needs to be more clarity on how the outcomes and impacts will be achieved, measured and monitored and an effective governance process to manage this. This is particularly important given that the programme is coming to an end in March 2022 with some strands ending in March and September 2021.

The business case demonstrated that the programme is expected to deliver £351m of primary benefits and £352m of secondary benefits over 10 years. The programme has faced delays and reduction in some strands and it is uncertain whether the programme will deliver the anticipated benefits. The programme currently does not maintain a governance process to monitor and compare the programme-wide total benefits to the benefits envisaged in the full business case. This should be included as part of the over-all programme MREL plan.

The programme is delivering several activities in six countries with five delivery partners with a budget of £19m. This makes the progamme complex and ambitious to manage, which may compromise efficiency and the potential to achieve value for money. An example of this is the milestone management process under the commercial contract. Whilst the process has evolved through the ambition to ensure the delivery of quality outputs and results, the large resources required to oversee the process both by the PMO and the FCDO may be disproportionate.

While the programme has successfully adapted to the C-19 delivery environment, the risk of delay as the pandemic continues remains. As some activities have been delayed/ rescheduled while awaiting the end of travel restrictions, there is a growing risk that the continued crisis will make it impossible to deliver some activities within the programme lifecycle.

As a programme that relies on the political will of counter-part governments, the AER programme has maintained a focus on ensuring buy-in through local engagement and monitoring. This should continue in the coming year as several PF6 countries have recently had or are entering into periods of political change, when both context and priorities can shift.

With some delivery strands entering into their final year of delivery in the coming year, the programme should focus on developing evidence of sustainable change, particularly relating to capacity enhancement interventions, through qualitative evidence gathering and delivery partner monitoring.

Recommendations

Recommendations to be met within three months of the Annual Review

As a matter of urgency, the programme should review the programme level theory of change and log frame, and monitoring mechanisms, to ensure that the programme is effectively delivering, measuring and monitoring outcomes and impacts. Following the review, a report on the process, results and strategy of delivering the outcomes and impacts should be communicated to the programme team, managers at posts and delivery partners, and a report presented to the PF Regional Steering Board. The implementation of the strategy should be overseen by the Steering Board.

The programme team should work closely with the MREL team to finalise the programme logframe on outstanding points related to impact, secondary benefits and GESI alignment.

The programme should carry out a benefit audit of the whole programme . The results of the audit should be assessed relative to the target promised in the full business case. The programme must demonstrate that its total forecasted benefits is satisfactory compared to its budget and the overarching ambitions that were agreed in the business case’s investment approval. The results should be applied to the additional funding that the Programme expects to be allocated in February 2021 to ensure the public funds are used at those projects and activities that provide best VfM. The FCDO Economics Unit should support the programme team in carrying out this assessment.

Quality of outputs produced by PwC has continued to be an issue and was also highlighted at the first annual review. The review team did not find any evidence of a Trade or Economic Development expert on PwC leadership team who is responsible for the quality of the outputs. After the completion of the interviews and the review, the review team has been informed that PwC has created a ‘Quality Panel’ to improve the quality of the outputs. Since this work was carried out after the review period, the review team has not assessed the quality and the composition of the Panel. The review team recommends that the programme team closely monitors the effectiveness of the panel and ensures that the ‘Quality Panel’ includes a trade / economic development expert to assess the level of improvement in the quality of deliverables. The ‘Quality Panel’ should be responsible and accountable for the overall quality of the outputs.

The highest risk noted by most of the programme stakeholders was time delay for all contract partners to deliver interventions. It is strongly recommended that the programme conduct an immediate rapid review of all projects and delivery timelines. Utilising the programme governance (supported by a commercial expert) to review delivery timelines to ensure that they are realistic within the term of the contract. This review will avoid unnecessary spending.

The programme team should review and update the governance process for changing the scope of the programme to ensure that benefit impacts are included as an equal decision criterion and drawn upon when deciding on any changes related to programme scope. This must be ingrained in its governance processes to ensure that public funds are being spent effectively

Recommendations to be met before the next Annual Review

The programme team should strengthen monitoring of G&I progress at country level through capacity building of managers at post where possible.

The programme team should work together with PwC to reduce 366 milestones to a manageable level – whilst the current operating model works, it requires a lot of time and resource on the part of both programme teams. Any potential changes should be reviewed in the light of VfM, by the programme team, noting that the programme will be entering it’s final year of delivery. It is also suggested that the programme undertake a lessons learned exercise on this particular delivery model, and share the findings across other PF programmes. The lessons learned will be assessed at the next annual review PF.

The review team recommends that the programme should use the relevant contract clause to carry out a Satisfaction Survey of the commercial contract to capture satisfaction levels which were observed to be variable.

The programme team should Identify opportunities to socialise research and policy outputs, supporting target stakeholders to apply training and knowledge products practically and measure this effectively to demonstrate application and sustainability of capacity enhancement interventions.

In addition to the reporting of ‘good news stories’, the programme should adopt further qualitative indicators as part of their MREL in order to strengthen reporting on primary purpose gains. A programme wide G&I review of existing evidence, challenges and progress, would help to support learning and target remaining efforts on activities with greatest potential impact.

The programme should strengthen localised approaches to G&I including expertise, partnerships and regular beneficiary engagement aided by beneficiary mapping exercises.

The programme should closely measure the unintended negative impacts on at risk groups, ensuring suppliers conduct regular analysis, adopt mitigation strategies and report accordingly.

Identify and act on opportunities to expand the programmes beyond a focus on gender, integrating wider aspects of inclusion such as disability where relevant.

The FCDO, BEIS and DIT should work together to identify UK firms that possess the capability to support the delivery of projects in ASEAN and, when opportunities begin to emerge, to raise their awareness of the Programme and the potential opportunities this could generate in support on secondary benefit realisation (outstanding).

Integrate SB advisors into programme implementation to enable them to identify and support potential benefits as they arise.

Draw up a programme wide SB plan, with updated findings from the recent mapping exercise and identify appropriate indicators to include in the programme log frame.

In terms of secondary benefits, it was noted that tangible benefits are likely to materialise towards the latter stage of the programme time line and beyond the current programme timeline. It is worthwhile to consider conducting an evaluation of impact beyond the lifetime of the programme to capture secondary benefits.

Recommendations for wider Prosperity Fund

When entering into large and complex contracts with the private sector it is strongly advisable that PF invests in skilled commercial contract management to manage the contracts. This, along with lack of clarity in the original procurement is likely to be the underlying cause to many of the issues noted by the review team. However, co-operation and partnership working has helped the programme make significant improvements this year. The programme should carry out a lesson learned exercise on the delivery models and share with the wider PF so that the lessons could be applied across the portfolio.

The programme was one of the first PF programmes to undertake procurement of a commercial contract, and it is now evident that the process could have been better, with suitably qualified commercial staff to provide support, greater clarity in the statement of requirements, and utilising all the framework contract tools that have since become available. The legacy of this early procurement has impacted both parties. However, there is clear evidence that both the Programme Team and PwC have worked very hard to overcome the challenges and have gone above and beyond their collective remit to continuously improve this. This is an example of good partnering and collaborative working. FCO Commercial should ensure that suitably qualified experts are procured to scope and procure contracts going forward and to also provide posts with dedicated expertise to execute the contract in fairness to both parties

At PF level it is recommended that the procurement and delivery models of the programme should be re-considered. Each programme is scoped and based on their bespoke requirements, evidence suggests that whilst the large global advisory services such as PMO and Project Management has their benefits, the technical expertise (particularly at project level) and relationships with overseas governments appears to be best placed with posts and local SME’s where technical advice needs to be contextualised and sector specific. In turn the PF may be paying a premium for others to procure this within their supply chain. Going forward PF should consider enabling and resourcing posts to deliver programmes with the correct experts and drawing more on OGD’s.

SRO Commentary

I am pleased to see that the programme has made positive progress to be awarded an ‘A’ by this annual review. On the whole, the programme is delivering well across all strands, with notable successes particularly for the UNDP strand looking at business integrity and anti-corruption in ASEAN, the RD BEIS implemented regulatory reform programme, and the In-House IP programme.

I welcome the recommendations provided by the review, and will give them careful consideration with my programme team. It is noted that the team are already addressing a number of these, such as strengthening the log frame; developing a programme wide action plan for G&I and secondary benefits; and reviewing whether management of the commercial contract can be made more efficient. It is helpful that these priorities have aligned. I also agree with the importance of achieving value for money at every level of implementation across the portfolio and I will be asking my team how best this can be achieved in the light of the recommendations made.

As the programme enters its’ final year of implementation, I think there are a number of issues raised as part of the review which may present an opportunity for lesson learning across the Prosperity Fund, and to inform programme design and implementation in future. I look forward to discussing these issues with PF colleagues.

My thanks to the Annual Review Team and to all the Programme Team for their hard work to date.

Kara Owen, British High Commissioner to Singapore
SRO ASEAN Economic Reform
19 February 2021

JFU Commentary
The JFU welcomes the recommendations made in this Annual Review. We recognise the important role the programme is playing in strengthening dialogue and relationships on economic reform issues across the Indo-Pacific region, and it is testament to the efforts of the team, and their commitment to acting on the recommendations of the 18-19 review, that this AR has achieved an ‘A’ rating, despite the challenges of the COVID-19 pandemic. In particular, we agree with the recommendation to review the logical framework and theory of change and to revisit the governance arrangements to ensure the full range of benefits are more routinely monitored, captured and communicated.
Many thanks also for the observations made about the wider PF procurement model and the need for the team to be able to access specialist commercial expertise. This is something that will be considered more broadly, in consultation with relevant commercial leads, as the transformation process progresses within FCDO.
Many thanks to the Annual Review Team and the Programme Team for their work on this review and on the programme.
Daniel Davis
Head, Prosperity Fund
Joint Funds Unit
Cabinet Secretrait
25 March 2021

List of Acronyms
List of Acronyms
Abbreviation
AMS	ASEAN Member States
AR	Annual Review
AER	ASEAN Economic Reform Programme
ASEAN	Association of Southeast Asian Nations
BEIS	Department for Business, Energy and Industrial Strategy
DIT	Department for International Trade
FCO	Foreign and Commonwealth Office
FinTech	Financial Services Technology
FS	Financial Services
IP	Intellectual Property
IPO	Intellectual Property Office
IPRs	Intellectual Property Rights
JFU	Joint Funds Unit
OECD	Organisation for Economic Co-operation and Development
PF	Prosperity Fund
PFDU	Prosperity Fund Delivery Unit
PwC	PricewaterhouseCoopers
RACI	Responsible, Accountable, Consult , Inform,
SB	Secondary benefits
SOEs	State owned enterprises
UNDP	United Nations Development Programme

## A. INTRODUCTION AND CONTEXT (1 page)

DevTracker Link to Business Case:	https://www.gov.uk/government/publications/asean-economic-reform-programme
DevTracker Link to Log frame:

Prosperity Fund
The cross-Government Prosperity Fund (PF) was created in 2015. The primary purpose of the Prosperity Fund is to support the inclusive economic growth needed to reduce poverty in partner countries. Through this primary purpose, the Fund’s activities will contribute to the UN Sustainable Development Goals (SDGs). The fund also looks to create new economic opportunities for international business, including UK companies, and mutually beneficial economic relationships as secondary benefits, as a result of this economic growth. The Fund has a budget of £1.2 billion over the 7 years (2015/16-22/23) to provide technical assistance to partner countries to promote economic reforms and remove barriers to trade, to strengthen policy capacity and build strong institutions and tackle corruption.

The ASEAN Economic Reform programme
The ASEAN Economic Reform (AER) programme is a GBP 19 million Prosperity Fund (PF) programme. Its main objective is to promote inclusive economic growth by improving the economic environment in six ASEAN member states – Indonesia, Malaysia, Myanmar, the Philippines, Thailand, and Vietnam, collectively referred to as the PF-6. The programme also aims to generate new opportunities for international business (including UK businesses) to contribute to, and benefit from, economic growth in those countries. The Business Case (approved in 2018) estimated that programme would deliver £351m of primary benefits and £352m of secondary benefits over 10 years. This assessment will be considerably impacted by the global economic downturn as a result of Covid-19; however, an assessment has not been carried out to assess these impacts.

The programme aligns with the 2015 Aid Strategy objective ‘Promoting global prosperity,’ namely using Official Development Assistance (ODA) to promote economic development and prosperity in the developing world, contributing to the reduction of poverty and also strengthening UK trade and investment opportunities around the world.

ASEAN has experienced a decade of high economic growth that has lifted 100m out of poverty. However, there are still 87m people below national poverty lines in SE Asia and 38m people who fall below the World Bank’s $1.90 a day poverty measure and economic inequality in the region is growing. While still comparatively strong, economic growth in Southeast Asia has moderated in recent years as it faces risks from, and in turn becomes a greater risk to, the wider global economy. Advances in innovation and productivity need to be made which requires tackling business, investment and trade barriers and pushing for regulatory reform to increase jobs and contribute to the prosperity of people at the bottom of the income pyramid. This includes identifying and addressing the gender and social exclusion dimensions of these barriers to increase job opportunities and productivity for women and men, in the formal and informal sectors, for small and medium enterprises as well as big business.

The programme seeks to reform the economic environment, supporting, extending and cementing poverty gains in ASEAN, through efforts under three ‘pillars’ of activity:
- ER 1. Strengthening the business environment through Intellectual Property (IP) enforcement (ER-1.1), strengthening regulatory frameworks (ER-1.2) and competition policy (ER-1.3);
- ER 2. Improvement of business and government transparency and compliance with anti-corruption reforms;
- ER3. Broadening and deepening financial markets with components including capital markets development, Financial Services technology (FinTech), and accounting standards.

These in turn feed into two intermediate outcomes in the Prosperity Fund’s Theory of Change:
- (IO4) Trade, Financial and Economic Reform: PF Countries have better financial and economic systems, which support business growth
- (IO5) Ease of Doing Business: PF Countries are on paper and in practice easier places to do business. Positive experiences of investors and other private sector actors become well known.

The programme outcomes, if achieved, are expected to contribute to inclusive economic growth and poverty reduction by enabling a fairer business environment and broadening and deepening financial markets.

Implementation Model
The programme is being implemented using a ‘multi-pathway’ approach including direct delivery by the Foreign and Development Commonwealth Office (FCDO), partnerships with other government departments, (the Department for Business, Energy and Industrial Strategy (BEIS) and the Intellectual Property Office (IPO)), the United Nations Development Programme (UNDP), the Organisation for Economic Co-operation and Development (OECD), and via a procured commercial provider, a consortium led by PricewaterhouseCoopers (PwC).

The agreement between FCDO and UNDP was finalised in May 2018. The MOU with OECD was signed in June 2018. At this point, preparatory work began on some elements, including in-house IP capacity building efforts, OECD competition assessments and UNDP transparency and anti-corruption efforts. The final AER Business Case was approved in December 2018. Procurement of a commercial provider was also completed in December 2018, when a consortium led by PwC was selected. PwC’s inception period began in January 2019. Since the last annual review, PwC have presented their inception report and after some discussion, a contract variation was signed to approve the move into implementation in November 2019.

C-19 had a significant impact on programme activities, delaying implementation for approximately 3 – 6 months. As a result, the UNDP MoU was extended by six months until September 2021. The RD BEIS MoU has been extended until March 2022. Most recently, preliminary agreement was reached for the Indonesia Regulatory Reform Programme to be merged into the ASEAN Economic Reform Programme as part of the RD BEIS strand.

Programme summary

Pillar - Code and Title	Project Sub-Strand - Code and Title	Total[1]	Primary benefits / Total	Secondary Benefits / Total
ER1 – Strengthening Business Environment	A1: Improving Country IP Systems and Development	£5.6m[2]	£351m	£352m
	A2: Supporting Regional IP Cooperation and Harmonisation
	B1: Deregulation Processes
	B2: Supporting Regional Regulatory Harmonisation
	C: Developing Competition Agencies
ER2 – Advancing Business & Government Transparency and Compliance	A: Transparency & Compliance	£5.8m[3]
	B: Construction Transparency
	C: Corporate Social Responsibility
	D: Anti-Corruption
ER3 - Broadening and deepening financial markets	A: Development & Integration of ASEAN Capital Markets	£7.6m[4]
	B: Islamic Finance
	C: FinTech Regulatory Development
	D: Developing Accounting Standards
	E: Financial Crime/Anti-Money Laundering
Total		£19m
[1] Including Admin and Transitional Funding spend
[2] Includes Admin spend prorated
[3] Includes Admin spend prorated
[4] Includes Admin spend prorated

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment (Primary Purpose – inclusive growth, gender equality, women’s economic empowerment and poverty reduction)
Despite implementation challenges related to Covid-19, most strands have met their output targets this year, using digital methods where they could to maintain progress. The FSIP strand, which was furthest behind in delivery in the previous annual review, has made good strides this year to now implement at speed, although reaching stated outcomes in the timeframe remaining will be a challenge. The anti-corruption strand, continues to demonstrate significant outcomes, including those that are unintended and stands out as a strong example on primary purpose gains.
The priority in the coming months is to monitor the extent to which the outputs are translating into outcomes with target stakeholders through implementation, uptake and change in practice and behaviour. Employing a range of qualitative methodologies would support this process to capture progress and facilitate learning exchanges on what works to realise meaningful change. This process would also help to identify where best to invest efforts, both for the remaining implementation period, but also in a potential phase two of the programme if funds are secured. Opportunities arising which are modest in scope and have the potential to lead to sustainable impact in line with the logframe (e.g. request for mentoring support or small seed funds for a pilot with a women-led business association), should be carefully nurtured with underspends or re-prioritised funds if possible.

Primary Purpose
G&I progress has been notable this year, particularly with the finalisation of the FSIP G&I action plan, although its ambition level, along with all strands except UNDP, is set to minimum compliance including some empowerment activities that could be implemented should the budget become available. This is in part a reflection of the limited PF G&I guidance that was available at the time the programme was designed. The majority of outputs thus far focus on training quotas, inputs into research products, standards or teaching syllabi. There remains a rather significant jump between these quantitative outputs and stated outcomes if they are to be achieved in the lifetime of the programme. Discussions with stakeholders do however, indicate that the linkage between outputs and primary purpose outcomes are there, with expectation that regulatory reform efforts, for example, will have inclusivity gains in the coming months with the likes of SMEs and small players. Similarly, gender assessments and data disaggregation measurements are largely new to both government actors and the private sector and, if adopted, could lead to positive gains through uptake of inclusive practices. In order for this to happen, the programme needs to now focus on helping willing stakeholders to move beyond knowledge acquisition to socialise recommendations, such as supporting trainees to set their own follow up actions and indicators going forward to measure change.
G&I expertise, reporting and accountability mechanisms as well as outputs (such as recommendation papers or tools) are largely regional in their outlook. Although this has led to some benefits in widening the scope of influence and alignment of good practice, it has often been at the expense of a number of country programmes who have struggled to feed in and apply the advice and findings contextually. FCDO should continue to encourage suppliers to localise their G&I expertise, engage more meaningfully and regularly with beneficiaries and establish and support strategic partnerships with local organisations that represent diverse groups such as women-led small businesses. This will support sustainability, better identify contextual priorities, entry points and concerns as well as help minimise the risk that G&I inputs are interpreted as a western imposition. PwC for example, notes that establishment of local partnerships has to be a priority in the next year to meet their outputs and outcomes. For other strands nearing completion, this recommendation will help to shape phase two methodologies and approaches of delivery.
FCDO programme managers at country level would benefit from additional capacity building on G&I to help monitor if partners are meeting minimum standards in implementation and identify good and harmful practice. The most effective and efficient methodologies should be determined in discussion with programme staff, relevant PF technical advisors and where relevant, G&I experts from suppliers. This will support the fast identification and mitigation of unintended harm and highlight positive impacts. The importance of ongoing analysis, reporting of G&I risk and setting mitigation measures remains high and needs to be more tangibly included in existing reporting mechanisms.
Covid-19 (C-19)
C-19 has created a sense of urgency and highlighted the importance and timeliness of numerous strands, notably with fintech in its reach to deliver social protection to unreached groups in the Philippines or in the need to reduce red-tape and corruption to enable SMEs to access funds and find their feet at this time. The programme should continue to closely analyse the impact of C-19 on at risk groups and flexibly respond to the needs, priorities and opportunities to strengthen primary purpose gains. C-19 has supported the accessibility and potential for inclusivity in online capacity building seminars with in house IP noting for example 350 participants, instead of the usual 70-80 expected and UNDP attracting 1900 registrants from 39 countries. Some interviewees have noted that online events have also reduced unequal power dynamics, providing more visibility for women to contribute. However, days of training have been squeezed into reduced hours online, inevitably reducing scope and quality of content and there have been limitations in face to face interaction with diverse groups in consultation and follow up. Furthermore, not all countries have noted the gains in virtual events, with some interviewees emphasising the critical importance of face to face engagement in their culture. It will be important in the next year to capture the learning and impact of online methods and look for hybrid models to engage stakeholders as and when the situation allows. C-19 also provides the opportunity to consider how to build on primary purpose through “building back better” with an impetus to be greener and more inclusive. The programme currently interprets inclusion as gender for the most part, and so there is more to do with wider excluded groups.
Annual outcome assessment (Secondary Benefit)
As the programme is now in full implementation, the focus is now widening to include a secondary benefits plan. Various opportunities have now been identified but tangible secondary benefits are likely to materialise as significant programme results are realised towards the latter stage of the programme timeline and beyond the current programme timeline. It is therefore worthwhile to consider conducting an evaluation of impact beyond the lifetime of the programme to capture extended secondary benefits. Progress has been made in the area of non-ODA funding usage to achieve secondary benefits aligned to ER programme objectives.
The following plans have been proposed and/or approved which will path the way for potential secondary benefit wins in the coming months:
- A regional UK SE Asia Fintech Series, bringing together a group of UK FinTechs based in the region to meet industry and government to pitch their products and services.
- A UK-Thailand Fintech event comprising of a series of webinars to promote opportunities for UK companies to engage with local stakeholders ahead of the event, a workshop to showcase UK expertise, business matching sessions and an online content library
- An upcoming visit to the UK for the Secretary General of the Thai Security and Exchange Commission, funding by non-ODA
- An outward mission approval in Myanmar for the Banking Sector Compliance, RegTech and FinTech (ERP), combined with the FinTech series above
- A UK ASEAN Business Challenge Programme for Digital Technology has been proposed by DIT and is under consideration.

There is a network of secondary benefit advisors in the region who provide a bridge between PF programme teams and other government departments in terms of programme potential to achieve secondary benefits. However, these SB advisers need to be more integrated into the programme implementation so they have the necessary knowledge to perform that role. The first workshop of all SB advisers and the programme team took place in October where an exercise to map secondary benefits to intermediate outcomes was done. The aim was to have more clarity around where the benefits can be found and which actions need to be taken to ensure they materialise and are measured accurately. Further work is needed to decide on secondary benefit indicators in the programme logframe.
Although some progress has been made to identify opportunities and link up with other government departments, the annual review recommendation from last year on this point remains valid (see key action 8 below).
Overall output score is A
Most of the strands are on track with outputs meeting expectations, albeit with tangible secondary benefits still to largely be realised. FSIP, with the largest share of the budget, is playing catch up after significant delays but is now making good progress to realise outputs. The key challenges for the programme are to acheive outcomes and impacts for the programme to be effective and VfM.
Summary of changes to the logframe since the last annual review
Substantial work has been undertaken to update strand level logframes and revise the over programme logframe in response to recommendations in last year’s Annual Review and in the cycle 1 Evaluation Report. This included:
- Streamlining the logframe by reducing the number of indicators
- Improving the alignment of the programme logframe to the strand/pillar logframes
- Reaching agreement with all delivery partners on indicator monitoring requirements
- Clarifying the sources and uses of data to be used to measure indicators
- Consulting with DIT and SB Advisor network on options for improved SB indicators
- Uploading the logframe to Prospero, inclusive of the meta data.

The programme logframe has some outstanding issues to resolve related to impact baselines and targets, secondary benefit indicators and reconciliation of GESI indicators with those of the FSIP strand. Quarterly reporting formats now include outputs and indicators to support clearer reporting.
Key Actions (Captured in the Recommendations in Section 1)
In addition to the reporting of ‘good news stories’, the programme should adopt further qualitative indicators as part of their MREL in order to strengthen reporting on primary purpose gains. A programme wide G&I review of existing evidence, challenges and progress, would help to support learning and target remaining efforts on activities with greatest potential impact.

The programme team should identify opportunities to socialise research and policy outputs, supporting target stakeholders to apply training and knowledge products practically and measure this effectively to demonstrate application and sustainability of capacity enhancement interventions.

Strengthen localised approaches to G&I, including expertise, partnerships and regular beneficiary engagement aided by beneficiary mapping exercises (outstanding).

Strengthen monitoring of G&I progress at country level through capacity building of managers at post where possible.

Closely measure unintended negative impacts on at risk groups, ensuring suppliers conduct regular analysis, adopt mitigation strategies and report accordingly.

Identify and act on opportunities to expand the programmes beyond a focus on gender, integrating wider aspects of inclusion such as disability where relevant.

The FCO, BEIS and DIT should work together to identify UK firms that possess the capability to support the delivery of projects in ASEAN and, when opportunities begin to emerge, to raise their awareness of the Programme and the potential opportunities this could generate in support on secondary benefit realisation (outstanding).

Integrate SB advisers into programme implementation to enable them to identify and support potential benefits as they arise.

Draw up a programme wide SB plan, with updated findings from the recent mapping exercise and identify indicators to include in the programme logframe.

Work with MREL team to finalise programme logframe on outstanding points

Key lessons
Key lessons learned are outlined throughout this report and within the summary section.

## C: DETAILED OUTPUT SCORING (1 page narrative per output)

Output 1A: FSIP - Inclusive IP capacity building through knowledge sharing and technical assistance to improve IP and related legal/policy frameworks, regulation and practices
Key Points[5]
[5] Please refer to Annex 1 for FSIP Indicator Table.
The IP workstream aims to promote the effective protection of Intellectual Property rights (IPR) and strengthen legal bases across 4 ASEAN countries; Indonesia, Myanmar, the Philippines, and Vietnam., The IP workstream identified a number of similar areas for support across the countries based on common issues and demands from national stakeholders. These areas include e-commerce regulatory regimes; studies on IP financing and valuation; studies and training for the creative industries; create an IP enforcement data template; and regional (ASEAN) enforcement manuals. The IP workstream developed 26 work packages and has begun implementation on 24 of these packages this year.

Over the past year, the workstream has produced a consolidated ASEAN manual which compiles IP laws and procedures for 10 ASEAN countries. In addition, 3 IP Enforcement Manuals have been created on how the IP enforcement system works in Indonesia, the Philippines and Vietnam. The manuals were published in cooperation with the British Chambers of Commerce, aiming to provide foreign businesses with a picture of how IP enforcement works in SEA.

In Indonesia, an IP Toolkit is under development to help creative businesses to discover and record different types of IP and intangible assets they own. The tools was delivered to the Ministry of Tourism and Creative Sector for testing in September 2020. In Vietnam, the programme has develivered a research report to the Copyright Office based on limitations and exceptions on copyright regulations across five jurisdictions.
       Gender and Inclusion
PwC has now completed its GESI action plan after several iterations. For the IP strand, there is evidence that G&I analysis has influenced decision making in favour of positive impact for women, such as the decision to focus on the creative and consumer sectors of intellectual property which are female and SME dominated. However, opportunities for impact beyond minimum standards have been capped due to budget limitations; PwC should be encouraged to expand its ambition where possible in the next year.

PwC has highlighted some of the potential risks for IP in the coming months in relation to excluded groups. For example, the potential short-term employment and income losses for women and socially excluded groups when tackling the counterfeit and piracy markets. Careful close monitoring of unintended harm and mitigation strategies will need to be outlined in quarterly reporting.

Recommendations:
Closely monitor PwC at country level to ensure that ongoing analysis of risks and opportunities takes place and that partners meet minimum standards on G&I in implementation.

Ensure local strategic partnerships are made and that community-based stakeholder consultation takes place in a meaningful way.

Output 1B: In-House IP: Inclusive IP capacity building through knowledge sharing and technical assistance to improve IP and related legal/policy frameworks, regulation and practices

Key Points[6]
[6] Please refer to Annex 2 for In-house IP Indicators.
The In-house IP Strand is complimentary to the FSIP programme. It began implementation in October 2018 and will conclude in March 2021. It focusses on IP capacity building in the areas of IP enforcement and IP innovation.Focus countries are: Indonesia, Myanmar, Philippines, and Vietnam. However, due to the nature of ASEAN as an intergovernmental organisation governed by consensus,all ten ASEAN member states are included. The PF 6, Cambodia and Laos are ODA eligible and funded through the programme. Brunei and Singapore are funded through a co-funding agreement with the Intellectual Property Office (IPO)The in-house IP strand supports the Economic Reform Programme’s wider objectives of improving ASEAN’s IP regimes and business environment and building positive impact on gender balance and inclusivity by organising and delivering capacity building seminars to facilitate knowledge and skills exchange to beneficiary countries.

The project has a total budget of £750,000Due to Covid-19 and the shift from in-person to virtual delivery the in-house IP strand is forecasting a significant underspend.

The project has successfully delivered three key events from July 2019 until the end of October 2020: the UK ASEAN IP Enforcement Seminar and the 5th ANIEE Meeting in September 2019 in the Philippines;a bilateral IP seminar with Indonesia on copyrights; and the UK-ASEAN IP Enforcement Webinar Series 2020. All events were well received by stakeholders.

Implementation of the IP In-House project strand has been severely impacted by the pandemic, with the continued postponement of delivery due to international travel restrictions and stakeholders being otherwise engaged. The decision was taken to postpone the events in the hope that it would be possible to deliver in person during quarters 3 and 4. However, as the likelihood of this happening has deteriorated, the team have now pivoted to virtual delivery. The first virtual webinar was the UK-ASEAN IP Enforcement Series focusing on digital piracy and e-commerce. The second webinar series is scheduled for November 2020 and will focus on ASEAN IP Innovation. .

The focus has largely been on meeting equitable targets of participants in their capacity building workshops to ensure that men and women benefit from trainings. There is evidence that the consolidation of training material for its digitalisation during Covid-19, has helped to increase accessibility for women to attend and participate. There have also been notable efforts to include senior female speakers to showcase female leadership and visibility. These largely gender-equitable participatory approaches are important. However, going forward it would be beneficial for the project to reflect on whether there are activities that could be implemented to address gender equity in the wider environment of IP.

Recommendation
Further analyse the potential impacts for women and excluded groups who are likely to suffer in the short-term from a crackdown in counterfeit production lines owing to their informal employment. Consider mitigation measures and ensure this is made prominent in further workshops and training.

Output 2 (BEIS): Increased capacity building and collaboration for government stakeholders to improve regulatory practices
Key Points[7]
[7] Please refer to Annex 3 for BEIS increased capacity building indicators.
The Department for Business, Energy and Industrial Strategy (BEIS) via Regulatory Delivery Directorate (RD) – is responsible for the regulatory reform component of ER-1.

The specific programme objectives are to improve the regulatory environment in Vietnam and the Philippines; support implementation of targeted reform programmes to improve regulatory environments in Vietnam and the Philippines, through the strengthening of approaches to the design, implementation and delivery of regulation; improve regulatory efficiency, transparency, predictability and harmonisation in ASEAN, strengthen the business environment for domestic and foreign firms; and support and influence regional regulatory harmonisation in the ASEAN region.

Programme implementation has been affected by Covid-19 with a number of planned activities being disrupted in both Vietnam and the Philippines. Whist activities are now back on track, RD BEIS asked for an extension of 6 months, to ensure that all activities could be completed in the most impactful way. The Regional PF Steering Board have now approved this request.

Despite the challenges of this period, the Regulatory Reform Programme has continued to achieve its programme objectives and is beginning to demonstrate sustainable outcomes and impact. The work the programme undertook with the Vietnamese Government to support the development and passing of Resolution 68 is a great example of this. The work with ARTA in the Philippines on the development of a Regulators Code, and with the Ministry of Justice in Vietnam on setting up a Policy Impact Assessment rating system, provide further examples of the programme drawing on UK strengths and technical expertise to showcase UK best practice, as well as to improve regulatory practices in the region.

G&I components are embedded into MREL activities. G&I standards in regulatory reform are also part of the training syllabus. Evidence of what works for gender equitable regulatory reform was commissioned through the WoW Helpdesk but it was felt the recommendations were high level and difficult to inform design of activities. Similarly, consultations this year to identify gender specific regulatory barriers have also lacked granular detail to action effectively. Interviews with stakeholders, have however, indicated that the G&I components of the training have been useful as a starting point to highlight what could be done and the potential for inclusivity gains for the likes of SMEs is evident.

IRRP submitted a request to merge with the RDI programme strand of AERP. Both programme teams support the merger, and approvals have been sought and given by the PF Regional Steering Board, the IIOC Committee and the JFU Portfolio Board. IRRP will merge with the RDI BEIS Regulatory Reform Programme Strand, adding Indonesia as a third target country. Work is underway to merge the log frame and theories of change, the finances and MREL reporting. The merger will formally take place on 1 January 2021.

Recommendations
Future in country consultation processes should be targeted and adapted to relevant local stakeholders, taking time to provide them with necessary background information and relevant details or skills to engage in a meaningful way.

Where possible, provide flexible inputs to targeted stakeholders on G&I, mentoring them to apply approaches and standards and understand how to monitor impact.

Encourage local actors to share good practice if they implement action plans in order to provide granular case studies on gender equitable regulatory reform.

Output 3 OECD: Increased adoptions of recommendations on use / misuse of competition assessments and special rights and privileges of SOE’s
Key Points[8]:
[8] Please refer to Annex 4 for OECD Indicators.
The overall objective of the Programme is to improve the regulatory environment in the logistics services sector of all ASEAN Member States by making the key regulations more pro-competitive and create a level playing field in the relevant markets. Increased competition will enhance competition and productivity, ultimately leading to reduced poverty and inequality and enhanced inclusive economic growth. The programme consists of two work streams:

  - Ten prioritised competition assessments of laws and regulations – one in every ASEAN Member States – in five sub-sectors in the logistics sector

  - A regional assessment – based on a country-by-country analysis – of the impact on competition of State-owned enterprises and/or government-linked monopolies in certain selected markets in the logistics sector
- The programme is on track for the most part. Key deliverables to date have been:
  - 5 Prioritised Competition Assessment (PCA) reports and 6 State Owned Enterprise (SOE) reports finalised.
  - PCA draft report for Myanmar and Singapore sent for stakeholder comments.
  - SOE Singapore report shared for stakeholder comments.
  - Finalised draft report for Indonesia PCA report
  - Prepared outline of the Regional report for discussion with ASEAN Secretariat
  - Completed the virtual launch in Thailand for mid-September
  - Prepared press briefings and package for Thailand Launch as well as for other launches.
  - Organised and prepared Sixth OECD South East Asia Regional Programme Steering Group meeting (ambassadors from OECD and from the region) that will be held virtually on 6-7 October 2020. Prepared AEGC meeting (delayed from September to 21 October) to be held in October.

The team have faced some challenges due to the pandemic, particularly regarding missions to Cambodia and Laos. However, alternative ways have been found to gather the necessary information, working with the Competition Commissions in country and hiring local consultants to assist with some of the work as necessary. Additional researchers have also been recruited to the programme team at OECD to assist with the additional work load.

As a result, OECD are on track to finalise all the reports by the end of the project in March 2021. However, they have flagged a risk that they may be unable to hold launches across all 10 countries, and have asked to explore the possibility of a short extension to accommodate this.

OECD consulted with women’s organisations during the consultation process, although it was noted retrospectively that the efficacy of this process is dependent on targeting the right groups, and ensuring that time is taken to help understanding of the purpose and goals of the activity. OECD has also included a gender and social inclusion checklist for activities to be completed, before, during and after field work. The recommendations in the competition assessment report, however, were not specific to gender. It was felt the standards were “gender neutral.”

Recommendations
Collect and document information on how adoption of recommendations is proceeding, what the barriers are and how to address these moving forward.

Encourage diverse representation, including CSOs, in the launch of the reports, providing background information on its purpose and goals before the event. Monitor the response to the recommendations and assess the extent to which women may be affected/positively or negatively by the adoption of these recommendations.

UNDP (see Annex 5 for detailed output scorings)
- Output 4a: Strengthened partnerships between civil society and public and private sectors to implement and monitor integrity policy, opening participation for women and under-represented groups.
- Output 4b: Improved transparency in government contracts and increased compliance with international procedures and trade standards.
- Output 4c: Adoption of responsible business practices and good corporate governance including gender and diversity by private companies and SOEs.
- Output 5: Strengthened anti-corruption policies, plans and strategies and improved redress mechanisms.

Key Points[9]
[9] Please refer to Annex 5 for UNDP indicators.
The UNDP led ER2 strand has progressed extensively on its outputs, as well as realising outcome level gains this year, expected and unintended. With the exception of some activities which have been delayed due to Covid-19, most are now in their final stage of implementation. In the Philippines, for example the activities have ended with no plan for year three. There is a need to review the sustainability of the activities, measure and capture successes and widely share innovative practice and key learnings at country, region and global level within the PF. It would be beneficial to work with UNDP to assess where efforts should be concentrated over the coming months in order to maximise potential gains for the remainder of the programme.
Achievements
- The FairBiz programme has been extended until September 2021 (6 months) to allow for completion of programme activities delayed due to Covid-19. Despite, the challenges brought by C-19, the move to virtual working and webinars have been highly successful – leading to an exponential growth in the programme’s online community and supporting government counterparts to embrace the “digital revolution”. Since May this year, it is estimated that almost 3000 people have engaged with the project for the first time. The project now has a YouTube channel and is in the process of developing a website to showcase and share its tools, knowledge and multi-media products enabling products to be easily accessible. Other programme strands would benefit from the lesson learnt and innovative adaptions of this strand in relation to the C-19. There has also been notable progress this year including the following:
  - In Indonesia and Thailand, public officials have been introduced to UK government standards and trained on using tools to verify supplier quality and compliance.

  - UNDP’s partner CoST (the Infrastructure Transparency Initiative), has helped the Thai government substantially reduce its procurement costs (estimated to be in the region of US$360m) by introducing higher standards of transparency and integrity into the procurement system.

  - In Vietnam, the project has established a positive working relationship with the Vietnam Chamber of Commerce and Industry (VCCI). As the 2020 ASEAN Chair, Vietnam will place business integrity and governance together with climate change, at the centre of the ASEAN Business and Investment Summit (ABIS) agenda in the margins of the ASEAN Summit later this year. The programme has also supported the VCCI and one of the largest state-owned enterprises in Vietnam, to enhance its business integrity by developing and applying codes of conduct and internal control systems. This will help reduce corruption, a key problem for business.

  - In Myanmar, the FairBiz Programme is working with the government to reduce corruption through the recently established Corruption Prevention Units (CPUs). Targeted technical support has been provided to two of the CPUs on how to apply a Corruption Risk Assessment when creating legislation.

UNDP’s consistent integration of a gender lens across the programme, alongside targeted G&I interventions, is resulting in significant primary purpose gains, both planned and unforeseen which has the potential for transformative level change within the programme timeline and beyond. For example, the regional webinar on investing in women-led businesses and the Business Integrity Toolkit for Young Entrepreneurs (output 4a) have both been pioneering in their context and very popular in their uptake. The latter, for example, is now the most downloaded document in the UNDP Asia Pacific website library.

The relationship with CoST to achieve output 4b has been a win-win, demonstrating the gains that can be made when linking a sector technical specialist partner (in this case infrastructure), with a development actor specialised in G&I. CoST was influenced to undertake a gender audit, resulting in a specific review of gender equality in infrastructure in Thailand. The findings are now being written up by CoST as guidelines which they intend to roll out globally next year.

Another interesting development has been the unexpected links forged with two of prominent women led associations in Thailand through the Diversity and Inclusion Regional Platform. There is an opportunity to join forces on policy dialogue, where UNDP can help make the connection between government, the private sector and civil society. Women led associations would be best placed to help progress the change required to realise the connections between gender equality and business integrity. They could also help to navigate the contextual barriers, and reduce the perception that G&I advocacy is a western owned concept. Seed funding, through flexible approaches to existing funds, could be worthwhile to support a potential pilot with bespoke training and support for women-led associations.

Challenges
During this year, the programme has prioritised research activities, production of papers and toolkits, media campaigns and online events. Challenges remain in ensuring that materials produced and events held at regional level, are easily interpreted and made relevant/applicable at country level. There has also been significant staff turnover, leading to delays in the Philippines and Indonesia. As with the other strands, ER2 could benefit from increased engagement with a diverse range of local organisations in partnership (beyond consultation and training) to test out materials, provide feedback and feed into decision making platforms and policy dialogue.

UNDP is quite independent, having a well-established network with governments and CSOs, given its huge presence and wide scope. Like other multi-laterals in this programme, this has meant that they could move forward relatively independently of the FCDO staff. The FCDO funding is part of the bigger picture which makes it more challenging to monitor progress, shape activities or attribute impact. Although this has also made it more challenging to keep the UK embassies meaningfully engaged, it has been worthwhile for the UK High Commissioner to Singapore (and SRO for the Programme) to launch key products and visibly support the recommendations coming through.

Recommendations
Capture learning and innovative techniques on digital learning and share with other programme implementers and the Prosperity Fund network

Encourage UNDP to engage more meaningfully with local partners, particularly women-led coalitions and associations, in its roll out of remaining activities.

Review sustainability options with UNDP for the remaining time of implementation including the possibility of flexible funds for targeted activities.

Strengthen links and maintain connection between UK embassies and UNDP in country for closer relationship building, promotion of activities, accountability and monitoring purposes.

Keep a close eye on impact of staff turnover and raise concerns early if gaps are not being filled and activities are delayed.

FSIP Consortium (see Annex 5 for detailed output scorings)
- Output 6: FSIP consortium and In-House – Positive influence on market regulation through ACMF and promotion of international standards in financial services.
- Output 7: Improved capacity and frameworks within key financial institutions and markets.
- Output 8: Capacity building and knowledge sharing to tacke financial crime and money laundering.
- Output 9: Facilitate increased selling of international funds including UK funds in ASEAN and vice-versa; improved links between international businesses including UK and SEA.

Key Points[10]
[10] Please refer to Annex 6 for FS indicators.
The purpose of FSIP is to promote more inclusive, efficient and diversified financial markets to create new financing opportunities for businesses and individuals. FSIP aim to achieve this through providing technical assistance – primarily policy & regulatory support to PF6 governments, with limited direct support to PF6 industry – across six workstreams:

  - Intellectual Property (considered under output 1A)
  - Capital markets;
  - FinTech regulation;
  - Accounting standards;
  - Anti-money laundering and financial crime; and
  - Islamic Finance

FSIP covers all six countries under the ASEAN ERP - Indonesia, Malaysia, Myanmar, the Philippines, Thailand and Vietnam. However, not all workstreams are covered in all six countries. This £7.9 m programme is delivered through a commercial contract by a consortium led by PwC. The FSIP implementation phase started in October 2019 and will run until March 2022.

The last annual review cited a number of challenges for the FSIP Programme. These challenges have been largely overcome, with the FSIP programme now under full-implementation with a fully operational management framework, and with the majority of work packages now active. However, there remain a number of issues to be addressed including: the complexity of the programme and the time and resource needed to manage it; effective engagement with stakeholders, increasing the ambition of the G&I plan; a focus on the realisation of secondary benefit opportunities; quality assurance through the new Quality Panel; focusing activity around deliverables which are realistic and achievable within the remaining programme timeframe; and improving reporting to consider how FSIP is progressing to achieve the intended outcomes rather than focusing on outputs.

The capital market (CM) workstream aims to strengthen regulatory frameworks and capacity for financial regulators in policies and legislation in order to develop and enhance capital markets in the Philippines and Vietnam. Primarily, the FSIP team aims to deliver tangible improvements particularly in the bond markets and capital markets. Proposed activities in the CM workstream are aimed at providing strategic and targeted implementation support in Vietnam and regulatory technical assistance and capacity building in the Philippines.

There are 2 work packages which have been developed by the CM workstream with both work packages now in implementation. The first work package in the Philippines is focused on strengthening regulations and supervisory capacity related to the Securities and Exchange Commission’s risk-based supervision of capital markets intermediaries. The second is in Vietnam. The FSIP team aims to support the development of the country’s capital markets through strategic and policy advice, with some targeted follow-on implementation support. This includes the development of a capital markets masterplan and providing technical, policy and capacity building advice through a combination of international and local consultants.

The FinTech workstream aims to assess the readiness and impact of FinTech adoption by providing regulatory advice, training and capacity building. The FSIP team will leverage regional insights and global best practice to provide capacity building and knowledge sharing, to improve the regulatory environment and expand the use of financial technology across 4 ASEAN countries including Indonesia, the Philippines, Thailand and Vietnam. This includes working with regulatory bodies and the private sector to identify specific focus areas. There is a total of 11 work packages in the FT workstream with all WPs now in implementation.

Key achievements under this work stream include supporting the Philippines Central Bank (BSP) to gain membership of the Global Financial Innovation Network (GFIN) , and work in Indonesia to complete a comparative analysis on UK and other jurisdictions’ P2P lending and Code of Conduct. The recommendations arising from this analysis were accepted by the beneficiary AFPO and incorporated into the AFPI’s new Code of Conduct. In Vietnam, FSIP completed a FinTech Ecosystem catalogue, aiming to serve as a starting point for local regulators and authorities to analyse key market characteristics, opportunities, trends and gaps in the country’s FinTech environment.

In addition to the above, the FSIP team have begun work on implementation of the ASEAN FinTech Regulatory Network (AFRN) work package, a cross-portfolio concept for the development of an FinTech Regulatory Network to include all PF6 country regulators. The overarching objective of the Regulatory Network is to contribute to developing South East Asian capital markets and financial services by expanding the use of financial technology, whilst balancing the tension between market stimulation and risk management.

The accounting standards workstream aims to provide technical assistance in the form of capacity building and knowledge sharing to align accountancy practices in ASEAN with internal standards and best practices, specifically IFRS. FSIP have identified top priorities for reforms in each market, and consulted with government officials and regulators to prepare the market for adoption of international standards. Six work packages have been developed across Myanmar, the Philippines, Thailand and Vietnam, with all packages now under implementation. Key achievements include the delivery of virtual training to the Central Bank of Myanmar (CBM); the delivery of IRFS9 capacity building sessions to a wide range of beneficiaries in the Philippines BSP, IC, SEC) including one special session on the impact of Covid-19 on IFRS9 implementation; working with the Ministry of Finance in Vietnam to develop a road map for IFRS implementation; and planning IFRS9 training in Thailand with the Bank of Thailand.

The AML/CFT workstream aims to provide technical assistance to the Myanmar government in implementing a more robust AML/CFT regime in line with international standards. The primary task for this workstream is to assist Myanmar in implementing required reforms and to build capacity to fill gaps in Myanmar’s AML/CFT regime identified by the Financial Action Task Force (FATF) Mutual Evaluation process. The support provided to the Myanmar government consists of an integrated set of long-term activities delivered by local and international experts. This includes drafting recommendations on regulatory frameworks for AML, training on international best practices for supervisors, prosecutors and law enforcement and mentoring across the different departments by specialists in areas including Financial Intelligence operations, AML prosecution and Risk-Based Supervision. The AML workstream is currently delivering 5 work packages in Myanmar. Key Achievements include:

  - One-week virtual training programme for Union Attorney General’s Office’s (UAGO) staff on AML/CFT prosecution (August 2020).

  - Work with Myanmar Financial Intelligence Unit (MFIU) to align training plans with the new requirements under the ICRG Action Plan.

  - First stage of this training plan delivered in September 2020 with Basic Intelligence Training for 20 MFIU officers on AML/CFT concepts.

  - On-going mentoring and bespoke TA to key AML stakeholders including training for the Consolidated Inter-Agency Supervisory Committee (CIASC) member on risk-based supervision.

  - Delivery of a Risk Management Manual (RMM) for the Financial Regulatory Department in July 2020 – FSIP provided technical assistance to the FRD in developing a comprehensive RMM.

Islamic Finance has been developed as a new workstream, emerging during the inception phase as a response to beneficiary requests. The aim is to expand and strengthen the Islamic Finance market in Malaysia , with a view to potential adoption across SEA. The project explores solutions for social funding in Malaysia by adopting and promoting ISF instruments such as Zakat, Waqf, Sadaqah, Takaful and Sukuk. There are three focus areas: research and recommendations for a Pre-Emergency Fund based on ISF instruments; a FinTech enabled Waqf solution; and Islamic Financing for social enterprises. The key achievement this year has been the completion of a research report on the establishment of the Pre-Emergency Fund, which would support vulnerable communities in flood-prone areas in Malaysia. Reports on the additional focus areas will be finalised by the end of December 2020.

Challenges
The capital markets work package in the Philippines has been compromised by Covid-19, given that the key stakeholder is the Securities and Exchange Commission (SEC) who have been re-prioritised to focus on mitigating the impact of Covid-19.

In Vietnam the CM master plan work package has been delayed by protracted negotiations with the Ministry of Finance, raising a request in April 2020 to change the overall delivery model of the work package, including a significantly reduced version of the Terms of Reference (ToR), internal MoF consultants to lead the programme delivery, and the inclusion of UK site visits. After lengthy discussions in Feb-Aug 2020, the Capital Markets Master Plan work package was approved on 4 Sep 2020. The technical assistance will be provided by a team of international and national capital markets experts and is aimed at implementing a consultative approach with extensive stakeholder involvement.

There have been delays with agreeing the FinTech work packages in Thailand due extended negotiations with SEC, a key stakeholder for the eKYC and cyber-security work packages, to agree the Terms of Reference. Facilitated by Post, these discussions have had a positive outcome, and the terms of reference were approved in September 2020.

Recommendations
Programme Management
The programme team should work together with PwC to reduce 366 milestones to a manageable level – whilst the current operating model works, it requires a lot of time and resource on the part of both programme teams. It is also suggested that the programme undertake a lessons learned exercise on this particular delivery model, and share the findings across other PF programmes.

The review team recommends that the programme should use the relevant contract clause to carry out a Satisfaction Survey of the commercial contract to capture satisfaction levels.

Governance – an immediate and robust review and stabilisation of governance is required. It is good practice to review this annually. Once agreed this should not change without express board, contract or SRO approval.

Rapid assessment is required to understand what is deliverable within the commercial terms, noting delays and risk related to nugatory work.

Ensure local strategic partnerships are made and that community-based stakeholder consultation takes place in a meaningful way.

The Programme Team should closely monitor the impact of the Quality Panel to ensure the quality of deliverables is as expected.

Financial and commercial audit – It is recommended under agreed terms of reference that there is an independent auditor and a commercial specialist assessment of PwC contract performance and finances prior to completion of the contract.

Gender and Inclusion
There is a need for FSIP to focus its efforts on strengthening implementing partners, to ensure they are able to deliver on G&I deliverables. It is noted that developing local strategic partnerships will be a priority for the coming year and this should be closely monitored.

Encourage FSIP to expand its level of G&I ambition to build assets, capabilities and opportunities for women and excluded groups over the next year.

Closely monitor FSIP at country level to ensure that ongoing analysis of risks and opportunities takes place and that partners meet minimum standards on G&I in implementation.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (2 pages)

Key cost drivers and performance
The programme’s total budget is £19m over four years (up to March 2022). The main cost across the programme is advisory services to deliver the technical assistance and capacity building activities. FCO staff costs to manage the programme make up 4% of the spend (238,000) of the programme (see figure 1). The programme spent for FY 2019/20 was £5.4m against a forecast of £5.8m. The underspend for UNDP, RD/BEIS and In-house IP was mainly due to delays in activities due to Covid19, which effected activities in the region from January 2020. In house IP and BEIS had also spent less than they forecast on activities earlier in the year, mainly due to changing numbers of delegates and exchange rate fluctuations. The table outlined below have been provided by the programme and assumed factual and correct.

Financial management
The programme team managed the commercially procured elements of the programme with a close eye to budget management and cost control. During FY19/20 PwC’s invoices were split between the FS and the IP lines by the finance team in London. This made the process difficult to manage and caused a number of large accruals to build up on these project codes. This has now been changed and all invoices are recorded against the PwC FS line. Whilst the original financial set up was to record spend as FS or IP, since the contract variation in Nov 2019, the contract is managed in accordance with the amount for inception £1,042,427 and the total amount for implementation of £6,855,430. The total contract value is £7,897,857. In FY19/20, the variance in spend across both the PwC IP and PwC FS lines was less than 1%.
Financial spend in Financial Year 19/20
	Programme overall Spend		19,000,000		100%
	Programme Admin Spend		1,300,000		6.8%
	Strand	Allocation	Allocation 2019/20		Actual 2019/20		Variance 2019/20
		£	£	%	£	%	£	%
PF STR 912001	Transitional funding	0	-	0%	-	0%	-	0%
PF STR 923002	PwC – FS	6,900,000	1,591,206	287%	1,836,065	34%	- 244,859	-15%
PF STR 923001	CM In-house	200,000	100,000	2%	86,334	2%	13,666	14%
PF STR 922001	PwC – IP	1,200,000	606,729	110%	367,222	7%	239,507	39%
PF STR 922003	RD BEIS	800,000	264,695	4.65%	254,162	5%	10,533	4%
PF STR 922002	IP In-house	750,000	189,746	4.53%	142,910	3%	46,836	25%
PF STR 922004	OECD	2,400,000	962,134	176%	962,134	18%	-	0%
PF STR 922005	UNDP	5,300,000	1,769,006	310%	1,468,080	27%	300,926	17%
PF STR 922006	Enabling Fund	-	33,170	-	30,575		2,595	8%
admin total	Admin	1,300,000	252,471	4.4%	238,237	4%	414,234	6%
	Total	19,029,000	5,769,157	100%	5,355,144	100%	485,243

The admin budget spend was less than predicted as during FY18/19 the ER program was overcharged for the platform costs. This was discussed with PFDU and in quarter 3 of FY19/20 they confirmed a refund  of £64,535 was going to take place, and that it had to be in FY19/20. This was not taken into account at the start of the year, and therefore reduced the program’s actual spend. This was offset by an increase in staff charges, due to a change mid-year which meant the programme was charged for 25% of the UK based D6 member of staff and due to the increase in salary costs after the Head of Programme and Programme Manager were recruited.

The total admin spend to total costs ratio for FY19/20 is 4.4% which is within the 5% cap. Additional staff costs for recruitment of Head of Programme and a Programme Manager were agreed with JFU.

PwC FS and PwC IP lines should be viewed together - the total allocation is £2,197,935 and total spend is £2,203,287 which equates to a variance of £5,353 or less than 1%.

The Capital Markets spend was for the visit to the UK for financial services regulators from all 10 ASEAN countries (described in the report). This trip was arranged in collaboration with the PF Low Carbon Energy Programme and therefore resulted in cost savings.

RD/BEIS had to postpone some missions due to Covid19 resulting in a small underspend.

UNDP were also unable to complete all of their planned activities in quarter 4, due to Covid19, the underspend formed part of the FY20/21 allocation and has now been fully utilised.

There was a small underspend on the Enabling Fund due to the restrictions on all of the programme managers in quarter 4 due to Covid19.

VfM performance
Economy
The programme has used a mix of inter-institutional, inter-governmental and commercially procured approaches to contracting implementation partners. Implementing partners are providing VfM to varying degrees.

The Programme Team have fully utilised the support provided by PFDU, the Commercial Dept and the PMO in terms of financial advice, contracts and VfM, ensuring that the approach is in line with PF rules and expectations.

For the commercial procurement, a consortium led by PwC is delivering almost 50% of the programme. The programme team has contained the cost of the commercial provider by challenging invoices for accuracy, challenging the day rates of consultants and using them only when necessary and for getting reimbursement for overpayment or incomplete work. For example, the programme team rejected a request to include a senior level partner in Vietnam due to the high cost and a charge for the outgoing team leader’s repatriation costs were successfully challenged and reimbursed.

The commercial provider is paid on the basis of payment by results which allows for close scrutiny of costs, but this has proved time consuming to manage. The changes in the contact to pay by milestone after the first annual review were made in good faith but the implementation has been overly complex with 366 milestones being managed and administered by the programme team. This has unintended consequences as the programme team spends a large amount of their time in managing the milestones and the payments. Both, the programme team and PwC, acknowledges this issue.

Recommendation:	The programme team should work together with PwC to reduce 366 milestones to a manageable level – whilst the current operating model works, it requires a lot of time and resource on the part of both programme teams. It is also suggested that the programme undertake a lessons learned exercise on this particular delivery model, and share the findings across other PF programmes.

Although cost containment is an improvement from the value for money perspective, the quality of the outputs produced by the commercial consortium continues to be an issue. There is evidence that FCDO resources spent a large amount of their time reviewing deliverables and on occasions carrying out multiple reviews of the same outputs which is not VfM. This causes a burden on FCDO over stretched resources which is not sustainable.

Economic Development programmes are complex and require specialist trade or economic development expertise to ensure the interventions delivered are fit for purpose and the outputs are of high standard. However, the review team did not find any evidence of a Trade or Economic Development expert on PwC leadership team who is responsible for the quality of the outputs. The review team identified this as a gap in the current level of service. After the completion of the interviews and the review, the review team has been informed that PwC has created a ‘Quality Panel’ to improve the quality of the outputs. Since this work was carried out after the review period, the review team has not assessed the quality and the composition of the Panel.

Recommendation: The review team recommends that the programme team closely monitors the effectiveness of the panel and ensures that ‘Quality Panel’ includes a trade / economic development expert to assess the level of improvement in the quality of deliverables. The ‘Quality Panel’ should be responsible and accountable for the overall quality of the outputs.

There is less oversight on cost for other delivery partners. For example, the agreements with OECD and UNDP limits detailed oversight, and the programme team rely on the strength of multilateral agreements to ensure accountability. However, there have been some progress with the UNDP as it now provides a more detailed breakdown of spend. The programme team have sought further clarification where required and have ensured that UNDP have kept to the agreed staff costs to activity costs ratio. The programme team has also adapted to the new PFDU requirements of obtaining authorisation from the PFDU before any pre-payments are made to multi-laterals.

There are similar limitations with RD BEIS and the UKIPO as OGDs. The programme team monitors and questions spend and forecasts at every monthly meeting.

Recommendation: At FCDO & Prosperity Fund level it is strongly recommended that MOU’s for all PF programmes are reviewed with an aim of improving terms in favour of FCDO and to ensure stronger accountability, VfM, milestone payments and reporting. This will also support closer engagement and control with programmes. Thus strengthening governance for the SRO’s.

Efficiency

The efficiency performance of the programme is mixed. The evidence suggests that working relationships in PF6 countries have been productive and indicate efficiency. For example, the working relationship between programme team, posts, beneficiaries and delivery partners are largely positive for BEIS RD, IPO, UNDP and OECD. However, the working relationship between the programme team in PF6 countries and the commercial provider is less positive, which is mainly due to lack of PwC expertise in engaging with the host Government and the stakeholders. Posts reported that they often had to manage stakeholder relationships to facilitate progress on programme interventions. This is inefficient due to the higher opportunity cost of these resources. However, there are also evidences that the commercial provider is showing efficiency to ensure the programme delivers VfM. For example a RAG rating and score for each work package is given against VfM assessment criteria and this information is shared with the FCDO for approval.

The interviews conducted by the review team suggest that the strands delivered by BEIS RD, IPO, UNDP and OECD are very efficient. For example, for UNDP, flexibility and autonomy in running the project is reported to have promoted ownership and commitment. UNDP’s experience and capability as a delivery partner has ensured the successful delivery of planned activities and outputs. Close consultation with stakeholders has ensured the project meets stakeholder needs. Resources were well budgeted and spent, with no unexpected delays and excess funds carried forward and repurposed.

The Programme Team is also looking for efficiencies to ensure the spend is VfM. For example the programme team is closely monitoring proposed budget changes in the light of re-programming due to Covid-19, ensuring that adjustments are recorded and any re-budgeting represents VfM – for example, appropriate re-allocation of cost-saving as a result of virtual delivery (rather than face-to-face). This scrutiny is particularly relevant to new workplans for FSIP and the Fair Biz Project in FY 2020/21.

It is noted that under FSIP, where work packages run over budget, these additional costs are absorbed by the delivery partners. Where work packages underspend against budget, these savings are passed back to the programme, and entered into an Agile Fund. Funds are disbursed from the Agile Fund only where an opportunity is presented for additional activities that (1) represent VfM, (2) align to the objectives of the theory of change, and (3) clearly originate from a beneficiary demand; and (4) according to defined governance processes with FCDO whereby approval has to be given.
However, there are wider efficiencies issues. The programme is delivering several activities in six countries with five delivery partners with a budget of £19m. This makes the progamme not only complex and ambitious to manage but less efficient and VfM. The trade off is that the already stretched FCDO resources are drawn in to administration and management of delivery partners, with less scope to engage their expertise programmatically with output quality and delivery of results. The excessive number of milestones for the PwC strand is one of such examples.

Recommendation: The programme should carry out a lesson learned exercise on the delivery models and share with the wider PF so that the lessons could be applied across the portfolio.
Effectiveness
The business case demonstrated that the programme is expected to deliver £351m of primary benefits and £352m of secondary benefits over 10 years. The programme currently does not maintain a governance process to monitor and compare the programme-wide total benefits to the benefits envisaged in the business case. This should be included as part of the over-all programme MREL plan.

The programme has faced numerous delays and a few strands have not been taken forward. Although the decision for not taking forward these strands could be to achieve value for money, there is limited evidence to suggest that the benefits to the overall programme were given due consideration in making this decision. Furthermore, any assessment was not carried out to understand the impact to the overall benefits of the programme.

The programme team has made a good progress in reviewing the Theory of Change and developing the programme log-frames – although the programme level log-frames are yet to be finalised. Based on last year’s annual review recommendations, the programme team has reduced the number of indicators and have made them more relevant and refined. However, in terms on delivering the benefits, the programme has focused on the outputs only. Therefore, the programme team and delivery partners need to urgently focus on outcomess and impacts, with clear reference as to how these relate to the benefits promised in the business case. This is of crucial importance as the programme enters the last year of implementation.

Recommendations:

The programme should carry out a benefit audit of the whole programme . The results of the audit should be assessed relative to the target promised in the full business case. The programme must demonstrate that its total forecasted benefits is satisfactory compared to its budget and the overarching ambitions that were agreed in the business case’s investment approval. The results should be applied to the additional funding that the Programme expects to be allocated in February 2021 to ensure the public funds are used at those activities that provide best VfM. The FCDO Economics Unit should support the programme team in carrying out this assessment.

The programme team should review and update the governance process for changing the scope of the programme to ensure that benefit impacts are included as an equal decision criterion and drawn upon when deciding on any changes related to programme scope. This must be ingrained in its governance processes to ensure that public funds are being spent effectively.

As a matter of urgency, the programme should review the programme level theory of change and log frame, and monitoring mechanisms, to ensure that the programme is effectively delivering, measuring and monitoring outcomes and impacts. Following the review, a report on the process, results and strategy of delivering the outcomes and impacts should be communicated to the programme team, managers at posts and delivery partners, and a report presented to the PF Regional Steering Board. The implementation of the strategy should be overseen by the Steering Board.

Equity
The G&I scorecard from this year’s evaluation (June 2020) rated the programme at amber overall (although UNDP alone is a green). This was owing to fact that there remained areas for development to evidence that the programme fully met PF G&I minimum standards. Notable progress has been made since then, particularly related to PwC and logframe updates but areas for improvement remain in accountability and delivery partners.

The programme focuses on gender-equitable participation rather than substantive consideration of G&I related issues in all but ER2. With the majority of outputs now achieved, the emphasis will need to now fall on monitoring the impact and uptake of the G&I sensitive products and coming alongside key stakeholders to translate knowledge and recommendations into tangible actions. For the FSIP strand, at an earlier implementation stage, there is still the possibility to extend G&I ambitions beyond minimum standard, drawing on the extensive and potential opportunities outlined in their G&I action plan completed this year. The ER2 strand stands as an example of best practice in bringing together consistent G&I mainstreaming and standalone activities. It has also found innovative ways to increase accessibility and uptake of its library of resources with the move to digitalisation in response to Covid-19.

There is evidence that the outputs selected may give way to primary purpose outcomes in the lifetime of the programme if research products and recommendations can be translated and applied at country level. Sector specific G&I expertise would also help to make this connection. Stronger qualitative monitoring processes would help to articulate whether the programme is truly making strides in the area of gender equality and equity. The recently updated logframe and increased disaggregation of data should support this process.

Recommendation: No additional G&I recommendations beyond those already captured in the G&I category of the summary recommendations.

Assessment of whether the programme continues to represent value for money
Overall, the VfM of the programme is assessed as adequate. The programme team has taken a number of steps, especially on cost reduction, to improve the VfM of the programme. However, the review team has concerns on the effectiveness of the programme due to an uncertainty on the level of benefits that will be achieved. The review team recommends that the programme team should finalise the programme level log frames, develop matrices for monitoring the benefits on an urgent basis so that the overall programme level benefits can be measured and monitored.

## E: RISK (1 page)

Overall risk rating: Moderate
The overall risk rating has declined to “moderate” from “moderate to major” last year, due to the resolution of a number of delivery risks related to the then incomplete commercial partner inception period. Currently, programme risks primarily relate to delivery risks and have remained little unchanged since the Covid-19 impacted the approach to delivery across a number of strands and required significant re-think of risk management.

The programme management team put significant effort over the past year into planning and managing these delivery risks. They remain low-to-medium in nature. An overview of the approach to management and the most significant risks is presented below. Compared to the Fund overall, the AER programme is relatively low-risk.

Overview of programme risk management
- Risk is managed with the programme Risk Register. This is a live document and is kept under review by the programme team and by the Programme Board at quarterly meetings.
  - Each of the programme delivery partner has a risk register, and they report on these risks every quarter as part of the quarterly reporting process. For the commercial contract, PwC are required to treat red risks as a higher priority, and have particular requirement on this detailed in the service level agreement.
  - There is a portfolio level risk register which captures the key high-level risks, which is adjusted on a quarterly basis according to inputs from the quarterly reports.
  - The top 15 risks are also reported on Prospero.
  - Programme Managers report of changing risks and if they are trending upwards or downward. Risks can be reported both through the Programme Working Group meetings or on an ad hoc basis, if necessary
  - High level risks and risks trending upwards are reported to the PF Steering Board quarterly; the Board signs off on the risk register.
  - The programme under went a re-stress test in May 2020, to ensure that the identified risks are the right ones, and are sign-posted at the right level.
  - The programme quarterly reports evidence active tracking and management of risks, with risks reported and tracked over time, with a fuller discussion of the most significant risks included in the narrative.

Key risks
Delay Risk due to Covid-19
Delays to programme activities as delivery partners respond to Covid19 and the restrictive orders on international and in some cases, domestic travel. Delivery partners are unlikely to be able to deliver the planned interventions within the specified time frame due to the time taken to re-programme and arrange remote delivery where possible.

Mitigation Approach

- Delivery partners are adopting different delivery models and programme team are extending agreements as necessary:
  - PwC: Consortium will utilise remote working tools such as conference calling, WebEx to continue FSIP business. Meetings or events which require physical spaces will be postponed. BCP is in effect. Meetings that are critical have been capped at 10 attendees. PMO has devised an alternative delivery model for delivery which has been agreed as a contract variation. The situation will be monitored constantly in order to reduce disruption.

  - UNDP: Meetings and webinars have been organized online and, to make this possible, UNDP has had first of all to support government agencies to put in place quickly and effectively business continuity plans, provide governments with the necessary software and hardware and support public officials acquiring the necessary skills to adapt to the new online working modalities.

  - RD BEIS: Explore the feasibility of different delivery methods and liaising with Post and government counterparts through pandemic to assess current situation and anticipate post Covid19 priorities. Mitigation efforts are being hampered by BEIS IT policy which only supports MS Teams and Stream.

  - OECD have moved to desk research where possible to complete their reports and are now planning to conduct the launches virtually. The first virtual launch has taken place in Thailand.

  - IP In house are preparing for alternative models, such as scaling down activities to bilateral seminars, and looking at how capacity building can be delivered through webinars and translated documents. The first IP webinars took place a the end of September / beginning of October and the second series in the middle of November 2020.

Government Counterpart Capacity
Delays to programme – e.g. through capacity limits of host government or local partners – leads to programme overrun or not achieving impacts expected

Mitigation Approach

  - Engage stakeholders throughout implementation phase to retain or secure buy-in. Apply strong programme management. Build in flexibility to redirect resources where blockages persist.

  - Work with delivery partners to address cause of delay and adjust delivery timeline. PFMO is notified, budget is re-profiled and potentially move the funds to another part of the programme or to another PF programme (subject to delegated authority).

Stakeholder Capacity:
Poor buy-in or lack of capacity of key stakeholders to engage due to Covid-19 related or other pressing priorities. These delays/ability to engage remotely could lead to activities becoming less relevant or requiring updating.

Mitigation Approach

  - Maintain open communication – flex and adapt as necessary. Re-naming or re-scoping programme activities as necessary in line with programme objectives and value for money requirements.

Outstanding actions and recommendations from risk assessment
The programme has successfully identified, planned for, and managed risks over the past year. A number of the risks and key actions from the last Annual Review have been addressed. In addition to the mitigations discussed above, recommendations on potential risk items include:

  - Programme stakeholders note that time delay for all contract partners to deliver interventions is the greatest risk to the programme. The vfm review recommends that the programme conduct an immediate rapid review of all projects and delivery timelines to ensure that they can be completed within the term of the contract.

  - As several strands approach the end of delivery in the coming year, contextual and government capacity risks may now start to affect sustainability of impacts. The programme should continue to monitor regional and national context, political will, and national government capacity by coordinating with the diplomatic mission to ASEAN as well as each Post to monitor the context and consider opportunities to advance programme goals. In particular, dialogue with Malaysia, post government change, and with Myanmar and Philippines, which have approaching elections, will be critical to ensure continued buy-in.

  - The programme has successfully migrated a number of activities to an on-line approach over the past year to address Covid-19 travel limitations. However, some programme activities have been delayed until travel can re-start or revised to avoid travel requirements. As the pandemic continues into the coming year, the limits to the current mitigation approach may begin to impact the programme delivery timeline. The programme should continue to engage delivery partners on what elements of the programme cannot be amended to fit the current context and proactively plan for how these will be re-planned if the pandemic continues through the next year.

## F: COMMERCIAL CONSIDERATIONS (1 page)

The programme is being implemented using a ‘multi-pathway’ approach including direct delivery by the Foreign and Commonwealth Office (FCO), partnerships with another government department, the Department for Business, Energy and Industrial Strategy (BEIS), the United Nations Development Programme (UNDP), the Organisation for Economic Co-operation and Development (OECD), and via a procured commercial provider, a consortium led by PricewaterhouseCoopers (PwC), as outlined below:

A: Financial Services and Intellectual Property (FSIP) - £7.8m – is delivered through a commercial contract by a consortium led by PwC
In November 2019 a contract variation was signed which approved the FSIP programme to move from the inception phase into an implementation phase. The contract variation highlighted three key areas which were yet to be finalised including: the finalisation of the Gender and Social Inclusion Action Plan; finalising the terms of reference for the FinTech work packages in Thailand; completing the programme logframe; and submission of a Closure/Exit strategy and Business Continuity and Disaster Recovery Plan. A sum was withheld from the payment due upon completion of the inception phase, with the agreement that it would be invoiced once all the above work was completed.

A number of issues were raised in the previous annual review which have been addressed this year. This has been a very time and resource intensive process for both the programme team in Singapore and programme managers at post. The team have drawn heavily on technical assistance provided by PFDU (MREL lead, Social Development Adviser, Commercial Team).

The situation was further complicated by the Covid-19 pandemic, which required the formulation of a second contract variation to govern changes in budget, scheduling and delivery of a number of milestones. This variation also provided an opportunity to correct some significant omissions in the previous contract, particularly regarding service level agreements. Commercial Department were hugely helpful to the programme team in navigating this process. PwC have been very supportive in negotiating and agreeing the changes. The contract variation was finally signed off in October 2020.

Regular meetings take place between FCDO and the PwC Programme Management Office – these have only recently changed from being weekly to taking place every fortnight. There are also a number of joint meetings across the particular programme strands. PwC country offices have monthly meetings with Post (and more often if necessary) to ensure that there is a good flow of information and to provide guidance and support as necessary. In this way it has been possible to quickly identify problems and programme bottlenecks, and to agree the best resolution.

While the programme team note good levels of improvement in the working relationship with PwC, there remains concerns as outlined below:

  - The PwC contract is highly complex with 366 milestones being managed and administered by the programme team. Both, the programme team and PwC agree this is resource intensive.

  - Although retrospective renegotiation of the PwC contract to include Payments By Results has given both parties additional clarity, this in turn has led to further complexity and administrative burden to the programme. This does not demonstrate VFM.

  - Programme governance reportedly is described as continually ‘moving’. Both parties alluded to changing templates, levels of delegation and approvals. It is important that Governance processes are clearly defined, processes mapped, and terms of reference agreed. Deviation or changes from agreed governance processes should be Board or SRO approved (depending on topic and value), and formally signed off via contract change notes. The support of a qualified commercial lead/contract manager would alleviate and improve.

  - The FCDO programme team continues to spend disproportionate amount of time managing the relationships with this supplier. This has led to a requirement for the programme team to increase their resource. There remains an issue in relation to work load and resilience for the programme team. The administration cap (5%) at PF level is not conducive to programme management delivery of this size and complexity and would benefit from review.

  - Quality Assurance continues to be an issue. The FCDO expectations are reportedly not being met as the programme team and managers are not receiving high quality ‘advisory’ services. The creation of a ‘Quality Panel’ is a welcome development, but as outined in the VfM section, the programme team will need to closely monitor the effectiveness of the panel and to assess the level of improvement in the quality of deliverables.

Recommendations
Commercial contracts carry the provision to carry out a Satisfaction Survey . This is recommended to gauge levels of satisfaction and better understand what improvements should and could be made both for the current programme and if relevant for future programming.

Governance – an immediate and robust review and stabilisation of governance is required. It is good practice to review this annually. Once agreed this should not change without express board, contract or SRO approval.

Financial and commercial audit – It is recommended under the agreed terms of reference that there is an independent audit and a commercial specialist assessment of the commercial contract performance and finances prior to completion of the contract.

B: FairBiz Programme - Advancing Business and Government Transparency and Anti Money Laundering (£5.3m): delivered by UNDP
The programme is demonstrating very positive results across all the pillars. The spend is on track. Programme teams in Singapore and the Bangkok regional hub work very closely together. Contact between country offices and Posts has been a little more variable, with programme managers sometimes feeling like they have not been closely enough informed (Indonesia, Malaysia). There has been some transition in staffing which has exacerbated this problem. The issue has been raised for the regional hub to address.

In response to the pandemic, UNDP requested a programme extension until September 2021. The necessary procedures were followed and the extension granted, with an amendment to the MoU being signed. There has been no additional cost to this extension.

UNDP have efficiently managed a transition to mainly virtual delivery, capitalising on the increased reach provided by regional webinars to amplify their business integrity messaging. At the beginning of the year, there was a strategy to devolve some of the regional programming to country level, on the basis that there would be limited regional travel, and less risk for in-country programming to be compromised. Country level plans were approved and signed off by Post before being included in a regional work plan.

C: Increasing the Competition Environment (£2.4m): delivered by multilateral OECD

The programme continues to demonstrate strong collaborative working with all key stakeholders in the region. The overall delivery of the project is proceeding as planned to the quality standards expected. The OECD’s continued engagement with ASEAN Secretariat and ASEAN Experts Group on Competition is helping them maintain credibility, traction and buy in from senior stakeholders whilst sustaining programme efforts for long term benefits.

The programme team in Paris have responded to the Covid-19 crisis with flexible and adaptive programming as necessary. Missions to Cambodia and Laos were compromised by the inability of the programme leads to travel. However, they have managed by working with local competition authorities, hiring local consultants as and when necessary, and shoring up support in Paris by recruiting additional staff to help with the additional research work required.

The first competition reports launch has taken place in Thailand and was very well received, a positive indicator for the remaining launches to be implemented over the next few months. OECD have flagged a risk in this regard, that they may not be able to complete all launches by March 2021. This would be only a short extension if it is required with minimal costs. OECD are currently working up a proposal.

D: Regulatory Reform (£800k): is being delivered by BEIS (Regulatory Delivery International Directorate (RDI): An inter-governmental agreement governs the relationship with RD/BEIS.

Programme implementation is well underway and has already demonstrated progress towards outcomes. As with other programme strands, delivery was affected by the Covid-19 pandemic. RDI requested an extension to the programme of 9 months, until December 2021. The proposal requested a budget uplift of authorities £41,762 as against the original business case. At the same time, the ASEAN ER programme received a proposal from the Indonesia Regulatory Reform Programme to merge with AERP. IRRP would merge with the RDI strand of the regulatory reform programme. The justification for the merger rested on the argument that IRRP is a relatively small PF programme with high administration costs, which had recently reduced its scope in Indonesia as a result of the changing country context and a re-ordering of government priorities. The merger with AERP represented good value for money. Even taking into account a budget increase for the AERP RR programme, over-all, there would still be a saving of approximately £700,000 to the Prosperity Fund.

The merger has been agreed by the Regional PF Steering Board, the IIOC Committee, and the JFU Portfolio Board. Programme teams are now working together to merge the log frames, the theories of change, financial management and MREL monitoring. It is expected that the merger will formally take place in January 2021.

E: Training and Capacity building IP Enforcement (£750m): (In house):

Following from last year, the programme has continue to carve out a niche amongst the larger donor countries (US & Japan in addition to the EU) in providing focussed technical assistance and capacity building leveraging on UK expertise in the areas of IP enforcement (in particular copyright) and IP innovation. There is a continued strong relationship with the ASEAN Secretariat with the UK continuing to be included in the ASEAN Network IP Enforcement Experts meetings (ANIEE).

This programme strand has probably been hardest hit by the Covid-19 pandemic which effectively brought all In-House IP activities to a stop for a few months. Recognising that the ability to travel will remain constrained for months to come, the programme have now shifted to virtual delivery and re-started delivery with two webinars (end of September, beginning of October) on IP innovation and digital piracy.

The Programme Manager was able to pivot into supporting the AERP more generally and undertook some valuable work, both compiling and editing good news stories to date and drafting a mid-term publication. The PM also researched options and possibilities for ER programming going forward.

It is likely that the In-House IP programme will request an extension in order to mitigate the effects of the delays. This is currently under discussion.

Changes in the Delivery Plan
Rapid review (COVID & ODA Reductions) – the highest risk noted by most of the programme stakeholders was time delay for all contract partners to deliver interventions. It is strongly recommended that the programme conduct an immediate rapid review of all projects and delivery timelines. Utilising the programme governance (supported by a commercial expert) to review delivery timelines to ensure that they are realistic within the term of the contract.

Virtual delivery – review the effectiveness and impact of programme delivery to date to understand if the revised dates are realistic. This needs to be closely and regularly monitored, and where delivery looks less likely projects should be re-purposed or stopped as quickly as possible to avoid unnecessary expenditure.

At FCDO & Prosperity Fund level it is recommended that MOU’s for all PF programmes are reviewed to ensure additional accountability, milestone payments and reporting. This will support closer engagement with programmes and stronger governance for the SRO’s.

Asset monitoring and control
The programme does not have any assets.

## G: BUSINESS ENVIRONMENT (½ page)

How has the business community and business environment responded to the programme?
- The business community has responded well to the programme in general, and with enthusiasm to certain components:
  - Competition policy with the Philippine judiciary has enabled critical relationships and positioning UK institutions in longer-term service provision in a niche area.

  - Promotion of more liberal Fintech regulation in Thailand is leading to opportunities for UK businesses, to highlight UK businesses that might be able to sell into the Thai market and to build relationships with the Thai regulators in support of commercial and PF objectives.

  - The Thai Security and Exchange Commission (SEC) – the programme’s key partner – is keen to organize a visit to the UK for their Secretary General to attend a series of meetings with key UK government and business contacts in the coming year. They have agreed to co-fund the visit. There is strong interest from UK businesses (including CEO of theCityUK, Bank of England, FCA and senior executives from fintech industry)

  - UNDP successfully engaged with the business community, and particularly SMEs on topics of business integrity and gender and inclusion. This has included the Business Integrity Toolkit for Young Entrepreneurs, which was co-designed with young business leaders across the region in Fair Biz workshops over the past year. Fair Biz webinars have seen more than 3,000 participants. This success is notable given the late shift to direct-UNDP delivery of these activities and their limited prior experience working with the private sector.

The Role that Non-ODA spending played in Promoting Programme Objectives
Non-ODA funding allows the programme to contribute to secondary benefits generation, both tangible and intangible ones. The non-ODA funded projects proved to be helpful to narrow down the gap where DIT does not do policy work and PF Programmes’ intervention does not go as far as promoting UK capabilities in the sector.

Non-ODA funded AER programme activities contributed to HMG’s priorities in 3 areas: trade, policy lobbying, and climate change. In terms of secondary benefits, they generated longer-term market opportunities for the UK by identifying the market barriers and keeping UK businesses informed about updated policies, regulations and potential projects in relevant sectors. They also promoted UK’s soft power which eventually result in influence to the purchasing decision of local stakeholders.

Specific non-ODA funded activities linking with the programme include:
A regional UK SE Asia FinTech Series has been approved and will be implemented over the coming months. This will be series of one day events across SE Asia bringing together a group of UK FinTechs based in the region to meet industry and government to pitch their products and services. The theme of the series will be sustainability. In Thailand, a UK-Thailand FinTech Event has been proposed and approved which would be a series of webinars to promote opportunities in Thailand to UK companies and engage with local stakeholders ahead of the event; a workshop to showcase UK expertise, business matching sessions, and an online content library (Jan / Feb 2021).

Also from Thailand, a non-ODA bid has been approved for a visit to the UK for the Secretary General of the Thai Security and Exchange Commission – this is planned for March 2021. This proposal is under consideration.

In Myanmar, an outward mission has been approved for Banking Sector Compliance, RegTech and FinTech (ERP), combined with the FinTech Series above.

A UK ASEAN Business Challenge Programme for Digital Technology has been proposed by DIT - In this pilot implementer will work with ASEAN based governments or businesses and help them explore, define and share appropriate challenges. They will then support digital SMEs from across the UK to develop innovative and deployable solutions to these challenges. This proposal is under consideration.

## H: MONITORING & EVALUATION (½ page)

Evidence and Evaluation
Learning has been emphasised across the programme, and has been included as a regular subject in the quarterly reporting and in reporting to the Steering Board. The programme team have worked closely with the JFU lead, and with the MR and EL contractors. Monthly meetings are convened to discuss progress, issues and risks around MREL. The programme team have also benefitted from targeted MREL days for developing both strand level and programme log frames. Currently, the team are looking at how to use any remaining allocated days in order to implement recommendations from the recent evaluation (cycle 2).

The Year 2 evaluation took place in April and May 2020, albeit a lighter touch evaluation due to the decision not to interview government counterparts or beneficiaries, in response to Covid-19-caused capacity and access limitations. Despite this limitation, the evaluation has been very useful in helping to assess programme progress to date, and identifying lessons and recommendations for improvement. The evaluation concluded with four key recommendation areas:

Theory of Change: Consider adding sense-check of new FSIP proposals to confirm alignment with the AER programme ToC as a routine element in the approval process; Consider engaging support via the evaluation and learning service, or elsewhere, in shoring up inclusive finance aspects of the FSIP programme and developing a better understanding of the change pathways.

G&I: Ensure that PF minimum standards (as set out in the G&I scorecard) are met across the programme; Reconnect with the allocated UK government Social Development Adviser for support with implementing minimum standards as needed; Document lessons learned from strands and activities that are seeking to exceed minimum standards through targeted work on G&I-related issues to inform a subsequent phase of programming; Support via added learning support on financial inclusion and sharing of best practice on how to implement successfully.

Dissemination of learning: Plan and execute an evaluation dissemination plan in coordination with EL, based on the evaluation findings and AER management response. Consider including delivery partners in the dissemination and using the case studies to support strand-level learning.

Evidence of sustainable change: To better track effectiveness, consider ensuring delivery partners’ monitoring systems extend beyond the quantitative logframe indicators to also determining whether new practices and capacities are becoming embedded and resulting in the desired outcomes. Note that this was also a Cycle 1 recommendation and remains relevant.

The programme team have also established links with the Finance Sector lead and have agreed to further support regarding financial inclusion. Other planned M&E actions include:

- Undertake a G&I review on compliance across the portfolio. Document best practice. Identify where more can be done. Drawing on support from PFDU/JFU advisers, identify best practice from the wider PF programme, particularly around financial inclusion, and disseminate this to DPs, promoting cross-strand learning.
The PMT are already in discussion with PFDU/JFU regarding publication of the evaluation and annual review from this year and previous years. The draft evaluation report as well as the pertinent case studies have been sent to delivery partners (DPs) for their factual review. DPs have responded very positively, indicating their willingness to discuss the findings and agree how improvements can be made.

Building on the logframe review undertaken last quarter, to identify different types of indicators (and other methods) to measure more comprehensively progress towards desired outcomes.

Recommendation: Developing qualitative evidence of the sustainability of capacity enhancement and change in general should be prioritised in the coming year.

Monitoring progress throughout the review period
The AER programme approach to monitoring in the review period has focused on:

  - Working with implementation partners to bring quarterly reporting into alignment with monitoring expectations, particularly reporting on progress against logframe milestones

  - Working with implementation partners to revise and finalise logframes in response to recommendations from the 2019 Annual Review and Evaluations

  - Working with MR and E&L services to revise the programme logframe, including contracting technical support via the E&L flexible day service

  - Uploading the revised logframes, both supplier and programmatic, to Prospero and starting the process of uploading milestone data with the support of the MR Hub

  - Conducting monthly calls with the programme, JFU, MR and E&L to coordinate monitoring and evaluation activities and maintain alignment on programme MREL priorities.

Annex 1: FSIP - Inclusive IP Indicators

Output Title	Output 1A - FSIP: Inclusive IP capacity building through knowledge sharing and technical assistance to improve IP and related legal/policy frameworks, regulation and practices
Output number per LF		Output 1A	Output Score	B
Risk:		Moderate	Impact weighting (%):	5
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
No. of new or improved IP policies, standards and regulations including targets, mandates, incentives and roadmaps that have benefitted from FSIPs support / (FSIP IO Primary 1.1.)	2020: 4 manuals have been developed for IP enforcement for ASEAN, Indonesia, Philippines and Vietnam. / 3 reports on IP enforcement data collection methodology for Indonesia, the Philippines and Vietnam and 2 reports on IP promotions in their creative and consumer industry in Indonesia have been completed.	Work on the FSIP outputs to achieve this IO include: / Consolidated ASEAN manual with 10 Chapters has been finalised and submitted as of June 2020 and compiles IP laws and procedures for 10 ASEAN member countries. / Submitted a proposal for e-commerce legislations/regulations to Intellectual Property Office of the Philippines / Developed and published the IP Enforcement Manuals on how the IP enforcement system works in Indonesia, Vietnam and the Philippines. / Promotion and support for Creative Industries in Indonesia on an IP Toolkit to analyse IP of SMEs. / Delivered a research report to the Copyright Office of Vietnam (COV) based on limitations and exceptions on copyright regulations across five jurisdictions.

Annex 2: In-house IP Indicators
Output Title	Output 1B – In-House IP: Inclusive IP capacity building through knowledge sharing and technical assistance to improve IP and related legal/policy frameworks, regulation and practices
Output number per LF		Output 1B	Output Score	A
Risk:		Minor	Impact weighting (%):	5
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
'Number of delegates reporting having used learning from the capacity building activities after 6 months (In-house IP Primary IO 1A)	Target: 30 / Achieved: 49	In the last year in house IP have run the following: / UK-ASEAN IP Enforcement Seminar in Sept 2019 / UK-Indonesia IP Seminar in Nov 19 / UK-ASEAN IP Enforcement webinar October 2020 / Number of delegates reporting having used learning from the capacity building activities after 6 months is 49.
Number of non-PF funded industry speakers delivering sessions at each capacity building seminar. (In-house IP SB IO Indicator 3)	Target: Achieved: 17	Achieved: 17

Annex 3: BEIS increased capacity building indicators
Output Title	Output 2 (BEIS): Increased capacity building and collaboration for government stakeholders to improve regulatory practices
Output number per LF		Output 2	Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
'Number of recommendations proposed for adoption by GoPh and GoV to implement/revise laws, regulations, rules and/or administrative practices to improve business environment (Cumulative) (RDI Primary IO Indicator 1a) (disaggregated by recommendations proposed for adoption that include gender considerations - RDI Primary IO Indicator 1b)	2019:2 / 2020:4 / 2021:6	3 achieved by Oct 2019 (exceeding milestone target). / As part of RD BEIS outputs, they have achieved (as at Oct 2019): / 76 days of TA to government counterparts / Submitted 3 reports on good regulatory practice.
'Number of officials trained (gender disaggregated) (RDI Primary Output Indicator 2a)	2019:50 / 2020:200 / 2021:350	As of October 2019, 128 officials had been trained in good regulatory practice.
% of positive feedback from selected domestic and international business organisations on reform plans and processes and views about future improvement (RDI Primary IO Indicator 2a)	' / 2019:50% / 2020: 75% / 2021: 80%	In support of reaching this IO, 3 training programmes and curriculum developed had been achieved by Oct 2019

Annex 4: OECD Indicators
Output Title	Output 3 (OECD): Increased adoptions of recommendations on use / misuse of competition assessments and special rights and privileges of SOE’s
Output number per LF		Activity 3	Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Output 3 / 'Number of Competition Authorities reporting increased knowledge and usage of competition assessment (OECD IO Indicator 1a)	Target: 6 by March 2021 (at project completion)	In support of this IO, OECD have achieved the following outputs: / Completed (or near completion) 8 country reports which will feed into the ASEAN wide report (as at March 2020). / Achieved an interaction with 91% of relevant stakeholders (as at March 2020)

Annex 5: UNDP Indicators
Output Title	Output 4a (UNDP): Strengthened partnerships between civil society and public and private sectors to implement and monitor integrity policy, opening participation for women and underrepresented groups.
Output number per LF		Output 4a	Output Score	A+
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4a (a): Number of learning & knowledge platforms for Government – private sector and civil society policy dialogue (UNDP Output Indicator 1.1)	2018: 1 / 2019: 3 / 2020: 5	Year 2 Target already achieved and surpassed (5 cumulative from Y1) : -Anti-corruption and Governance Community of Practice - Public procurement -Business Integrity - Gender / diversity and Inclusion - Court excellence and judicial integrity
4a (b): % of involved stakeholders reporting feeling more comfortable on dialogue on integrity and transparency with counterparts following participation in the platforms (disaggregated by gender) - referring to the ability of understand and trust each other and work for common goals (UNDP Output Indicator 1.2)	' / 2019: 70% / 2020: 80%	Year 2 Target achieved and surpassed 88.3% of questionnaire respondents participating in the regional dialogues / Year 3: 88.3% as of Apr 2020
4a (c)# stakeholders engaged through the regional platforms (sex- disaggregated and sector-disaggregated: public sector, private sector, CSO...) (UNDP Output Indicator 1.3)	' / 2018: 100 / 2019: 300 / 2020: 500	Year 2 Target achieved and surpassed / 602 stakeholders engaged in regional dialogues: 293 women (48%) 309 men (52%) of which 209 from Gov 149 from Biz sector 41 from CSO / In year 3: 2860 (602 through face-face trainings + 2258 webinars) registrants surpassing the year 3 target of 500

Output Title	Output 4b (UNDP): Improved transparency in government contracts and increased compliance with international procedures and trade standards
Output number per LF		Output 4b	Output Score	A+
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4b (a) # of countries that have established open and innovative service delivery mechanisms (Indicator 2.2.2 in RPD) (UNDP IO A2)	' / 2019: 1 / 2020: 2(cum) / 2021: 3 (cum)	Output indicator towards this IO achievements are: / 2 new/revised policy instruments on public procurement reform developed. Achieved in Indonesia and Thailand / 4 public procurement interventions conducted in the target countries: Indonesia ,Thailand, Philippines.
4b (b) # of new infrastructure projects where data is disclosed by governments of Thailand and Indonesia following COST methodology (UNDP IO A3)	' / 2019: 123 / 2020: 260 / 2021: 400	Output indicator towards this IO achievements are: / 408 stakeholders engaged in workshops and events in Thailand in Y1 and Y2. These included the ‘Train the Trainers for CGD officers’ in 9 regions in Thailand wherein in all regions, estimated 80% attendees were female and 20% male / In Indonesia, a total of 116 stakeholders have been engaged in CoST activities in Y1 and Y2, nearly 40% female and 60% male attendees
4b (c) IO A4 CoST West Lombok and CoST Thailand uses the guidance developed by the CoST IS to promote and increase the participation of women (UNDP IO A4)	2021: 2	Output indicator towards this IO achievements are: / Gender audit conducted and year 2 target was achieved.

Output Title	Output 4c (UNDP): Adoption of responsible business practices & good corporate governance including gender and diversity by private companies & SOEs
Output number per LF		Output 4c	Output Score	A+
Risk:		Minor	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
4c (a): # of business integrity instruments adopted (trainings and/or tools on code of conduct, internal control mechanisms or whistleblowing mechanisms developed for business sector) (UNDP Output 3.2)	2019: 0 / 2020: 2(cum)/ 2021: 3 (cum)	In year 2: 6 business integrity instruments adopted/developed / In year 3 so far: 7 cumulative (3 trainings on COC, ICM, whistleblowing in VN, 1 BI Pledge in VN, 1 biz integrity toolkit for start-ups, 1 series of training in Myanmar on B.I. ToT on BI for start-ups in VN as of Jul 20) Exceeding the target for Y3 which was 4.
4c (b) # of companies in ASEAN that have joined responsible business conduct initiatives by project (UNDP IO A5)	2019: 0 / 2020: 2(cum) / 2021: 4 (cum)	Output indicator towards this IO achievements are: / In year 2: 20 (17 companies + 3 business associations companies engaged in the regional dialogue) engaged in dialogue on gender and inclusion through participation in project platforms.

Output Title	Output 5 (UNDP): Strengthened anti-corruption policies, plans and strategies and improved redress mechanisms
Output number per LF		Output 5	Output Score	A+
Risk:		Minor	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
5a: # countries supported to develop or update preventive anti-corruption policies, plans or strategies (Indicator 2.2.1 in RPD) (UNDP Output 4.1)	2019: 1 / 2020: 2(cum) / 2021: 3 (cum)	Year 2 Target achieved and surpassed: 3 countries were supported to develop/update their strategies and policies on anti-corruption: Malaysia, Myanmar and Vietnam
5b: # of new in country judicial initiatives initiated following regional peer to peer exchanges (targeted countries) (UNDP Output 4.2)	2019: 1 / 2020: 2(cum) / 2021: 3(cum)	Year 2 target achieved and surpassed: 3 countries were supported on judicial integrity and court excellence: Malaysia, Vietnam and Thailand

Annex 6: Financial Services Indicators
Output Title	Activity 6 (PwC): Positive influence on market regulation through ACMF and promotion of international standards in FS
Output number per LF		Activity 6	Output Score	B
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
6(a) No of strategic recommendations reports developed (FSIP Output Indicator 2.1)	2020: 2 / 2021: 1 / 2022: 1	Work on the FSIP outputs to achieve this IO include: / Action plan on strengthened risk-based supervision of capital markets intermediaries and capital markets supervisory practices, and quarterly advisory reports are in progress for the Philippines. / Agreeing the ToRs with the Ministry of Finance in Vietnam after a year of discussions / Philippines – check earlier QRs

Output Title	Activity 7 (PwC): Improved capacity and frameworks within key financial institutions and markets
Output number per LF		Output 7	Output Score	B
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
7 (a): No. of new frameworks or systems developed (FSIP Output 3.1)	2020: 1 / 2021: 4 / 2022: 0 / Actual: 4 - Regulatory guidance provided in support of industry sandbox in Philippines; 1 survey questionnaire prepared on FinTech landscape and 1 FinTech ecosystem report completed for Vietnam; 1 documentation on crowdfunding regulation from the region and UK	Work on the FSIP outputs to achieve this IO include: / The development of an ASEAN FinTech Regulatory Network concept to include all PF6 country regulators / Supporting and getting the Philippines Central Bank approved as a member of the Financial Conduct Authority (FCA) supported Global Financial Innovation Network (GFIN).
7 (b): No of strategic recommendations reports developed (FSIP Output 3.2)	2020: 3 / 2021: 2 / 2022: 0 / Actual: 1 – Report on code of conduct for functions of SRO P2P / IT based lending issued to AFPI (Indonesian FinTech Lending Association).	Work on the FSIP outputs to achieve this IO include: / In Indonesia FSIP completed a comparative analysis on UK and other jurisdictions’ P2P lending and code of conduct (CoC) and recommendations were accepted by beneficiary AFPO and incorporated into the AFPI’s new CoC / FinTech Ecosystem Catalogue was successfully completed in Vietnam

Output Title	Output 8 (PwC): Capacity building and knowledge sharing to tackle financial crime and money laundering
Output number per LF		Output 8	Output Score	B
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
8 (a) No of strategic recommendations reports developed (FSIP Output 5.1)	2020: 0 / 2021: 0 / 2022: 3 / Actual: 6 - 3 TA & Mentoring reports completed on national coordination and risk-based approach; 2 TA & Mentoring reports completed on supporting improved financial sector AML/CFT compliance - in particular STRs and CDD. 1 TA & Mentoring report completed on improving the prosecution's capacity of the Union Attorney General's Office (UAGO)	Work on the FSIP outputs to achieve this IO include: / Supporting the Central Bank of Myanmar (CBM) in improving the application of risk-based supervision principles and providing technical assistance to the Financial Regulatory Department issuing effective and understandable directives, manuals and guidance for their reporting entities in line with Financial Action Task Force (FATF) standards / GovRisk have supported MFIU on Myanmar’s engagement with the Financial Action Task Force‘s (FATF) International Cooperation Review Group (ICRG) process and national AML / CFT compliance matters.
8 (b) 'No. of new frameworks or systems developed (FSIP Output 5.2)	2020: 0 / 2021: 2 / 2022: 0 / Actual: 5 - 3 implementation support activities completed to provide support for improvements in National coordination and implementation of risk-based approach; 2 Manuals sections on Risk Management (4 chapters total)

Output Title	Output 9 (PwC): Facilitate increased selling of international funds including UK funds in ASEAN and vice-versa; Improved links between international business, including UK and SEA
Output number per LF		Output 9	Output Score	B
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Output 9: Number of working relationships established between UK organisations & target FSIP stakeholders (FSIP IO SB 6.1)	2020: 3 / 2021: 5 / 2022: 7