Annual Review - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.
Title: Better Health Programme
Programme Value: £79.3m		Review Date: November 2020
Programme Code: / GB-GOV-50-PF-20-BHP (including GB-GOV-3-PF-HEA-911; GB-GOV-3-PF-HEA-913; GB-GOV-3-PF-HEA-926; GB-GOV-3-PF-HEA-BR-921; GB-GOV-3-PF-HEA-MM-921; GB-GOV-3-PF-HEA-MX-921; GB-GOV-3-PF-HEA-MY-921; GB-GOV-3-PF-HEA-PH-921; GB-GOV-3-PF-HEA-REG-921; GB-GOV-3-PF-HEA-TH-921; GB-GOV-3-PF-HEA-VN-921; GB-GOV-3-PF-HEA-ZA-921)	Start Date: / August 2018 (OBC approval)	End Date: / March 2023

Summary of Programme Performance
Year	19/20	20/21
Programme Score	A	A
Risk Rating	Moderate/ / Major	Moderate/ / Major

Summary of progress and lessons learnt since last review
Transition to implementation

The Better Health Programme (BHP) moved from inception into implementation over a staggered period due to differences in completion of inception activity in each partner country. Inception should have finished in October 2019, but was delayed by approximately two-three months due to activity being significantly more time-consuming and resource-intensive than first anticipated. The risk of delay was accepted to ensure that planning was not rushed and to avoid further delays or poor outputs in implementation. The final country to move into implementation was Brazil in April 2020. By the time of the Annual Review, BHP will have been in implementation for 11 months (seven in Brazil), with 24 months remaining.

Immediate impact

BHP is already demonstrating impact on its primary objectives despite the challenges of 2020. Examples include; a collaboration by BHP and the health authorities in Malaysia to complete the world’s first mixed-methods study of lifestyle impacts of lockdown on the urban poor population, and the significance for Non Communicable Disease (NCD) risk factors; successful nursing and medical curriculum reviews in Thailand; strong engagement with senior officials in South Africa on the strategy BHP is developing for inspection of primary care and hospital services; and, in Mexico, advancing the role of nurses in primary care.

The BHP can demonstrate three examples of early commercial wins through its work. These are in the form of new partnerships between the UK and Thailand around genomics; agreement for UK institutions to provide wider health systems strengthening support to South Africa’s Government of the Western Cape; agreement for the UK’s Cell and Gene Therapy Catapult to support the development of a similar project in Brazil’s Sao Paolo state. At the time of this Annual Review, the Department for International Trade (DIT) has attributed £28m of commercial wins to the BHP, and 48 non-commercial secondary benefits wins, with a busy pipeline to follow. Furthermore, Posts have reported that BHP is a significant soft power tool for their wider diplomatic work especially in health cooperation during COVID-19. We are working with Joint Funds Unit (JFU) to better capture and report soft power wins.

A global learning Technical Working Group (TWG) now exists, managed by the BHP Programme Management Office but including Delivery Partners and Health Advisers from across the BHP. This is to share emerging best practice and lessons learned from across our eight countries, and is already proving an important tool to improve value for money and leverage the advantages of being a global programme. Examples of the effectiveness of the TWG are: Ministry of Health Malaysia has made a direct request to the Strategic Partner for knowledge sharing on the Health Education England (HEE) / Public Health England (PHE) ‘Making every contact count (MECC) approach. A Knowledge Exchange webinar is planned for February 2021 with invites extended to the teams in Thailand, South Africa, Myanmar and, observers from FCDO, Delivery Partners and national government; FCDO Thailand and DIT are planning a non-ODA conference-style event for March 2021 in Thailand on the topic of Community Health Workers for all BHP and broader Prosperity Fund (PF) countries, and; PWC and Mott Macdonald have set-up an information exchange on Community Health Worker activities in their respective countries.

Risks to the Programme during review period:

The main risks and challenges that the programme faces that have potential to affect implementation are COVID-19 and its ongoing impact on the BHP through strained health system capacity and, very significantly, the ODA funding cuts. Other risks highlighted include political instability, policy uncertainty in health at the country level, and capacity issues with delivery partners in some countries. Solutions to these have included pivoting the BHP to manage COVID-19, transparent and effective communication between stakeholders within and between countries, government-to-government dialogue, strong leadership, improved country governance and continued adaptive programming.
COVID-19:

COVID-19 has posed three key risks and challenges for BHP: firstly, the restrictions on movement have hindered actual frontline delivery of interventions; secondly, health officials in our partner countries have been understandably distracted by the crisis; and the thirdly, the need for BHP to pivot and address new health priorities without losing sight of its purpose.

Nonetheless, COVID-19 has not resulted in any significant changes to what we expect to achieve in the first year of implementation. Delivery plans were rapidly adjusted to the new environment by moving to virtual communication where possible and by postponing face-to-face activities until movement restrictions are eased (which has already occurred in several partner countries). Furthermore, the programme has successfully pivoted by adding new projects, which focus on Quality of Care and managing NCDs in a COVID -19 environment. This has become a high priority for our partners, due to the well-documented co-morbidities between COVID-19 and NCDs/underlying health conditions, meaning the BHP is in fact unusually well placed to support this critical aspect of the COVID-19 health response. For example, the BHP is supporting the development of standards and tools to be used in South Africa to inspect COVID-19 field hospitals across the country (incl. Gauteng, North West and Northern Cape) with the aim to provide basic sets of standards to be applied in such settings and document an understanding of the management, administration and functioning.  A brief produced by BHP in South Africa on the global evidence on the relationship between NCDs (e.g. diabetes, hypertension, asthma and heart disease) and COVID-19 has received attention from the World Health Organisation (WHO).

The BHP has commissioned a review by UK academics (through ‘Knowledge for Development’ (K4D)) into the overall impact from COVID-19 on the wider health systems of the middle-income countries we are working in. This will make an important contribution to the emerging global evidence base in its own right. It will also be a key source for the BHP and wider UK global health policy, to strengthen programme results going forwards in this new environment.

One positive from the current situation is that BHP has seen the cost of delivery decrease substantially, primarily due to the reduction in travel. This has meant that the additional COVID-19 projects could be funded from the original budget – effectively delivering more with less and so improving value for money.

ODA reductions:

The other major risk to BHP in 2020 has come from the ODA reductions exercise. BHP has mitigated this successfully by reducing April-December 2020 delivery budgets by an average of 17% across the programme. This has led to some activities not going ahead, however impact has been further mitigated by the lower costs of delivery in 2020. Those activities have been postponed to later years, and BHP still expects to have its full budget over the life of the programme, meaning that the overall impact of reductions in 2020 should be manageable without affecting BHP final outcomes.

Planning for Year 2 Delivery:

A priority now for the programme is to plan delivery for the second year of implementation, which in most cases will run from January to December 2021. Plans will need to demonstrate how they continue and build on the work in Year 1. Outstanding details to the country programme log frames should also be finalised before starting Year 2.

SRO commentary:

The Better Health Programme has delivered as expected despite the significant disruption caused by COVID-19 and the ODA reductions exercise. This programme is already delivering high quality partnerships with partner countries in healthcare as well as delivering commercial benefits and non-commercial benefits for HMG, the NHS and Public Health England. I am content that risks are being effectively managed and mitigated.

List of Acronyms
ABHI - Association of British HealthTech Industries
AR – Annual Review
ASEAN – Association of Southeast Asian Nations
BHP - Better Health Programme
BHPSA – Better Health Programme South Africa
CHV – Community Health Volunteer
CHW – Community Health Worker
CN – Concept Note
CPD – Continuing Professional Development
CSO – Chief Scientific Officer
CTAS – NHS Consortium Technical Advisory Service
DFID – Department for International Development
DHIS - District Health Information System
DHSC – Department of Health and Social Care
DIT – Department for International Trade
DP - Delivery Partner(s) (there are 4)
DoH – Department of Health
EL – Evaluation & Learning
FCDO - Foreign and Commonwealth Office
FCDO - Foreign, Commonwealth and Development Office
FDI – Foreign Direct Investment
FoPL – Front of Package Labelling
GAMBICA - Trade Association for Instrumentation, Control, Automation and Laboratory Technology in the UK
GDM – Gestational Diabetes Mellitus
GHOG - Global Health Oversight Group
G&I – Gender and Inclusion
HCUK - Healthcare UK
HEE – Health Education England
HTA – Health Technical Adviser
HRH – Human Resources for Health
HSS – Health System Strengthening
IIOC – Investment, Infrastructure and Operations Committee
JFU – Joint Funds Unit
K4D – Knowledge for Development
KPIs – Key Performance Indicators
L&D- Learning and Development
LF - Log Frame
LGU – Local Government Unit
LLN – Local Learning Network
MoH – Ministry of Health
MoU – Memorandum of Understanding
MECC – Making Every Contact Count
M&E – Monitoring & Evaluation
MICs - Middle Income Countries
MREL – Monitoring, Reporting, Evaluation, Learning
NCD – Non-Communicable Disease
NHS – National Health Service
NHS ALB – National Health Service Arm’s Length Bodies
NICE – National Institute for Health and Care Excellence
NIHR – National Institute for Health Research
NSP – National Strategic Plan
ODA - Official Development Assistance
OHO – Office of the Health Ombud
OHSC – Office of Health Standards Compliance
PbR – Payment by Results
PF – Prosperity Fund
PT – Programme Team
PHE – Public Health England
PHC – Primary Health Care
PHSO - Parliamentary and Health Service Ombudsman
PM – Programme Manager
PMC – Programme Management Committee
PwC – PricewaterhouseCooper
QA – Quality Assurance
QSB – Quarterly Strategic Board
RACI - Responsible, Accountable, Consulted, Informed
R&D – Research & Development
SA – South Africa
SB – Secondary Benefits
SEA – South East Asia
SNOMED CT - Systematized Nomenclature of Medicine -- Clinical Terms
SOBC – Strategic Outline Business Case
SoR _- Scope of Requirements
SP - Strategic Partner (made up of NHS bodies such as HEE and PHE)
SRO – Senior Responsible Officer
TA – Technical Adviser
TB – Tuberculosis
ToC - Theory of Change
TWG – Technical Working Group
VfM – Value for Money
WEE - Women’s Economic Empowerment
WHO – World Health Organisation
WHO AFRO – World Health Organisation Regional Office for Africa
UKIHMA - UK International Healthcare Management Association
UPCPH – University of the Philippines College of Public Health
A. Introduction and Context
DevTracker Link to Business Case:	https://www.gov.uk/government/publications/better-health-programme
DevTracker Link to Log frame:	Not yet published

The Prosperity Fund Better Health Programme (BHP) is a three year, £79.3m programme, which aims to improve health outcomes, and thereby contribute to economic growth and poverty reduction, in eight partner Middle-Income Countries (Brazil, Mexico, South Africa, Malaysia, Myanmar, Philippines, Thailand and Vietnam)

At outcome level, the programme has two main primary and secondary outcomes. BHP aims[1] to:
[1] Since the last AR there has been a change in the Theory of Change (ToC). It has now identified two higher-level outcomes (improved NCD interventions and improved equitable access to health care) and three pathways to change (digital health, education and training and life sciences). This has added clarity for all stakeholders and reflected in the ToC.

Primary
Increase coverage of effective Non-Communicable Disease (NCD) services for prevention, treatment, and management of conditions for populations (especially women and marginalised groups).
Improve equitable access to safe and quality health care for populations (especially women and marginalised groups).
Secondary
Secondary Benefit (SB) 1 - Increase commercial opportunities for business and NHS generated by the BHP (exports, Foreign Direct Investment (FDI), outward direct investment, soft power, market access, network effects)Secondary Benefit (SB) 2 - New or strengthened collaborations with UK institutions (science, research, private sector, NHS)

All country programmes contribute into three programme outputs of the programme. Areas for technical collaboration at country level represent the best match between partner country priorities, potential for development impact and areas of UK capability.

The programme has a multi partner delivery model consisting of (i) commercial contracts with four Delivery Partners (DP), to implement a programme of interventions in eight countries (Mexico, Brazil, South Africa and five in South East Asia (SEA)) (ii) a Memorandum of Understanding (MoU) with a NHS consortium (lead by Public Health England) as Strategic Partner (SP) to lead collaboration between NHS Arm Length Bodies (ALB) and partner governments. Health Advisers in each of the eight BHP countries support programme implementation, government relationships and dialogue.
Additionally, the FCDO and DIT have collaborated on the development of the secondary benefits approach for the BHP. Secondary benefits are achieved through the creation of opportunities through the ODA programme and additional Non-ODA funding. The Non-ODA funding for the programme comes from the Opportunities Fund and is not covered in the scope of this Annual Review (AR), however has enabled secondary benefits outcomes on BHP.
## B: PERFORMANCE AND CONCLUSIONS

Over the past year, the programme successfully moved from inception to full implementation. BHP is now well set up and configured to deliver on primary purpose and secondary benefits. Last year’s AR reported a slow inception, but the decision to work on programme design and the role of the SP has meant that the move from inception to implementation has been smoother than in some other programmes.
The BHP went through a lengthy phase to design, consult and scope the programme and set up the delivery model. The revised timeline of 2.5 years is ambitious for a programme yielding very promising, early results in the context of major risks materialising (pandemic, FCDO merger and impact on ODA). In the context of a declining ODA budget, BHP will need to continue to demonstrate strong relevance to global health objectives (including Indo Pacific Tilt), value for money and impact on poverty.
Annual outcome assessment (Primary Purpose)

1. Increase coverage of effective NCD services for prevention, treatment, and management of conditions for populations (especially women and marginalised groups).
2. Improve equitable access to safe and quality health care for populations (especially women and marginalised groups).

The overall assessment of progress is an A. Outputs have been met, and in some cases exceeded expectations. After just nine months of implementation (six in the case of Brazil), it is too early to demonstrate contributions at outcome level.
A significant part of 2019/20 was dominated by COVID-19 requiring the programme to rapidly adapt. Despite the major setbacks due to COVID-19, and other challenges and risks materialising (FCDO merger* [2] and the impact of pandemic on ODA allocations), the programme is already making a significant contribution towards both outcomes. There have been promising early deliverables towards outcome 1 - the increased coverage of NCDs and integration into health systems (early gains in South Africa and SEA) and strengthening health systems to reach poor and excluded groups as part of Universal Health Coverage reforms in partner countries. Achievements in the ‘Doctors Across Brazil’ project (PHC provision for remote areas) and activities in support of quality of care in South Africa have both paved the way towards improving health for the poorest and most excluded people.
[2] At the time of review, there were significant uncertainties around the strategic direction for prosperity policy and for global health policy.  In addition, there was the potential impact on funding and staffing to take into consideration, should there be substantial reductions in programme funding.
The A rating is given based on country reports, programme-wide scorecards completed by the Evaluation & Learning Team (EL), interviews and deep dives into three countries (Brazil, South Africa, Philippines) chosen as a sample to represent the programme. Deep dives have reflected impressive results in keeping the programme on track and pivoting to respond to COVID-19. Early deliverables are also coming out of reports from other countries (Malaysia and Thailand). This A assessment also draws on the conclusions of the Strategic Board in September 2020, reflecting the view that the programme is mature, with promising early deliverables on primary outcomes and a strong secondary benefits framework. The programme log frame, showing progress against the outputs, is due to be completed within three months of this AR. The AR team recommends that the timing of the next AR be aligned with the log frame process in the coming year to support a quantitative and qualitative assessment, and a review of the Theory of Change (TOC).
Impact of COVID-19: COVID-19 presented a significant risk – the BHP team, delivery partners and strategic partner were able to adjust, and indeed were well placed at the start of the implementation phase, to support partners’ health system during the crisis. Many stakeholders reported the success in keeping the programme on track, adapt to changing needs, providing relevant and high-quality support during the pandemic. The ability of FCDO and DPs to adapt was commended by all stakeholders – for example, analysis of evidence on COVID-19 and NCDs in SA, endorsed by WHO and shared across the WHO AFRO region. The pandemic also catalysed swifter action in some areas and brought forward deliverables in digital health that were not yet expected until Year 2. The BHP’s health focus has also meant that FCDO was able to build stronger bilateral relationships on health in these partner countries. COVID-19 has injected more urgency into the need to strengthen health systems, tackle NCDs and their drivers and the TOC remains relevant.
Annual outcome assessment (Secondary Benefits)

1. SB1 - Increase commercial opportunities for business and NHS generated by the BHP (exports, FDI, outward direct investment, soft power, market access, network effects)
2. SB2 - New or strengthened collaborations with UK institutions (science, research, private sector, NHS)

The BHP was quoted as having one of the most mature secondary benefits frameworks and FCDO and DIT have collaborated in the UK and overseas to achieve outcomes. Secondary benefits are beginning to be seen with over 120 opportunities identified as of November 2020 (Annex B Secondary Benefit tracker). Many stakeholders indicated the high opportunity in secondary benefits for the programme.
SB1: Commercial benefits: There is a robust approach to identifying and tracking across multiple pillars. BHP SB advisors have good networks with UK NHS and UK businesses. They have made connections around opportunities, which have already realised some commercial wins. This activity has been mainly non-ODA enabled and is outside the scope of this AR.
SB2: Non-Commercial benefits (soft power, network effects/mutual learning, Research & Development (R&D)): The majority of non-commercial benefits are in soft power. The wide range of these relate to strategic dialogues in health and wider NHS collaboration. Benefits have been seen with Philippines and Mexico (bilateral relationship), Vietnam (digital health), Thailand (education & training, Brazil (HTA and wider COVID-19) and South Africa (work with the Western Cape). However, there is a need to trace the secondary benefits to the strategic level, especially in SEA, to see where relationships used to support UK objectives on ASEAN Dialogue Partner Status). There will be more case studies developed on realised wins that can be shared across the network.

Both the strategic partner and DIT have been delivering mutual learning webinars connecting the NHS to overseas stakeholders. This includes areas of community health, COVID-19, and nursing. However, having a clearer separation between what the strategic partner and DIT role is in this area can help these to be joined-up and mutually reinforcing. There have been multiple opportunities in the research and development sphere particular in life sciences and wider NHS organisations. The largest of these is the Genomics UK partnership in Thailand.

Although a challenge to operations, many stakeholders have indicated that COVID-19 has also presented opportunities for secondary benefits with partners linking up with UK expertise and experience in both SB1 and SB2 outcomes above.
Risks

Last year’s AR recommended greater communication between the BHP team, Health Advisers and Delivery Partners to manage and mitigate risks as the programme moved to implementation. There is evidence that this management has been implemented with required risk governance in place. Going forward there are several moderate/major risks. These priority risks identified by the AR team relate to (i) ability to deliver within the timelines (ii) impact of reductions to ODA (iii) smooth transition to new FCDO organisation. See Annex E for mitigation action being taken.
## On financial spend, performance has not reached the desired level in the period under review but there are clear signs of improvement which are on course to resolve the issues faced. The key issues in regard of financial management were an underspend of more than 10% in the FY 2019/2020. These issues can be attributed to delays in reaching full implementation across all programme strands. Now the programme has reached this stage, the level of underspend is reducing. Admin spend was well within the 3.5% cap at 2% for FY19/20.
In terms of value for money (VfM), it is still too early to provide a comprehensive assessment, with mixed evidence so far. The programme is delivering VfM in terms of economy and efficiency, with continuous improvements in these regards. However, in terms of effectiveness the case for good VfM is difficult to assess due to the limitations of outputs and outcomes to date. This can be attributed to the relative infancy of the programme. There are signs that the programme will deliver VfM in these regards, but more time and work is needed to evidence this. There are strong equity goals and achievements to date for the programme. On balance, we believe that the programme is on course to deliver VfM and with further improvements, the programme can achieve that.
On commercial considerations, performance amongst the different DPs has been mixed but is effective and improving with strong management from the programme team. The programme DPs have faced a range of challenges dependent on individual contractual arrangements and regional differences, though ultimately none of these issues have been insurmountable.

Governance: The programme Quarterly Steering Boards (chaired by the Senior Responsible Officer (SRO)) met regularly as recommended in last AR. These involve key decision makers from across FCDO, the Department of Health and Social Care (DHSC), Department for International Trade (DIT), and the NHS. The Programme Lead joined the cross-Whitehall Global Health Oversight Group (GHOG) and several work streams on global health to ensure strategic alignment with wider international health policy and programmes in FCDO and DHSC.
Progress against 2019 Recommendations:

Most recommendations were taken on board. Please see Annex C for detail against each 2019 recommendation

Key lessons and Recommendations summary

The key recommendations of this year’s AR include (see Annex A for more detail on the below and additional recommendations)

KEY Recommendation: Flexibility and adaptation needs to continue into next year. A significant part of 2019/20 has been dominated by COVID-19 requiring the programme to adapt activities and re forecast financials due to impacts of COVID-19 on ODA.

KEY Recommendation: Relationships to be built on by FCDO in global health diplomacy, re-establish regular policy dialogue channels with new partners/governments as the COVID-19 crisis subsides and give greater prominence to SP and NHS ‘brand’ where appropriate

KEY Recommendation: BHP team to build on wide range of Technical Collaboration methods to achieve the ‘step change’ envisaged in the innovative design model for BHP model & mitigate the risk of dependency on inputs and ensure long lasting technical assistance, mutual learning and ultimately transition from aid.

KEY Recommendation: Impact of FCDO merger has already offered opportunities to align development and foreign policy goals – take this further in 2021.

Secondary benefits
KEY Recommendation: Delivery Partners outlined their support to help identify secondary benefits and outlined potential areas in their annual reports, however there is still an element of clarity needed around the role of the delivery partner (ODA vs Non-ODA) in supporting secondary benefits and more information to share
Monitoring
- KEY Recommendation: Programme team to develop a process for reporting consolidated programme level indicators and set milestone targets for the indicators.
- KEY Recommendation: Programme team to agree new timing of annual review to align with reporting against log frames.

Summary of changes to the log frame since the last annual review

The original log frame was drafted with the business case in June 2018. The log frame was revised in 2019 to move intermediate outcomes to outcome level, and the latest version (October 2020) was used for this review. The country log frames are complete but do not fully align with the programme log frame, which does not include baselines, milestones, or targets (for primary and secondary benefits). We recommend this be updated within three months of this AR. Additional documentation/milestones have been used for this AR, which are discussed in section C.

## C: DETAILED OUTPUT SCORING

The period under review covered three months of inception and nine months of implementation (Brazil six months inception and six implementation). As the Inception Report and Implementation Plan was approved by SRO, it was agreed that this AR would assess the implementation period (January – September 2020). Quantitative data on outputs was not collected due to timing of log frames (see recommendations). In the absence of this data, we have scored outputs based on other sources.
1. Report ‘BHP Review of progress 2019/2020’ based on document review, workshops & collation of evidence lead by the BHP Evaluation team [Annex E]
2. Quarterly programme reports for the period under review, Strategic Board minutes & contract management milestones (table 1 below).
3. Deep dives into three countries: Brazil, Philippines, and South Africa
  1. Review of delivery partner annual reports
4. Interviews with internal and external stakeholders during week c. 23/11 [See Annex E for list of interviews]
5. Review of secondary benefits tracker and framework

Table 1: Overview of contract/milestones met/missed for the period under review.

	Jan-Mar 20				Apr-Jun 20				July-Sept 20
Delivery Partner:	DAI	McK	MM	PwC	DAI	McK	MM	PwC	DAI	McK	MM	PwC
Achieved / On-track	4	0	2	0	7	8	2	0	8	9	8	1
Missed / At risk	0	0	0	0	0	0	0	0	0	0	0	0

Output 1: Overall A. All milestones met/on track.

Output name	Capability building through education and training, knowledge exchange, strategy, and policy development/implementation to tackle the burden of NCDs and improve quality of care
Output number per LF		Output Score	Brazil - A / Philippines - A / South Africa - A / Overall - A
Risk:	Moderate	Impact weighting (%):	N/A
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Key Points: Key indicators are under revision. No milestones were set at programme level, log frame not yet due to be completed. Scoring based on contract milestones met, quarterly reports and sampled countries. As currently defined, the programme level output indicators are: / # of health workers accessing training (including CPD) interventions on national NCD standards / # of countries with operational guidance (action plans, protocols, and guidelines) to tackle NCDs, working to improve quality of implementation at national, regional, local levels. Standards for prevention, treatment, and management / Feedback obtained on service quality, used to inform policy, strategy, clinical and quality standards / Significant progress was made over the past year in contribution to output 1 (specifically 1.2 & 1.3) in South Africa (SA), Brazil and Philippines further reported in deep dives. There was also support action plans, protocols, and guideline for the COVID-19 response. In many cases, rollout of training (1.1) will commence in Y2 of implementation. Highlights include: / Highly valued long-term technical assistance to the HRH Directorate for COVID human resources planning – SA / Formal approval given for a twining agreement between the UK Parliamentary and Health Service Ombudsman (PHSO) and the Office of the Health Ombud (OHO) in SA. / Evidence Brief on COVID-19 and NCDs in SA, endorsed by WHO and shared in the Afro region & webinars on NCDs and COVID-19 sharing SA evidence with other BHP countries / International lessons from surge hospitals (June 2020) opened by the Deputy Minister of Health SA. / Capacity building for the Ministry of Health on tools to help prioritise business models to implement remote diagnostics in Brazil / Providing technical benchmarks and implementation roadmaps to establish a genomic database in Brazil / Developed scoping tool criteria and planning guidelines for Pasig City and Iloilo City in Philippines / Developed training course designs for hypertension, GDM and clinical pathway development in Philippines / Facilitated Local Learning Network co-creation workshop with Pasig City and identified city-based learning hub. / Examples from other countries do not include in deep dives below, include: / In Thailand: Delivery of Physician and Nursing CPD Models; A rapid review of literature on Health Accreditation models in Thailand and in the UK; literature of social marketing rapid review - practices in Thailand and internationally; Completion of the front-of-pack labelling (FoPL) rapid review / In Myanmar: BHP initiated the review and development of the NCD public health module and teaching and training method & review of WHO’s voluntary NCD global targets to assess how NCD related data is used in the national health system, identifying future intervention. / Malaysia’s focus on Community Health Workers, progress was made in developing and implementation of Gender and Social Inclusion (GSI)-responsive comprehensive packages of obesity prevention interventions for pilot interventions & preparation and development of digital health solutions to enable the delivery of intervention packages and education and training for Community Health Volunteers (CHVs).

Output 2: Overall A. All milestones met/on track.

Output Title	Increased use of digital technology and improved integration and utilisation of health information and data to inform practice and tackle the burden of NCDs and improve quality of care
Output number per LF	2	Output Score	Brazil A / Philippines A / South Africa - A / Overall A
Risk:	Moderate	Impact weighting (%):	N/A
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Key Points: Key indicators are under revision. No milestones were set. As currently defined, the programme level output indicators are: / Evidence of NCD data available via digital health information systems, used to improve practice in NCDs / Evidence of health workers accessing digital learning mechanisms, used to improve Quality of Care practice in NCDs / Significant contribution to output 2, especially in Brazil, where COVID-19 provided even greater impetus to push forward with the digital health strategy. / In SA work underway in integrating NCDs into national data systems / The design of key processes and indicators for the implementation of “Doctors Across Brazil” was undertaken and inputs were gathered for career plans that will lead to more sustainable primary care provision to remote areas in Brazil and improved primary care medical training. / Supporting data usage by helping the Brazil Ministry of Health (MoH) address patient consent in the new digital health data network and by ensuring that the new MoH data portals for healthcare professionals addresses the needs of users. / Advancement of national capacity for research and the technical capacity for expanding clinical trials by helping set a new ambition for clinical research in the country and defining the role the national clinical research network will play in this space. / Developed the ‘Policy Anchors Report in Support of National Level Health Information Systems’ with a focus on NCDs, which includes a review of the e-health and digital health intervention-related policies and programs in the Philippines. / Facilitated Joint Application Design workshops with Pasig City and Iloilo City in the Philippines for the development of NCD MuPLoR. / Examples from South East Asia (SEA) not include in deep dives below, include: / Vietnam: review of best practice healthcare service delivery models enabled by technology & site visits to evaluate the application of Smart Health in Vietnam; dossier of international best practices on the SNOMED CT (SCT) health information system to support the development of recommendations & approach to standardising and integrating SCT into pilot hospitals.

Output 3: Overall A. All milestones met/on track.

Output Title	Life sciences research and development and health technology assessment capability to tackle the burden of NCDs and improve quality of care
Output number per LF	3	Output Score	Brazil A / Philippines A / South Africa A / Overall A
Risk:	Moderate	Impact weighting (%):	N/A
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Key Points: Key indicators are under revision. No milestones were set. As currently defined, the programme level output indicators are: / Number of new NCD findings and articles published (linked to BHP) in quality peer reviewed journals / Number of new NCD related Health Technology Assessments initiated and/or completed to inform policy, standards, guidelines, and priority setting / Contributions to output 3 include: / South Africa includes a component on HTA which commenced in 2020, and will continue in year 2 / Provision of technical assistance to the Essential Medicines List and the Standard Treatment Guidelines in support of the Health Technology Assessment work stream in SA. / Advancement of national capacity for research and the technical capacity for expanding clinical trials by helping set a new ambition for clinical research in Brazil and defining the role the national clinical research network will play in this space. / Engaged the University of Glasgow for the co-creation of HTA course in Philippines

Summary of responses to issues raised in previous annual reviews (where relevant)
Most AR 2018/2019 recommendations have been addressed. See Annex A. Those not addressed (Log frame) needs to be reviewed within 3 months.
DEEP DIVE 1 – BRAZIL

The programme in Brazil started implementation in April 2020. The SRO has approved the inception report and implementation plan, so the progress reviewed here relates to the first six months of implementation. The Brazil programme is reporting against three outcomes: Primary Care, Data and Innovation and Evidence, which are broadly compatible with the three programme outputs. The outputs associated with the three outcomes are:

Outcome	Output
Primary care	1.1 Improved, aligned, and reformed primary care training for medical graduates across the country
	1.2 Increased availability of professionals into primary care
Data	2.1 Data usage, payments and reimbursement systems and evidence-based quality improvement in primary care
Innovation and Evidence	3.1 Enhance federal and state capacity to conduct health technology assessments
	3.2 Strengthened policy and regulation for digital health
	3.3. Enhance national capacity for prioritizing, commissioning, incentivizing, dissemination research
	3.4 Enhanced technical capacity and regulatory environment to conduct phase 1 and 2 clinical trials

Summary of progress.
All projects and milestones are on track to deliver to the agreed plan and are expected to contribute to outputs and outcomes. Three key milestones were delivered:
  - Methodology and diagnostic inputs for Digital Health Strategy
  - Diagnostic of clinical research environment in the country
  - Mapping options for remote diagnostic business model.
Some changes in the programme were needed to react to COVID-19; these included, for example, acceleration of the National Health Data Network expansion activities and postponement of pilot activities. In addition, there were frequent changes at the Ministerial level in the Department of Health (DoH). The programme was able to adapt its activities very quickly and maintain momentum towards impact. Notable achievements are:
- Support to the Doctors across Brazil programme to attract, train and send doctors to remote areas to reduce regional disparities in primary care. This work stream is a good demonstration of the G&I ambitions of the programme and of contribution to primary purpose. On G&I, focus group discussions were held with female doctors and doctors from different ethnic and LGBT groups to understand additional barriers faced if posted to remote areas. By addressing regional disparities, Doctors across Brazil will help to bring primary care to the poorest and most excluded people in society. This work stream contributes to Brazil outputs 1.1. and 1.2
- In support of outputs 3.2 and 2.1, BHP delivered benchmarks (both UK and international) that helped strengthen the Ministry of Health’s (MoH) digital health strategy. In an example of adaptive programming, the focus was shifted in response to requests from the MoH towards help with the General Data Protection Regulation and design for a new data portal. The aim of the new data portal is to improve the experience of health professionals accessing the data to encourage them to submit data.
- The programmes’ activities on developing the vision for a clinical research network supports Brazil outputs 3.3 and 3.4. The programme produced an evidence-based assessment of the challenges and opportunities in the area to support the MoH to revamp the National Clinical Research Network. It undertook extensive stakeholder consultations to inform and build consensus around the plan. “The programme enabled us to think outside the box”. In addition, the programme is supporting the area of genomics in Brazil, with the aim to help them become the leader in genomic medicine among middle-income countries.
UK Collaboration

- The programme has facilitated 12 learning sessions with the Strategic Partners, bringing in NHS, NHS Digital, NHSx, Health Education England (HEE), National Institute for Health and Care Excellence (NICE), National Institute of Health Research (NIHR) and Genomics England as appropriate.
- Relationships built in the programme have contributed to laying the groundwork for COVID-19 partnerships including testing the AstraZeneca COVID-19 vaccine.
- Brazil and UK cooperation agreement on public healthcare aiming to promote cooperation between the Ministry of Health of Brazil and the FCDO in health under the framework of the BHP. The agreement will encourage collaboration in jointly decided areas that reflect strategic priorities for both countries, based on mutual interest and promoting inclusive economic growth and social development.
- BHP and DIT supported a workshop in Brasilia, Brazil, with multiple stakeholders delivered by the UK NICE covering topics around Health Technology Assessment (HTA) with the aim of establishing a longer-term relationship

Stakeholder reflections

- The stakeholders interviewed all recognised the high quality of the deliverables and the relevance of the programme to their needs.
- Most stakeholders valued the flexibility of the programme delivery, although some thought there could be more flexibility on time scales.
- The participation of the SP was valued in bringing relevant NHS experience to the project, as the NHS is seen as a key partner for the Brazil SUS system. For some stakeholders, their contribution was either not sufficient or not visible enough.
- Health diplomacy is a key factor in Brazil. Both overseas external stakeholders and HMG Brazil colleagues emphasised the desire for wider and longer-term partnerships with the NHS beyond the programme. The on -line training and stakeholder events were appreciated by most stakeholders, but the majority also mentioned that lack of simultaneous translation limited participation, particularly for technical training.
- On national priorities, external stakeholders recognise that the BHP has a role in driving digital health, solving regional disparities especially in the North and North East and the ongoing problem of weak primary care system
- For some stakeholders, their knowledge of the programme was limited to the area in which they were directly involved, although they expressed interest in learning more about other Brazil interventions and the other eight countries of the BHP
- There are secondary benefit opportunities linked in the change of regulation on telemedicine and in wider life sciences that need to be explored
- Working with the MoH closely on COVID-19 has found opportunities and been positive, with little impact in moving the project forward.
Recommendations (specific to the Brazil programme)

- Increase use of simultaneous translation for all events (including on-line ones) to ensure maximum participation from stakeholders
- As the programme moves to implementation, the role of regions and municipalities is more important and is not yet adequately reflected in the stakeholder engagement.
- Involve the strategic partners more in meetings to give direct feedback, for example, the project team has plans to do this for career path planning developed by the MoH.

DEEP DIVE 2 – SOUTH AFRICA

Summary of progress. All projects and milestones are on track to deliver to the agreed plan and are expected to contribute to outputs and outcomes. Three milestones were delivered:

1. Symposium on latest research on NCDs and COVID-19
2. Literature reviews and clinical reviews for the evidence brief on COVID-19 and NCDs in South African (SA) context
3. Supported the implementation of the National Quality Improvement Plan
4. Groundwork for support to the Community Health Worker (CHW) training

The programme pivoted to respond to COVID-19 quickly and responsively which was highly valued by counterparts. BHPSA’s (BHP South Africa) adaptive and responsive approach to the crisis raised the programme’s profile with key stakeholders and forge important links between UK and SA institutions. There are high quality communication products profiling the work of the programme.

Delivery of outputs

There is a broad range of work to strengthen SA’s integrated response to NCDs and prepare to the rollout of national health insurance in SA by building quality of care and accountability in the health system. SA’s programme in year 1 was most relevant to output 1 (education and training, knowledge exchange, strategy, and policy development/implementation). Notable achievements are delivered across four sub outputs:

1.1 An integrated multi-sectoral NCD response. In 2020, BHPSA built the evidence for NCD response and groundwork for CHW programme (which has to date focused on HIV, TB, and Maternal and Child Health interventions) work that will be influential in shaping in Y2 & Y3
- Evidence brief on COVID-19 and NCDs, endorsed by WHO and shared in the Afro region;
- NCD management adapted to meet the needs of older people and their vulnerability to COVID-19;
- Support to finalise National Strategic Plan (NSP) for NCDs (2021 – 2026), an M&E framework for the NSP, and a detailed costing (underway) delayed due to COVID-19 & CSO inputs;
- Support to develop the social and behaviour communication change and evaluation framework for the national NCD campaign;
- Review of CHW NCD interventions and developing draft NCD modules for a national CHW upskilling programme, pre- and post-training assessment of knowledge and skills.
1.2 HSS support for strategic mechanisms and processes
- Situational analysis of Strategic Purchasing incl. international best practice, focus on PHC;
- Highly valued technical assistance to the HRH Directorate (1 full time TA embedded for 10 months) – COVID-19 HR planning and integration of medical students into Internship and Community Service programmes.
1.3 Building oversight and accountability of health service
A twining agreement between the UK Health Service Ombudsman (PHSO) and the Office of the Health Ombud (OHO).
1.4 Capacity for improved quality assurance and quality improvement strengthened
Support to the Office of Health Standards Compliance (OHSC) business case;
COVID-19 related work
- Development of a rapid inspection tool for Temporary Hospitals with the OHSC within a period of 10 working days and adapt the tool for COVID-19-specific wards set up in existing hospitals;
- Webinar on international lessons from surge hospitals opened by the Deputy Minister of Health.

Output two aims to improve the integration of data sets, data collection and data use improved
In 2020, technical support was provided to integrate NCD data and improve surveillance with National Indicator Data Set (NIDS) and routine data collected through the District Health Information System (DHIS).

Output three aims to strengthen the use of Health Technology Assessment (HTA) for decision-making. In 2020, BHPSA produced a Situational Analysis on HTA.

UK Collaboration:

- As part of the NHS Joint Unit CTAS engagement, learning sessions commenced between the SA Office of Health Standards Compliance (OHSC) and the UK Care Quality Commission (CQC), which the OHSC has reported to be very valuable;
- The NHS Joint Unit facilitated discussions with the UK Parliamentary and Health Service Ombudsman (PHSO) and formal approval has been given for a twining agreement between the PHSO and the Office of the Health Ombud (OHO);
- A webinar on lessons learned from the UK Surge Hospital Programme was hosted with National Director of Estates, NHS England, and Improvement and opened by the SA Deputy Minister of Health.

Stakeholders Reflections

- All stakeholders noted that programme on a strong footing with high quality relevant support that meets the needs of the poorest and most excluded people in SA;
- Excellent relationships established and maintained between BHPSA Work stream Leads and key national counterparts & between the delivery partner, BHPSA FCDO Health Adviser at Post, members of the NHS Joint Unit and members of DIT at country and UK level. Mott McDonald TA recognise as high quality and spot on;
- High regard for NHS (through scoping and as SP) – approach of shared learning and partnership, open dialogue learning as well. Twinning, webinars and learning exchanged have been particularly valued;
- Governance structure has not been established, (due to changes in senior leadership and the pressures to prioritise the COIVD-19 emergency), senior management and leadership are engaged in the programme and BHPSA is recognised as a role-player in the sector.

Recommendations (specific to South Africa programme)

- Year 1 has shown advanced research capacity in NCDs that exists in SA; continue to draw on highly specialised local consultants to provide technical assistance under the programme. Potential for sharing of technical expertise with other BHP countries and the UK;
- Considerable management time on contract compliance and reporting. The demand-led, highly flexible, and responsive approach to HSS ensures quick wins and effective counterpart support and buy in. COVID-19 brings home the benefits of adaptive programming. This can be at odds with stringent contracting requirements and process for changes, which can affected DP ability to provide timely support. Consider approaches to contract management that support adaptive programming;
- Very promising early results but risk of over-reliance on short-term consultancies. COVID-19 provided pressures to deliver quickly. As the crisis subsides and efforts move to building back, BHPSA will need to shift a gear to demonstrate ‘step change’ in FCDO’s approach in SA. This means broader range of approaches to collaboration – from time sensitive pieces of work by consultants[3], embedded advisers within MoH, support from NHS/CTAS, twinning and peer- peer arrangements, working with regional bodies (WHO AFRO), south-south collaboration and mutual learning.
  [3] In BHPSA in year 1, 40 technical assistance assignments in 2020, by 73 individuals, issued under 40 contracts.

DEEP DIVE 3 – PHILIPPINES
Summary of progress: All projects and milestones are on track to deliver to the agreed plan and are expected to contribute to outputs and outcomes. There is a broad range of work in the Philippines to strengthen the Philippine local health system towards improving health outcomes over the medium- to longer-term and to address growing burden of non-communicable diseases (NCDs) – with focus on developing Gestational Diabetes and hypertension training materials for primary health care providers in Y1. Additionally, there is a model to assist selected Local Government Units (LGUs) in developing NCD-related policy documents on multisector strategic plan aligned with the Philippine Universal Health Care Law.

Notable achievements

- MoUs were signed with both University of the Philippines College of Public Health (UPCPH) and Iloilo City. For UPCPH this marked the British Embassy’s first formal partnership with a Philippine academic institution;
- NECoD Study protocol was approved by the Regional DP;
- BHP health diplomacy and mechanism to engage with ministries of health including during COVID-19 pandemic – narrative of UK supporting HSS and using global experts resonated well and opened other avenues of discussion;
- Iloilo City local government’s recognised BHP contribution and impact to local health systems development to the city’s adaptive response to COVID-19;
- While it is early in the programme cycle to attribute BHP interventions directly to G&I impact, our work with Pasig City in particular will benefit mothers and infants, as one of the priority NCDs identified by the local government is Gestational Diabetes.

Deliverables over the past year are outlined across three sub-outputs:
1.1 NCD Strategies
- Completed and submitted documentary requirements for Situational Analysis ethical review working with FCDO Post in the country to facilitate this;
- Developed scoping tool criteria and planning guidelines for Pasig City and Iloilo City;
- Developed training course designs for hypertension, Gestational Diabetes Mellitus (GDM), and clinical pathway development;
- Engaged the University of Glasgow for the co-creation of HTA course.

1.2 Education and Training
- Developed and presented the Local Learning Framework and presentation to Pasig City and Iloilo City;
- Facilitated Local Learning Network (LLN) co-creation workshop with Pasig City and identified city-based learning hub;
- Mapped out possible partners for the LLN in both cities;
- Developed the Reference Notes on Competency, Learner, and Gap Assessment for Local Learning Providers and on Expansion of Non-Communicable Diseases Training through Transnational Linkages. These were both shared with FCDO and SP.

1.3 Digital Health Interventions
- Developed the Policy Anchors report in Support of National Level Health Information Systems with a focus on Non-Communicable Diseases, which includes a review of the e-health and digital health intervention-related policies and programs in the Philippines;
- Facilitated Joint Application Design workshops with Pasig City and Iloilo City for the development of NCD MuPLoR;
- Developed and validated MuPLoR high-level design and mapping of LGU registry and reporting forms;
- Developed MuPLoR prototype build based on high-level design intended for pilot use in the LGU setting. The eventual adoption and utilization of MuPLoR will be based on the LGU adoption policies and approved agreements with the LGU partners.

UK Collaboration:

- Starting to set up for successful UK collaboration in the future to deliver many learning exchanges between UK and NHS and regional visits;
- Peer-to-peer learning approach established in collaboration with Strategic Partner and NICE has worked well in the Philippine context where a developing system is learning directly from parallel counterparts in the UK. The NHS Joint Unit and NICE have supported Post in establishing a more proactive and collaborative working relationship with the Department of Health;
- A range of secondary benefits have been identified including around COVID-19 learning exchanges, vaccines, public health collaboration and wider soft power benefits from learning linkages featuring UK expertise, as well as one commercially in digital health;
- Webinar series with UK experts and University of Philippines on public health seen active participation and generating feeling of mutual partnership and promoted the public health agenda of Philippines as a platform.

Stakeholders Reflections:

- Interventions aligned well with national universal health goals including matching digital interventions to NCD programmes. The national government has responded positively to BHP’s narrative of supporting a growing, global community of learning and practice (by amplifying in public comms);
- The NHS SP has helped raise the profile of UK expertise in the Philippines through learning exchanges. The SP model has worked well in the Philippines, particularly to deliver the global community of practice and learning. All external stakeholders want longer term partnerships with NHS in other support areas;
- External stakeholders very impressed with the BHP and NICE strategic partnership affirming processes and methods but also inspiring them to improve, deal with private sector companies and involve patients;
- The BHP has contributed to wider health diplomacy by supporting meaningful system-to-system engagement. The programme’s multi-stakeholder approach builds on long-term technical partnerships between the UK, and the Ambassador to the Philippines talks about BHP as key enabler to partnership with the Philippines foreign minister;
- Strong connection with the local government units (LGU) who have good political will to drive the programme. Enabling this are strong stakeholders on the ground; all parties working closely with decentralised LGU and ensuring ownership to these units;
- BHP Philippines and Malaysia had a valuable COVID-19 learning exchange in May, and looking into exchanges with Thailand on vaccine deployment and planning;
- Teething problems with on boarding of the delivery partners but sub-contractors driving the relationship to the technical front facing delivery;
- On COVID-19, operations have slowed but one of the positives has been the realisation that surveillance systems, currently infectious disease focused also be NCD focused.

Lessons and recommendations (specific to Philippines or wider SEA):

- Given the context of the pandemic, the BHP has an opportunity to capitalise as a global health programme and leading HMG role in health in Philippines and SEA. A regional role/programme advisor for SEA on policy would help look at the broader impact and relationships and expanding in post recovery context;
- Consideration to a more structured HMG strategy for longer-term partnerships with Philippines and NHS as well as wider health objectives in country. Also, more connections with Philippine external stakeholders of other seven countries;
- Improve UK Linkages team roles and communication to all HMG colleagues across SEA
- Positioning the programme management team – there are some DP partners in Singapore and maybe need to be closer to the countries.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE
#### Cost drivers and performance:

The programme only spent around 90% of its FY19/20 budget, due to delays in reaching full implementation and the early disruption of COVID-19. The key cost drivers of the programme are the programme delivery phase costs (including the Strategic Partner) and the staff costs, accounting for 82.4% and 8.4% of the actual spend in FY 19/20 respectively. Admin staff costs for FY19/20 were within the cap of 3.5% at 2%. All projects show variances from budget in FY 2019/20, most notably an underspend of £1m on the delivery phase line which caused the underperformance in that financial year. The effects of this underspend are also reflected in FY 2020/21, with a forecast overspend on the delivery phase, resulting from delays in the previous financial year.

	FY 19/20 Budget	FY 19/20 Actuals	Variance	FY 20/21 Budget	FY 20/21 Actuals	FY 20/21 End Forecast*
FCDO Staff	£290,020	£326,016	112%	£289,952	£146,452	£289,952
LE Staff	£235,781	£258,301	109%	£254,209	£122,209	£254,209
Platform Charges	£252,885	£254,012	101%	£228,796	£228,796	£228,796
Non staff admin	£15,999	£4,563	28%	£10,709	£709	£10,709
BC Development	£0	£34,330	-	£0	£0	£0
UKB T&S	£13,821	£8,032	58%	£9,013	£13	£9,013
LEs T&S	£55,890	£67,771	121%	£24,489	£1,989	£24,489
Training	£23,411	£12,774	54%	£10,006	£6	£10,006
Other Consultancy	£185,000	£190,223	102%	£92,545	£81,670	£92,545
Prog Enabling Activity	£280,000	£265,341	94%	£30,459	£459	£30,459
Delivery Phase	£6,991,460	£5,954,884	85%	£15,536,924	£8,355,793	£21,569,843
Strategic Partner	£685,344	£719,597	104%	£1,012,898	£468,232	£1,012,898
GRAND TOTAL	£9,029,611	£8,095,845	89%	£17,500,000	£9,406,328	£23,532,919

#### Value for Money (VfM)
The programme is on track to deliver good value for money (VfM) and has already overcome several challenges to stay on track. Whilst it is still too early to fully assess programme outputs, the performance to date is encouraging with early signs of effectiveness across various strands of the programme. There is evidence that the programme is increasing efficiency and delivering in an economic manner, though there are still areas for improvement, which could deliver greater efficiency and economy. On balance, the review team believe that the programme represents good VfM, with potential for greater effectiveness than had previously been anticipated before COVID-19.
#### Economy:
The programme is being delivered through a unique model utilising the expertise of the NHS Strategic Partner (SP) alongside a range of agreements divided geographically across country and regional programmes. This model has offered an adaptive and flexible mechanism to support delivery, which has been very effective following the onset of COVID-19. These adaptions have included the realisation of savings on travel spending, which have been repurposed to support continuity of delivery. The delivery model assumes that the role of the SP should be focused on the relationship with government partners and providing QA. It is important that the SP is not drawn-into delivery of DP products as happened initially.

The delivery model also utilises contractually agreed profit caps, which can be effective in delivering value for money. However, the caps are monitored through delivery partners self-audit, which is not the most effective use of this contract mechanism. The report recognises, however, that these contractual terms are set at the PF Framework level, and not by individual programmes.

All the programmes’ budgets show an over or underestimation, however the report recognises that this is inevitable in a programme like BHP. Technical Assistance is inherently demand-driven and dependent upon wider factors so perfect forecasting cannot be reasonably expected. The programme has established procedures to monitor spending of internal and contracted costs. The contracted costs are monitored against pre-agreed work plans, with variations between forecast and actual spend regularly queried by the programme team. This process has showed signs of improving financial management, with underspend reducing as a percentage from FY18/19 to FY19/20.

The programme team does not track currently benchmark activities and input costs across the Delivery Partners and countries to ensure costs are justifiable, which would be an effective process to support economy. We recommend that the programme team should look to benchmark across delivery partners and countries, where possible and that they should track unit costs of activities, inputs or outputs with other programmes. This would support further improvements in delivery VfM.
#### Efficiency:
The programme has experienced delays in moving from the inception phase into full implementation, like other PF programmes, though the transition from inception to implementation has been comparatively smoother. This can arguably be attributed to the extensive engagements and development during the strategic development phase of the programme.

While most of the products have been high quality, there have been some concerns about duplication of efforts (poor quality products (such as reports or presentations) requiring additional Technical Assistance) this has been resolved and the SP TA is now triaged to where NHS expertise is most needed.

The programme has been able to deliver on all outputs for the year and leverage some early successes in terms of engagements with Ministries of Health to pivot to COVID-19 in a very efficient way, optimising interventions for the challenging and changing environment. Virtual and remote working during COVID-19 has proven to be an efficient alternative to face-to-face meetings for some of the planned interventions. With this, the programme has also been able to receive additional input from more senior staff within partner countries and UK ministries/stakeholders, which has likely improved the quality of deliverables and of the engagement between partners.

Reductions in spending on staff costs, consultancy costs and programme enabling costs from FY19/20 to FY20/21 demonstrate improvements in the efficiency of delivering the programme, particularly alongside scaling up interventions.

#### Effectiveness:
The programme ToC was refined in the summer of 2020 to reflect what the team expect to achieve within the life of the programme and what will be achievable downstream. The revision sought to re-align outputs-outcomes-impacts with the log frame, review assumptions, check pathways of change, and update the Secondary Benefits. Country log frames and work plans have been nested into the global programme ToC. Further reviews of the reporting structure are planned in the coming year to ensure alignment between programme level and country level ToCs and log frames.

It is too early to fully assess effectiveness, as actual results are not yet being reported. As previously noted the programme has only entered full implementation across all programme strands within the period under review. However, there are some early examples of impact, such as strong engagement from partner governments and a growing pipeline of commercial ‘wins’ emerging.

Amongst the successes of pivoting to COVID-19 effectively, there have been a number of advancements in the Brazil programme strand, which has progressed work in telemedicine and engagement on clinical trials at a greater pace than previously anticipated.

#### Equity:
BHP’s outcomes have equity at the heart - support for expanding access and quality of care for poorest and most excluded groups in relation to NCDs. Many of the world’s ‘Bottom Billion’ live in Middle Income Countries (MIC) and the programme focuses on addressing inequalities in access to health services and issues disproportionately facing the poorest and most excluded groups – which have been exacerbated by the COVID-19 crisis.

The programme has a strong methodological approach to Gender and Inclusion (G&I) with elements included viewed as best practice for G&I-sensitive procurement. Programme countries have conducted G&I assessments to improve the evidence base on the G&I dimensions of proposed interventions, which have been used to develop G&I action plans. It is clear that the programme understands the importance of gender equality and social inclusion and that project-level plans are in place to deliver interventions in an equitable manner, but it is less clear that appropriate tracking is in place to evidence the distribution of benefits. The programme would benefit from developing a programme level G&I action plan which clearly sets out the vision, level of ambition and sets milestones for learning and reporting at the programme level by Q4 20/21.

The interventions on G&I are at a higher level of transformative change and are mainly focussed on gender equality. However, more work is needed for the programme to go beyond the current gender to focus on other excluded groups.

This approach to promote public health outreach and reduce inequalities is clear through the early focus on Community Health Workers, Primary Health Care, CSO consultations, public health communications and remote / the poorest regions. There are strong elements in South Africa to promote greater accountability and in Brazil and the Philippines on primary health care and reaching remote areas. The review team recommend continuing steps to ensure the equitable distribution of benefits, define how the indicators in the LF will be measured in the lifetime of the programme, including disaggregation of data by equity dimensions. Ensure equity sufficiently reflected in the ToC, since the emphasis on the poorest in society, while present in the activities, is not explicitly referenced in the ToC.
#### Quality of financial management:
The programme has financial management processes in place to set budgets, track expenditure, invoices and forecasts, which has improved financial management in FY19/20. The information provided by delivery partners is reasonably consistent and provides an appropriate level of detail to allow the programme to manage its finances effectively.

It should be noted that financial management has not been aided by a great deal of uncertainty in 2020 e.g. due to reductions in ODA allocations and impact of COVID-19, the programme team have navigated these challenges effectively and this has not hindered financial management.

Date of last narrative financial report	November 2020
Date of last audited annual statement	2019 Annual Review

E: RISK
Overall risk rating: Moderate/Major
The review’s conclusion is that the main risks (see Annex F) to the programme are related to delivery risks, include:
1. The ability to deliver within the timelines;
2. The impact of reductions to ODA and demonstrating strong relevance to global health objectives, including Indo Pacific Tilt, VfM and impact on poverty,
3. BHP smooth transition to the new FCDO structure.

There remain significant MREL risks including:
1. Ensuring learning and better understanding on the link between outputs and outcomes and what is really working;
2. The inherent difficulty in defining metrics and evaluating the success of technical collaboration. This is not unique to BHP, but if it is not addressed in the context of declining ODA, it poses a risk to making the case for BHP. The MREL team should look across the portfolio of FCDO ‘partnership programmes’;
3. Demonstrating quantitative impact and giving more attention to the process of inputting quality data to the log frames (explored more in MREL section).

Reputational risks identified:
Some reputational risks have materialised including reception of UK response to COVID-19 (mitigated through mutual learning). Also, negative reactions in press and wider community to Better Health and NHS (such as use of NHS resources outside of the UK).

Finally, some operational risks
1. In country, operational, and contextual risks include political shifts and subsequent changes in the Ministries of Health in each of the partner countries require a re-establishment of relationships and buy-in in several countries;
2. Risk of increasing capability needs of staffing to achieve results in wider health diplomacy link up at Post, which was not envisioned at start of programme.
Overview of programme risk:

Commercial risks have been well managed this year as outlined in section F.
- In the last AR, good communication between the BHP team, Health Advisers and Delivery Partners to manage and mitigate risks was recommended as it goes into implementation. There is good evidence that this management has been implemented;
- Programme and country risk registers are maintained, and Health Advisers report back on in-country risk intelligence; they are particularly agile at identifying, analysing, and proposing mitigations to in-country risks. Ongoing, risk is reported and analysed in detail on the Quarterly Reports to the JFU, and risk is discussed at the quarterly Strategic Board and monthly Programme Management Committee (PMC) meetings. Additionally, Delivery Partners and Strategic Partner report monthly on risks through the reporting governance system managed by the programme team that all major BHP partners have visibility over;
- As reported in the last AR, the BHP went through a lengthy phase to design, consult and scope the programme and set up the complex delivery model. The revised timeline (2.5 years of implementation) is ambitious for a programme yielding very promising, early results in the context of major risks materialising (pandemic, FCDO merger, and impact on ODA). The promising early result may warrant an extension beyond March 2023;
- In terms of COVID-19, stakeholders have indicated this has been more an opportunity than a risk to the programme and levels of support and engagement have adapted to these requests for support. There is more of a risk now about expectations management on scope of the programme.
F: COMMERCIAL CONSIDERATIONS
#### Delivery:
- The impact of COVID-19 has been felt by the programme, but this has been less severe than first feared and the programme has been able to adapt delivery effectively to the changing circumstances. The knock-on effect of COVID-19 for ODA budgets has also been disruptive with uncertainty over budgets impeding delivery to some extent but ultimately delivery has been maintained;
- There have been some delays in reaching implementation, particularly in Brazil where some pilots have been delayed quarter by quarter, though all programme strands are now in full implementation.
#### Performance of partnerships:
- Delivery Partners have performed reasonably well in delivering implementation plans and adapting to changing requirements of the programme as the challenging circumstances necessitated. The performance of partnerships does vary somewhat between the different delivery partners, with some considerable start up delays in SEA including recruitment, some delivery partners have been able to flex their approach more effectively in responsive to the situation than others, though the nature of the challenges faced do vary by country/region.
- In some cases, the issues faced are not eased by contractual arrangements, such as in South Africa, where flexibility and adaptation are not aided by restrictive contractual commitments. Whereas in Brazil this has not been the case, the Delivery Partner has been able to adapt much more easily, though they face a different challenge in regard of communication. The need for and at times lack of a translator has adversely affected engagement with the partner government and relevant ministries;
- In other cases, there have been problems with Delivery Partners not providing the necessary level of detail on log frame indicators and reporting underspending too late in the process, making financial management difficult. Where there have been issues with the performance of partnerships, the programme team have utilised contract management systems effectively to manage improvements, which will be covered in the subsequent section;
- The more direct relationships with suppliers appear to be the most effective, especially in SEA where relationships with sub-contractors appear to be more effective than the relationships with the main contractor. The additional layers of complexity, which come with the SEA model, could go some way to explaining the teething problems experienced so far in regard of working remits and ownership of relationships. This was also not helped by concerns earlier in the year over the delivery partner’s ability to mobilise technical resources. This issue appears to have been overcome but did require a fair amount of input from the programme team which did not represent optimal delivery by the main Delivery Partner;
- The partnership with the Strategic Partner is a valuable but could go further in terms of impact. Discussions with teams at post and with Delivery Partners have highlighted that the expertise of the Strategic Partner is highly valued by partner governments. The consensus is that more should be done with the Strategic Partner, that greater involvement is needed from the Strategic Partner to improve effectiveness in country.
#### Commercial management systems and service level agreements:
The commercial agreements are managed by Key Performance Indicators (KPIs) and Payment by Results (PbR) mechanisms to ensure high quality of delivery. Performance against these measures is monitored monthly and where action is required to improve performance, the appropriate steps are taken. There is evidence that these mechanisms are being used effectively, most notably in the withholding of payments to a delivery partner, which had not delivered as intended against performance metrics.

G: BUSINESS ENVIRONMENT
Secondary Benefits Approach:
- FCDO BHP Programme team and DIT Healthcare and Life Sciences team have developed a close working relationship to identify and deliver secondary benefits on the programme. They have jointly developed a detailed secondary benefits strategy and framework that is considered to be one of the most mature across all Prosperity Funds according to SROs of the programme and have shared their best practice to other programmes accordingly;
- Outlined in this framework, DIT trade officers, Health Advisors, Strategic Partner, and Delivery Partner has roles defined and secondary benefits are coordinated by a lead and two Non-ODA funded specialists in the DIT sector team. This also includes managing a central secondary benefits tracker that tracks and records both commercial (mainly exports) and non-commercial secondary benefits (soft power, R&D, network affects etc.) pipeline opportunities that all parties input into. Achieved wins are then recorded onto the Prosperity Fund Prospero system.
What role has non-ODA spending played in promoting programme objectives?
DIT has two dedicated, non-ODA funded, BHP business secondary benefit relationship managers who have spearheaded outreach to all aspects of the business community;
- BHP also has an allocation of non-ODA funding for events and activities outlined above and engaged in over 15 activities across the eight countries and UK in the last year to enable secondary benefits to be achieved;
- Some examples the activities in the past year have included:
- UK Pavilion at CONAHP 2019 conference Brazil
- Digital Health Mission to Vietnam
- Telemedicine and digital health roundtables in Malaysia and Philippines
- International Health Systems Strengthening workshops with NHS
- Prince Mahidol Award Conference on Universal Health Coverage in Thailand
How has the business community and business environment responded to the programme?
- The business community is seen as international healthcare businesses, UK based healthcare businesses and NHS Arm’s-Length Bodies and NHS Trusts that sell NHS services overseas;
- Businesses have been engaged through various channels to promote the BHP overseas and in the UK. This includes:
  - Regional NHS commercial directors’ networks and engaging private sector business associations, industry groups and multipliers (Association of British HealthTech Industries (ABHI), GAMBICA, UK International Healthcare Management Association (UKIHMA));
  - UK and overseas conferences and roundtables and missions that connect UK suppliers to overseas stakeholders;
  - Articles, DIT newsletters and social media as well as collateral and videos;
  - Webinars to wider UK Sector and overseas partners.
- On the public sector side, there is demand for NHS expertise, but BHP is not presenting the NHS in a box but holding discussions with country governments to identify specific needs. There is therefore a key role of overseas HMG staff making connections with country governments so BHP can respond to needs and requests. DIT already have UK offers in the pillars of the programme and are also developing a Health Systems Strengthening (HSS) UK offer. There are also “ripple effect” countries where non-BHP countries are asking for BHP style interventions that are potential secondary benefits. DIT is managing a balance of what countries want with what the NHS can do;
- On the private sector side, there is demand for UK expertise in digital health and life sciences and there have been multiple activities to connect business to overseas partners. DIT sector team and the SB advisor have used their existing networks and channels to promote specific opportunities of the BHP. All commercial wins on the BHP have come on the private sector side so far. There are also market access opportunities that have been ongoing in the last year;
- As of November 2020, over 120 secondary benefits opportunities have been identified with a rough 50:50 split between commercial and non-commercial opportunities, with a number of these recorded as already realised. Some examples of secondary benefits include: emerging Genomics partnership with Thailand, Health Systems Partnership with Western Cape government and NICE HTA in Brazil;
- COVID-19 has presented opportunities for secondary benefits for commercial and non-commercial partnerships to access wider UK expertise in all eight countries;
- Overseas partner and internal stakeholders all acknowledged the importance and potential opportunity for secondary benefits, particularly longer-term partnerships between UK and overseas. Even with a mature framework and strong pipeline, there are recommendations that could improve the approach.
Recommendations:
1. Delivery Partners outlined their support to help identify secondary benefits and outlined potential areas in their annual reports, however there is still an element of clarity needed around the role of the Delivery Partner (ODA vs Non-ODA) in supporting secondary benefits;
  1. More examples and case studies on non-commercial secondary benefits including soft power;
  2. Clearer separation between what the Strategic Partner and DIT role in this area, especially with DHSC ALB participation;
2. As outlined above, all stakeholders see potential long term partnership opportunities, and the BHP needs to map these out with a clear plan long term plan of delivery and how these reinforce and avoid duplicating wider activities and initiatives in country for a one HMG approach;
3. Scoping opportunities around potential clean growth and climate change secondary benefits as this is a key policy priority for the UK and NHS.

H: MONITORING & EVALUATION
Evidence and evaluation:
An evaluation was planned during early implementation but was postponed because of ODA reprioritisation work. The Evaluation and Learning Team therefore prepared a report to review progress and identify the evidence base for the AR.
- The latest programme Theory of Change (ToC) was developed at the start of implementation together with nested country level ToCs. The country level ToCs are not entirely consistent with each other or with the programme level ToC, e.g. Brazil’s outcomes are more like the outputs at programme level. This in part reflects the different focus for implementation in different countries;
- The impact of COVID-19 on the ToC was assessed and the pathways and assumptions were found to be still valid;
- The programme ToC articulates the connection to SDG3, and language of equity is included in most of the ToCs. The emphasis on the poorest and most excluded in society, while present in the activities, is not explicitly referenced in the ToC;
- During interviews, the ToC was referenced by the project team, the Delivery Partner and the Strategic Partner suggesting that it is used actively to guide activities and set strategic direction. This is particularly valuable in a demand-led programme such as this one to avoid switching to activities that, while viewed as important by stakeholders, weaken contribution to primary purpose. The programme team also recognises that a ToC should be regarded as a ‘living’ document.
Learning:
The programme has a Learning Strategy, which sets out how the global BHP aims to achieve greater impact than eight separate country programmes. It defines the underlying principles and sets out clear roles and responsibilities. For the programme team and Strategic Partner and for the Delivery Partners in the sampled countries this strategic approach is reflected by a culture of learning;
Examples of learning activities include:
- A Technical Working Group (TWG), which provides a cross-programme learning group, which meets monthly. The Community Health Worker programme in Malaysia for example is of interest in several countries and is being discussed in this working group;
- A web platform to share information is being investigated for use by BHP;
- Commissioning a piece of work from the Prosperity Fund’s Knowledge For Development (K4D) Evidence and Learning Initiative (through a FCDO-funded programme drawing on UK based academic networks) to look into the impact of COVID-19 on access to health services for NCDs in the eight BHP countries, in particular to look at the impacts on different societal groups;
- Outputs from the programme that are shared more widely for example the review of evidence on the link between COVID-19 and NCDs prepared in South Africa has been shared with a WHO representative in South Africa.
Monitoring progress throughout the review period:
Each country programme is monitored against a set of well-defined milestones, which enables programme management (see Section D and F);
- In addition, the country programmes have defined annual log frames. At the time of writing this AR none of these log frames were, or had been scheduled to be, completed;
- There is a programme level log frame, which has been improved during the year to include realistic indicators. However, no milestone targets have been set, nor is there a clear process for consolidating country log frames;
- There is a good system for tracking secondary benefits at the country and programme level (see Section G).
MREL Recommendations:
- As a matter of urgency develop a process for reporting consolidated programme level indicators (by Q4 20/21);
- It is suggested that the programme level and country level ToCs are reviewed considering experience from the first year of implementation and to ensure consistency as far as is possible. After that review, it is suggested to check country-level log frames for consistency and completeness;
- Bring the timing of the annual review and the reporting against annual milestones more into synchronicity. Or move the annual review until after most annual milestones have been reported;
- Evidence on social impact of COVID-19 is emerging in countries and there is evidence that this is being considered in design and delivery. This should continue to be monitored and will be an important part of the context for the evaluation.

Annex A – Recommendations

Programme implementation/ delivery of primary benefits:
1. KEY Recommendation: Flexibility & Adaptation needs to continue into next year. A significant part of 2019/20 has been dominated by COVID-19 requiring the programme to rapidly re-purpose, and financial re-forecasting due to impacts of COVID-19 on ODA: Results have been impressive despite these challenges. The ability of FCDO to ‘keep the programme going’ and suppliers to adapt to balance MoH demands with delivery of planned is to be commended and has been welcomed by all stakeholders interviewed. It is hard to predict what will happen next in 2021 in the eight partner countries (specifically in SA, Mexico and Brazil - pathway of the virus, deployment of vaccine, direct and indirect impacts), and changes agreed now may have to be revisited again during the course of next year. DPs and FCDO teams will need to continue to adapt, important to ensure changes that respond to COVID-19 balance the need to respond to urgent needs with focus on outcomes – and where ensuring all interventions offer opportunity to build back stronger systems after COVID-19.
2. KEY Recommendation: Relationships: to be built on by FCDO in global health diplomacy, re-establish regular policy dialogue channels and give greater prominence for SP/NHS ‘brand’ where appropriate: Throughout the year the programme has successfully built partnerships with new actors (govt., civil society), different stakeholders, academia and the private sector, and acted as an enabler on global health diplomacy in many countries where there was no presence. This was particularly important for HMG’s global response to COVID-19 and will be critical to FCDO global health diplomacy going forward, including the Indo Pacific Tilt. Collaborative ways of working have been developed and challenges overcome;
  1. Changes within MoH partners – work to re-establish policy dialogues in Brazil and South Africa;
  2. Inclusion of the Strategic Partner (SP) in the design and scoping phase was extremely positive, opening doors with the Ministries of Health and building government-to-government relationships. During implementation, SP is playing a key role but this ‘NHS brand’ is not always visible. FCDO to agree plans with the DP on how to increase visibility of the SP over the next year, through greater involvement in discussions with government and where needed.
3. KEY Recommendation: Technical Collaboration – achieving the ‘step change’ envisaged in the innovative BHP Model in Year 2. To mitigate the risk of dependency on input and ensure long lasting technical assistance, mutual learning and ultimately transition from aid: BHP envisages an innovative design model with a broad range of technical collaboration methods have been used - delivery of time sensitive pieces of work by consultants,[4] embedded advisers within MoH, support from the SP, twinning and peer- peer arrangements, working with regional bodies (WHO AFRO), south-south collaboration. It is important to focus the TA on facilitating and building capacity, and not substituting for lack of capacity or funding. Some of this is already apparent, but with COVID-19, while the principal of building and transferring capacity was clear, there was also a need/pressure to deliver outputs given scarce technical and human resources to respond.
  [4] 40 technical assistance assignments in 2020, by 73 individuals, issued under 40 contracts.

  1. As the crises subsides, efforts will need to be made to really shift a gear away from transactional towards mentoring and skills transfer, demonstrating the step change in approach in MICs;
  2. Build on programme’s approach and tone has been very much one of collaboration, well received by our partner countries. NHS staff who participate in the BHP as part of CTAS or from one of the NHS organisations are reporting that they are also taking learnings away from these events and sharing them with colleagues in the UK.
2. KEY Recommendation: Impact of FCDO merger has already offered opportunities to align development and foreign policy goals – take this further in 2021. In the next year continue to align this programme with wider ODA health portfolio; share lessons with the global health network, feeding this into the work of the Africa Strategy and Indo Pacific Tilt, and assess the impact of the delivery model for other HSS programmes;
3. The programme has a good system through which lessons are shared, which could be strengthened further in two aspects. Programme team to add elements to the learning strategy to communicate the full range of BHP activities within a country to local stakeholders and to share learnings with FCDO colleagues outside the BHP countries;
4. Moving from national policy to implementation: The programme has worked to support several policy processes – this is necessary, but not sufficient intervention for health system reform. As programmes move further into implementation, the role of regional and local health systems will become more important. Delivery Partner to ensure appropriate level of engagement with regional and local organisations. FCDO and SP to also engage in dialogue at lower levels of government;
5. Some Delivery Partners had identified opportunities to deliver impacts related to climate change as part of the programme. Delivery Partners to carry out a climate change analysis of their programme to identify risks and opportunities, including for secondary benefits.
Commercial:
The model of delivery in SEA of one implementing partner with country subcontractors adds layers of complexity, which has required management time to address problems. Programme team to record lessons on this model and share with other PF programmes for future planning.
There continues to be a strong appetite for NHS expertise and knowledge, and the Strategic Partner is growing ever more adept at drawing in the expertise from across the NHS network, but also in packaging and designing webinars and collaborative events, which are enabling delivery to go forward despite COVID-19.

Secondary benefits:
1. KEY Recommendation: Delivery Partners outlined their support to help identify secondary benefits and outlined potential areas in their annual reports; however there is still an element of clarity needed around the role of the Delivery Partner (ODA vs Non-ODA) in supporting secondary benefits and more information to share. Programme team to provide to delivery partners:
  1. More examples and case studies on non-commercial secondary benefits including soft power.
2. Clearer separation between what the strategic partner and DIT role in this area, especially with DHSC ALB participation. All stakeholders see potential long-term partnership opportunities. Project team (or SB team), needs to map these out with a clear plan long-term plan of delivery and how these reinforce and avoid duplicating wider activities and initiatives in country for a one HMG approach.

Value for Money (VfM) and financial performance:
The economy of the programme has improved this year but could be improved further. Programme team to introduce auditing of the profit caps in the delivery partner contracts and to benchmark unit costs against other programmes.
VfM analysis to be done of programme outputs/outcomes against other partnership programmes.
The programme understands the importance of gender equality and social inclusion and has set the level of ambition as empowerment. While some interventions go beyond this to transformative, the focus is heavily on gender equality and is less clear that appropriate tracking is in place. Programme team to develop a programme level G&I action plan, setting out the vision and milestones for learning and reporting at the programme level. Outcome indicators need to be defined in a way that is more measurable than currently or alternative approaches to demonstrating contribution developed. Programme team and Delivery Partners to include more consideration on wider excluded groups in designing interventions.
Monitoring:
KEY Recommendation: The programme level log frame has been updated during this year to include more realistic indicators, but no milestone targets have been set and there is no clear process for consolidating country log frames. Programme team to develop a process for reporting consolidated programme level indicators and set milestone targets for the indicators.
KEY Recommendation: The timing of this AR was such that no annual log frames updates had been (or had been due to) be completed. Programme team to agree new timing of AR after the log frames are reported.
The programme ToC was updated at the start of implementation and is used actively by project team, Delivery Partners and Strategic Partner. Programme team, Strategic Partner, and Delivery Partners (with the support of EL Team,) review programme level and country level ToCs considering experience from the first year of implementation and to ensure consistency as far as is possible. After that review, it is suggested to check country-level log frames for consistency and completeness.

Annex B – Secondary Benefits Tracker* (*Secondary Benefits Tracker is commercially sensitive and owned by DIT. Provided below is a snapshot of how Secondary Benefits in BHP are tracked):

Annex C Progress against 2019 Recommendations (highlighted where team feels not sufficiently addressed)

RECOMMENDATION: CATEGORY	2019 RECOMMENDATION	BHP ACTION TAKEN
Governance	The programme strategic board has not met since June and should revert to meeting quarterly rather than as and when required.	Completed. Strategic Board held quarterly.
Resourcing	The programme team should consider ways to provide more dedicated staff time to stakeholder coordination efforts and additional MREL expertise.	Dedicated Comms and Stakeholder Manager joined BHP in November 2019. / INTRAC M&EL training – completed by six member’s staff in May 2020. A further two will aim complete before end-2020. / Quarterly Comms Meeting now meets quarterly. / Technical Working Group (TWG) now meets quarterly. / Additional resource from SP on MREL and additional Triangulation meetings arranged (held fortnightly). / DPs – making use of their expertise via TWG, K4D.
	The programme should continue to review whether the countries are receiving the right level of support (PM/Advisory), which is proportionate to the budget allocations by country e.g. to support country teams work to ensure health ministries are fully on board and ready to move into implementation (see Rec. 6).	Audit of in-country governance completed. / New governance structure set-up by PPM specialist. Includes regular reviews of risks at country-level and stakeholder engagement. Issues identified are flagged appropriately. / Tracking status of MOUs across the programme. Five signed and eight to be completed.
Inception	Due in part to the anticipated scope changes, it is critical that the programme ensures that Inception report QA and approval mechanism is exhaustive and robust and feeds into properly updated and approved contracts to ensure a successful implementation.	Completed. Contract Manager oversaw process. HAs, SP, DIT and SRO involved.
	When reviewing the G&I Inception plans it will be important for the programme to understand how the poorest will be targeted and how issues of inequity, gender, age, disability will be addressed.	Included in the process at point 4. Social Development Advisers involved in the process. The next AR will be an opportunity to review this. G&I resource is often difficult to obtain – internally this area is under-resourced.
Implementation – year 2	Approaching the planned end of Inception, it appears that health ministries are not all fully on board and ready to move into implementation. The programme team should carefully review this situation, working closely with Post and the Health Adviser network.	See recommendation no. 3. / Despite impact of COVID-19, engagement with stakeholders has continued and remains impressive. / ODA review does, however, put this at risk.
	Roles and responsibilities of the various stakeholders of the BHP require strong ongoing definition and coordination, with dedicated staff time to this.	Comprehensive RACI exercise completed.
	Once the planned activities and outputs are known, it will be important for the BHP to do a ‘light check’ whether the interventions planned meet the original basis for the strategic and economic cases, to ensure that investments planned are still likely to add value and generate the higher level results anticipated.	ToC review completed by EL partners. Review conducted of log frames and that they still fitted ToC. Improved ToC by clarifying assumptions and timelines and indicators. / AR 2020 – BHP request review team to check if further changes should be made, particularly considering COVID-19.
VfM and Financial Performance	There is a need for the BHP to review the BHP 2019/20 and 2020/21 financial forecasts and adjust these in line with the implementation delays and remaining delivery timeline.	Completed. New forecasts. Clear process for updates and KPIs to incentivise DPs.
	The BHP team to track and benchmark key DP costs including admin costs, consultancy fees and other key cost drivers.	Information collected by BHP e.g. costs breakdowns. Work plans are scrutinised for fair charges and plans are efficient. / Suppliers chosen via competitive process. / Contractual profit-cap included, and DPs are required to self-audit.
	The BHP team to closely review the Inception reports to minimise the risk of effectiveness being affected by scope creep.	Completed as part of Inception process. / Key part of process described in Point 4. / Will be part of future planning exercise (Yr3). / Alignment between log frames and ToC as part of review (Point 8).
	During the planned revision to the ToC and Log frames following Inception, the BHP team should ensure that the log frame still aligns with programme objectives and that appropriate and robust milestones and indicators are in place to provide measurement of successful delivery.	See point 8.
	The BHP programme team should closely monitor contract delivery and ensure it remains in line with desired outputs and the programme’s Primary Purpose and Secondary Benefits.	Contract Management Plan in-place. Re-negotiated governance mechanisms and were agreed via contract variation. / DIT created Secondary Benefits Tracker.
	BHP team to plan specific actions, with monitoring and timelines, on how buy-in reluctance will be unblocked in relevant partner countries.	See Point 2. / Questions from MoH in Brazil successfully resolved to allow Implementation to start in April 2020.
	BHP to implement recommendations of G&I Scorecard assessment and ensure that DPs support these deliverables and have that role clearly defined in their contracts – see Equity	G&I Plans provided by DPs as part of Inception (part of contract). / Social Development Adviser review as part of QA process.
	Progress on G&I to be added as an agenda item at Programme Management Committees and Strategic Board to provide greater focus.	DPs report (monthly) on process against G&I but only discussed by exception.
	It is crucial that mitigating actions (as identified and any additional) to the key risks are clearly identified by the BHP team, with clear ownership and timeframes.	All risk reporting includes mitigating actions and owners. Regularly updated.
	The FCDO BHP team should conduct regular checks of a sample of delivery partner invoices each year against individual receipts.	DPs required to self-audit (annually). FCDO retains right to conduct full audit at any time. BHP follows FCDO commercial guidance on requirement for this (part of commercial framework contract).
Commercial	BHP team should closely monitor contract delivery and ensure it remains in line with desired outputs and the programme’s Primary Purpose and Secondary Benefits	See point 13.
	BHP team and Post Has to pay particular attention to the different approach required to manage the SEA DP i.e. one size does not fit all – the DP should be encouraged to be flexible in their approaches in each of the five countries.	In progress. Plans to recruit a regional co-ordinator to enable this flexibility. / DPs have a country plan, not a regional plan. Regional plans are overviews. / HAs consulted on crosscutting deliverables.
Monitoring & Evaluation	Any changes to the LFs need to be dated and approved at the Strategic Board level.	LFs signed-off as part of Inception Report. / ToC updates also signed-off by SRO and JFU Deputy Head.
	The final BHP LFs (at programme and country levels) should include baselines, milestones and targets and link how risks are managed to ensure primary and secondary benefit realisation. This should also be set out in DP contract specifications.	Completed. Risks are managed separately but are reviewed regularly. / Completed. Set out in contracts.
	All data sources need to be identified including timelines and who is responsible.	Completed. / Country level – DPs are responsible. Global level – SPs are responsible**.
	The LF needs to include indicators to measure progress on secondary benefits, on gender and inclusion, and VfM.	Completed – indicators will provide performance data on G&I. / VfM Plans required from DPs as part of contract. Not included in log frame.
	The ToC (at programme and country levels) will require updating following the Inception phase. The links between outputs, intermediate outcomes and outcomes needs to be clearer and a realignment will be necessary for the implementation phase.	See Point 21.

Annex D Summary of Interviews

Monday	23-Nov-20	09:30 - 10:30	External stakeholders	Philippines
Monday	23-Nov-20	12:30 - 13:30	Brazil Govt. Partners	Brazil
Tuesday	24-Nov-20	11:00 - 12:00	SRO + Portfolio Lead	UK Programme Team
Tuesday	24-Nov-20	12:00 - 13:00	South Africa Govt. Partners	South Africa
Wednesday	25-Nov-20	08:30 - 09:30	Health Advisers (SEA)	Health Advisers
Wednesday	25-Nov-20	08:30 - 10:00	Philippines Govt. Partners (separate interview per city)	Philippines
Wednesday	25-Nov-20	09:30 - 10:30	South Africa Govt. Partners	South Africa
Wednesday	25-Nov-20	12:00 - 13:00	External stakeholders	Brazil
Wednesday	25-Nov-20	13:00 - 14:30	BHP Programme Team	UK Programme Team
Thursday	26-Nov-20	08:00 - 09:00	FCDO Team (Philippines)	Philippines
Thursday	26-Nov-20	08:00 - 09:00	FCDO Team (South Africa)	South Africa
Thursday	26-Nov-20	09:00 - 10:00	DIT Team	UK Programme Team
Thursday	26-Nov-20	09:00 - 10:00	Philippines Govt. Partners (separate interview per city)	Philippines
Thursday	26-Nov-20	11:00 - 12:00	Mott Macdonald	Delivery Partners
Thursday	26-Nov-20	12:00 - 13:30	Brazil Govt. Partners	Brazil
Thursday	26-Nov-20	15:00 - 16:00	Strategic Partner Team	UK Programme Team
Friday	27-Nov-20	08:00 - 09:00	PwC	Delivery Partners
Friday	27-Nov-20	11:00-12:00	MREL
Friday	27-Nov-20	13:00 - 14:00	FCDO Team (Brazil)	Brazil
Friday	27-Nov-20	16:00-17:00	McKinsey	Delivery Partners
Tuesday	1-Dec-20	09:00 - 10:00	South Africa External Stakeholders	South Africa
Tuesday	1-Dec-20	14:00 - 15:00	Health Advisers (Mexico / SA / Brazil)	Health Advisers

ANNEX E: HIGH LEVEL RISK REGISTER (NOVEMBER 2020)

	Risk Description	Risk Mitigations
1	The ability to deliver within the timelines.	The programme has mitigated this risk well in light of the impact of Covid-19. DPs have been able to demonstrate meaningful delivery progress despite the challenges of working remotely, movement restrictions and having limited access to key stakeholders. Health Advisors and DPs report separately to the Programme Team every month on their delivery progress and risks. DPs, supported by the Strategic Partner and Health Advisers, were asked in late-March 2021 to adapt the programme to the new Covid-19 context while remaining within programme scope. This mitigates delays and also ensures that the BHP remains relevant to changing health priorities. DPs have already had 14 ideas for adaptation of interventions approved by SRO (June 2020). However, the risk remains in place because the nature of Covid-19 means that it could still generate unforeseen challenges.
2	The impact of reductions to ODA and demonstrating strong relevance to global health objectives, including Indo-Pacific Tilt, VfM and impact on poverty.	The programme’s reduced budgets for this financial year have now been confirmed and while the impact varies across regions, at the global level the programme has secured sufficient budget to continue. This is largely a result of demonstrating the programme’s continued relevance to the UK’s priorities globally and in the countries and regions where it operates. To ensure the programme was able to effectively plan and agree the extent of Year 2 activities in FY21/22, all teams were kept informed of the potential for reductions and Minimum Viable Plans were drafted by Delivery Partners to reduce time to respond once new allocations were understood.
3	BHP smooth transition to the new FCDO structure.	BHP was confirmed as transitioning to Global Health Directorate with the team confident that BHP associated programmes and activity will continue to be a priority (particularly interest in MICs and global health security). / Introductory meetings were held at an early stage with GHD senior leadership and the team brought-in to team meetings and at key workshops to ensure their smooth transition. The upcoming Spending Review will provide an important opportunity for the BHP to further consolidate its plans within the new FCDO’s global health portfolio.
4	Ensuring learning and better understanding on the link between outputs and outcomes and what is really working.	Year 2 planning has allowed a review of Theories of Change (ToC) and log frames as part of a requirement to sense-check continued relevance between outputs and outcomes, and to ensure consistency and completeness. / The programme recognises that further work is needed but this was delayed due to the IR. Following the budget changes, revisions are currently being finalised to all of the country level ToC and log frames and subsequently to the global level ToC and log frame. The programme continues with its Learning Technical Working Group to share best practice and learnings across the countries. The programme also commissioned a review by K4D into the impact of COVID 19 on NCD services in its partner countries, which has been shared widely with programme stakeholders and will inform further programme interventions.
5	The inherent difficulty in defining metrics and evaluating the success of technical collaboration.	In the last period of the programme pragmatic reporting is what is required whilst avoiding anything radically different or new – most likely BHP will remove and readjust metrics. Subsequent Annual Reviews will need to take into account any adaptation resulting from budget changes over FY20/21 and FY21/22 period. / Usually, BHP may have been expecting some emerging results and this may still be the case, however we have agreed with our MREL Adviser that the last period should focus more on qualitative – case study type evidence e.g. Mexico example which will be tailored to meet the needs of both Post and Government in country and provide a good test case of what may be possible and desirable to apply in other BHP countries.
6	Demonstrating quantitative impact and giving more attention to the process of inputting quality data to the log frames.	At the time of the Annual Review, there was limited data available for the log frames. This was expected due to the long-term nature of some of the metrics chosen to measure system change, and was mitigated by use of supplementary qualitative reporting. For the next annual review, significantly more quantitative data is expected to be available. Prospero ceased to operate from 31 March 2021. Programme will therefore use the spreadsheets used to export data to Prospero (which was not fit for purpose for the programme). / MREL team are looking at consolidation but no substantive changes at present and more reliance on country log frames to demonstrate outcomes rather than programme-level which was always difficult to demonstrate.
7	Some reputational risks have materialised including reception of UK response to COVID-19 and use of NHS resources outside of the UK.	BHP has not attracted any significant negative attention to date despite the impact of the ODA reductions and despite the role of the NHS. We have clear defensive lines if required explaining how reductions were made in line with the Foreign Secretary’s strategic priorities and how the NHS is fully remunerated for its role in BHP and derives significant benefits itself. Comms strategy is in place (including robust rebuttal lines, which are cleared and co-ordinated with Dept. of Health) and material is released as part of wider FCDO transparency commitment. Programme vets / agrees programme comms and looks for opportunities to promote positive impact of the programme. / Minister is kept updated on any risks associated with programme that may be made public. All NHS activity on the BHP will be funded entirely from the programme, and no frontline health workers will be distracted from their domestic responsibilities. We anticipate benefits to the NHS service in the UK because of the programme.
8	In country, operational and contextual risks include political shifts and subsequent changes in the Ministries of Health in each of the partner countries require a re-establishment of relationships and buy-in in several countries.	COVID-19 still of significant impact and particularly in some partner countries. This type of re-engagement will need to be paused until their resources allow time away from COVID-19 responses. Nonetheless, a number of new MoUs were signed in the last year with various country stakeholders demonstrating their continued engagement despite the pressures of COVID-19. / Significant engagement and demonstration of good relations has taken place during re-planning of BHP activity because of ODA reductions to allocations and resulting reduction to programming. Country partners have been well involved in much of the re-planning work. / NHS – the NHS consortium ‘offer’ work is ongoing with engagement from FCDO. Programme continues to build relationships with planning ongoing for NHS to build-upon the relationships BHP / results in future.
9	Risk of increasing capability needs of staffing to achieve results in wider health diplomacy link-up at Post, which was not envisioned at start of the programme.	Recognised. However, in the new environment of limited funding BHP unlikely to be able to increase capability / capacity due to limited funding. Strategic Workforce Planning commission will shortly be received and will be discussed to get to a decision on the viability of increased capability.