## Annual Review Template

Title: Better Health Programme
Programme Value £79.3m now expected to be max. £38m		Review date: November 2021
Programme Code: GB-GOV-50-PF-20-BHP	start date: August 2018 (OBC approval)	end date: September 2022

Summary of Programme Performance
Year	19/20	20/21	21/22	22/23
Overall Output Score	A	A	B
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://www.gov.uk/government/publications/better-health-programme
DevTracker Link to results framework:	Not yet published

A. SUMMARY AND OVERVIEW

Description of programme

The Global Better Health Programme (BHP) is a three-year programme, which aims to improve health outcomes, and thereby contribute to economic growth and poverty reduction, in eight partner Middle-Income Countries (MIC) (Brazil, Mexico, South Africa, Malaysia, Myanmar, Philippines, Thailand and Vietnam). The programme aims to improve health outcomes by working to strengthen country health systems with a primary focus on non-communicable diseases (NCDs) and improving quality of care, while also capturing secondary benefits by creating opportunities for international and UK businesses and the NHS.

BHP has a unique, multi-partner, delivery model consisting of:
- Commercial contracts with four key Implementation Partners who work with FCDO to implement a programme of health system strengthening interventions in eight countries;
- A Memorandum of Understanding (MoU) with the NHS Consortium for Global Health (representing a wide range of NHS technical arms lengths bodies[1]) as Strategic Partner (SP) to provide peer-to-peer health systems technical support to partner governments and provide strategic technical advice to the FCDO during BHP implementation;.
- Programme-funded Health Advisers (HAs) in each of the BHP countries supporting programme implementation, government relationships and dialogue;
- Collaboration between the Foreign, Commonwealth and Development Office (FCDO) and Department for International Trade (DIT) to maximise secondary benefits through the creation of opportunities through the Official Development Assistance (ODA) programme and additional non-ODA funding. Non-ODA funding for the programme is not covered in the scope of this Annual Review (AR).

Originally designed as a 3-year £79.3million programme, following the 2021 ODA cuts the total budget was cut to £36million (see note on this at the end of this section). This necessitated the cutting of some activities, closure of the Mexico programme and the reduced scope of others which has impacted scoring the programme’s effectiveness via the log frame. For example:
- Three projects in Brazil (remote diagnostics, digital primary care, Health Technology Appraisal methodology) were cancelled, three (Doctors Across Brazil, Dissemination of Health Data, National Clinical Research Network review) were wound down early and support to the Hospital das Clinicas’ Digital Health strategy was reduced;
- All projects in Mexico have been closed and wound-down early;
- In Thailand, work on social marketing was reduced and two other pieces of work delayed.
- In Malaysia, the successful pilot of a community-based digital health project to reduce obesity and prevent NCDs was not scaled up to another 10 districts as planned.

At the same time as these cuts, as part of the wider merger of the FCO and DFID, the overall management of the BHP moved from the Prosperity Fund to the new Global Health and C19 Directorate, with management of the South Africa portfolio moving across to the British High Commission. Following the February 2021 coup, activities in Myanmar were also then closed in November 2021 in light of ongoing operational and safeguarding risks. As such this AR assesses the BHP against a backdrop of significant change.

This AR reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets which remain under review. As a result, the findings of this AR reflect on a programme in transition and highlight the need to update the results framework to better assess true impact at end-2022.

Summary supporting narrative for the overall score in this review

This is the first year that this former Prosperity Fund (PF) Programme is being assessed using this standard FCDO Annual Review Template and presents some reporting challenges particularly given log frame weaknesses (that we recommend are urgently addressed following this review). While it is clear that the programme is delivering a breadth of health systems strengthening interventions across its footprint, the narrow focus of the log frame indicators and impact of the budget cuts on some activities means that overall the programme has scored a ‘B’ (Outputs moderately did not meet expectations).

An external evaluation, published in April 2021, and subsequent reporting including this review, point to some strong implementation progress and effective programme pivot in spite of significant changes in context – namely the impacts of both the Covid-19 pandemic and cuts to the programme (see section above) - but notes that it remains too soon to comment on progress towards the desired outcomes. Overall likely contribution to the desired primary outcomes is likely to be lower than anticipated given the cuts to the programme. At the output level where possible to assess quantitative progress against narrowly log frame indicator targets performance has largely been positive across two of the three output areas, with wider programme reporting pointing to particularly strong delivery in the areas of digital health and healthcare worker training. E.g. the Doctors Across Brazil programme which manages federal primary care programmes and attract and retain primary care healthcare professionals. The programme has enabled remote communities to access primary care without travelling long distances – communities reached are sometimes 12 hours travel from the nearest medical facility. Long-term, it has potential to become the largest programme providing primary care doctors in the world.

The programme has also secured significant commercial and non-commercial “secondary” benefits. The programmes performance on secondary benefits was also assessed favourably in the external evaluation. Over this reporting period, over 25 non-commercial opportunities have been tracked across the eight original BHP countries and five commercial wins at a value of £190 million attributed by DIT, including through its non-ODA component (not covered by this review). BHP has achieved an overall 13 commercial wins at a value of £393m.

Overall, an External Evaluation held in April 2021 concluded that the programme continues to score ‘good’ on Value for Money (VfM) with a strong approach to procurement and cost controls, governance and programme and risk management. Indications are that, with strong foundational relationships in place, in many cases a shift from in-person to virtual trainings and meetings may have driven improved VfM both through cost savings associated with travel and significantly increased intervention reach and coverage. The impact of the shift to online delivery on the quality of coverage is however not clear and needs further analysis.

Major lessons and recommendations for the year ahead

Lessons:

- Importance of BHP Health Advisers: BHP Health Advisers (HAs) in-country are central not only for effective oversight of project implementation and establishing UK-host country training and peer learning fora with the SP in country but to wider stakeholder and national health policy influencing as well. Without in-country BHP HAs the SP draw-down mechanism would not work. Lesson: Any successor to BHP will require the same / similar level of dedicated staff resource with credible health backgrounds where possible.
- Access to NHS expertise and brand: Access to wider NHS expertise through the NHSC consortium has resulted in significant knowledge-sharing and learning exchanges between the UK and BHP partner countries, not possible without access to over 195 subject matter specialists through the SP. The NHS brand clearly holds much high level political and technical currency across the country network, helping to strengthen not only technical HSS and NCD delivery but UK health sector influencing capabilities.
- Sharing an innovative model of health programming: Much of BHP’s work is new or innovative within FCDO for example working in middle income countries, around non-communicable diseases, quality of care, digital health, and trade and prosperity amongst other areas.
- Collaboration across HMG on secondary benefits: Any successor programme should also take account of lessons learned through the BHPs experience e.g. provision of non-ODA funding to support secondary benefits realisation, bringing in external specialists and HAs at Post.

Recommendations to be progressed over final 9 months of delivery:
Retention of Country-based HA: As noted above, the HAs play a critical role in connecting all elements of the BHP programme together and building links between the SP and host governments. It is critical these posts are retained until the end of the programme.
- Update the Log frame: –Indicators currently only capture a small proportion of the work delivered and end of programme milestones should be updated to take account of earlier programme cuts well before the Project Completion Report. The log frame should be reviewed and updated in lines with changes to the programme. Action: SP Monitoring and Evaluation (M&E) Officer to lead with implementation partner leads and FCDO. Before end April 2022.
- Wider reporting: - Country Implementation Partners and the SP should include a clear assessment of their contribution to the overall results pathway – with an emphasis on translation of output level results to outcome level impact and assessment against the log frame – as part of the Project Closure Report (PCR). Action: Implementation Partners & SP. End of programme.
- Transition Planning - Implementation Partners and HAs at post should ensure there are clear transition plans in place to pass key projects and activities on to host government partners for continued delivery beyond the end of the programme. Efforts should focus on those activities most likely to have sustained impact on NCD prevention and treatment strategies and delivery at greatest scale. FCDO HAs should work with host governments and implementing partners to attempt to secure continued external financing if required
Action: Implementation Partners to develop transition plans by end May 2022. HAs to lead any resource mobilisation efforts required.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The overarching global Theory of Change (ToC) (shown below) illustrates the pathways through which activities delivered in, originally, eight countries are expected to lead to the delivery of three outputs which, in turn, are expected to contribute to increased coverage and utilisation of effective support and services for NCD prevention, treatment, management and improved equitable access to safe and quality healthcare. Alongside the primary impact goal of reduced premature mortality from NCDs, as a legacy Prosperity Fund Programme, BHP seeks to garner secondary commercial and non-commercial benefits for the UK through the relationships forged through the programme.

Theory of Change:

Both this AR and the April 2021 external Evaluation suggest that the ToC remains valid, though there is a need – following this review – to tighten the pathway between programme outputs and the desired outcomes as far as possible, including a re-assessment of the overall level of ambition given budget cuts.

The associated results framework (in the form of the global log frame used to conduct this review and the nested country level ones that sit behind it) also requires a significant overhaul given (again) the need to review ambition in light of the cuts and, most critically, ongoing challenges aggregating country level results to the global level and ensuring indicators truly represent the breadth of activity contributing to each output area. This is a priority for the programme team.

Recommendations:

Immediate: The over-arching log frame be substantially reviewed and amended following this AR. Action: Expertise in Better Delivery Department, the strategic partner and in Human Development department should be mobilised and involved in revising the log frame by end-April 2022.

Immediate: There needs to be a greater focus on using both the country and the global log frames to monitor and manage the programmes performance, including through current contract management arrangements. Action: PRO, Contract Manager and SP M&E Adviser to review progress against milestones each quarter with Implementation Partners and HAs, flagging where expected progress has not been made. Until end of programme.

Immediate: When the log frame is revised, a separate output should be included for both secondary benefits with separate commercial and non-commercial indicators and milestones set for the remaining life of the programme and for the contribution to the programme by the SP. Action: SP, DIT and Health Sector Adviser to draft and have approvals via PRO and SB for new indicators and milestones by end-April 2022.

Immediate: Assess what is the most valuable route to providing wider NHS expertise through the SP. Action: FCDO programme team with SP to develop a Concept Note outlining the SP ‘offer’ and how Posts would potentially draw-down on the expertise.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is moderately off-track to contribute to the expected outcomes and impact. This is in part a result of overly ambitious outcome and impact statements and in part a result of cuts to planned programme activities as a result of significant budget reductions. Cuts to activities have for example meant that some pilot projects have not been rolled out at scale and other initiatives not implemented reducing the programmes’ ability to instrument systems change and health outcomes at the macro level. Progress towards outcomes and impact have also proved hard to assess given weaknesses in the higher levels of the theory of change.

That all said, BHP programme activities are of a generally high standard, well aligned with and responding to country priorities, and are valued by partner governments and health institutions. This review’s assessment is that they are supporting meaningful progress towards the two outcomes of better services for NCD prevention, treatment and management and improved equitable access to safe and quality healthcare and that the relationships built through BHP have led to significant UK influence within and beyond the health sector. Progress on outcomes and impact on secondary benefits is easier to quantify and the programme appears to be performing strongly (but are largely beyond the scope of this review).

Recommendation: The overall level of ambition, including expected outcomes and impact, should be reviewed as part of the suggested log frame review.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

This review’s assessment is that there is sufficient and compelling evidence of delivery, value for money, and wider benefits (commercial and non-commercial / diplomatic and the recognition[2] that tackling NCDs can reduce health costs and increase prosperity) to justify the programme continuing. Any further cuts (possible as part of the ongoing business planning process) would undermine progress delivered to date and threaten both the ability of ongoing activities to have a sustained impact on health systems delivery and wider host government – British Embassy / High Commission relationships developed through BHP. Further, given the exit costs involved in early termination of implementation partner contracts the cost-savings associated with any early closures are likely to be limited.
[2] 13/12/2021 WHO Press Release ‘Investing 1 dollar per person per year could save 7 million lives in low and middle income countries.

There continues to be recognition from stakeholders, HAs and other stakeholders of the value of the SP to the work of the BHP, particularly the ability of the SP to reach expertise across the Arm’s Length Bodies (ALBs) (see Annex B for comprehensive list of ALBs) and into the UK NHS. The SPs work reviewing deliverables and providing technical expertise is valued, but needs to be more contextualised to local settings. The SP appears to also provide an important function in ensuring the quality of in-country delivery partner programming, alongside the in-country health advisers.

## C. DETAILED OUTPUT SCORING

While this review qualitatively assesses BHP to be performing well, weaknesses in the programme log frame mean that output performance must be judged against an artificially narrow set of indicators and missing milestones. As such it should be noted that individual output scores do not necessarily reflect overall performance and should be read alongside the supporting, wider output narrative.

Output Title	Increased use of digital technology and improved integration and utilisation of health information and data to inform practice and tackle the burden of NCDs and improve quality of care.
Output number:		1	Output Score:	B
Impact weighting (%):		33% (all three outputs weighted equally)	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (2021)	End line target (September 2021)	Progress
1.1 Evidence of NCD data available via digital health information systems, used to improve practice in NCDs	NA	30	Off-track: 11 / (Brazil = 6 / Thailand = 1 / Vietnam = 1 / Malaysia = 1 / Philippines = 1)
1.2 Evidence of health workers accessing digital learning mechanisms, used to improve QoC practice in NCDs	NA	Evidenced in 6 projects	On-track: 5 / (Brazil = 2 / Malaysia = 1 / Mexico = 2)

Briefly describe the output’s activities, and provide supporting narrative for the score.

The programme supported a wide range of different activities in five of the seven BHP countries (Brazil, Malaysia, Philippines, Vietnam and South Africa) to support the use of digital technology and health information and data. Interventions included, for example the development of a downloadable app (called ‘MicroGuide’) and associated training materials to improve primary healthcare workers’ use of clinical guidelines for diagnosis and treatment of diabetes and hypertension in Mexico; the establishment of an e-journal to support health workers’ continuous professional development in Thailand; support on electronic medical records and support to the development of a digital transformation roadmap in Vietnam; and, in Brazil, support to the national health data network, support to the development of the digital health strategy at the country’s leading hospital, and support to the development of an innovative Digital Primary Care Service Model offering primary care teleconsultations to understaffed remote health outposts.

As no annual milestones were set against the two core indicators for this year performance is assessed against progress to achieving the end-line milestones for September 2022. Here we see that while the programme is delivering a huge range of projects already leading to increased use of digital technology, BHP is on track to achieve the original ambition set for one indicator (1.2) but off-track in the case of the other (1.1).

Positive examples included the Brazil teleconsultations project and the ‘Let’s Get Moving’ (MyJomSihat) app pilot in Malaysia, providing training awareness on NCDs and improving outcomes. In Brazil, the proof of concept started in September 2021 in a remote Amazon community (12 hours from nearest doctor) and early results showing 143 patients served and with 88% satisfaction and 94% of consultations resulting in no need for further in-person consultation and the Brazilian Ministry of Health expressing interest in funding a larger pilot programme in 2022 covering a larger number of municipalities. In Malaysia, ‘MyJomSihat’ pilot app was delivered largely virtually due to ODA budget reductions. However, this generated significant increase in enthusiasm at the local level with younger, more technologically-savvy, ‘influencers’ adopting the app and promoting it to the younger generation.

While the indicators both show positive progress this year the programme is unlikely to meet the end of programme milestones as currently set based on the programme’s original £79m budget. This is particularly the case for indicator 1.1. Cuts affecting this output include for example, two projects in Brazil on remote diagnostics and digital primary care being cancelled before commencing and the closure of the project supporting the national health data network; in Mexico cutting support to the implementation of the MicroGuide platform and ceasing development of a Knowledge & Transformation Health Hub platform for medical practitioner.

Given that the programme will not meet its eventual end milestones this output is scored a ‘B’ - outputs moderately did not meet expectations. However these milestones will need to be revised down in response to budget cuts.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Overall, as identified in the April 2021 External Evaluation, the programme continues to score “good” on VfM overall with a strong approach to procurement and cost controls, governance, programme and risk management.  The emphasis on building digital systems in this output area represents particularly good VfM noting that the tools developed will have sustained long-term impact through continued use beyond the end of the programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Changes to programme activities as a result of budget cuts are set out in section A. Particular changes relevant to this output were the scaling back of the MicroGuide rollout in Mexico and the cancelling of the second phase in Malaysia extending rollout of the pilot to a further ten districts. The end of programme output targets will need revising down accordingly. The programme team, health advisers and delivery partners should also work with the Mexico and Malaysian governments to support rollout of the MicroGuide in Mexico and support further Malaysian interventions on NCDs learning from the pilot, in both cases to ensure return on investment and sustained impact.

Recommendation: the indicators for this output should be reviewed and new milestones set for the last year of the programme; follow up on MicroGuide rollout in Mexico and learning from NCD pilot in Malaysia

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the 2020 AR and prioritised action taken against these have been included at Annex A.

Output Title	Capability building through education and training, knowledge exchange, strategy and policy development/implementation to tackle the burden of NCDs and improve quality of care
Output number:		2	Output Score:	B
Impact weighting (%):		33%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (2021)	Progress
2.1 # of health workers accessing training (including Continuing Professional Development) interventions on national NCD standards for prevention, treatment and management	275	Significantly exceeded: 2341 / (Brazil = 700 / Thailand = 1364 / Vietnam = 76 / Malaysia = 75 / Mexico = 126)
2.2 # of countries with operational guidance (action plans, protocols and guidelines) to tackle NCDs, working to improve quality of implementation at national, regional, local levels.	9	Significantly underachieved:3 / (Brazil = 2 / Vietnam = 1)
2.3 Feedback obtained on service quality, used to inform policy, strategy, clinical and quality standards	Indicator based solely on proposed activity in South Africa (contracted and reviewed separately) so excluded from consideration

Briefly describe the output’s activities, and provide supporting narrative for the score.

The programme supported a range of different activities under this output in six of the BHP countries (Malaysia, Mexico, Myanmar, Philippines, Thailand and Vietnam). Interventions were highly varied and tailored to the country contexts. Health workforce education and training included, for example, the development and delivery of a nursing diploma in Mexico, the training of community health volunteers in Malaysia, and support to continued professional development on NCDs to healthcare workers in Thailand. Activities around policy and strategy development and implementation included, for example, support on hospital accreditation on incident reporting and on front of package labelling in Thailand; in the Philippines support on operational planning for two city authorities, and in Mexico support to a local municipality area on the planning and implementation of obesity prevention strategies.

Performance against this output was mixed. Activities related to education and training have performed relatively positively. In addition, these areas were relatively less affected than others by the reductions to programme budgets. As such for indicator 2.1 the milestone was significantly exceeded, driven in large part by higher-than-expected numbers in Brazil and Thailand. Over-achievement in Thailand particularly, though this was also a factor for other countries, was by driven by a shift from in-person to virtual training which allowed for a substantial increase in the numbers participating. We have not been able to assess whether the move to more virtual training will have reduced the training’s impact; this would merit further investigation ahead of the PCR

Performance on policy and strategy development and implementation has been less strong (Indicator 2.2). In some cases, this is reflecting reductions in programme budgets and cuts to activities e.g. in Mexico by not moving to implementation of the municipality obesity prevention strategy but instead ending the intervention at handing over the proposed approach. Elsewhere, this has reflected slower than expected progress, such as for front of package labelling and social marketing work in Thailand. However, in other areas work has progressed very positively and looks like it will have significant longer term outcomes, for example the work on hospital accreditation in Thailand.

Based on the above we have assessed this output at a ‘B’ – outputs moderately did not meet expectations.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Refer to Output 1.

Noting that the shift to virtual working had a disproportionate impact on this output area, this shift allowed over fivefold increases in the numbers of Health Care Wworkers (HCWs) accessing training in some cases (e.g. Malaysia) and driving significant efficiency savings. What is less clear at this time is whether the shift in how training was delivered influenced its effectiveness.

Recommendation: Implementation Partners to explore the impact of the shift to virtual delivery not only on the numbers of HCWs reached by the quality and impact of training delivered, sharing lessons for future delivery.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Changes to activities are set out in section A.

Recommendation: the indicators for this output should be reviewed and new milestones set for the last year of the programme by end-April 2022.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

See Annex A on previous recommendations.

Output Title	Life sciences research and development and health technology assessment capability to tackle the burden of NCDs and improve quality of care
Output number:		3	Output Score:	A
Impact weighting (%):		33%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (2021)	End line target (September 2021)	Progress
3.1 Number of new NCD findings and articles published (linked to BHP) in quality peer reviewed journals	5	10	Significantly exceeded: 10 / (Thailand = 3 / Malaysia = 7)
3.2 # of new NCD related Health Technology Assessments (HTA) initiated and/or completed to inform policy, standards, guidelines and priority setting	0	1	Unlikely to be achieved.

Briefly describe the output’s activities, and provide supporting narrative for the score.

This output covers activities in five of the BHP countries: Malaysia, Brazil, Philippines, Thailand and South Africa. Activities include, for example, the generation and publication of research findings from the piloting of community approaches to reducing obesity and NCD prevention in Malaysia, in Brazil a Health Technology Appraisal Methodology Review and support to developing the country’s clinical research and genomics capacity, in Thailand support to develop the country’s capacity in genomics, and in the Philippines support to training health workers around Health Technology Assessments (HTA). Progress was positive across most of these activities, in particular on the Malaysia pilot. The ODA reductions however led to the Brazil HTA and National Clinic Research network projects being closed.

The two indicators do not reflect the breadth of activity under this output – the first is primarily based on work in one BHP country (Malaysia) and there is no milestone for indicator 3.2 for 2021 and an end target of one. The performance against the indicators does therefore not necessarily reflect well overall performance of activities under this output.

Indicator 3.1 saw the milestone exceeded. This was due to a higher than expected number of articles published from the Malaysia pilot[1] and three published manuscripts on health professional education published for Thailand. Three further Malaysia articles are in prospect, two submitted to journals and a third waiting on FCDO review before submission, and - assuming published - will see the programme exceed the target milestone by the last year.
[1] The seven Malaysia papers include a paper for the journal Implementation Science Communications (7 Oct 2020), four papers for the Asia-Oceania Conference & Malaysian Association for the Study of Obesity Scientific Conference (6 – 8 April 2021), a paper for the Global Digital Health Forum (6 – 8 December 2021) and an article published on RTIs Insight blog (2nd September 2021).

Indicator 3.2: the closure of the projects in Brazil mean that this indicator will not be achieved by the end of the programme.

Based on the above, given 3.1 was exceeded and indicator 3.2 is an end-line target and is no longer relevant, this output is assessed as an A – met.

Recommendation: The recommended update to the log frame should consider moving to a new set of indicators that better reflect the activities under this output or alternatively reducing the weighting of this output relative to the first two outputs.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

See Output 1 commentary on VfM. An effective approach to stakeholder engagement through virtual means has meant that delivery has been innovatively delivered in most cases rather than stopped completely. However, Implementation Partners acknowledged that whilst in some areas virtual engagement, e.g. via social media, has increased opportunities for inclusiveness, there have been trade-offs as a result of this and virtual engagement is not as effective as in-person (for certain activities).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Changes to programme activities are covered in section A. Of particular relevance to this output was the decision for the programme in Brazil to cut back work streams to develop capacity to conduct health technology assessments and research capacity.

Recommendation: the indicators for this output should be reviewed and new milestones set for the last year of the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

See Annex A on previous recommendations.

D: RISK

Overview of risk management

The overall risk rating for the programme is Moderate. Reflecting the limited change in the operating environment, there remain significant M&E risks (explored in depth in Section C), delivery risks as a result of ODA reductions (reduction in programme activity required to fall within reduced allocation and realignment of activity and continued uncertainty going into the final year of the programme), and operational risks already realised as a result of staffing gaps and potential reductions as a result of Strategic Workforce Planning.

The programme regularly reviews and monitors risks through e.g. fortnightly review of top risks and issues and review of country-level risks and issues at monthly Programme Delivery Boards (membership: HAs, SP and DIT) and quarterly review at the quarterly Programme Strategic Board. A central risk register is maintained and updated on a monthly basis to track risks across the programme and owners and action owners assigned to mitigate and monitor.

Risk Summary table: December 2021

Risk / Issue Description	Pre-mitigation RAYG	Mitigation Actions	Current Impact RAYG
RISK: Uncertainty of continuation of the health adviser resource due to funding pressures, meaning the programme has no resources (funding or staff) to continue the delivery of BHP primary benefits, but also risks reputational damage. Additionally, funding may reduce for the SP impacting Posts / HAs ability to draw-down on their expertise.	R	Majority of Posts have confirmed that programme-funded Country Based Staff (CBS) will be funded to end-March 2022, however funding beyond this point cannot be confirmed after business planning. BHP team plugged-in to budget discussions to ensure justification for continued resourcing is recognised. BHP team engaged with GHD Health Strategies Team and will input particularly into e.g. themes of prosperity, MICs, NCDs and the NHS partnership. Initial Concept Note has been drafted and is going through peer review within HDD before being sent to Director. Early indications from Post indicate health programme funding available but work needs to be done to ensure BHP isn’t duplicating work of other xDFID programmes / SEA planned bilateral work. SP is centrally-funded and requires approx. £500k for FY22/23 to continue providing expertise.	R
ISSUE: The BHP has a number of administrative challenges associated with its move to GHD in relation to financial management processes which is causing delays to PO approvals and paying Implementation Partners.	A	BHP London Team have communicated with key finance managers within GHD and monthly meetings with GHD finance lead are being held. A workaround is in-place re. payments and the programme continues to be able to pay SP / Implementation Partners, however they are having to manage expectations on time taken to provide PO nos. etc. Head of Dept. has confirmed they are content to be part of BHP purchasing hierarchy. Work progressing to get this set up with GTPC. This will be a longer-term solution than first expected as new ERP rollout to FCDO has been delayed to Autumn 2022.	A
RISK: Uncertainty around where funding for exit costs will come from. Potential for confusion over who is responsible for paying exit costs I.e. central GHD or Post. This could delay decision making.	R	The BHP delivery contracts and SP are centrally-managed and centrally-funded, but since the 2021 ODA reductions the delivery contracts and local programme managers are now funded at the regional/country level. There is a risk that the country/regional budget holders will expect those exit costs to be met by GHD as the contract holders – particularly as this is how exit costs were treated in FY21/22 for centrally-managed programmes in the Prosperity Fund Dept. such as BHP.	R

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Implementation Partner Performance

The BHP contractual set-up is challenging with four Implementation Partners implementing programme activities and performance varying across them and different milestone arrangements and payment schedules. Despite this complexity, the direct relationships between Implementation Partners, HAs, FCDO Programme Team and SP remains effective with all highlighting the value of their respective expertise. Monthly reports of what has been achieved and progress against Milestones are shared with their work reviewed by HAs, and the Contract Manager in London with input from the Strategic Partner where required. The HAs manage the bulk of the relationship management with each being positive about the progress made over the past 12 months and highlighting a willingness to work together to realise the impact of the programme outputs.

Where issues in performance have been identified, they have been dealt with well and consistently using contract management systems to manage improvements i.e. against KPI Framework. This was put into practice in 2021 when one Implementation Partner’s performance was cause for concern when financial performance, reporting and monitoring was found to be inconsistent with contractual agreements. A cross-team approach was employed to work through issues, which included engagement from the SP, Implementation Partner, FCDO teams (BHP teams at Post and in UK and Commercial) and a lessons learned exercise held, moderated by the former PF Evaluation Partner (Integrity Global), to acknowledge the difficulties and learn from them to move forward and agree new parameters for their performance. Whilst the programme in Mexico was subsequently unable to secure sufficient ODA funding to complete the programme there, a small allocation was made to allow the programme to close responsibly by November 2021 as a result of the progress made in agreeing new reporting parameters with the Implementation Partner. ToRs for final audit of the Implementation Partners work there have been agreed and a collaborative approach taken to programme closure. This allowed the Implementation Partner to finish key deliverables that had already been started and allow work to be handed to our in-country partners, so allowing BHP to maximise the benefit from the investment made so far in terms of health outcomes and the UK’s relationship with the health authorities there.

BHP contracts continue to be managed by Key Performance Indicators (KPIs) Framework and Payment by Results (PbR) mechanisms to maintain high quality delivery. KPIs applicable within each contract include (but are not limited to):

- KPI Measure: budget variance – monthly (monthly forecasting versus actual spend: 10% target variance or less)
- KPI Measure: M&E (report on milestone progress to Authority within Quarterly Report submitted 2 days prior to agree date for review)
- KPI Measure: Client Relationship Management (# of formal written complaints received by Authority from beneficiaries (external stakeholders) and/or Programme Team)

The PbR mechanism in-place is part of a framework that all BHP Implementation Partners have agreed, describing the KPIs against which the Implementation Partners will be measured by and equates to a fixed monthly charge ‘at risk’ of 10%, which will be the total maximum deduction. Each Implementation Partner completes a monthly performance measurement return, highlighting actual performance against KPIs in the ‘Performance Monitoring Report’. This allows for a greater degree of scrutiny and has allowed the programme team to monitor against and any slips in performance can be identified at an early stage and remedial action taken with the Implementation Partner. It has however made overall assessment against log frame milestones more challenging with Implementation Partner reporting focussing on KPI delivery rather than wider performance against the overarching theory of change. It will be critical for final reports to pivot to focus more on overall performance and country/partner-level contributions towards the achievement of overall BHP health-related indicators.

VfM

Specific VfM metrics were not developed (in common with other legacy PF programmes) in line with the programme log frame. To assess VfM the review had to judge whether delivery of outputs met expectations and places the programme on/off track according to the ToC.

Economy: Due to the bespoke nature of BHP interventions, which makes direct comparisons difficult to measure, direct benchmarking of costs was carried out against technical and commercial criteria only (including fee rates). However, the contract tendering process did provide cost comparison from the detail in the bids received prior to implementation. Some ad hoc benchmarking activities have taken place e.g. any additional consultancy costs are required to be approved by HAs, FCDO programme team and commercial colleagues to benchmark against commercial consultancy costs. The programme did remove the bulk of spending on consultancy and programme enabling costs (c£400k) from FY 20/21, as a result of reducing dependency on outside consultants and, due to the unplanned inability to host large-scale functions.

Profit caps on Implementing Partners are also contractually agreed. Implementation Partners have absorbed some staffing gaps by increasing responsibilities of staff already in country to allow developmental opportunities but also avoid cost increases. The value of HAs contribution to the programme far outweighs their remuneration, particularly when reviewing their contribution over the last 12 months when liaising for Post with their MoH counterparts on Covid-19 evacuations and in-country action plans.

Efficiency: Virtual and remote working during the continuing Covid-19 pandemic have proven to be a relatively effective means of delivery, meaning the programme’s delivery has broadly remained on-track where activities were able to shift to a virtual medium. As a result of the reduction in ODA allocations, Implementation Partners were invited to submit their ‘Minimum Viable Programme’ plans which allowed for the team, SP and Implementation Partners to review together and agree where the work streams for each country would continue to meet certain criteria i.e. stakeholder engagement / delivery confidence / VfM. This allowed for an informed planning process to understand where most impact could be felt and where savings could be made e.g. to the SEA Implementation Partner regional oversight role / administrative costs. The closure of the Myanmar programme in November 2021 has allowed Implementation Partners in South East Asia to explore reallocation the programme’s funding there via a ‘Minor Additional Distribution’ (MAD) process to support specific, cross-country work in the region that can be delivered by end FY2021/22.

The model of the programme has had to allow for adaptations in delivery which has realised savings as the world has shifted to virtual working during the Covid-19 pandemic which forced a shift away from in-person travel and events and a greater reliance on virtual interactions, generating significant operational cost savings. Implementation Partners have had to be agile and adaptive to respond to the changing priorities in-country and continued shifts to e.g. vaccine deployments / continued lockdowns.

Effectiveness: Whilst results are now being reported and delivery remains mostly on-track, particularly against country log frames, it is harder to assess what the BHP expects to achieve within the life of the programme as stated above, because the outcomes cannot be expected to be realised in the medium term and only likely to be achieved within a 10-year timeframe.

There are a significant number of qualitative results to support the effectiveness of outcomes e.g. stakeholder engagement, despite a global pandemic when many stakeholders have been drawn-into their own Covid-19 responses. Qualitative benefits include the 25 non-commercial ‘wins’ reported and includes strengthening the UK relationship with beneficiary countries from events such as the Vietnam’s e-Health National Conference for which the UK shared experiences at. BHP has also seen significant success generating secondary benefits this year, continuing to identify and deliver both commercial and non-commercial benefits which are progressed and tracked by DIT colleagues. These include R&D, Soft Power, Frugal Innovation and Network Effects.

Equity: BHP meets the former Prosperity Fund’s minimum standards on Gender Equality and Social Inclusion (GESI) across all six scorecard dimensions. All Implementation Partners have a GESI Action Plan which has been reviewed extensively by the former Prosperity Fund Gender and Social Inclusion Adviser. Implementation Partners have G&I Advisers embedded within their programme management teams. BHP Brazil has demonstrated significant progress towards equity where using remote / virtual medical appointments has meant those in remote areas have been able to access doctors easily. In the Philippines, Community Health Workers have moved virtually and using social media has allowed greater ‘download’ of their products by communities in remote areas and widened the age-range of those accessing the products.
#### Quality of financial management:
The programme has extensive financial management processes in place to set budgets, track expenditure, invoices and forecasts. The information provided by delivery partners is reasonably consistent and provides an appropriate level of detail to allow the programme to manage its finances effectively: Via monthly progress meetings with delivery partners, the programme team has been able to monitor their spend against forecast and raise questions / areas of concern

	FY 20/21 Actuals	FY 21/22 Budget	FY 21/22 Actuals + Forecast	FY22/23 Outline forecast to end-Programme
Programme Enabling Activity (incl. administrative costs)	£942,893	£400,000	£51,000	-
Delivery Phase	£18,401,994	£7,300,000	£6,851,001	£3,150,000
Strategic Partner	£745,742	£1,500,000	£689,133	£650,000
GRAND TOTAL	£20,090,628	£9,200,000	£7,591,134	£3,800,000

*FY20/21 BHP Budget was reduced from £25 million to £17.5 million as a result of ODA reduction exercise and Spending Review in FY20/21. FY20/21 Actuals are reflective of spend against the reduced budget. The overspend was able to be absorbed by the wider Prosperity Fund Department budget as other programmes, not able to pivot to Covid-19 related activity or more innovative delivery, had underspent. It should be noted that financial management has, had to respond to uncertainty. Other challenges have included the centralisation of e.g. salary and platform costs which would make up a significant proportion of Programme Enabling Activity spend during previous FYs. Continued inability to travel has also reduced spend in this area in FY21/22.

The FY21/22 budget sources are:

Budget source	Value
BHP central exit budget	£1,800,000
GHD central allocation	£1,500,000
Brazil allocation	£1,000,000
South East Asia allocation	£4,900,000
TOTAL	£9,200,000

Date of last narrative financial report	30 November 2021	Date of last audited annual statement	31/3/2021

Annex A

Recommendations from Annual Review 2020

During interview, the programme team agreed that progress on a number of the recommendations made below has not been as extensive as needed, due to disruptions and challenges of the past 12 months. The review recommends that the team take this opportunity to reset and reprioritise, particularly where recurring recommendations are highlighted, for the final year of delivery. Where recommendations are no longer relevant or no longer feasible to action due to increased demands on a much-reduced programme team, the PRO and SRO should consider whether to progress.

RECOMMENDATION: CATEGORY	RECOMMENDATION	BHP ACTION OWNERS AND PROGRESS
Programme Governance / Delivery	Flexibility and adaptation to continue to next year. A signification part of 2019/20 has been dominated by CV-19 requiring the programme to adapt activities and re-forecast financials due to impacts of CV-19 on ODA.	Continuing process. Programme has again adapted to reduction in funding and closure of programme activity in two countries (Mexico & Myanmar) and worked with Delivery Partners to agree focus in countries where outcomes and benefits will be demonstrable.
	Relationships to be built on by FCDO in global health diplomacy, re-establish regular policy dialogue channels with new partners / governments as the CV-19 crisis subsides and give greater prominence to SP and NHS ‘brand’ where appropriate.	Ongoing. Since move to GHD in July 2021 the team are engaging with a wider audience of health-focussed teams. Opportunities to showcase BHP with new Director / DG have been taken. Worked with DIT to produce a BHP ‘brochure’ to further showcase the achievements of BHP – this is being shared widely across health industry.
	BHP team to build on wide range of Technical Collaboration methods to achieve the ‘step change’ envisaged in the innovative design model for BHP model and mitigate the risk of dependency on inputs and ensure long-lasting technical assistance, mutual learning and ultimately transition from aid.	Technical Working Group formed in September 2019.
	Impact of FCDO merger has already offered opportunities to align development and foreign policy goals – take this further in 2021.	Dependent upon outcome of the next SR and BHPs move to a new Directorate where Health is focus. Opportunities being investigated beyond programme-end with the wider team and to what extent learnings / activities from BHP can be continued.
Secondary Benefits	Implementation Partners outlined their support to help identify secondary benefits and outlined potential areas in their annual reports, however there is still an element of clarity needed around the role of the delivery partner (ODA vs Non-ODA) in supporting secondary benefits and more information to share	DIT to lead. / BHP have agreement for further support for a Health Sector Specialist to explore and identify secondary benefits that have arisen (on-boarding in progress). This specialist will work closely with Implementation Partners to provide clarity and support.
Monitoring & Evaluation	Programme team to develop a process for reporting consolidated programme level indicators and set milestone targets for the indicators.	Milestone targets within the programme log frame have not been set to standard and will need to be progressed in tandem with recommendations from this AR.
	Programme team to agree new timing of annual review to align with reporting against log frames.	Indicative timeline agreed for 2021 AR which should allow for this. Next reports (annual) due from Implementation Partners in November 2021. / Review of log frame not possible within PrOF guidelines before AR.
	Programme team, strategic partner, and delivery partners (with the support of E&L) review programme level and country level ToCs considering experience from the first year of implementation and to ensure consistency as far as is possible. After that review, it is suggested to check country-level log frames for consistency and completeness.	Dependent upon further reductions and changes to the programme. Team are currently looking at what changes are required and working with GHD team and NHS Consortium to agree next steps. / Focus was on programme scaling down. In final year of delivery focus now needs to be on M&E and update of log frame, rather than ToC which remains valid.
GESI	The programme would benefit from developing a programme level GESI action plan which clearly sets out the vision and sets milestones for learning and reporting at the programme level.	GESI Adviser closely involved in GESI plans provided by each Implementation Partner which are revised each year.
	Ensure the equitable distribution of benefits, define how the indicators in the Log frame will be measured in the lifetime of the programme, including disaggregation of data by equity dimensions. Ensure equity sufficiently reflected in the ToC.	Will need to be reviewed with any changes to log frame.
Secondary Benefits and Sustainability	Implementation Partners outlined their support to help identify secondary benefits and outlined potential areas in their annual reports, however there is still an element of clarity needed around the role of the delivery partner (ODA vs Non-ODA) in supporting secondary benefits / More examples and case studies on non-commercial secondary benefits including soft power / Clearer separation between what the strategic partner and DIT role in this area, especially with DHSC ALB participation	See previous point on Secondary Benefits. (Duplicate)
	Scoping opportunities around potential clean growth and climate change secondary benefits as this is a key policy priority for the UK and NHS. Implementation Partner should also carry out climate change analysis of their programmes to identify risks and opportunities.	Will need input from climate adviser to progress. Not available when team part of Prosperity Fund so not progressed whilst team were dealing with day-to-day programme activities. / Will look to understand what support is available within GHD to advise programme team and Implementation Partners.
Learning	Programme team to add elements to the learning strategy to communicate the full range of BHP activities within a country to local stakeholders and to share learnings with FCDO colleagues outside the BHP countries.	This would need to be done via Health Advisers who have the local stakeholder engagement. To be revisited now that TWG is back up-and-running (November 2021).
Stakeholder Engagement	Delivery partner to ensure appropriate level of engagement with regional and local organisations. FCDO and SP to also engage in dialogue at lower levels of government.	Engagement with local govt. is carried out by Implementation Partner and Health Advisers and/or Post not central programme team where it is difficult to see what value could be added.
Commercial	Programme team to record lessons on this model and share with other PF programmes for future planning.	Noted – to be progressed with Commercial Team contacts.
VfM	Programme team to introduce auditing of the profit caps in the delivery partner contracts and to benchmark unit costs against other programmes.	Programme team, with commercial team, have introduced e.g. auditing of Implementation Partner in Mexico at programme closure in-line with FCDO guidance. Similar model of auditing to be considered for DPs in November 2022 and programme closure.
	VfM analysis to be done of programme outputs/outcomes against other partnership programmes.

Annex B: LIST OF ACRONYMS
ALB – Arm’s Length Bodies / (NHS England & Improvement / Health Education England / / Public Health England / NHS Digital / Care Quality Commission / National Institute for Health & Care Excellence / NHS Resolution / Genomics England / Office for National Statistics)	MMed – Master of Medicine
AR – Annual Review	MCh – Master of Surgery
BHP – Better Health Programme	MOU – Memorandum of Understanding
CBS – Country Based Staff	MoH – Ministry of Health
CHV – Community Health Volunteer	MoPH – Ministry of Public Health
CHW – Community Health Worker	M&E – Monitoring and Evaluation
CONAPH – Congresso Nacional de Hospitais Privados	NCD – Non Communicable Disease
CPD – Continuing Professional Development	NHSE – NHS England
DFID – Dept. for International Development	NHSI – NHS Improvement
DG – Director General	NRLS – National Reporting & Learning System
DHSC – Dept. of Health & Social Care	NSHC – National School of Healthcare Science
DIT – Dept. for International Trade	ODA – Official Development Assistance
	PbR – Payment by Results
ERP – Enterprise Resource Planning	PF – Prosperity Fund
FCDO – Foreign, Commonwealth & Development Office	PHE – Public Health England
FCO – Foreign & Commonwealth Office	PwC – PricewaterhouseCooper
FoPL – Front of Pack Labelling	PRO – Programme Responsible Officer
G&I – Gender & Inclusion	PrOF – Programme Operating Framework
GESI – Gender, Equality & Social Inclusion	SDA – Social Development Adviser
GDP – Gross Domestic Product	SP – Strategic Partner
GHD – Global Health Directorate	SB – Strategic Board
GNI – Gross National Income	SEA – South East Asia
HA – Health Adviser	SWP – Strategic Workforce Plan
HAI – (Thai) Healthcare Accreditation Institute	ToC – Theory of Change
HEE – Health Education England	TWG – Technical Working Group
HEO – Higher Executive Officer	VfM – Value for Money
KPI – Key Performance Indicator
MAD – Minor Additional Distribution
MIC – Middle Income Country