Prosperity Fund Programme Completion Review

Title: Global Trade Programme (GTP)
Final Programme Spend £ (full life): £49.65m	Review Date:	March 2022
Programme Code: GB-GOV-3-PF-TRA	Start Date: / April 2017	End Date: / December 2021

Summary of Programme Performance

Year	2019	2020	2021 (PCR)
Programme Score	A	C	B
Residual Risk Exposure Rating	Moderate	Major/Severe	Major

Link to Business Case (and any addendum):	GTP Full Business Case
DevTracker Links to all logframes used during programme lifetime:	Logframe not uploaded to Devtracker

## A. Summary and Overview

Description of the programme

The Global Trade Programme (GTP) was a Prosperity Fund programme, originally designed to be up to £150 million over four years, providing technical assistance and other support to Official Development Assistance (ODA) eligible countries to identify and address non-tariff barriers (NTBs) to trade, open their markets, and increase capability to trade with the rest of the world.

The GTP had two primary objectives which were intended to boost equitable economic growth and reduce poverty: 1) to enable partner countries to identify and remove non-tariff barriers (NTBs); and
2) to create the conditions for increased international trade in support of the UK Government’s objectives. The programme also aimed to deliver secondary benefits by increasing market access for international business, including from the UK, as well as by building bilateral partnerships on trade related issues with key emerging markets in support of the UK trade strategy.

The programme employed a mix of global and country-specific research, analysis and implementation to tackle a set of non-tariff barriers, specifically on improved use of international standards; better regulatory practice; improved intellectual property rights systems; streamlined customs and wider trade facilitation measures. It also supported the transition and implementation of UK Economic Partnership Agreements (EPAs). This was a complex programme with a mix of components and sub-components detailed in the following section.

The programme was severely affected both by the pandemic, and by subsequent reductions to the UK’s ODA budget. In 2020, due to budget reductions, difficult decisions were taken to halt, cancel, delay or scale down activities. In 2021, after the UK moved to a target of spending 0.5% of GNI as ODA, business planning decisions which re-prioritised ODA spending plans led to the early closure of the GTP.

At the time of programme closure in December 2021, approximately one third of the original budget was spent. Several intervention programmes were in the design phase, or ready to move to procurement, but as a result of ODA reductions, never moved to implementation. Others had significantly reduced budgets and/or closed early. Three programme activities continue as discrete programmes under new governance arrangements.

Given these substantive changes, the programme did not implement the portfolio of interventions to the scale anticipated at its inception. Despite those challenges, continuing programme activities performed well against revised project level logframes, delivering positive results. Overall, the GTP has therefore scored a B (Outputs moderately did not meet expectation) at the PCR stage, reflecting results achieved by ongoing interventions, but also the inability of the programme to deliver at its original anticipated scale.

Results are described in more detail in future sections of this review, but include discrete achievements in select countries towards:
- Bolstering improved regulatory practice;
- Supporting the adoption of international standards;
- Analysis and interventions to streamline customs procedures to increase efficiencies, and reduce time and costs to businesses;
- Strengthening national intellectual property rights (IPRs) institutions and systems (Brazil);
- Providing support for implementation of new UK Economic Partnership Agreements (EPAs); and
- Adoption of partner governments recommendations generated by the GTP’s Research strand.

Overview

The GTP was originally designed as a 4 year programme (2017-21) but was subsequently extended to 2023 to allow additional time for delivery. This was a complex programme with three main delivery components:

A demand-driven Flexible Fund facility to support innovative delivery projects to tackle specific NTBs. These included country level interventions managed by an external Service Manager (EY) and two projects managed centrally by HMG, and delivered by multilateral agencies (food standards by DEFRA and the Food Standards Agency – FSA; World Bank for Mexico Better Regulations). Original Budget £55m;

Trade Facilitation in Middle Income Countries (TFMICs) – a programme implemented by the World Bank and World Customs Organisation in five MICs (Brazil, India, Philippines, Nigeria and South Africa) to help improve trade facilitation systems and institutions. Original Budget £25m;

UK Trade Promotion (UKTP) – a programme initially managed by DFID, and then FCDO[1] , and implemented by the International Trade Centre (ITC). This programme delivered technical assistance and capacity building in countries party to Economic Partnership Agreements (EPAs) - trade agreements between African, Caribbean and Pacific (ACP) countries and the UK, transitioning from EPAs with the EU.  Original Budget £20m.
[1] FCO and DFID merged on 2 September 2020 and the Foreign, Commonwealth and Development Office (FCDO) was created. GTP continued to be managed by FCDO Prosperity Fund staff until end March 2021, with the UKTP component led and managed separately by the Trade Directorate. From April 2021, GTP and UKTP were both managed by FCDO’s Trade Directorate.

In addition to the £100m allocated to interventions listed above, a further £50m was allocated to: research and analysis (£20m); scoping and design (£20m) and management costs (£10m).

The GTP originally had been designed to support ODA eligible Middle Income Countries (MICs) and regions, including Brazil, China, Colombia, India, Indonesia, Mexico, Nigeria, Southern Africa, Turkey, and Vietnam (and South East Asia). The country focus extended to include some Least Developed Countries (LDCs) and LMICs, under the Trade Forward Southern Africa programme and when UKTP was added to the portfolio in FY18/19[2]. Ultimately, no GTP activity occurred in China.
[2] TFSA countries include Southern Africa Customs Union countries (Botswana, Lesotho, Namibia, South Africa and Swaziland) and Mozambique. Countries currently covered by UKTP ODA support include Antigua and Barbuda, Belize, Cameroon, Comoros, Cote d’Ivoire, Dominica, Dominican Republic, Fiji, Ghana, Grenada, Guyana, Jamaica, Madagascar, Mauritius, Papua New Guinea, Saint Lucia, St. Vincent & Grenadines, Suriname, Zimbabwe.

The GTP was a FCO (and subsequently FCDO)-led programme that was supported by other government departments including BEIS, DEFRA, DFID, DIT, and HMRC who contributed to programme governance and helped to deliver some of its interventions. Non-ministerial departments (Food Standards Agency) and other agencies (Intellectual Property Office) were also critical in supporting delivery of components of the programme.

An external ‘Service Manager’ was procured to assist in the design and development of the programme, particularly the ‘Flexible Fund’, and in overall programme management. Initially, while commercial procurement was underway for the Service Manager, 4 pilot programmes were initiated by FCO staff at select posts: i) Brazil Intellectual Property; ii) Mexico Better Regulations; iii) Brazil Regulations; and iv) South Africa trade programming consisting of two subcomponents - Trade Forward Southern Africa (TFSA), and support to the Southern Africa Customs Union (SACU) Secretariat’s Customs Modernisation Programme (CMP).

EY were appointed as an externally contracted Service Manager in April 2019. The Service Manager was responsible for the inception phase (April to December 2019), research and analysis, design and management of the Flexible Fund portfolio, and programme and financial management of the overall programme. A ‘design and build’ approach was applied to the Flexible Fund, developing programmes from concept through to implementation. This initially involved production of nine country plans exploring potential interventions to tackle NTBs, some of which were subsequently developed into New Project Concepts (NPCs). Approved NPCs were then developed into more detailed Business Cases before procurement of delivery partners for each intervention. Twenty-two projects were originally planned under the Flexible Fund, with twenty of these developed by the Service Manager, in partnership with FCDO and country partners.

Other GTP programming included the (Flexible Fund) CODEX Food Standards programme, jointly delivered by DEFRA and the Food Standards Agency (FSA), initiated in FY 18/19. The Trade Facilitation in Middle Income Countries (TFMICs) programme began in FY 19/20.

In spring 2020, Covid greatly affected GTP delivery and programmes made significant changes in order to pivot to alternative approaches including on-line training. GTP programmes also supported partner countries in their response to the pandemic, particularly in the streamlining of customs and trade procedures which helped move personal protective equipment (PPE) and vaccines (see section B).

Impacts of ODA budget cuts and reprioritisation:
The seismic impact of the pandemic on the UK economy forced the UK government to take tough but necessary decisions, and as announced in 2020, the UK has now moved to a target of spending 0.5% of GNI as Official Development Assistance (ODA) in 2021. Following a thorough review, the FCDO’s programme budget was allocated in accordance with UK strategic priorities against a challenging financial climate of Covid.

Throughout the business planning process, the FCDO strived to ensure that every penny of the ODA spend brought maximum strategic coherence, impact and value for taxpayers’ money. In 2021, the FCDO focused on core HMG priorities for poverty reduction, including getting more girls into school, providing urgent humanitarian support to those who need it most, and tackling global threats like climate change, Covid recovery and other international health priorities. Following the move to 0.5%, this programme has been closed earlier than planned. This Programme Completion Review reflects that the programme has had limited time to deliver planned results, as well as reflecting the progress and achievements that have been possible. Where objectives have not been completed this does not necessarily reflect on the quality of programme design or delivery.

The UK remains a world leader in international development, not only through the impact of these financial allocations but also through the creation of the FCDO, integrating diplomacy and development to deliver greater impact. We will return to our commitment to spend 0.7% of gross national income on ODA when the fiscal situation allows.

Due to ODA reprioritisation in 2020 to respond to the pandemic, the GTP budget of live programmes was reduced by £9m, and new procurements to deliver pipeline projects were either paused or cancelled. This included six planned Flexible Fund interventions (£17.4m in total) where Business Cases had been developed. The expectation was to revisit its paused interventions once new budget decisions were made for FY21/22.

In Spring 2021, due to ODA reductions to 0.5% GNI as outlined above, and ensuing business planning decisions for ODA reprioritisation, the UK government then took the difficult decision to close early some live components: TFMICs, Mexico Better Regulations, and Brazil Intellectual Property, and cancel Flexible Fund interventions in Brazil, Indonesia, Nigeria and Turkey. Scaled back activities at reduced budgets continued on the UK Trade Partnerships (UKTP), Trade Forward Southern Africa (TFSA), and the Vietnam National Trade Repository (VNTR) under new governance structures. In addition, a separate programme on trade facilitation (the HMRC-UNCTAD-WCO Capacity Building for Trade Facilitation) took on additional activities to reach some countries previously participating in TFMICs. The contract with the Service Manager also closed early in June 21, with programme management and technical support for closing and continuing activities transferring to the FCDO.

Table 1 below outlines the full list of GTP planned activities to tackle selected NTBs and the stage of implementation reached. A total of seven programmes reached implementation stage: five sub-projects under the Flexible Fund (of which three were over overseen by the Service Manager), TFMICs, and UKTP. The red lines in Table 1 below indicate the timing of the two budget re-prioritisation exercises with a view to showing the impact that this had on the overall portfolio. Seventeen country-level projects planned under the Flexible Fund did not proceed beyond the Scoping, New Project Concept, Business Case stage or procurement stage.

Table 1 – GTP Initial Planned Portfolio of Programmes

A decision was taken at the GTP Programme Board in October 21 that the programme should close as an entity in December 21, with continuing components operating as independent programmes. The GTP worked closely with delivery partners, to adjust contracts and to revisit sustainability arrangements, which helped to minimise the challenges and risks resulting from early closure.

As such, the primary projects or programmes under GTP that are considered in the review on results include:
- Flexible Fund activities:
  - Brazil Intellectual Property – closed early, reduced budget;
  - Mexico Better Regulations – closed early, reduced budget;
  - Trade Forward South Africa – ongoing, transferred to management by BHC Johannesburg and proceeding as a discrete programme;
  - Vietnam National Trade Repository – ongoing as discrete programme, ends July 22;
  - CODEX Food Standards – ended as planned in 2021; no funding for any future phase
- TFMICs – closed early, reduced budget;
- UKTP – ongoing, proceeds as discrete programme with a reduced budget; ends March 23; and
- additional results emerging from the research and analysis strand and country programme design.

Achievements

All of the GTP interventions that moved into the implementation stage have registered positive initial results and have delivered in line with revised individual project logframe targets despite the operational environment changing over time. Evidence confirms that interventions were a good strategic fit to meet the needs and priorities of partner countries. Gender and Inclusion (G&I) has been embedded into programmes, and collaborative work with programme beneficiaries supports sustainability of interventions. Although the longer-term impact of discrete project interventions still needs to be determined, foundations are in place to enable them to succeed. In some cases, interventions were also able to support wider UK trade interests. For example, the implementation of the Vietnam National Trade Repository also supports Vietnam’s trade engagement in ASEAN, of which the UK now is a dialogue partner.

Examples of results from the Flexible Fund programmes include:

Brazil Intellectual Property (IP) supported the Brazilian Patent & Trademark Office (INPI) to deliver improvements to the quality of the country’s Intellectual Property (IP) Rights process. INPI climbed 20 positions in the latest IP Office Innovation Ranking undertaken by the World Trademark Review (to 6 out of 60 offices around the world), and up a total of 35 positions from 41 since activity started in 2018. The programme was implemented by Palladium, with support from UK IPO.

Vietnam National Trade Repository (VNTR) is a free to access online information platform providing access to trade regulations and information that businesses need to import and export to and from Vietnam. It is becoming an essential tool to supporting Vietnam to meet its ASEAN trade commitments. Launched on 30 March 2022, the programme was delivered by Nathan Associates, in close collaboration with the Vietnamese Ministry of Industry & Trade (MOIT), Business Chamber of Commerce, women-led businesses and FCDO staff at post and in the UK.

Trade Programming Southern Africa – Trade Forward Southern Africa provided free and easy access to the latest information and tools for businesses in SACU+M (Southern Africa Customs Union + Mozambique) to competitively grow their exports and markets. Over 4,000 users per month accessed the TFSA Trade & Information Hub by February 2021. The SACU Customs Modernisation Programme (CMP) contributed to 135 African firms being accredited as preferred traders; a status provided to firms with substantial import/export transactions, and which have a level of confidence about their operations (including tax administration) by the Customs Dept. The accreditation scheme is reducing the experience of delays and costs at the border for SACU member countries (Botswana, Eswatini, Lesotho, Namibia and South Africa).

CODEX: Managed by DEFRA and FSA, support to the CODEX Trust Fund contributed to building capacity in 44 developing countries to enable their participation in the international food standards setting process. GTP’s funding supported 34 projects (30 individual projects and 4 group projects) to deliver training on CODEX standards, technical assistance on national requirements for food safety, development of national protocols, capacity building on phytosanitary measures, and assistance on key expert committees.

Mexico Better Regulations: This World Bank implemented programme designed, developed and began implementation of SINAGER, Mexico’s National System of Regulatory Governance, developing three of four tools accessible on a national and government-wide platform. SINAGER is targeting reform and uptake at national, state and municipality levels.

Other Components:

The UK Trade Partnerships (UKTP) programme, implemented by the ITC, supported technical assistance and capacity building activities in target EPA countries in Africa, Caribbean and Pacific (ACP), including development and use of market access tools and digital transformation. UKTP support has led to development of 12,955 jobs, including over 7,330 women and additional direct annual sales to the UK and the EU of over US$20m (including over US$7.56m for women business enterprises). Over 1,560 participants have been reached through training and awareness raising initiatives, trade data updates and embedding of market access tools; 30 business support organisations coached; and over 1,110 MSMEs reached, at least 280 of which are women business enterprises, and 298 have provided evidence of adoption of new practices.

Trade Facilitation in Middle Income Countries (TFMICs) implemented by the World Bank (WB) and World Customs Organisation (WCO), despite closing early, has supported partner countries - Brazil, India, Philippines, Nigeria and South Africa - to implement more efficient and coordinated border management processes. This has been critical in response to Covid. In the Philippines, it supported the Bureau of Customs to increase digitalization, effectively streamlining the processing of import and export transactions essential for business continuity. It also created a One-Stop Shop involving the Anti-Red Tape Authority, the Bureau of Customs and the Food and Drug Administration to help accelerate the import of Covid critical commodities such as Personal Protective Equipment (PPE) and other emergency medical devices. In South Africa, an increase in automation enabled the South Africa Revenue Service (SARS) to reduce face-to-face contact by transitioning to virtually managed controls (cameras, virtual meetings and self-certification).

Research activities: Twelve Service Manager-led research projects supported planned interventions in countries including Indonesia, Vietnam, Turkey and Nigeria, with a particular focus on Gender & Inclusion (3 projects). In Nigeria, the government adopted trade facilitation research recommendations: (i) a truck electronic call-up system to reduce traffic congestion; (ii) review of the 25 year Ports Master Plan, which aims to reduce traffic congestions at ports and; (iii) to reinstate a National Single Window committee (adopted in June 2021). The Nigerian government drew on a GTP aggregation and growth study to develop an SME aggregation model, and took forward recommendations to conduct analysis to identify export value chains of interest to key European markets and to develop an e-commerce platform to enable Nigerian SMEs to showcase their products to the regional and global market. ASEAN research exploring the feasibility and impact of creating an ASEAN regional digital trade facilitation system produced a roadmap for digital connectivity, to be delivered by the private sector. This project was included in the joint statement on UK-ASEAN economic dialogue and supported UK application to become an ASEAN dialogue partner.

Lessons learned and evidence generated

Despite the programme closing early and operating at a much reduced scale, the design and implementation yielded a number of lessons around trade interventions, and programme design and delivery:

Trade interventions

The experience of Covid helped provide momentum for some countries to adopt new technologies and tackle customs barriers. Digitisation of customs and movement to single trade windows can have significant impacts on reducing time, and thereby costs, of trade. In the Philippines, for example, the introduction of streamlining and automation resulted in a 43% reduction in import times (from 10 days 19 hours to 6 days 3 hours) as evidenced in the TFMICS led October 2020 Time Release Study. In South Africa and the Philippines, support to implement WCO Immediate Release Guidelines for air cargo helped expedite the swift distribution of Covid vaccines.

Phased and adaptive tools for regulatory reform can support uptake at different levels of government where capacity varies. The Mexico Better Regulations project adapted design to have stand-alone modules to enable national government, states and municipalities which have a wide variation of capacity to gradually incorporate tools depending on capability. Regulatory reform at the municipal level has impact: in the municipality of Queretaro, a reduction of 55 percent time and administrative procedures businesses face when dealing with the municipal government represented a reduction of the municipality’s regulatory burden of around $300 million after implementing one of the SINAGER platform’s tools.

An inclusive process of developing national trade tools (such as a national trade repository) may strengthen use and uptake. In Vietnam, the project developed a bespoke NTR, building on best practice but further adapting and developing to respond to and meet needs and interests from business and government stakeholders. This has helped build shared ownership and interest in the product, and is strengthening adoption and (it is hoped) sustainability of the product.

Strong attention to gender and inclusion in programme and review objectives helped generate data and analysis on constraints facing women owned businesses and traders; design and develop interventions to tackle, or at minimum take into account, differences between women, men and diverse groups; and strengthen institutional capability. TFMICs studies to generate data on constraints facing women owned businesses and traders in Brazil, South Africa and the Philippines highlighted lack of access to finance, formal business networks, and market information; lack of information about rights, trade regulations and procedures; and higher probability of being exposed to additional difficulties at the border, including corruption and sexual harassment. Evidence helped in facilitating discussion with stakeholders to design approaches to tackle these gendered constraints. Having high ambition, clear dedicated G&I resource, and support from senior stakeholders helped strengthen G&I approach and results.

Programme Design and Delivery

Programme design and timescales underestimated time required to fully design a new, large complex programme and associated projects, including design and procurement of sub-projects, and particularly one at this scale. Time to develop the full business case, procure the Service Manager (appointed in April 19 two years after the initial business case was approved), and time for development of sub-components were underestimated, placing additional pressure on the programme to mobilise interventions quickly. While aspects of the programme delivery could have been streamlined (including development and approval of country based interventions), it is essential large programmes incorporate sufficient time for design, procurement and delivery into overall design.

GTP was not able to achieve value for money in the Flexible Fund due to disproportionate spend on research and design costs, compared to interventions. VFM was impacted by the changing context of reduced ODA budgets and delivery interventions being cancelled, which led to a high ratio of costs to outputs delivered. The programme design had identified high advisory costs in the programme (£40m of £150m original budget) reflecting the design and build approach, and expectation was this would balance over time. However, the programme was not agile enough to respond to vfm challenges identified in the annual review. Design that involved a phased or more scale-able approach to project design and management may have enabled the programme to adapt more readily and potentially be more cost-effective. Clear milestone based contracts may also have supported additional cost savings.

A more phased approach to the programme, alternatives to project design (e.g. expanded use of pilots, calls for proposals for the Flexible Fund), and a more adaptive management approach may have strengthened programme delivery. The scale of the programme was ambitious (£150m), with aims of strengthening capability of emerging economies to trade with the UK (and rest of the world). However, it struggled to deliver at pace and at scale. Bringing a phased approach into design, and using a pilot approach, supports an approach to build on lessons learned but may also ultimately facilitate scale up and expansion over time.

Programme management, commercial and policy skills were essential to deliver a large, complex, and adaptive programme like GTP. Some of these skills had to be outsourced from early stages of the programme due to limited expertise available at FCO and difficulties recruiting relevant expertise; the programme also suffered from high turnover of staff through its duration. While programme expertise has expanded at FCDO after the merger of its legacy departments, FCDO should continue to develop departmental capacity in this area though FCDO’s ‘Programme Operating Framework’ training.

Roles and responsibilities of multiple actors in delivery (FCDO staff centrally and at post; Service Manager staff centrally and in country; in country delivery partners) were not always clear. For example, the Service Manager contract started at a point where four pilot interventions were underway. As the Service Manager was responsible for overseeing all Flexible Fund programmes, their involvement created a perceived duplication of effort, leading to some tension and confusion at the beginning of the contract. In addition to clarification on roles, a more adaptive or hybrid design in management and delivery of the Flexible Fund activities may have been useful, that better incorporated post expertise.

The programme components (Service Manager led Flexible Fund; UKTP; TFMICs) for the most part operated as discrete activities, and the added value of having those initiatives together in the same programme were not realised. While some synergies happened at the local country level (e.g. engagement of posts on TFMICs and TFSA), this could have been more effectively built into the design and delivery from the outset, and in programme operations. This may have been better integrated in the programme if it had continued, with more delivery results and lessons to be shared throughout the portfolio, but was a gap in implementation from early stages. The lack of an overall programme logframe exacerbated this, as this could have been a useful tool to bring together partners to better understand how initiatives contributed to collective objectives.

GTP benefited from cross HMG governance, with a Board consisting of other government departments and agencies which helped support its delivery, such as DFID in delivering UKTP; DEFRA and FSA in delivery of CODEX; IPO in delivery of the Brazil IP programme, and DIT inputs into design and prioritisation of interventions and support of delivery at post. Their support was critical in ensuring strong delivery. For example Brazil national partners and the supplier highlighted the critical role IPO played in providing support, guidance, and quality assurance in its ‘critical friend’ role in the programme. The Board could have been used more effectively, for example, in tackling risks early, and for communicating and sharing programme results or best practice.

Recommendations

Despite the GTP’s early closure and constraints, continued investment is needed in capacity strengthening and technical assistance to tackle the critical non-tariff barriers identified in the programme: supporting adoption of international standards, improved business regulatory environment, streamlined and transparent customs, improved intellectual property regimes, and wider support for businesses to take advantage of trade agreements. Lack of institutional capacity, and limited understanding and uptake of trade reforms continue to be constraints.

The FCDO must be realistic about the length of time and the level of capability required to develop and implement (i) flexible and adaptive and (ii) large and complex ODA programmes, and ensure that appropriate capability is in place for duration of the programme.

Clear parameters need to be set to ensure that the time and budget allocated to design and development of activities is proportionate to the overall lifespan and budget of the programme.

Programmes need to have proactive processes in place to recognise when and how to adapt in response to contextual changes. This requires robust governance and risk management processes and VFM frameworks.

For large complex programmes, phased approaches to delivery and flexible contract arrangements may be helpful to scale-up or scale-down delivery depending on external context, and help build on successful approaches and lessons learned.

FCDO needs to ensure that people with appropriate skills are recruited into teams where large budget scale up is anticipated over time. The merger of the two legacy departments ensures a high level of relevant expertise but capability is still being developed in some areas. FCDO’s Operating Framework, the development and use of competency frameworks, and strategic workforce planning are key to this process.

Beneficiaries should be involved where possible in the design of implementation activities as these can support the relevance and uptake of interventions and maximise impact. Bilateral relationships should ideally be underpinned by high level political agreements such as Memorandum of Understanding (MoU) agreements. These aspects are essential to supporting longer-term sustainability.

Results from the programme can be more effectively shared or communicated widely. FCDO should continue to identify mechanisms where any key programme outputs or products, evidence or lessons can be shared or disseminated.

How this report was conducted

The PCR review team assessed the progress of the GTP against the Outcome and Outputs set out in the Business Case and against updated (post ODA re-prioritisation) logframes. This report was completed by Trade Programme Team with FCDO economist, MREL, and commercial support. The review team conducted more than 15 interviews with FCDO programme staff at centre and at post, delivery partners, and representatives from government organisations. The team also drew on findings from end of project meetings, and programme related documentation including data, reports, annual reviews, and logframes. The PCR focuses on performance over the lifecycle of the programme as well as the sustainability of achievements beyond its 31 December 21 end date.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£150m	£49.65m
Timeframe	4 Years (2017-21)	4.75 years (2017-2021)
Outcomes	Better adherence to international standards and rules creates a better business climate. Government policies promote a more strategic integration with the global economy. Barriers to trade reduced leads to more trade. / Increased openness to international trade promotes sustainable growth paths.	The GTP has delivered a set of programmes that are supporting target countries to address NTBs and create conditions for increased international trade. Despite the relative infancy of its interventions, there is already evidence of a more inclusive trading environment (TFSA and UKTP), more innovation and quicker processing times at borders (TFMICs) and improvements in Intellectual Property processes (Brazil IP).

Overall assessment of programme outcomes

The original Business Case assumed that up to £150m spend would support GTP activity in several countries across a 4 year time scale. The overall outcomes in the original business case were ambitious: 1) more inclusive economic growth, due to factors such as higher employment and lower prices that reaches the poor; and 2) higher UK GDP growth, due to improved export revenues, returns to capital and lower cost imports. Intermediate outcomes included a) better adherence to international standards and rules creates a better business climate; b) government policies promotes a more strategic integration with the global economy; c) barriers to trade reduced leads to more trade; and d) increased openness to international trade promotes sustainable growth paths.

The early closure of the GTP, and reduction of spend to one third of its original budget across a significantly smaller portfolio, meant that the programme did not to deliver activity to the scale anticipated in the Business Case. Many country-level interventions were not initiated, others were significantly reduced in scale and closed early. As such the programme was not able to achieve the scale of intended impact, outcomes, outputs, or secondary benefits.

The 2019 and 2020 annual reviews highlighted the need for an overarching programme logframe to reflect the overall programme and its components, and in particular the inclusion of projects implemented by multilateral partners. A key recommendation was to revise outcomes, outputs and relevant indicators. However, with the decision to close the programme early, and the significant reduction of spend, the programme team focused on scaling down contracts, enacting exit arrangements, and instead revised the component or project level logframes.

Still, progress was made towards intermediate outcomes in select countries, in particular related to a) increased adherence to international standards, for example in food standards, phytosanitary conditions and customs regulation; b) in trade facilitation and customs policies and systems through streamlined processes, implementation of customs regulations, and digitisation which also helped reduce time and red tape at borders; and c) increased market analysis and support to the implementation of the EPAs to help increase trade between developing countries, with the UK, and with other countries.
The most recent Annual Review, completed in September 2020, rated the GTP as a ‘C’ - Outputs substantially did not meet expectation, due to concerns which included limited progress on outputs and outcomes of the programme, Value For Money (VFM), and the approach taken to Gender & Inclusion. An internal mid-year review (April 2021) assessed progress made against Annual Review recommendations, noted success in approaches to gender and inclusion and some progress on improving value for money through changes to programme management.  While some progress was made on the overall logframe, this work was overtaken by the business planning decisions noted above.

The assessment that follows outlines the Theory of Change and progress towards the overall outputs and outcomes organised. The subsequent output section gives details on results against the logframes and outputs of the programme ‘live’ components.

Theory of Change
The Theory of Change (ToC) in the GTP Business Case (see Figure 2 below) outlined an approach that inclusive economic growth and poverty reduction in developing countries would be delivered via improved employment and mutual prosperity. This impact would be underpinned by outcomes including lower cost of inputs for businesses, improved competitiveness, higher levels of innovation, and a more conducive and open environment for trade and investment. Better adherence to international standards and rules and improvements in government practice would also create greater opportunities for priority countries to expand trade and integrate more effectively in global value chains.

The GTP identified the need to address the following NTBs as its pathways to generating those outcomes: i) contributing to the adoption of international standards; ii) better IPR protection; iii) improved and more coherent regulatory practice; iv) streamlined customs procedures; and v) greater commitment to (and understanding of) opportunities arising from trade openness and more capacity to negotiate trade deals. Outputs that contributed to these changes included increased skills and capacity of businesses and government agencies in these areas; improved trade regulations, processes and policies; improved communications between government and business; improved capacity of trade associations and service providers supporting SMEs; and a focus on businesses owned by women and/or identified vulnerable groups.

The 2020 Annual Review produced a set of recommendations to further develop the GTP’s ToC, including clear articulation of the causal pathways and assumptions, and how the programme would support gender and inclusion, and to revise the logframe as noted above.

Progress towards Outputs and Outcomes on tackling NTBs
As reflected in Table 1 on page five, the GTP undertook activity across all of the main NTBs targeted in the GTP Business Case: Intellectual Property; Regulatory Reform; Standards; and Customs, as well as an additional area to support EPA implementation. This section provides more information as to how specific GTP programmes have yielded results towards outputs (and outcomes) in each of these thematic areas.

Intellectual Property:
Although the GTP initiated four Intellectual Property interventions, three were closed at the NPC stage. Despite the reduced scale and timeframe, the Brazil Intellectual Property (IP) programme has helped equip the Brazil National Patent Office (INPI) with knowledge and tools to modernise processes and increase office efficiency, leading to a reduction in time taken to process applications, reduce patent backlogs, and increased human resources productivity. Results included a set of specific recommendations to improve logistics and infrastructure, trademarks, budget and finance, patents and international patents, and IT; a tariff simulator to be used by INPI; and establishment of a cross-departmental committee on gender equality and social inclusion.

Emerging results from the programme, completed in March 2022, have already demonstrated positive impact. A benchmarking study produced by delivery partner, Palladium, at the design phase assessed INPI’s performance alongside ‘best practice’ Intellectual Property Offices including the UK, US, Singapore, Japan and Australia to help determine systemic deficiencies and process improvements to inform the project workstreams. Project support helped INPI to climb nearly 20 positions (to 6 out of 60) in the latest IP Office Innovation Ranking undertaken by the World Trademark Review, and up over 35 positions throughout the duration of the project.

Improved regulatory practice:
Two of the four pilot programmes specifically targeted regulatory barriers and aimed to improve regulatory practice: 1) Mexico Better Regulations (which closed early due to ODA reductions); and 2) the £6.3m Brazil Regulatory Reform, which reached procurement stage (January 2020) but was paused and then subsequently cancelled due to ODA reductions. TFSA, UKTP, VNTR, and TFMICs also contributed to building capacity and awareness of regulations and improved practice.
The Mexico Better Regulations Flexible Fund programme focussed on reigniting growth, investments and well-functioning markets in response to Covid by strengthening Mexico’s business regulatory environment. WBG worked with Mexico’s National Commission of Better Regulation (CONAMER) to design, develop and implement SINAGER (Mexico’s National System for Regulatory Governance). SINAGER is an innovative national digital platform to manage and improve business regulation at federal, state and municipal levels. It integrates and manages all stages of the regulatory governance cycle from design, through to implementation and evaluation. It will ultimately help businesses to return to their pre-pandemic production and employment levels and will set the foundations for longer-term productivity-driven growth.
WBG and CONAMER designed, developed, and translated in to a functional digital platform three of the four planned regulation tools comprising SINAGER: regulatory agenda; ex ante regulatory impact analysis (RIA); and better regulation programmes. The fourth area of Ex Post Regulatory Impact Analysis or Evaluations was paused due to budget reductions. A preliminary shortlist of 8 states, 8 municipalities and 3 economic sectors (manufacturing industries, commerce and temporary accommodation; and food and beverage preparation services) were identified to roll out. Final development of the last area, and additional resources to promote the roll out are being taken forward by WBG and CONAMER.

Adoption of International Standards:
CODEX: Global food standards such as those developed by the Codex Alimentarius Commission are critical to ensure the availability of safe and nutritious food for all, to promote fair practices in the food trade, and to enable more countries to participate in international food trade. UK support to the CODEX Trust Fund (delivered through an MoU with DEFRA and FSA), contributed to building capacity in 44 developing countries to engage more effectively in the CODEX standard setting process. This included training of government staff on CODEX standards, technical assistance on national requirements for food safety, development of national protocols, capacity building on phytosanitary measures, and assistance on key expert committees. This activity ended as planned in 2021.

Turkey – Two planned programmes to enhance standards and customs in Turkey were paused and subsequently cancelled due to ODA reductions. However, project design has supported needs analysis and has developed capacity. Despite the programmes not going forward in their originally intended form, FCDO staff at post worked with British Standards Institute and HMRC colleagues to arrange pro-bono workshops for Turkish Ministry counterparts which set out best practice approaches. Subsequently, BSI and TSE (Turkey Standards Institution) have agreed to sign a Memorandum of Understanding (MoU) to formalise their relationship at the International Organization for Standardization (ISO) General Assembly be held in Abu Dhabi from 19-23 September 2022.

TFSA: TFSA has provided standards and compliance training in six priority value chains (fruit, nuts and veg, cosmetics, natural ingredients, aquaculture, green tech/renewable energy, and speciality ingredients), working with 18 BSOs across SACU+M on 15 different interventions.

Streamlining Customs:
TFMICs supported five countries (Brazil, India, Philippines, Nigeria and South Africa) to meet their obligations under the WTO Trade Facilitation Agreement (TFA). The implementing partners, WBG and WCO, worked collaboratively to undertake diagnostics studies, and provide technical assistance and capacity building to partner countries to implement trade facilitation measures and reforms, in order to tackle inconsistent, unpredictable trade transactions and improve customs and border efficiency. Despite the early closure of the programme due to ODA reductions, it yielded good results, including in supporting partner countries to respond to the Covid crisis. Maintaining trade flows during the Covid pandemic has been crucial to providing access to essential food and medical items and in limiting the negative impacts on jobs and poverty. Trade facilitation measures have contributed to the response to the crisis by expediting the movement, release, and clearance of goods, including PPE and vaccines. Achievements include:

 Improvement to customs and border procedures:
- Digitalisation/ Automation: Support to the Philippines Bureau of Customs and other agencies to expand automation protocols and streamline port clearance procedures (e.g. customer care portal; modified goods declaration verification systems; and enhanced cargo selectivity system) reduced time for import clearance as well as reducing face-to-face contact and potential transmission of the virus. This resulted in a 43% reduction in import times (from 10 days 19 hours in 2019 to 6 days 3 hours in 2020[3] as evidenced in the October 2020 Time Release Study. Export clearance times increased however from 1 hour 11 min in 2019 to 4 hours and 45 minutes in 2020, but a reduction in staff due to Covid is likely to be the reason for this result;
  [3] TFMICS Final Report (2022).
- The South Africa Revenue Service (SARS) increased the use of cameras, virtual meetings, and self-verification to undertake verification checks for audits which has helped to eliminate the need for face-to-face contact;
- Transparency and Streamlining: Support was provided to South Africa and the Philippines to implement WCO Immediate Release Guidelines for air cargo, which has expedited the swift distribution of Covid vaccines;
- In the Philippines, risk management has now been embedded in the Bureau of Customs organisational culture and meets ISO standards. Detection rates have increased from 18% to 40%, and compliance has also improved from 57% to 98%.

Support to trade facilitation institutions and planning:
- Helped to foster commitment to the Authorised Economic Operator (AEO) programme in Brazil through the ‘Sao Paulo Declaration’ and to expand the AEO programme in South Africa;
- Supported establishment of the Philippines National Trade Facilitation Centre (NTFC) in May 2021 to streamline processes to help expand the country’s trade markets and support post-pandemic recovery;
- Updated the Nigeria Trade Facilitation Roadmap;
- Brought together partner country NTFCs in a 4 day forum, along with other advanced NTFCs, private sector, and public bodies to discuss best practice and share lessons on effective management, delivery and operations of NTFCs to improve trade facilitation objectives.

Diagnostics/analysis has included:
- WTO Gap Assessments (Brazil and the Philippines) and Time Release Studies in Philippines, India and South Africa;
- In Brazil, as part of the Poverty Impact Study completed, an assessment of import transaction data between 2003-2019 confirmed a reduction in release times had led to substantial increases in trade flows at the port level with waiting times reduced by 50% and an associated increase in imports of 22.1%;
- Trade Facilitation and Gender studies in Brazil, the Philippines, and South Africa informed gendered differences in cross-border trade. Across the 3 studies 4,577 trade firms and customs clearing agents were surveyed (of which 46.3% of respondents were women), providing evidence of women consistently having less understanding of customs and trading information; results were used in discussions with governments to develop strategies to make information more widely accessible;
- Customs Integrity Diagnostics and Customs Integrity Perception Surveys (CIPS) were completed both among customs officials and the private sector in Brazil, South Africa and Philippines to help move forward the Customs Integrity Agenda.

SACU Customs Modernisation Programme (Flexible Fund pilot activity) contributed to 135 African firms being accredited as preferred traders - a status provided to firms with substantial import/export transactions, and which have a level of confidence about their operations (including tax administration) by the Customs Dept. The accreditation scheme is reducing the experience of delays and costs at the border and by extension increasing revenue for SACU member countries (Botswana, Eswatini, Lesotho, Namibia and South Africa).

Vietnam National Trade Repository (VNTR) is a free to access online information platform providing access to trade regulations and information that businesses need to import and export to and from Vietnam. It is becoming an essential tool to supporting Vietnam to meet its ASEAN trade commitments. Launched on 30 March 2022, the programme was delivered by Nathan Associates, in close collaboration with the Vietnamese Ministry of Industry & Trade (MOIT), Business Chamber of Commerce, women led businesses and FCDO staff at post and in the UK

Support implementation of EPAs in particular, to businesses on market analysis, navigating regulations, export processes, and trade promotion.

TFSA - provided free and easy access to latest trade information and tools for businesses in SACU+M to competitively grow exports and markets. Over 4,000 users per month accessed the TFSA Info Hub (www.tfsouthernafrica.org) by February 2022, and traffic peaked 4,290 unique users in Jan 22 due to an online marketing and social media campaign. 48 Business Support Organisations act as knowledge centres to facilitate training and outreach. To date, 1,629 participants attended TFSA led or collaboration virtual events, exceeding targets by more than 50%.
- 3 Covid-19 related assessments were conducted in Namibia, Lesotho, and Mozambique to improve the ability of governments, through trade reforms, to address trade in the Covid-19 environment. All assessment recommendations connected to this output have been accepted, for example-in September 2021, the Govt of Mozambique confirmed they will adopt the Covid-19 Business Recovery Strategy produced under the TFSA programme.
- TFSA Export School Training (10 week programme), supported by business management modules, coaching and business expert consultations developed and delivered to women entrepreneurs and business owners.
N.B. Responsibility for managing the TFSA programme transferred from GTP to South Africa on 1 July 2021.

UK Trade Partnerships (UKTP) programme, implemented by the ITC, supports technical assistance and capacity building activities in target EPA countries in Africa, Caribbean and Pacific (ACP), including development and use of market access tools and digital transformation. This activity is ongoing as a discrete programme activity, building on the base developed as part of GTP delivery. To date, UKTP support has led to development of 12,955 jobs, including over 7,330 women and additional direct annual sales to the UK and the EU of over US$20.7m (including over US$7.56m for women business enterprises). ITC estimate that interventions on EPA awareness and knowledge and use alone have indirectly facilitated $11.9m in exports.

Over 1,560 participants have been reached through training and awareness raising initiatives, trade data updates and embedding of market access tools; 30 business support organisations reached through a mix of webinars and coaching; and over 1,110 MSMEs reached, at least 280 of which are women-led business enterprises, and 290 have provided evidence of adoption of new practices.

During the period of the pandemic, UKTP supported beneficiaries to pivot to participate in virtual trade fairs. In 2020/21 this included the Food Matters Live Trade Fair in London, BIOFACH 21 (leading trade fair in organic food products); and Food Ingredients (Fi) Europe Connect food and beverage trade fair (Frankfurt). The programme also piloted the REACT – Ready, Expert, Agile, Connected and Trusted (REACT) methodology to determine BSO resilience in face of Covid disruptions.

The 2021 edition of the Speciality & Fine Food Fair hosted the inaugural UK Trade Partnerships Programme (UKTP) pavilion which connected 16 export-ready businesses from the Caribbean (6), Comoros (7), Ivory Coast (2) and Cameroon (1) with UK businesses. Their participation generated 340 contacts over the two days at London’s Olympia exhibition centre; and concrete opportunities to elevate these businesses to make their mark on the international fine food scene are being pursued.
Despite Covid challenges, some developing country businesses benefiting from the programme were able to expand linkages with UK and other global suppliers. In Ghana, for example, Niche Cocoa, a cocoa-processing company was able to increase sales to the UK by $2.7m (71%) over the period Jan to Dec 2020 despite challenges during the pandemic. This was due to applying ITC Market Access Tools learned through training to better identify market opportunities and make data-informed trading decisions and participation in digital trade fairs linking suppliers to buyers.

One of the key successes of the UKTP programme to date has been its original design as a pilot allowing it to test countries, sectors and firm sizes. This has allowed it to scale up and down as needed in response to emerging opportunities or reduced budgets.

Value for Money
An assessment of economy and efficiency are included in Section E: Programme Management below.
Effectiveness
The programmes delivered by multilateral partners (e.g. TFMICs, UKTP, and Mexico Regulations), whilst operating in a difficult context of Covid, reduced budgets, and in some cases early closure, have delivered results whilst flexibly adapting to budget constraints. Programmes have been required to adjust work plans and modalities, including the need to rapidly pivot to remote delivery. In the case of TFMICs, this involved shifting focus to Covid specific challenges whilst continuing to maintain business continuity and supporting recovery efforts. In some cases, pandemic requirements encouraged governments to adopt more quickly digitised or automated systems (e.g.TFMICS) or to strengthen training of businesses in those areas (e.g. UKTP). In the case of TFMICs and Mexico regulations, despite having to refrain from further commitments, putting other activities on a ‘slow burner’ while decisions were being taken, and exiting earlier than had been planned, these programmes were able to deliver good outputs.
The Flexible Fund was less successful in delivering value for money due to the limited number of interventions reaching the ‘go-live’ stage, despite significant costs invested in analysis and programme design. Delays in interventions reaching the go-live stage prior to Covid, and the subsequent impact of ODA re-prioritisation cuts preventing programmes from proceeding as planned contributed to this, resulting in disproportionately high advisory and management costs compared to intervention outputs or outcomes, as outlined in more detail below. £22.38m was spent in total on Service Manager Management (£4.94m) and Advisory Costs including country plan analysis, research and business case development (£17.89m). N.B. The range of services covered by these costs is set out in more detail in the Commercial Section.
The GTP Business Case assumed that the programme would be in a position to spend £43m in its second year of delivery with the aim to increase spending to a steady £50m per annum. However, this approach did not adequately factor in time for full inception, project design and procurement for each of the sub-component activities. Furthermore, activity was largely driven by small programmes delivering technical assistance which did not spend at this scale. In hindsight, the assumption that the full allocation would be spent in 4 years set unrealistic expectations on the scale and pace of spend; however, this could have been mitigated with no-cost extensions if resources had been available. The programme also could have put in place some efficiencies in design which may have streamlined or fast tracked production of some of the activities.

The Prosperity Fund Cycle 1 Evaluation Report for GTP undertaken in July 2020 assessed that the cost-benefit ratio of the GTP had already been affected by the pandemic. The Annual Review that followed in September 2020 flagged that ratio was even higher as a result of ODA budget reductions, and continued relatively high advisory costs, and raised the question of whether the programme would meet its effectiveness obligations over the implementation period without radical restructuring and reprioritisation. Those re-prioritisation decisions were ultimately overtaken by the business planning exercise which resulted in the early closure of several components of the programme, and the programme as a whole in December 2021.

When the first set of ODA reductions were announced via the ODA re-prioritisation exercise in July 2020, the GTP was required to find £9m of immediate savings from live projects, reducing the total budget allocation form £150 to £141m. Pipelined Flexible Fund interventions were paused including 6 interventions (£17.4m in total) where Business Cases had been developed. In April 2021, due to further reduced ODA budgets, the UK government took the decision to close early some components with significantly reduced budgets.

As a result of the ODA reductions and decisions taken, GTP has only been able to deliver 5 Flexible Fund projects out of an initial pipeline of 22 Flexible Fund projects. Three of these had been managed by the Service Manager (TFSA, Brazil IP, VNTR). At the time of its closure, the GTP therefore had incurred disproportionately high advisory and management costs when measured against delivery costs, particularly for the Flexible Fund activities. The programmes that were implemented have been a good strategic fit with partner countries and have achieved positive initial results. (See Section C). The VNTR and TFSA programmes that were previously part of the Flexible Fund continued as discrete project components whilst operating within reduced budgets after the closure of the GTP. This is also the case for UKTP. These projects are continuing under new governance structures and have performed well according to their most recent annual reviews.

Equity

The GTP acted upon a 2020 Annual Review recommendation to produce a G&I Action Plan which was approved by FCDO and Social Development Advisors in March 2021. Each programme has adopted a robust approach to meeting G&I targets, and these activities have been used to inform project design and implementation, for example:

Brazil Intellectual Property (IP) – The programme delivery partner, Palladium, embedded a GESI (Gender Equality and Social Inclusion) advisory team to provide expert advice in relation to the programme’s approach to risk, delivery, and its results framework. By developing a thorough understanding of the issues, Brazil IP has mainstreamed GESI across project activities and workstreams. As a result of this work, INPI has a new gender and inclusion framework to support institutionalisation of these issues within INPI.

Vietnam National Trade Repository (VNTR) – the online trade portal has been designed to be inclusive and compliant with the Web Content Accessibility Guidelines (WCAG).  In addition, the deliver partner has incorporated feedback from the Hanoi Women’s SME Association (HAWASME) into the portal design and included its members as part of the user testing. The online portal therefore reflects views of women-led enterprises and their requirements and feedback have helped to shape the overall design.

TFSA – This programme has a strong focus on improving the trade environment for women and other excluded groups and has selected interventions in sectors and sub-sectors accordingly. An example is the programme’s Export Trade Training for South African women entrepreneurs which is being delivered in partnership with the UK-SA Tech Hub and Future Females. TFSA has developed a Learning Management System (LMS) to guide businesses with different levels of export experience. This helps them to prepare for export, identify markets and potential buyers, and find necessary information about compliance and import/export requirements. The LMS has received excellent feedback from female entrepreneurs who have undertaken the training.

TFMICs – WBG completed three surveys (the Trade and Gender Study) in Brazil, the Philippines, and South Africa. The objective of the studies was to identify the additional challenges that women traders and customs agents face when undertaking border processes and procedures related to the movement, release, and clearance of goods. The findings and recommendations have been discussed with the respective governments, and WBG is currently exploring technical assistance needs to help address the gender-specific challenges to cross-border trade.

The WCO completed Gender Equality and Diversity Organizational Assessments with four partner countries: Brazil, India, South Africa, and the Philippines which resulted in the identification of several strengths and gaps, as well as forward recommendations to enhance the overall gender equality and diversity agenda within these customs administrations.

UKTP – Across the Africa, Caribbean and Pacific countries covered by the programme, gender assessment reports and action plans have been completed and adopted to ensure that opportunities for women-owned enterprises are fully maximised. Barriers to inclusion in the programme, which if not addressed may lead to further marginalisation of groups and thus increased social or economic inequalities, have been monitored in the ITC’s final programme inception report.

Sustainability

The GTP has laid strong foundations to support the sustainability of its programmes beyond the life of the programme. This work includes:

Vietnamese National Trade Repository: The VNTR was designed in consultation with the programme beneficiary, the Vietnamese Ministry of Industry and Trade (MOIT). During the design phase, MOIT were fully engaged in the review and sign-off of programme milestones, and they received extensive training and handover from the VNTR supplier, Nathan Associates. Public awareness of the portal was raised through social media campaigns and a series of well attended roadshows before and after the official launch in March 2022. The launch of the VNTR was attended by UK and Vietnamese Ministers building on the bilateral partnership formalised through the signing of a Ministerial letter of Intent at the beginning of the programme. FCDO staff finalised a transfer agreement with MOIT in July 2022 to help establish commitment for continued uptake. Tan Dan JSC will continue to provide technical support for 1 year post handover.

Brazil IP: The Brazil IP programme is delivering transformational change in the country’s intellectual property sector. The sustainability of the programme is underpinned by work undertaken to modernise processes, increase operational efficiency and improve the quality of Intellectual Property (IP) rights. Emerging results show that this is already helping to deliver a reduction of backlogs, better management and control systems, and better and quicker IT infrastructure systems. This capacity building activity has been underpinned by support from UKIPO who have signed a high level MOU agreement with INPI.

TFMICs: Although TFMICs was forced to close early, which threatened to undermine momentum built in target countries, those risks have partly been mitigated through the identification of new WBG funding sources to continue activity in Brazil, India and Nigeria. Activity in support of Philippines and South Africa was added to the HMRC-UNCTAD-WCO Capacity Building for Trade Facilitation programme in 21/22, and subsequently from April 22, its successor programme, the HMRC-led Accelerate Trade Facilitation programme.

TFSA: Export training and outreach is delivered via partner Business Support Officers (BSOs), with 46 targeted so far as potential Knowledge Centres. Each BSO will receive Short Term Technical Cooperation (STTC) support to enable them to deliver exporter training as an integral part of their services beyond the lifetime of TFSA. We anticipate that BSOs will be able to apply the lessons and knowledge provided by TFSA to develop sustainability strategies to be implemented as part of their exporter training service from January 2023. TFSA has also developed an Export Training User Guide that can be adapted and used by any BSO that may not have been included in the Women in Trade Roll-Out. This user guide will provide BSOs with the toolkit that they can use to facilitate or deliver exporter training to women and men.

UKTP: The UKTP is delivering sustainable impact by making firms and export promotion agencies in target countries more aware of the benefits of EPA preferential trading arrangements and how to use them. Help continues to be provided to firms and institutions to enable them to export to UK/EU markets across diverse sectors. For example, support for digital transformation included a mix of webinars and individual coaching, reaching all 30 BSOs involved in the programme to date.

## C: Detailed Output Assessment

The full GTP log-frame was still under production and review during the first and second rounds of ODA reductions in 2020 and 2021, which ultimately substantively reduced the intended scope of the programme. A partially completed logframe for the Flexible Fund was used in the 2020 review along with separate logframes for UKTP and TFMICS; however this included outputs without fully defined targets, and outputs which refer to aspects of the programme that were not taken forward. This Output Assessment focuses on project logframe details for interventions that reached the delivery phase and where activity/outputs were produced: UKTP, TFMICs, Brazil Intellectual Property, VNTR and TFSA.

UK Trade Partnerships, Outputs

UKTP provides technical assistance and capacity building to support countries party to UK Economic Partnership Agreements (EPAs), and trade agreements between African, Caribbean and Pacific (ACP) countries. The programme delivers on commitments in the UK’s EPAs to provide expert advice and skills training to both the government and private sector to help target countries to maximise benefits of trading under the preferential schemes offered by the UK (and previous EU EPA).

As per agreement by the Programme Board in November 2020, UKTP management was segregated from the GTP in FY 21/22 and is one of the ongoing components that continues after the closure of the GTP overall programme. UKTP activities currently are due to continue until March 2023, with the programme managed by FCDO’s Economic Security Directorate.  The primary delivery partner is ITC. A second component with Cariforum remains under development.

An overview of outputs up to March 2022 follows. The UKTP in 2021 scored an ‘A’ in delivery of outputs demonstrating their delivery against objectives despite the changing conditions, and are on track to deliver an A+ or A++ in the following year. Overall progress against outputs is outlined below.

Output 1 – UKTP is progressing as planned with the completion of Output 1 deliverables including: (1) Training and awareness raising, (2) Trade data updates, and (3) Embedding of the ITC Market Access Tools (MAT) in selected websites. Notably, to date, UKTP has embedded 11 (out of a programme target of 10 and currently expected 15) market analysis tools. Additional financial support from FCDO allowed UKTP to propose embedding the export potential map tool with CARIFORUM. To date, UKTP completed 5 Editions of the two-week workshop “Understanding UK EPAs and spotting trade opportunities in the UK” and continued working intensively in trade data collection and dissemination. Overall, the intervention on EPA awareness and knowledge and use has indirectly facilitated $11.9m in exports (47% of the programme target). In FY2022-23, UKTP results will be supported by newly embedded Market Access tools (MAT).

Output 2 – UKTP is also soon to complete Output 2 focused on Comoros, Côte d’Ivoire, Mauritius and Madagascar enabling an improved business environment for international trading between the UK and these select UKTP countries. UKTP launched two updated Trade Obstacle Alert Mechanisms (TOAM) in Côte d’Ivoire and Mauritius. UKTP is still to launch a new TOAM in Madagascar and, if additional non-ODA funding becomes available, the new TOAM in Seychelles which is already available online in its beta version. UKTP achieved a major milestone against output 2 through the adoption of the National Policy on Quality in Comoros. Follow-on activities in FY2022-2023 in these countries, now that these reforms have been achieved, will contribute to achieving the targeted regulatory reforms.

Output 3 – UKTP is in the process of completing activities for Output 3. UKTP supported partner institutions on their digital transformation journey, a significant adaptation of UKTP compared to the originally planned intervention, while continuing support on strategic planning, business models and customer relationship management. Already, the Association of Ghana Industries (AGI) has launched its ecommerce platform for cocoa products. Institutions in the Caribbean, Côte d’Ivoire, Cameroon, Zimbabwe and Madagascar have adopted digital transformation plans and initiated the proposed actions. The Organisation of Eastern Caribbean States (OECS) is working with UKTP to create an online trade fair to be held in FY2022-23.

Output 4 – UKTP has delivered strongly on Output 4 with training and tailored coaching to beneficiary enterprises across UKTP countries, particularly in the areas of marketing, branding and/or packaging to prepare beneficiaries most directly to succeed in the UK and EU markets. UKTP engaged with music and film companies through training and individualized coaching in specialized topics in product-specific distribution, marketing, financing and publishing. UKTP evidenced uptake of new practices in resource efficiency, lean manufacturing and product design and development in Madagascar, crop production and access to finance among smallholder farmers in Zimbabwe and Fiji. To date, 1,112 MSMEs, at least 281 of which are women business enterprises, have been reached with advisory services. 290 MSMEs have provided evidence of adoption of new practices and at least $1m has been facilitated, mostly to ginger farmers in Fiji. Whether it is by increasing the availability of produce, as was the case in Fiji and Zimbabwe, by allowing enterprises to meet industry best practices, or by giving beneficiaries the tools to position their products or creative services in target market, UKTP has improved the competitiveness of enterprises across UKTP countries to open up new market opportunities.

Output 5 – Emerging strongly from the pandemic lockdowns, UKTP intensified its work on market linkages ultimately meeting its Output 5 programme targets, including the facilitation of 2,769 business contacts for 89 SMEs. In the year ahead, UKTP will mostly focus market linkages for enterprises supported in the first two years of implementation. UKTP has pursued a mixed approach involving direct facilitation of market linkages, capacity development for market engagement, and sponsoring participation in trade fairs. UKTP was present at major trade fairs for food products (Speciality and Fine Food, Food and Drink Expo; Salon du Chocolat, Caffè Culture, Texworld, Paris Première Vision, Berlin film market) and organized or promoted national events such as Cashew Connect in Côte d’Ivoire. With most exporting and export-ready beneficiaries having attended at least one fair, beneficiaries are well poised to take advantage of FY2022-2023 fairs and to cement new business relationships.

Key lessons from the programme include:
- The programme benefitted from its original design as a pilot which allowed it to test countries, sectors, and firm sizes. This supported the programme to identify where and how to scale up, and also to reduce budgets when required
- The programme’s country breadth and activity variation was a positive during the Covid pandemic because it allowed resources to be redirected as lockdowns or restrictions were introduced.
- Training support on how to use market access tools enabled businesses (e.g. in Ghana) to expand their sales to the UK even when faced with human resource constraints and operational challenges during the pandemic.

Output Number and Title	1. Firms and institutions are aware of how to use EPA preferences and potential benefits
Impact Weighting		20%	Score	A++

Indicator(s) Baseline Target Achieved Progress / 1.1 Number of trainings on EPA and market access 0 25 29 Target achieved. / 1.2 Number of participants to trainings on EPA and market access (by gender) 0 1000 1,561 UKTP has been able to reach 1,561 participants by providing more EPA-focused webinars. (56% above the programme target). / 1.3 Number of EPA countries for which market access information (trade, tariffs and regulatory requirements) is complete and up-to-date in market analysis tools 1 100 147 Target achieved. To improve market access information, UKTP has uploaded 147 country data batches into ITC’s suite of Market Access Tools (MAT) in addition to integrating UK tariff data. / To improve market access information, UKTP has uploaded 147 country data batches into ITC’s suite of Market Access Tools (MAT) in addition to integrating UK tariff data. / 1.4 Number of market analysis tools embedded in national or regional institutions’ websites 0 10 11 UKTP has completed embedding 11 (out of a programme target of 10) market analysis tools. Many countries have confirmed their interest in embedding the MATs and proposals are being finalised. Caribbean OECS is due to finalise embedding of MATs next quarter. Madagascar’s EDBM is due to finalise embedding by this year. / 1.5 Number of visits of the market analysis tool in EPA countries 0 10,000 17,230 The programme has seen a steady quarterly increase in usage for both MacMap (market access) and TradeMap (trade statistics) tools. In total, UKTP achieved 17,230 more users against a programme target of 10,000. In the next reporting period, UKTP will have a full year of data on TradeMap usage to compare to the baseline. In addition, UKTP will be able to incorporate usage data from the embedded tools that further widen the reach of available market intelligence tools.

Output Number and Title	2. Business Environment more transparent for export to UK / EU markets
Impact Weighting		15%	Score	A

Indicator(s) Baseline Target Achieved Progress / 2.1 Number of mechanisms to monitor trade obstacles that are formalized in EPA countries 2 2 2 Target met although it should be noted that UKTP has not yet recorded regulatory changes arising from the trade obstacles alert mechanisms (TOAM). / Number of trade-related policies, strategies or regulations developed or changed with business sector input – on which actions are taken 1 1 1 Target met. UKTP achieved a major milestone through the adoption of the National Policy on Quality in Comoros. / 2.6 Number of changes that were implemented to mitigate regulatory and procedural trade obstacles 0 5 0 Business surveys will help identify regulatory and procedural adjustments that will help the recovery post Covid-19. Business surveys have been delayed to the second year of implementation due to Covid-19. In Ghana the survey is likely to be delayed further due to the protracted signing of an EPA. UKTP will be compiling business registries at the national level that will allow to determine the sample size for the survey. Exploratory work on compilation of business registry is underway in multiple African countries. Business registries have been completed by the ITC across other African and Caribbean geographies in the past and an interest in follow-up surveys in 2021 has been expressed.

Output Number and Title	3. Trade and support institutions and trade/ business support providers extend and improve their services to the focus sector for UK / EU Market entry (pilot countries only)
Impact Weighting		15%	Score	A+

Indicator(s) Baseline Target Achieved Progress / 3.1 Number of cases of institutions having improved operational or managerial performance in serving SMEs to enter UK / EU as a result of UKTP support 0 15 10 Institutions in Ghana, the Caribbean, Côte d’Ivoire, Cameroon, Zimbabwe and Madagascar have been supported. / 3.2 Number of workshops/coaching sessions delivered to strengthen the managerial and operational capacity of institutions 0 20 34 UKTP has delivered 34 workshops / training sessions including strategy coaching to KKFU, Ghana, Train the Trainers events to businesses in Côte d’Ivoire on participation in trade fairs, and training 4 Ivorian BSO’s in strategic planning. An e-learning course/webinar on Customer Relationship Management was delivered in December 2021 in Cameroon. / 3.3 Number of institutions participating in workshops/coaching sessions to strengthen the managerial and operational capacity of institutions 0 30 30 Target met.

Output Number and Title	4. Targeted firms have increased capacity to export to UK/EU market
Impact Weighting		30%	Score	A++

Indicator(s) Baseline Target Achieved Progress / 4.1 Number of enterprises reached with advisory services (including women business enterprises) 264 300 1,112 Outputs substantially exceeded expectation / 4.2 Number of enterprises in pilot countries having made changes to their business operations for increased competitiveness toward UK/EU markets as a result of UKTP support (including women business enterprises) 0 240 300 / Jan-Mar) Target met. UKTP has delivered training and tailored / coaching to beneficiary enterprises across UKTP / countries, particularly in the areas of marketing, / branding and/or packaging to prepare beneficiaries / most directly to succeed in the UK and EU markets. UKTP engaged with music and film companies through training and individualized coaching in specialized topics in product- / specific distribution, marketing, financing and / publishing. / 4.3 Value of financing facilitated (including to women business enterprises) ($) 0 $300,000($100,000) $1,054,420 By the end of the reporting period, access to finance / efforts had already translated in more than $1.05m / in financing facilitated to farmers in Fiji and Zimbabwe, / to cooperatives in Comoros. The ability of UKTP to / engage with Fijian farmers for a second round of / lending committed before the budget cuts allowed / UKTP to overachieve against the financing target.

Output Number and Title	5. Market opportunities activated
Impact Weighting		20%	Score	A+

Indicator(s) Baseline Target Achieved Progress / 5.1 Number of business contacts established (including in women-owned SMEs) 0 1200 2,769 Of beneficiary enterprises, 89 have made 2769 business contacts to date. In FY2021-2022, major events for UKTP included: (1) Caffè Culture and London Coffee Festival / for PNG coffee, (2) Salon du Chocolat in Paris, attended / by beneficiary companies from the Caribbean, Ghana / and Cameroon, and (3) Cashew Connect in Côte d’Ivoire co-hosted by UKTP and CBI, (4) Speciality & Fine Food / Fair for the Caribbean, Comoros, Ivory Coast and Cameroon, (5) International Food and Drink Event for 12 countries, (6) Texworld and Paris Première Vision for 2 editions each to showcase clothing products from Madagascar. In parallel, UKTP is also facilitating direct linkages between beneficiary companies and buyers. / 5.2 Number of enterprises that have made business contacts as a result of UKTP support (including women business enterprises) 0 70 89 Target met. See 5.1 for additional detail. / 5.3 Number of market studies completed 0 8 8 Target met.

Trade Facilitation in Middle Income Countries, Outputs

The TFMICs programme provided joint and/or complementary WBG and WCO country-specific diagnostics, technical assistance, and capacity building support to five MICs – Brazil, India, Nigeria, the Philippines and South Africa between October 2019 – October 2021. The outbreak of Covid-19 changed the operational environment and ODA business planning decisions ultimately resulted in the programme closing earlier than had been planned, and at a much reduced overall budget (£2.86m compared to original £25m planned budget). Project activities continued at a slower pace as resource decisions were being finalised.

Notable successes include the following:

Output 1.1.1 and 1.1.2 – Brazil and South Africa received capacity building support to prepare for the implementation of WCO Immediate Release Guidelines which align with provisions of TFA Article 7.8 on expedited shipments.

Output 1.1.3 – In the Philippines, the implementation of Joint Memorandum Circular 01-2020 increased electronic transactions at the port area from 22% to more than 75%. This was the result of work to streamline port clearance procedures and reduce face-to-face contact and was critical in response to Covid.

Output 1.1.4 – The TFMICs programme has resulted in enhanced momentum on the Customs Integrity Agenda in Brazil, South Africa, and the Philippines. The Customs Integrity Perception Survey (CIPS) was important in this process. In all three countries, integrity support directly supported the vision statement of the respective administrations, each recognizing that integrity is a cornerstone of successful and sustainable trade facilitation modernization initiatives.

Output 1.1.5 – In the Philippines, risk management has now been embedded in the Bureau of Customs organizational culture and meets ISO standards. Detection rates have increased from 18% to 40%, and compliance has also improved from 57% to 98%.

Output 1.1.6 – The successful validation of the Time Release Study (TRS) in Brazil has provided an opportunity for evidence-based dialogue between stakeholders to improve the effectiveness & efficiency at the borders. This work gained a significant profile with over 23k views of the livestreamed launch.

Output 1.1.9 - Gender Data Gap analysis has been undertaken to support trading opportunities for women in Brazil, the Philippines, and South Africa. 4,577 trade firms and customs clearing agents were surveyed (of which 46.3% of respondents were women). (See Equity Section).

Output 1.1.11 – The Nigerian Trade Facilitation Roadmap has been updated. This is a key step toward improving Nigeria’s trade landscape (including securing high-level political buy-in, increasing advocacy, and improving border agency coordination). Heads of Customs Administrations in Brazil and other countries expressed commitment to strengthen AEO programs, to engage other cross border regulatory agencies, and to explore MRAs (the “Sao Paulo Declaration”).

Output 1.1.12 –A Webinar series and Guide on Customs Human Resource Management in Times of Crisis – sharing experiences of Customs administrations and the private sector on business continuity, risk mitigation, and safeguarding the health and well-being of staff and (mental) health, has been produced. The Guide will be leveraged by the WCO membership overall in the HMRC Programme in specific going forward (Madagascar, Nigeria).

Output 1.2.1 and 1.2.2 – TFMICs hosted a four day forum on effective NTFCs in April 2021. This provided a platform for public and private sector participants to share best practices on the strategic priorities for the NTFC. In a post-event survey, all attendees reported that the event was very useful to their work at national levels.

Output 1.2.5 – A TRS) Working Group has been established under the leadership of the Bureau of Customs. The Working Group will design and conduct regular TRSs at selected border posts.

Output Number and Title	1.1. Technical assistance and training to reform trade facilitation laws, procedures, processes, systems, and consultative mechanisms within the context of the WTO TFA is provided to selected MIC countries
Impact Weighting		NA	Score	A

Indicator(s) Baseline Target Achieved Progress / 1.1.1 Number of WTO TFA measures supported in TFMICs countries (#) 0 13-15 14 Article 1.3: India, Philippines / - Article 7.2: Philippines / - Article 7.4: Philippines, India, Nigeria, South Africa / - Article 7.5: India / - Article 7.6: Brazil, Philippines, South Africa / - Article 7.7: Brazil, India, South Africa / - Article: 7.8: Philippines, South Africa / - Article 8: Brazil, South Africa / - Article 10.1: Brazil, Philippines / - Article 10.2: Philippines / - Article 10.3: Brazil / - Article 10.4: Brazil, Nigeria, Philippines, South Africa / - Article 12: Brazil / - Article 23.2: Brazil, Nigeria, Philippines, South Africa / 1.1.2 Number of new laws/regulations/amendments/codes /government policies drafted, or contributed to the drafting (#) 0 7 (Est) 4 • Brazil: / - WBG provided support for temporary Measure 1040, which was approved by parliament and converted in the Law no 14195, 2021. / • Philippines: / - Customs Memorandum Order for Air Express Cargo / • South Africa: / - Amendment to the Customs and Excise Act, 1964 Rules for Section 64E of Act 91, for Accreditation of Clients, to include AEO legislation (came into force 07/23/2021) / - Policy drafted providing for the WCO-Immediate Release Guidelines and TFA 7.8 key elements. The Policy was issued in Customs Memorandum Order ‘Guidelines in the Implementation in the Customs Administrative Order (CAO) No. 05-2020 on Customs Clearance Procedures on Express Shipments’ providing a clear governance structure and establishing directions, predictability and consistency for the courier companies / 1.1.3 Number of procedures/firm-level policies/practices/standards recommended for improvement or elimination (#) 0 9 (Est) 9 Brazil: / - 2021-2022 NTFC Work Plan / - As part of the Single Window development, the project supported the advancement of the catalogue of products. / • India: / - CBIC undertook a restructuring of the PCA organization and reporting system in parallel to TFMICs consultations on the finalization of TORs / • Philippines: / - Joint Memorandum Circular on Digital Payments, and / - Joint Memorandum Circular on the creation of an electronic One-Stop Shop for Covid-related Emergency Medical Importations / - Re-engineered clearance process for Cat 1 & 224 courier shipments. / - Order issued by BOC Commissioner designating the WCO trained National Customs Trade Facilitation Champions to play key role as part of PTFC Secretariat and in coordinating Philippine Government on TFA implementation. / • South Africa: / - Assessment on compliance of the Customs Control Act No. 31 of 2014 (CCA) and the Customs Duty Act No. 30 of 2014 to the WCO Revised Kyoto Convention (RKC) and the WTO TFA / - Re-engineered clearance process for courier shipments aligned with TFA 7.8. / 1.1.4 Number of organizational development recommendations / (Leadership / Management / Development, Human / Resource / Management, Stakeholder / collaboration, Integrity, gender equality and diversity etc.) adopted by relevant customs administration (#) / - out of which A. WCO customs / integrity / recommendations / (#) / WCO gender responsive and / inclusive / recommendations / (#) / WCO Human / Resource / Management / (HRM) / Leadership / Management and / Development / (LMD) tools and policies (#) A 0 / B 0 / C 0 A 15 / B 40 / C 30 A 0 / B 0 / C 0 Overall, deliberation on recommendations will take place outside of TFMICs in light of closing. However, significant preparatory work was undertaken, particularly on diagnostics and custom integration surveys. / Brazil: / Integrity: Customs Integrity Diagnostics and Customs Integrity Perception Survey concluded. Deliberations on RFB action planning to incorporate the findings and recommendations will take place outside of TFMICs in light of closing. / G&I: Deliberations with RFB on recommendations will take place outside of TFMICs in light of closing. / Philippines: / Integrity: Customs Integrity Diagnostics and Customs Integrity Perception Survey concluded and deliberations on the action planning will take place under the HMRC programme. / G&I: Deliberations with Bureau of Customs (BOC) on the issued recommendations will take place under the HMRC programme. / HRM: Deliberations with BOC on their Work Plan following the issued recommendations will take place under the HMRC programme. / South Africa / Integrity: Customs Integrity Diagnostics and Customs Integrity Perception Survey conducted. Deliberations on the action planning based on the findings and recommendations will take place under HMRC Programme. / G&I: Deliberations with SARS on recommendations will take place under the HMRC Programme / • India: / - G&I: Customs assessment finalized. Deliberations on recommendations will take place outside of the TFMICs programme in light of closing. / 1.1.5 Number of TFMICs customs administration country subject specialists trained (out of which # of women) (#) 0 150 92 (36 women) WCO Philippines: / 6 (2) TFA Champions / 23 (11) TFA Article 7.8/WCO Immediate Release Guidelines / 30 (14) TRS / 85 (25) Risk Management / WCO South Africa: / 10 (03) TFA Article 7.8/WCO Immediate Release Guidelines / 23 (06) TRS / 1.1.6 Number of baseline Time Release Studies (TRS) completed (#) 0 5 3 Brazil: TRS completed and launched in June 2020 / India: JNCH TRS 2019 was validated for baselining purposes. / Philippines: support review of the TRS 2020 on 5 sea ports/container terminals. / South Africa: Capacity Building to TRS Working group and sub-working groups took place, working towards SARS leading 6 TRSs across 6 border posts. First 2 TRS to take place in February 2022. Follow-up support will take / Place. / 1.1.7 Number of end program TRS completed (#) 0 5 0 N/A / 1.1.8 Number of WTO TFA gap analysis reports completed (#) 1 9 (TBC) 3 Brazil and the Philippines have finalized TFA gap analysis reports. / Nigeria: Baseline Gap analysis completed pre-TFMICs / 1.1.9 Number of in country WBG gender reports and WCO customs gender equality and diversity organizational assessments completed (#) 0 Est. 10 7 WBG: Trade and Gender Study completed in Brazil, the Philippines, and South Africa. In India, the TOR is finalized and industry consultations with FICCi were held. / WCO: Customs Gender Equality & Diversity assessments completed for India, Brazil, the Philippines, and South Africa. / 1.1.10 Number of in country studies on impact of trade facilitation measures on poverty and inequality completed (#) 0 Est 3-5 1 Brazil: The Brazil poverty impact assessment has been completed, notably with a narrower scope than initially planned due to program closure. / 1.1.11 Number of country-level events delivered and/or facilitated by TFMICs (including trainings and workshops, etc.) (# of which are gender- 0 Est 20-21 36 Brazil: (5) / WBG/WCO: Live de Lançamento do TRS – June 30, 2020. / WBG: Webinar Time Release Study- July 15, 2020 / WBG: Presentation of TRS findings- June 5, 2020 / WCO: Integrity Executive Kick-off - December 2020 / WCO: GED assessment completed for RFB in April 2020 over multiple sessions / Nigeria: (6) / WBG: Trade Facilitation (1 workshop) / WBG: National Single Window – including a subtopic on border agency collaboration (3 workshops) / WBG: Risk Management (2 workshops). / Philippines: (11) / WBG: Webinar on Trade Facilitation and the Roles of Customs Brokers, Jan 29, 2021 co-hosted by Chamber of Chamber of Customs Brokers Inc. (CCBI) and the Academy of Developmental Logistics. Total of 409 online participants. / WCO: TRS two-day workshop & 06 capacity / building sessions / WCO/WBG - 1 training on TFA 7.8 (12 sessions spread over multiple months) / WCO/WBG: Training on Risk Management / (Workshop in November 2020) / WCO/WBG: Risk Management Fact Finding mission in December 2020 / WCO/WBG: two-day virtual Risk Management Workshop to BOC focusing on database management and data analytics, 12-13 August 2021 / WCO GED assessment completed for BOC in November 2020 over multiple sessions / WCO: HRM Diagnostic completed over 10 days in March 2021. / WCO: Training for National Customs Trade Facilitation Champions November 2020 –June 2021 / WCO: Integrity Diagnostics over multiple sessions, including high-level kick-off and closing, August- / September 2021 / WCO: Customs Integrity Perception Survey July- / August 2021, including promotional campaign. / South Africa: (13) / WCO/WBG event on Risk management – February / 27 / WCO/WBG event on AEO – March 2/3 / WCO/WBG - 1 training on TFA 7.8 (12 sessions spread over multiple months) / WBG: SA Agency presentations on risk and compliance and developing a single government workplan approach - March 10-12. / WBG: Benchmarking sessions with New Zealand Customs Services –2 sessions in October 2021. / WBG: The TRS peer learning with Brazil customs – September 6, 2021. / WCO: TRS: Workshop (05-06 October 2020) / WCO: TRS virtual capacity building sessions (08 Oct, 14-15 Oct 2021, and 17 Mar, 22 Mar, 13 April 2021. / WCO: WTO TFA 7.8 consisting of 12 sessions virtual capacity building sessions. / WBG: Workshop with the private sector on National Single Window in South Africa – September 16, 2021. / WCO: GED assessment completed for SARS in August 2020 over multiple sessions / WCO: Integrity Diagnostics over multiple sessions, including high-level kick-off and closing with participation of the private sector, May-June 2021 / WCO: Customs Integrity Perception Survey March April 2021, including promotional campaign. / India: (1) / WCO GED assessment completed in June 2020 over multiple sessions / 1.1.12 Number of completed in-country validation scoring sheets, in accordance with the WTO TFA tracking tool methodology (#) 0 Est 19-20 4 Brazil and the Philippines scoring sheets completed as of October 31, 2021. / Nigeria scoring sheet was completed pre-TFMICs. / All three scoring sheets are uploaded to the TFA Tracking Tool website WBG: A four-day peer-to-peer event for all five TFMICs countries on efficient NTFCs – April 6, ,7, 13, and 14, 2021. The event had 147 public and private sector participants. / WTO-WBG event ‘Trade Facilitation: Critical for Covid-19 recovery” – March 25, 2021. / WCO: “Global Webinars Series: Managing Human Resources through Crisis and Beyond”, 19-21 January 2021 - 400 participants / WCO: Launch ‘Compendium Gender & Diversity in Customs’ on International Women’s Day, 8 March 2021.

Output Number and Title	1.2. Global knowledge, learning and measurement products are generated for MICs
Impact Weighting		NA	Score	B

Indicator(s) Baseline Target Achieved Progress / 1.2.1 Number of global and regional events delivered (e.g. peer-to-peer, learning events, webinars) (#) 0 Est 19-20 4 WBG: A four-day peer-to-peer event for all five TFMICs countries on efficient NTFCs – April 6, 7, 13, and 14, 2021. The event had 147 public and private sector participants. / WTO-WBG event ‘Trade Facilitation: Critical for Covid-19 recovery” – March 25, 2021. / WCO: “Global Webinars Series: Managing Human / 1.2.2 Percentage of female participants in events (%) N/A 30-40% 45% (NTFC event) WBG: / The four-day NTFC event had 65 female participants (out of 147) / WTO-WBG Event was open to public, thus information on the gender of participants is not available. / WCO: Due to the remote nature of the events and multiple participants of the same administration joining from one location through the same connection, information on the gender of participants is not available / 1.2.4 Number of communications materials developed (e.g., videos, blogs, brochures, / newsletters, etc.) (#) 0 1 1 Enhancement of the methodology has been completed and includes a whole-of-government approach which enables the evaluation of a particular border agency’s implementation of TFA measures. / 1.2.5 Enhancement of the time release study methodology completed (Y) N Y Y The WBG and WCO have finalized an enhanced methodology for the TRS to not only look at clearance and release processes at the border, but also at the regulatory processes away from the border. / 1.2.6 Flagship reports on best practice of trade facilitation interventions completed (#) 0 2 0 Due to TFMICs closing, work in this area was put on hold. / 1.2.7 The number of users that completed the WCO e-learning modules on Trade Facilitation measures, as well as Customs organizational development (for example Gender / Equality in Customs and Integrity (#) 0 860 400 Brazil (24) / India (182) / Nigeria (34) / Philippines (132) / South Africa (28) / E-learning courses on Coordinated Border Management, PCA, TRS, Risk Management, Gender Equality & Diversity, LMD and the WTO TFA / 1.2.8 Number of customs officials trained as global pre-accredited or accredited experts (out of which # of women) (#) 0 12 0 N/A as this was planned for end 2021 onwards and not pursued in light of TFMICs closing.

Brazil IPO Outputs,

The Brazil IP Programme goal was to support Brazil in improving the management of Intellectual Property Rights by implementing targeted interventions that would bring the country closer to international standards and practices in this sector. This programme was delivered by Palladium, in collaboration with INPI, and supported by the UK IPO. Results equipped Brazil National Patent Office (INPI) with knowledge and tools to support future modernisation of processes and increase office efficiency, leading to a reduction in the time taken to process applications, a reduced backlog and an improved IP management service.

The Brazil IP project logframe underwent significant changes in light ODA reductions and the ongoing pandemic. Indicators at the Impact and Outcome levels were discontinued and changes were made to the indicators and milestones at the Output and Intermediate Outcome levels to align better with the revised scope, workplan, budget and timeline for the programme. Despite the various changes, the Brazil IP programme was able to achieve (or in some cases, overachieve) all milestones against its output indicators. The programme has scored an ‘A’ in delivery on revised outcomes.

The implementation of the programme involved close collaboration between Palladium and INPI, with UK IPO playing a key role as ‘critical friend’ and quality assurer which was greatly appreciated by delivery partners. The project focused on 3 workstreams: processes, pricing and IT, as outlined in objectives 2-4 below. In addition, there was a gender and inclusion component, where assessment led to the proposal to establish a cross departmental committee on gender equality and social inclusion to institutionalise GESI sensitivity in decision making and activity planning.

Output 1: Discontinued as a result of revised scope post-ODA reductions.

Output 2: Achieved - The Process Workstream delivered six reports to INPI with specific recommendations to improve 6 macro processes: (i) Logistics and Infrastructure, (ii) Trademarks, (iii) IT, (iv) Budget and Finance, (v) Patents, and (vi) International Patents. All information reflected in the reports came from discussions between internal and external stakeholders during mapping workshops for each of the macro processes.

Output 3: Achieved - Time Driven Activity Based Cost (TD-ABC) methodology and cost tables were implemented and approved by INPI for 4 macroprocesses (Industrial Design, Trademarks, Patents, and International Patents) relating to the Service Pricing Policy workstream.

Output 4:- Achieved - All 4 reports delivered by the IT Workstream, including an IT Service Catalogue report (including identification of 168 IT services) and strategic plan for the IT department were approved by INPI.

Output Number and Title	2. Process Management System Workstream
Impact Weighting		NA	Score	A

Indicator(s) Baseline Target Achieved Progress / 2a Number of As-Is and / To-Be processes for INPI macroprocesses mapped 0 6 as-is, 6 to-be, 6 implementation reports 6 as-is, 6 to-be, 6 implementation reports 6 as-is processes mapped, one for each macroprocess, / and 6 to-be processes mapped, with 6 implementation reports with recommendations to implement and / possible challenges highlighted. / 2b Number of macroprocesses for which use journey maps are developed, including considerations to improve G&I sensitivity 0 6 6 Delivered for all 6, with recommendations based on / input for users at all stages of the customer journey through INPI products.

Output Number and Title	3. Service Pricing Policy Workstream
Impact Weighting		NA	Score	A

Indicator(s) Baseline Target Achieved Progress / 3a Number of macroprocesses for which cost tables were developed for all services under the macroprocess 0 4 4 The TD-ABC methodology and cost tables will support the INPI in calculating its costs per service annually or longer periods, as needed. INPI teams were provided hands-on training by the Pricing Workstream during the development of the methodology and finally through 4 training workshops. / 3b Framework for Pricing developed and recommended to INPI 0 Y Y Excel simulators produced allowing INPI to calculate prices for their four macroprocesses, setting parameters for discounting, subsidisation etc.

Output Number and Title	4. IT Service Workstream
Impact Weighting		NA	Score	A

Indicator(s) Baseline Target Achieved Progress / 4a Number of reports and/or strategic documents drafted and submitted to INPI IT department 0 3 4 By-laws for the IT Governance and IT information / security committee developed, strategic plan for the IT / department delivered, and IT services catalogue / produces, providing a roadmap to INPI for best practice / in IT procedures and compliance with regulation/legislation.

Vietnam NTR, Outputs

The Vietnam National Trade Repository (VNTR) programme has delivered a trade portal, as requested by the Vietnamese Ministry of Industry and Trade (MOIT), which will provide easier access to trade regulations and information. The portal, which will be linked to the ASEAN Trade Repository, will increase the level of compliance with legislation & regulation; increasing the speed at which business is transacted and reduce costs. The portal will therefore support businesses with a particular focus on Micro, Small and Medium-sized Enterprises (MSMEs) and women-owned enterprises (WOE).

The programme was delivered by Nathan Associates, in collaboration with MOIT, with outputs met to a high standard. VNTR, which has scored an ‘A’ against outputs, ended on 1 July 22, and a transfer agreement has been agreed between the UK and MOIT to facilitate uptake and sustainability of the portal.

Output 1 – This indicator has been met. The supplier engaged with MOIT on the design and build of the VNTR at the beginning of the project, and both parties have collaborated successfully and maintained effective communications over the project lifecycle. As beneficiary, MOIT have played an important role in quality assuring deliverables which will support the longer term sustainability of the portal. The supplier has also performed well bringing private sector groups such as HAWASME and BritCham into the design and build of the trade portal and involving focus groups and local businesses during the user testing phase.

Output 2 – This indicator has been met. The content for VNTR was agreed during the design phase with all of the relevant information uploaded for the public launch of the portal in March 22. The supplier has collaborated well with MOIT to build capability to ensure that the portal can be maintained successfully in the longer term.

Output 3 – This indicator has been achieved with MOIT submitting feedback and change requests during the iterative design and build of the portal that were met and accepted.

Output 4 – The Supplier has established a publicity strategy that generated awareness and interest in the portal. This has included social media campaigns, a public launch event with invited national media and roadshows to highlight the trade portal. In addition, the supplier has worked with various stakeholder groups to amplify its messaging amongst the business community in Vietnam and the UK.

Output Number and Title	1. MOIT and other official and private sector stakeholders are actively engaged in the development of the VNTR platform.
Impact Weighting		25%	Score	A

Indicator(s) Baseline Target Achieved Progress / 1.1 Number of interactions on the VNTR with the MOIT Operational Project Team. 0 28 27 Interactions with the MOIT team proceeded according / to schedule across the project / 1.2 % of ministries that engage with MOIT in the development and promotion of the VNTR. N/A 55% of ministries engaged at least once 64% Higher than planned engagement with stakeholder ministries in Vietnam was achieved / 1.3 Number of meetings with representatives of different private sector stakeholder groups (including representatives of women-led enterprises) on the VNTR. 55 61 After conducting a mapping exercise to identify stakeholder groups in UK/Vietnam Private Sector, a contacts database was created, and a higher number / of stakeholders reached than originally targeted.

Output Number and Title	2. MOIT accepts VNTR Information Governance Framework to allow for ongoing content delivery and updating on the VNTR platform.
Impact Weighting		25%	Score	A

Indicator(s) Baseline Target Achieved Progress / 2.1 % of content identified for upload onto the VNTR platform. 0 100% 100% A content catalogue was compiled by the end of Q1, and by Q3, 99% of content was agreed and identified for upload, in advance of schedule.

Output Number and Title	3 VNTR platform system is set up in line with MOIT and ASEAN ATIGA requirements.
Impact Weighting		25%	Score	A

Indicator(s) Baseline Target Achieved Progress / 3.1 Number of rounds of feedback/change requests between MOIT and the IT firm. 0 10 26 10 rounds of feedback were targeted, spread linearly throughout the programme lifecycle. An intensive period of review in fact occurred happened in Q2-3, with a total of 26 rounds recorded by Q4 (Nov 21), at which point this process concluded

Output Number and Title	4 VNTR publicity strategy effectively creates momentum to raise awareness among VNTR target users in Vietnam, the UK and worldwide.
Impact Weighting		25%	Score	A++

Indicator(s) Baseline Target Achieved Progress / 4.1 Number of target users from Vietnam and the UK reached through various awareness raising activities under the VNTR publicity strategy (data will be disaggregated country of origin and by women-led enterprises reached in Vietnam whenever possible). 0 5000 target users reached 16,787 Programme outreach and PR proved highly effective, with 16,787 end users by June 22. 8,506 were logged by Q1, well in advance of target of 500, reflecting impactful early promotion and initial publicity, and a steady stream of ongoing engagement throughout programme lifecycle including several public events and an active social media presence.

Trade Forward Southern Africa, Outputs

Output 1 - The indicators relating to TFSA-supported outreach have been broadly met. The TFSA Info Hub www.tfsouthernafrica.org was launched in October 2020 and re-launched in October 2021 to provide an enhanced user experience. Traffic to the TFSA Hub site increased significantly in Q4 21/22 due to an online marketing and social media campaign, with a peak of 4,290 unique users achieved in Jan 22, the largest increase being from users from the target SACU+M countries. Work is being undertaken to build on this performance to ensure repeated visit/continued use. Alongside this, 48 BSOs have been identified as potential knowledge centres, hosting TFSA resources, facilitating training and outreach, and promoting TFSA. All 48 are featured on the TFSA Hub. Feedback indicates that the Hub presents a high quality, accessible and sustainable trade and information support offer for SACU+M businesses that provides value for money in the long term. To date, 1,629 participants attended TFSA led or collaboration virtual events, succeeding targets by more than 50%.

Output 2 - Export training, initially championed via the TFSA Women in Trade Initiative, has been successfully designed and launched. This was piloted in South Africa in partnership with UK-SA tech hub and the Future Females initiative, enabling 34 of 44 inducted learners to complete the 10 week TFSA Export School Training, supported by 7 business management modules coaching and business expert consultations. The full Export School is available online via the TFSA hub. The success of the pilot in South Africa has proven the concept, with the scaling of the Women in Trade Export Training to all 6 SACU+M countries in Year 2, a further 116 of 134 participants successfully completed the training, with a total of 172 trainees accessing the 7 modules produced to date.

Output 3 - TFSA has provided standards and compliance training in the 6 TFSA priority value chains (fruit, nuts and veg, cosmetics, natural ingredients, aquaculture, green tech/renewable Energy, and speciality ingredients), working with 18 BSOs across SACU+M on 15 different interventions with further interventions planned through additional Calls for Proposals in Year 2. The BSO’s have been drawn from a wide range of sectors in SACU+M countries.

Output 4 - Though originally outside TFSA’s scope of work, the Covid-19 pandemic presented both the need and the opportunity for expanding the work of TFSA to include some limited support to policy reform at the national level.  From this, 3 assessments were conducted in Namibia, Lesotho, and Mozambique to improve the ability of governments, through trade reforms, to address trade in the Covid-19 environment. All assessment recommendations connected to this output have been accepted, for example-in September 2021, the Govt of Mozambique confirmed they will adopt the C19 Business Recovery Strategy produced under the TFSA programme. Plans to launch in November were delayed due to external factors but took place on the 5th April.

Output 5:- A 5th TFSA output - Capacity built and technical knowledge transferred on EPA standards – has not been reported on in this PCR as it was not funded by GTP.

Output Number and Title	1 Business in SACU+M have increased access (ensuring Women in Trade equity) to enabling resources for trade information and trade promotion.
Impact Weighting		25%	Score	A

Indicator(s) Baseline Target Achieved Progress / Short-term: Utilisation of the Website (Level of website traffic) 0 900 users per month/ 2 minutes 1787 per month Exceeded. / 1 Nov 2020-17 Aug 2021 / 250 (new and returning) users per month/ 3minutes / 1-31 Jan 2022 / 4290 users per month/ 2 minutes 04 seconds / (New users- 2115, Returning users-2175) / 1-28 February 2022 / 661 users per month/ 3 minutes 04 seconds / (New users =297, Returning users=364) / 1-31 March 2022 / 411 users per month/ 0 minutes 58 seconds / (new users=207, Returning users=204) / Short-term: No. times resource page (Export Knowledge Guides, Export Toolkit, Reference Library, External Training Resources) is accessed on the hub 0 600 times per month 98 per month Not met. / 1 Nov 2020-17 Aug 2021 / 344 times / 1-31 Jan 2022 / 371 times (Export Knowledge Guides= 90, Export Toolkit = 95, Reference Library= 88 / External Training Resources=98) / 1-28 February 2022 / 176 times / (Export Knowledge Guides= 42, Export Toolkit = 35, Reference Library= 40, / External Training Resources= 59) / 1-31 March 2022 / 49 times / (Export Knowledge Guides= 12, Export Toolkit = 15, Reference Library= 11, / External Training Resources= 11) / Intermediate: No. of TFSA led or collaboration events requiring material inputs 0 10 events per annum 13 Exceeded. 13 events - a breakdown of the list of events can be found in the Operational Review / (5 TFSA led webinars, 3 additional events and 5 TFSA-JCCI collaborated events) / Intermediate: / No. of participants attending the TFSA led or collaboration events requiring material inputs 0 1000 participants 1629 Exceeded. 1629 participants – a breakdown of participation by event/ sex/ country can be found in the Operational Review / Participants by TFSA or JCCI / (TFSA webinars=1185, TFSA Intra African Trade Fair breakfast event= 108, / TFSA Africa Energy Indaba event= 12, TFSA/JCCI Trade Power Days= 444 participants) / Intermediate: No. of external trade activation events TFSA participated in 0 20 external trade activation events 20 Completed. 20 events – a full list of the events can be found in the Operational Review

Output Number and Title	2 Improved understanding of export procedures and processes, including those that pertain to the UK EPA.
Impact Weighting		25%	Score	B

Indicator(s) Baseline Target Achieved Progress / Intermediate: No. of times training modules are accessed in the Learning Management System (LMS) by trainees / No changes to indicator 0 1500 times per annum 1253 Partly completed. / 1253-times (172 enrolled trainees) - a breakdown of the list of events can be found in the Operational Review / Trainees who graduated / 34 women, South Africa (WIT pilot) / Intermediate: / Increased understanding of export training by trainees 0 80% report increased understanding (Y1/2) 100% Completed. / 34 women completed the training / 21 of those women (62%) responded to the survey / Of the 21 women who responded, 100% said that they had an increased understanding of export after the training / Intermediate: % of trainees who report applying their new skills 3-months after their training 0 40% report applying skills (Y1/2) 41% Completed. / 14 women (41%) responded to the question positively. / Intermediate: No. of Women in Trade (WIT) BSOs delivering TFSA the exporter training via the School of Export in SACU+M countries 0 8 WIT BSOs 6 Partly completed. / 6 WIT BSOs / -Future Females- Regional (covering South Africa, Botswana, Namibia, Lesotho, and Mozambique) / -Minori Skinfield- Namibia / -Africa Women in Business – Regional (covering Botswana, South Africa, and Mozambique) / -Akoma Tradings – Namibia / -Association of Women in Small Business – Lesotho / -SWIFT – Eswatini / Intermediate: No. of participants reached through WIT BSOs TFSA exporter training via the School of Export in SACU+M countries 0 120 participants 168 Exceeded. / 168 participants total / 34 graduated from South Africa pilot, / 134 enrolled for the first cohort of training from the 6 SACU+ M countries in March 2022.

Output Number and Title	3 Increased capacity of BSOs in selected sectors and Value Chains to overcome barriers to export.
Impact Weighting		25%	Score	B

Indicator(s) Baseline Target Achieved Progress / Intermediate: / No. of Business Support Organisations in value chains receiving TFSA Short Term Technical Cooperation(STTC) whose members report improved ability to address barriers to trade as a result of TFSA Technical Assistance/Capacity Building 0 18 BSOs 18 Partly completed. / 18 BSOs are contracted and in implementation. / (Business Botswana (BB), Natural Products Association Botswana (NPAB), NAMBOARD, SWIFT, Association of Women Small Business, LCCI, Lesotho National Wool and Mohair Growers Association, SMME network, AMAQUA, FRUITSUL, NANCI, CECOSO, CITRUS Growers Association, Eastern Cape Development Assoc., NAMC – SAMAC, Raisins SA, SAEEC, WESGRO) / Intermediate: / No. of interventions implemented in selected value chain through TFSA assistance 0 15 15 Partly completed. / 15 interventions are contracted and in process. These include 11 training interventions on standards/ compliance and 4 on addressing specific barriers to trade, including duty exemption guidelines, product testing for certification in the cosmetics and speciality food sectors. Implementation will involve collection of samples and drafting of technical applications for a certification, then samples will be sent for approval in the coming months.
Output Number and Title	4 Improved ability of governments, through trade reforms, to address trade in the Covid-19 environment
Impact Weighting		5%	Score	A

Indicator(s) Baseline Target Achieved Progress / Intermediate: / Strategy report validated and accepted by the relevant country focus ministry. 0 3 3 Completed. / 3 strategies were completed (Namibia, Lesotho, and Mozambique), validated and accepted by the relevant focus ministry. / 4.2 No. of assessment recommendations recognised as priorities by the government. 0 5 0 None.

Mexico Better Regulations – Achievements (no logframe available)

The FCDO supported the World Bank to deliver a technical assistance project in Mexico that focused on policy responses during the Covid recovery phase to reignite growth, investments and well-functioning markets. The goal was to strengthen Mexico’s business regulatory environment to boost competition, trade and investment by supporting CONAMER (the National Commission for Better Regulation) with the design and implementation of SINAGER, (Mexico’s National System for Regulatory Governance). Through this engagement, the WB aimed to ultimately support competitive firms return to their pre-crisis production and employment levels and set the foundations for longer-term productivity-driven growth.

Although the budget and lifecycle was impacted by ODA budget reductions (closed early, and a formal logframe was not developed), the programme successfully adapted to its new operational context.

SINAGER is an innovative digital platform to manage and improve the way business regulations are undertaken. In Mexico, SINAGER is enabling all three tiers of government (federal, state and municipal levels) to improve regulation by bringing predictability, transparency, participation, evidence and uniformity to the regulatory process. The Mexico Better Regulations programme activities were organized around the design, development and integration of each of the four better regulation tools comprising SINAGER:

1. Regulatory Agenda, which allows for the planning of regulatory changes by publicly announcing them six months before they are introduced. This creates transparency and predictability of the regulatory environment.

2. Ex Ante Regulatory Impact Analysis (RIA), which uses evidence to assess the expected impact of new regulation and possible alternatives, usually evaluated by their costs and benefits.

3. Better Regulation Programs, which promote actions to improve the current regulatory framework, by simplifying or reducing regulatory burdens and red-tape. This is one of the most visible tools as it focuses on improving regulatory requirements and administrative procedures that businesses and citizens have to comply with currently.

4. Ex Post Regulatory Impact Analysis or evaluations, which are conducted 5 years after business regulation has been implemented, with the purpose of evaluating whether it has achieved its intended objectives. This is important as many business regulations become outdated or simply inadequate because original conditions have changed public policy objectives were not met.
The programme was successful in delivering 3 key stages of the programme:-
- The Programme undertook a conceptual design of the four tools based on existing definitions, the regulatory framework, diagnoses of the operational environment, as well as their integration with other SINAGER tools;
- A technological design of the visual characteristics and requirements of each of the tools, so they could be understood by the software developers in charge of creating SINAGER as a digital platform;
- WG then transformed each of the tools that comprises SINAGER into a digital platform.

Lessons included:
The programme highlighted the importance of strengthening government functions to improve the quality of the regulatory environment – a key gap resulting in significant burdens for business and inhibiting growth, trade and investment.

In particular it showcased the need and opportunity to support business reform at both national and sub-national (e.g. state, municipality) levels. The project adapted its design to enable states and municipalities – at various stages of capacity – to gradually incorporate tools depending on capability. Due to the free-access nature of the platform, some states may be able to leapfrog and build capacity in a cost-effective way. Municipality of Queretaro was able to reduce by 55% the time and administrative procedures citizens and business face when dealing with the municipal government, representing a reduction of the municipality’s regulatory burden of around US$300 million, after implementing only one of four SINAGER’s tools.

High-technical capacity of CONAMER was critical to success of programme, along with a team of local consultants who facilitated interaction and exchanges with CONAMER and the WBG.

D: Risk

The scale, timeframe and ambition of the programme, combined with its complexity, made the GTP a high risk programme to deliver. Over the last two years, the most significant risks, as outlined below, were financial and delivery risks as a result of the ODA reductions which then resulted in early closure of the programme and the majority of its components.

The 2020 Annual Review reported that the GTP's processes in relation to risk were generally robust and in line with Joint Funds Unit (JFU) guidelines. Before the Service Manager contract ended in June 21, a monthly process, coordinated by the Service Manager, was used to identify new risks and issues which were then logged on the GTP Portal (Programme management information system). All risk and issues were reviewed centrally before being escalated to the appropriate governance body (Operations Committee / Programme Board) for action. Risk registers were also maintained at intervention level.

The GTP throughout its duration held a number of strategic, delivery and external risks, at programme and project levels. At the time of closure 25 of an estimated 142 risks throughout duration of the programme remained open. Key risks focused on financial (due to decreasing budget); impact (recognising interventions may not achieve anticipated levels of benefits or returns); and external context (managing response to the pandemic). Throughout the course of the programme, risks related to the complexity of programme design and related impacts on delivery; stakeholder and partner relationships for paused and cancelled programmes; and sustainability of interventions post-programme, were acknowledged but perhaps underestimated.

Evidence suggests that the programme could have been more proactive in managing VFM prior to ODA re-prioritisation. The 2019 and 2020 ARs recommended that the programme establish a VFM framework to accompany results interventions, and noted it was increasingly important to monitor the contractor‘s progress against key milestones given ambitious plans for scale up.

ODA budget reductions both in 2020 and in 2021, generated new financial and delivery risks for the programme. Delivery partners played a major role in supporting the FCDO during this period by adjusting delivery plans and contracts at very short notice, which enabled the GTP to operate within significantly reduced budget limits. Through effective collaboration with suppliers, programmes have continued to deliver outputs while gradually managing down programmes (i.e. Brazil IP, TFMICs, and Mexico Better Regulations). This has reduced the impact of exit / sunk costs.

In addition, after closure of the Service Manager contract, the FCDO GTP programme team, together with the Service Manager, posts, and other delivery partners successfully managed the risk of disruption resulting from (i) the transfer of Service Manager responsibilities back to FCDO; and (ii) the transfer of some programme responsibilities from the centre to post. When notice was served on the Service Manager contract, EY colleagues worked collaboratively with the GTP to manage the successful handover of financial management, project management (including risk) and customer representative responsibilities with no or limited adverse impact on the live interventions. Those former Service Manager functions were moved to be managed by FCDO, drawing on departmental wide Commercial and IT expertise.

A key risk focused on over the last year was programme sustainability. The success of the Vietnam National Trade Repository will depend on whether the portal is maintained with the most up to date trade details (including HS codes). To mitigate this risk, the programme’s Delivery Partner and colleagues at post have ensured that the programme beneficiary, MOIT, have been involved from the outset in the VNTR design and a transfer agreement has been signed to help in facilitating commitment for uptake. The Brazil IP programme has applied a similar approach to sustainability by ensuring the involvement of key stakeholders throughout the programme cycle.

## E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and the programme team notably on commercial and financial issues and including VfM measures of economy and efficiency.

Economy

The GTP has endeavoured to ensure ‘economy’ through the procurement of inputs (through use of competitive tendering processes), effective use of those inputs, risk identification and mitigation, and cost containment measures.

Third party suppliers responsible for the direct delivery of the Flexible Fund programmes (Brazil IP, TFSA and VNTR) were procured by the Service Manager via the Prosperity Fund Procurement Framework, which provided a pricing mechanism and a spend ceiling for all goods or services. Contractual arrangements with multilateral agencies included (i) an Administration Agreement (WBG) and an Accountable Grant (WCO) in relation to TFMICs; (ii) an Externally Financed Output arrangement (Mexico Better Regulations); and (iii) MoUs (UKTP). HMG-managed support to CODEX was also delivered via a MoU.

The Service Manager, EY, was appointed through a competitive process completed in April 19. GTP design and delivery involved outsourcing operations to an external supplier(s) with trade, legal and academic expertise. The Service Manager was responsible for day-to-day programme management of the GTP on behalf of the FCO, and for leading the design and build, and management, of the Flexible Fund component. The Service Manager was envisioned to play a central role in GTP implementation, advising on strategy, design, and operation of the programme and the intervention project pipeline; assisting in building a strategic and coherent approach across the programme; and help mobilise a large and complex portfolio more quickly. FCO, at the time of design, did not have in-house staff with the relevant experience and expertise (policy, programme, commercial) to manage an ODA programme on this scale. As outlined in the Business Case, it was expected this model would allow HMG’s trade policy expertise to focus on other post-EU Exit trade priorities; and that this approach would support the longer-term development of in-house capability and skills, which would reduce future reliance on external resource.

This approach, however, required a significant proportion of the total programme budget to be dedicated to central design and advisory costs relative to programme implementation.

The GTP adopted a design and build approach to developing its Flexible Fund portfolio, which involved:
- research and analysis, and development of Country Plans, to identify the interventions that were likely to have the most significant primary purpose and secondary benefits;
- developing those initial ideas into (i) New Project Concepts and then (ii) Business Cases;
- procuring a delivery partner; and
- implementation of interventions.
As described earlier, the majority of the Service Manager-led Flexible Fund projects did not make it to procurement or implementation stage as they were paused and subsequently cancelled due to ODA reductions.
The programme allocated £40m of its overall budget to the categories of ‘Research & Analysis,’ ‘Access and Enabling’, and (Service Manager) Management costs. This spend included the ‘design and build’ costs research and analysis, Country Plans, NPCs, business cases, and procurement. These costs were frontloaded in the programme to develop the GTP to the £150m scale anticipated in the Business Case, with the aim of getting interventions designed, procured and implemented as early as possible. However, delays in finalising and approving business cases, followed by ODA reductions, led to disproportionate costs for design and development, when compared to delivery of interventions, particularly for the Flexible Fund activities. This is covered in more detail in the Effectiveness section.
Cost Containment

There is evidence to demonstrate that the GTP has adjusted its resources in response to changes to the operational context (and therefore contained costs) during the lifecycle of the programme. Examples include:

- Programmes successfully pivoted to online platforms to deliver technical assistance during Covid, and reduced travel costs have resulted in savings;
- When it became apparent that ODA budget cuts would limit the number of live interventions, the GTP worked with the Service Manager, within the constraints of the contract, to scale down the core Service Manager team responsible for delivering activities including financial management, communications, information management etc. This ensured services were more proportionate to the reduced portfolio and resulted in cost savings;
- Further savings were achieved when the Service Manager revisited the methodology used to charge for services in support of live interventions;
- FCDO worked with suppliers to adapt to, and exit from, contracts in a managed way which reduced sunk costs, and supported programmes to have clear outputs that could be used by partner countries. This has supported longer-term sustainability; and
- Ending the Service Manager contract in June 21, shortly after ODA reductions were announced.

Efficiency

Overall, GTP was a complex programme of which costs included: (i) delivery of the three main delivery components (Flexible Fund; TFMICs, UKTP); (ii) Service Manager involvement in inception, Flexible Fund design and build, and overall management of the programme; and (iii) in-house management costs for delivery.
As described earlier, due to the early closure of the programme, and the limited number of country Flexible Fund interventions, the scale of ambition on reaching outputs (and outcomes) was not met. ‘Research and Analysis’ and ‘Access and Enabling’ costs were disproportionately high to outputs achieved. Still, despite early closure and reduced budgets, the programme as a whole did yield some useful discrete country level outputs towards trade facilitation and customs modernisation (TFMICs); modernisation of intellectual property processes (Brazil); regulatory reform and digitisation (Mexico, VNTR); and support for businesses to trade with the UK and elsewhere (TFSA, and UKTP).
The design of the programme itself always had high frontloaded inputs with the aim of getting country level interventions up and running quickly. However, this did not always happen, and a number of lessons are useful for future programming:
- Although the initial Business Case was approved in 2017, the procurement of the Service Manager was only finalised in April 19, two years into the GTP programme lifecycle. The programme design did not adequately consider timescales involved;
- Prior to the Service Manager’s appointment, FCO initiated work on four pilot projects to fill the gap. Part of the Service Manager’s role was to ensure coherence of the GTP programme which involved reviewing, and in some cases adapting, analytical work that had already been produced by post. This led to some frustration and perception of an unnecessary duplication of effort at the beginning of the Service Manager contract. Clarity on roles and responsibilities, and more hybrid management approaches may have been useful;
- In some cases, Country Plan and NPC analysis produced by the Service Manager received pushback at the quality review stage. One concern raised by FCDO reviewers was that the analysis produced was too London-centric and did not adequately capture the in-country view. The benefits data included in Economic Cases also came under scrutiny. Similarly there were concerns regarding a lack of clarity on what was required for Business Case approval. Delays ensued, adding to time and costs. Efforts were made to streamline and standardise processes, e.g. a change request was produced in August 19 setting out the level of detail required in NPCs. However, delays, combined with ODA reductions, led to only 3 Service Manager-led Flexible Fund interventions reached the delivery phase.
Although GTP business case assumed that Advisory Costs would initially be high and would scale down in comparison to Delivery Costs over time, it is unclear how the FCO and the Service Manager were monitoring VFM in the period prior to interventions going live. With the benefit of hindsight:
- it may have been more prudent to focus on scaling up fewer interventions before spreading the net wider over a longer time period. This would have been in line with FCDO guidance supporting adaptive programming which recommends:- testing key assumptions and understanding how to use the evidence from that testing to target resources on what works’.
- adopting an alternative contractual approach after the inception phase (i.e. using a milestone based / payment by results approach rather than Time & Materials) may have led to a more efficient process yielding better VFM.
The GTP Business Case set out that the programme would need to adopt a flexible and adaptive approach to maximise impact and value for money. It was ultimately not possible for the GTP to be adaptive in the manner described due to the lead-in time required to get the programme up and running (including the production of the GTP Business Case and the appointment and procurement of the Service Manager) and the subsequent reduction and closure of the programme. Although the GTP struggled to produce a delivery model to manage a programme on this scale whilst delivering at pace, it could be argued that, even without Covid impact and subsequent budget cuts, the ambition to spend £150m within the allotted 4 year timeframe (on small technical assistance projects) was overly optimistic.

Lastly, while the GTP consisted of three programme delivery components (Flexible Fund, TFMICs, and UKTP) that were all contributing to tackling the priority NTBs, these workstreams remained predominantly discrete even before ODA reductions. Interactions between components remained limited, and opportunities for more sharing of lessons (e.g. on trade facilitation / customs/ standards) could have been strengthened. This was exacerbated with ODA reductions, but as a result, the programme remained a compilation of its components rather than capitalising on the benefits of being a global programme. It is hoped that some of the projects continuing under different governance schemes, the creation of the Trade Centre of Expertise, and communication of some of the results achieved can support wider sharing of lessons.

Programme Management

A central FCO GTP Programme Management Office (PMO) oversaw and managed the programme, and the Service Manager contract. This was a new and innovative arrangement for the FCO requiring specialist programme management and commercial skills and expertise. The team had a skills gap in this area, relied on external contractors for support, and also experienced a heavy turnover in staff throughout the duration of the programme, including four SROs during the programme lifecycle.

Programme management responsibilities were also outsourced to the Service Manager including project and portfolio management; financial management of the overall programme; management information; procurement and contract management with Flexible Fund commercial delivery partners in country; MREL; project risk management; benefits management; and stakeholder management and communications. The PMO and Service Manager worked to create a one-team ethic at the beginning of the programme, sharing office space and collaborating via team building events and workshops. Weekly calls with the network, to share learning, were also organised through the Service Manager Communications Team, although the value of those meetings was impacted by delays to portfolio scale up, and decreased to a more manageable monthly meeting over time.

FCDO staff at post in priority countries (e.g. Brazil, SACU+M, Indonesia, Nigeria, Mexico, India, Vietnam) assisted in the development of interventions, and implementation where these activities went ‘live’. This additional expertise at post supported strong join up with wider FCDO initiatives in the regions.

Commercial

At the time of design and procurement of the programme, FCO Commercial department had limited programme capability; as such FCO hired external expertise to assist with the procurement. The GTP service manager role underwent procurement and EY won the competitive tender in April 2019.

As Service Manager, EY’s responsibilities were for programme management as outlined in the previous section, and for advisory services for the design, delivery and management of the Flexible Fund component. This included sub-contracting out to other delivery partners in research, analysis and design of programmes as well as overseeing for the UK the procurement and management of third party suppliers to deliver Flexible Fund interventions. In this latter case, the contract was between the UK and third party suppliers (for TFSA, VNTR, Brazil IP programmes), but managed by EY. This work involved setting milestones, quality assuring deliverables, providing technical oversight and monitoring and reporting on performance against the project plan.

For flexible fund interventions, programmes with high programme management capacity and capability at post (e.g. South Africa) have maintained high levels of delivery performance) after the Service Manager contract ended.

The Service Manager also led on the GTP’s financial management and information management. This required transferring financial (and other) data from FCDO systems onto the Service Manager’s offline portal, which was unwieldy in practice and created an unnecessary additional overhead. The effect of having ‘more than one version of the truth’ – particularly in relation to the way that costs were reported against Business Case spend categories - added extra complexity and ambiguity to discussions relating to finance. Despite those challenges, the GTP was able to manage its budget to outturn broadly in line with yearly budget allocations. The information portal, while a useful construction to make data accessible by delivery partners, was unfortunately not utilised to its full potential, partly as a result of its limited usefulness in the context of a reduced portfolio of live interventions. The extensive Country Plan research produced by the Service Manager will be a useful reference point for future Trade analysis beyond the lifecycle of the GTP.

Analysis suggests that the original Service Manager contract was overly complex given the nature of the services being delivered. The majority of KPIs were administrative or routine rather than performance and outcome based, with a few advisory; feedback suggests that requests for additional strategic contributions could have been worked more explicitly into KPIs. The programme inception period (Apr-Dec 2019) was managed on a Fixed Price basis, but the contract switched to a Time & Materials approach thereafter. Stakeholder feedback confirms that it was not always easy to determine how much Service Manager resource (and at what level) was appropriate to deliver post-inception activity. At a later stage, both parties agreed to a switch to a milestone based approach in support of the live interventions, which resulted in a cost saving to the FCDO. Further cost savings were achieved when FCDO asked the Service Manager to revisit and scale down its core team requirements after the first round of budget reductions. The FCDO ended the Service Manager contract earlier than planned in June 21 after a 3 month notice period. Both parties collaborated successfully to return services back to FCDO during the notice period.

Lessons learned on contract management which may be useful for future programmes include:
- More explicit KPIs for strategic contributions by Service Manager to complement more programme management related ones;
- Milestone or results based payments to assist in containing costs;
- More detail on requirements for milestones and performance criteria to ensure clarity to all parties;
- Consider a more adaptive approach within contracts, that may build on allow for greater flexibility in delivery.

As above, EY managed the contracts with third party suppliers for the three private sector delivered Flexible Fund interventions on behalf of the UK government until June 21 when management transferred to the FCDO (either centrally or by post).

Nathan Associates have performed well in support of the VNTR programme since they were contracted in December 2020, consistently delivering in line with milestones and to the logframe. They were able to work well, despite the pandemic restrictions, as a result of effective leadership and a strong in-country team. Key to the success has been the close working with the beneficiary MOIT on the design, build and review of the portal. They have also worked extensively with businesses which has supported adoption. As contract manager, Nathan Associates successfully adapted activities to meet a reduced budget. Regular performance and update meetings has allowed the supplier to keep the project on track including the ability to raise issues and risks early and offer mitigations. Stakeholder feedback has been positive on their performance.

The TFSA programme team and delivery partners, worked collaboratively to ensure the intervention remained on track despite the impact of Covid-19. The relationship continues to be productive, open, adaptable, and flexible and MREL has been significantly strengthened with design and implementation of the programme MREL strategy. Recent in-country visits by the PRO and delivery partner helped to identify where further resourcing and interventions were needed, as well as reaffirming the programmes proposed interventions in line with the ToC remain valid.

Despite the complexity and issues that the programme has faced due to impacts of Covid-19 around the world, the delivery team have gained momentum through adaptive delivery, introducing new technology to replace face-to-face activities and providing a model that has previously not been tested in the Export School, enabling the delivery of strong results. The TFSA has value well beyond its current geographical focus and there is genuine commitment on the part of the delivery partners to find a long-term home for the Hub once the programme closes. There is also a willingness on the part of the team to collaborate to add-value across UK initiatives, as the work on EISP demonstrates.

FCDO colleagues at post worked closely with its supplier, Palladium, to overcome some initial delivery challenges to ensure that KPIs were met. When the Service Manager contract ended in June 21, FCDO colleagues were required to step into the Customer Representative role vacated by EY. In Brazil, this resulted in a more streamlined operation which enabled FCDO to collaborate successfully with Palladium to support innovation, and to deliver the numerous systemic improvements covered in the output assessment section.  Palladium deployed specialist contractors (i.e. GESI) to deliver work that included a comprehensive international IP benchmarking report, which has underpinned project design and delivery in an innovative manner.

UKTP’s primary delivery partner, ITC, has consistently delivered against the project workplan and budget, with good and accurate forecasting. ITC helped the programme to maintain momentum despite Covid challenges by applying creative workarounds and by implementing new technology to replace face-to-face activities. The good working relationship developed during the programme’s inception phase has been maintained through open and productive dialogue and a flexible approach. ITC kept FCDO updated on progress, impending risks and expected delays. Quarterly reports have been produced in a timely manner with narrative on actions taken. Spend on the programme has been in line with agreed targets and work plans. A second component is with Cariforum but activities have not yet commenced.

For TFMICs, WBG and WCO collaborated successfully to deliver positive results by adjusting TFMICs work plans and work modalities in response to Covid and changes to the operational context. During periods of uncertainty regarding the budget, both partners were asked by the FCDO on two occasions to refrain from further commitments and to delay activities. Despite those challenges, WBG and WCO were able to use their reputation and in-country reach to focus on rapid response and Covid-19 specific challenges, while maintaining business continuity and supporting recovery efforts. Both WBG and WCO collaborated effectively with FCDO to ensure a responsible exit from the programme, and to capture key results across the programme to date. Some work on customs modernisation was taken up in other WCO initiatives (including the HMRC-UNCTAD-WCO programme on capacity strengthening for trade facilitation). Over course of programme, WB and WCO reported effectively on delivery and financial reporting.

The WBG was also a partner in the delivery of the Mexico Better Regulations programme, and similarly worked with FCDO and CONAMER to scale down scope, budget and delivery plans of the programme and exit responsibly when the programme was closed early.

Financial Performance

The GTP spent approximately one third of its overall £150m original budget over the lifecycle of the programme (see Table 2 below). The GTP was operational during the original timeframe set out in the programme Business Case (2017-21), but as outlined earlier, due to ODA reductions, programmes were closed early and several planned projects did not commence.

The GTP spent £16.4m on Access & Enabling (which included the cost of developing Business Cases and also HMG Staff Costs) and £8.1m on Research and Analysis (the cost of developing country plans, New Project Concepts and research projects). The cost of this design phase is proportionately high as many of the interventions in development did not reach the implementation stage due to the timing of the ODA budget reductions.

Table 2 shows that programmes outside of the Flexible Fund scaled up spend more rapidly. The UKTP programme, delivered via ITC, delivered over £4m of activity in its first year. The TFMICs programme was also mobilised quickly before it was asked to slow down delivery to help the GTP (and the wider Prosperity Fund portfolio) to manage calendar year ODA budget reductions in 2020. TFMICs incurred a £6m budget reduction as a result of the July 2020 ODA re-prioritisation exercise, which also saw the closure of 9 programmes which had been in the design phase. (See Table 1 on Page 5).

In the final year of the programme the GTP worked with its delivery partners to manage the closure of programmes that occurred as a result of ODA Business Planning decisions (April 21). The TFSA programme transferred to new governance arrangements in July 21 and is now being managed by the FCDO post in South Africa with support from other posts in the region. The programme is due to close in FY 22/23. The UKTP also continues as an independent programme managed by the FCDO Economic Security Directorate; and VNTR, also managed by ESD, continues until the programme ends as planned in July 22. Despite the challenges resulting from the change of operational context in the final two years of the programme, the GTP was able to outturn broadly in line with its yearly budget allocation through proactive and successful collaboration with its suppliers.

Table 2 – Financial Overview

Monitoring, Reporting, Evaluation & Learning

GTP held a number of monthly monitoring meetings including sub-committees on programmes, finance, and MREL (the latter including FCDO, EY and Prosperity Fund programme, advisory and MREL staff) which fed into monthly Operational Boards (chaired by FCDO). A quarterly GTP Programme Board at SCS level (chaired by FCDO) helped provide oversight and quality assurance. In addition, the FCDO PMO and Service Manager were in frequent contact on day to day management; with economics, gender and inclusion, and MREL expertise helping provide quality assurance to delivery. Flexible Fund project level interventions were monitored by weekly meetings that included the implementing supplier team, Service manager and FCDO centrally and at post; with monthly meetings held with multilateral delivery partners (TFMICs, UKTP). Field visits occurred early in design but were hampered in 2020 and 2021 by the pandemic; FCDO staff (including GTP staff) at posts were critical in assisting with ongoing monitoring of activities in country.

The MREL Sub-Committee aimed to standardise approaches to facilitate a space for lesson-learning, and streamline reporting to oversight committees. Intervention suppliers developed project level logframes, monitoring and reporting to feed into the Sub-Committee. Fortnightly network calls between programme managers were also used to share best practices and lessons learned. Research reports, and best practice on themes, were shared across programme, although this in practice became more limited in the programme, in part because of the cancellations of interventions, and reductions in staff across the network.

A number of programme level reviews and evaluations were completed including annual reviews in 2019 and 2020, a Prosperity Fund Programme Evaluation Cycle 1 (July 2020); and an internal mid-year review (March 2021) to assess progress on delivering against 2020 Annual Review Recommendations (including VFM, financial management, Gender & Inclusion and MREL.)

A key recommendation of the 2020 (and the 2019) Annual Review was to develop an over-arching GTP programme level (capping) logframe, including establishing clear indicators and targets for annual progress, as well as updating the Theory of Change. Work progressed on developing this overarching logframe; however, when ODA reductions became finalised with (March/April 21), the focus shifted to revising project level components and ensuring responsible early exits from programmes. As such this work remained unfinished. With early closure of the programme, it was no longer going to deliver at anticipated scale. Still, a final capping logframe would have been useful to capture the overall outputs across the NTBs and overall programme components.

On gender and inclusion, a G&I action plan was developed focusing on capability, mainstreaming G&I, and maintaining a G&I aware approach to intervention design and delivery. Elements of this plan were implemented by ongoing programme components.

Although the MYR found the GTP had made less progress in improving VFM, some actions had been taken such as downsizing Service Manager programme management staffing and costs given the reduced portfolio. When ODA reductions led to early closure and/or reductions of programme spend, the focus shifted to enacting the required programme closure / transition arrangements, including working with delivery partners to arrange contract variations (where the exit process was managed over an extended timeframe).

The Service Manager contract ended In June 2021. FCDO worked closely with the Service Manager during the three month notice period to manage the successful transfer of responsibilities, including oversight for risk and financial management, back to FCDO.

The GTP was a new, innovative and large-scale programme with a focus on adaptive learning. GTP programme staff are working with colleagues in the FCDO’s Better Delivery Dept to use the lessons learned and recommendations produced by this review to support future ODA programming.

F: BUSINESS ENVIRONMENT

The Global Trade Programme was sensitive to the wider business environment and this context was factored into the design phase. From the outset, there was strong engagement with stakeholders such as DIT, exporter groups and Chambers of Commerce in priority countries to test ideas and seek buy in. This enabled interventions to gauge the likely level of support and interest from the private sector to ensure that the interventions would deliver an increase of international trade and secondary benefits. During the initial stages of the Covid pandemic, some scoping work was undertaken to look at developing interventions to support business supply chains. Although these were subsequently not taken forward due to budget cuts, programmes that were already in delivery have adapted to the new operational context to support businesses to expedite trade (i.e. See Section B – Non-Tariff Barriers).
The support provided by the UKTP programme to businesses in the ACP is opening up new opportunities for UK businesses. The UKTP programme brought 16 export-ready businesses from developing countries to the Speciality & Fine Food Fair in 2021. The event generated more than 300 business connections over two days. Products on display included gourmet peppers grown in the volcanic soils of Cameroon’s Penja Valley, raw and processed cashews from the Ivory Coast, vanilla and cloves from Comoros and fine chocolate, hot sauces, organic baby food and plant based meats and snacks from the Caribbean. The event exposed UK businesses to products not seen in the UK before which has helped to create new revenue opportunities. It also supports compliance with international product certification and product packaging which simplifies the import and sale of products to UK consumers.
During the delivery of the Vietnam National Trade Repository, the supplier ensured private sector engagement was at the centre of the trade portal design. This included early focus group meetings with organisations such as the British Chamber of Commerce, Hanoi Women Association of Small and Medium Enterprises and Vietnam Chamber of Commerce and Industry to understand the demands of the trade portal’s potential end users. They were also involved in the user testing of the portal and the business community has remained positive and supportive of the project.
From 170 SACU+M Business Support Organisations (BSOs), 46 were identified as key partners for TFSA, to be targeted and developed as Knowledge Centres, promoting the export resources and training on the TFSA Hub, and partnering with TFSA on business outreach. Many of these organisation already work in export training or export promotion, and target groups, sectors, and geographies that are priority for TFSA. To date, 16 are co-operating with TFSA on interventions, and 11 have been engaged with partnership certificates, committing to disseminate TFSA Hub amongst members, help spread training, and attend/collaborate on TFSA events.
TFSA participated in the high-profile Intra-Africa Trade Fair held in Durban, South Africa, in November 2021, which welcomed over 38,000 in-person and virtual attendees from 128 countries. The programme used this event to publicise its TFSA’s Women in Trade initiatives and promote the School of Export training modules. This helped to solidify its BSO relationships with major SACU+M trade actors and increased brand awareness across the business community. The programme has also developed a database of renewable energy projects (wind, solar and green hydrogen) in the sub-Sahara African market to showcase the supply opportunities, and to show the types of projects and the countries with the greatest potential for South African manufacturers to export into. TFSA is also supporting the development of digital content for 50 MSMEs involved in renewable energy equipment and/or components manufacturing, to improve their competitiveness in the market.

## List of Acronyms

ACP	African Caribbean and Pacific
AEO	Authorised Economic Operators
AR	Annual Review
ASEAN	Association of Southeast Asian Nations (ASEAN)
BC	Business Case
BEIS	Department for Business, Energy & Industrial Strategy
BSI	British Standards Institution
CODEX	Codex Alimentarius Commission, established by the Food and Agriculture Organization of the United Nations (FAO)
CONAMER	(Mexico’s) National Commission of Better Regulation
DEFRA	Department for Environment, Food and Rural Affairs
DFID	Department for International Development
DIT	Department for International Trade
EPA	Economic Partnerships Agreement
EL	Evaluation and Learning
EY	Ernst & Young
FBC	Full Business Case
FCO	Foreign and Commonwealth Office
FCDO	Foreign, Commonwealth & Development Office
GEA	Gender Equality Act
GESI	Gender Equality Social Inclusion
GTP	Global Trade Programme
G&I	Gender and Inclusion
G&G	Government to Government
HAWASME	Hanoi Women’s Small and Medium-sized Enterprises Association
HMR&C	HM Revenue & Customs
IDA	International Development Act
IIOC	Investment, Infrastructure and Operations Committee
INPI	Brazilian (Intellectual Property) Patent &Trademark Office
IP	Intellectual Property
IPO	Intellectual Property Office
ITC	International Trade Centre
JFU	Joint Funds Unit
KPIs	Key Performance Indicators
MCA	Mutual Coalition Agreement
MIC	Middle Income Countries
MOIT	(Vietnamese) Ministry of Industry and Trade
MoU	Memorandum of Understanding
MRA	Mutual Recognition Agreement
MREL	Monitoring, Reporting, Evaluation, Learning
NPC	New Project Concept
NTB	Non-Tariff Barrier
NTFCs	National Trade Facilitation Centres
ODA	Official Development Assistance
PF	Prosperity Fund
SB	Secondary Benefits
SACU&M	South African Customs Union & Mozambique
SARS	South Africa Revenue Service
SINAGER	(Mexico’s) National System of Regulatory Governance
SM	Service Manager
SME	Small and Medium-size Enterprises
TFMICs	Trade Facilitation in Middle Income Countries
TFSA	Trade Forward Southern Africa
TRS	Time Related Studies
ToC	Theory of Change
TSE	Turkish Standards Institution
UKTP	UK Trade Partnerships Programme
UKIPO	UK Intellectual Property Office
VNTR	Vietnam National Trade Repository
WBG	World Bank Group
WCO	World Customs Organisation
WTO	World Trade Organisation