Annual Review - Summary Sheet
Title: India Economic Reform Programme (IERP), Prosperity Fund / Period of review: August 2019 – July 2020
Programme Value: £47.85m		Review Date: 30 Nov 2020
Programme Code: N/A	Start Date: 1 September 2017	End Date: 31 March 2023

Summary of Programme Performance
Years	April 2017 – July 2019	August 2019 – July 2020
Programme Score	A	A
Risk Rating	Moderate	Moderate

Summary of progress and lessons learnt since last review
This second Annual Review of the UK-India Economic Reform & Prosperity Programme covers August 2019 to July 2020. A period marked by portfolio strands starting implementation, as well as the programme responding to the significant implications of the coronavirus. Since March, the programme had to adapt to the direct and indirect impacts of a global pandemic, with some activities becoming impractical, and others requiring refocus. The knock-on impact on Official Development Assistance (ODA) budgets also necessitated a prioritisation[1] exercise.
[1] https://www.gov.uk/government/publications/official-development-assistance-oda-spending-for-2020-first-secretary-of-states-letter
The table below outlines the recommendations from the Annual Review 2019 and actions taken to address the recommendations during the current review period.

Annual Review 2019 Recommendation	Action taken
Monitoring, Reporting, Evaluation, Learning (MREL)
Plans in place to promote the use of outputs from Tranche 2 (T2) projects and track outcomes and impacts for evidence of primary and secondary benefits (SB). / Learn lessons between strands on the development of strong logframes and Theories of Change (ToCs) – ensuring consistency of approach as they move into full implementation.	Programme teams are regularly documenting outcomes and impacts of T2 projects. / Project Completion Report template for T2 revised to document evidence for ongoing projects. / Developed strong logframes, ToCs, narratives for projects along with regular updates.
Value for Money (VfM) Processes
Programme team to use the PF VfM scorecard to self-assess the programme in advance of Annual Reviews. PF monitoring and evaluation partners can assist.	Strands self-assessed the programme on VfM using the VfM Score Card. Terms of Reference include this. The exercise was conducted in March 2020 and will continue annually.
Programme team to track the costs of individual activities in Tranche 1 (T1) and benchmark these against similar activities from other India development programmes.	Benchmarking has been challenging due to sensitivities around sharing of financial/ commercial information. The programme will continue to pursue.
Programme to ensure it has processes in place to mitigate risks of delays to delivery and constraints on the availability of Her Majesty’s Government (HMG) technical expertise.	Quarterly update of Risk Registers with mitigation in place. Regular meetings with Joint Funds Unit (JFU), Prosperity Fund Delivery Unit (PFDU) to draw on technical expertise.
Programme to work with delivery partners to ensure specifics of T1 projects represent VfM before design reports are signed off and throughout implementation. Business case to be updated if required.	VfM is ensured in the design phase through the VfM Strategy document and scorecard along with capacity building workshops delivered by the Foreign, Commonwealth and Development Office (FCDO).
Climate change and Environment
Programme to develop with other PF programmes and PFDU a tool to assess programmes’ likely impacts and vulnerabilities to climate and environment (including natural disasters) and realign programmes where necessary.	JFU has recently released Climate Change mainstreaming guidelines. This recommendation will be addressed this year. We have taken the opportunity of the ODA prioritisation exercise to ensure that our programmes are COVID-19 and climate resilient.
Primary Purpose and Gender & Inclusion
Programme teams to hold suppliers to account on the primary and Gender & Inclusion (G&I) elements of the Statement of Requirements.	Each T1 supplier prepared a ‘Gender Action Plan and Impact Assessment’ document. Programme team ensured Gender Action Plan recommendations are reflected in ToCs and logframes. / Strands used Evaluation and Learning (EL) supplier’s ‘Flexible Evaluation support’ to prepare Gender Scorecard.
Programme team should ensure it has sufficient UK Government social development advisor resource available as strands work through inception phases. To support detailed design, development of internal G&I action plans and upskilling of strand teams.	Social Development Advisor (SDA) at the FCDO worked regularly with the suppliers. / Regular engagement with SDA to review Gender Action Plan and Impact Assessment document submitted by Suppliers.
Secondary Benefits (SB)
Programme to consider whether SB enabling activities e.g. formation of UK-India private sector networks (Energy & Low Carbon, Financial Services), city partnerships (Urban) can be applied to all strands to support delivery of SB.	Each strand has a specific SB Action Plan. / Each logframe has specific SB indicators.
Capability
PF in London to provide further support to the team in country to review strands during inception phases, specifically on ToCs and logframes, and to identify G&I entry points, develop G&I action plans and hold suppliers to account.	Regularly engaging with MREL Expert, Social Development Advisor, VfM Expert to review ToCs, logframes, Gender Action Plans and Impact Assessments, and VfM Strategy.
Governance
Action taken: The Programme has added gender & inclusion progress to quarterly reports and it is covered at the India Programme Portfolio Board annually.
Financial Management (budgeting/ forecasting)
Action taken: The Programme follows Activity Based Budgeting (ABB) to ensure annual budgets are well informed. We have ensured budgets and forecasts are linked to milestone payments to improve accuracy and allow programmes to flag under/overspend risks as early as possible.

Recommendations for the next year
Portfolio:
1. Value for Money: Programme team and delivery partners to track costs of individual Tranche 1 activities and benchmark them internally/ externally, to check that costs remain competitive with the market and where efficiencies might be realised. Additional support from Economics Unit will be required for data from other PF programmes, as well as clear guidelines on sharing this information with delivery partners.
2. Climate Change: Programme team to comply with climate change guidelines issued by JFU recently
3. Gender Equality & Social Inclusion (GESI): Programme to continue to work with suppliers to ensure GESI aspects are robustly monitored (ensuring disaggregated data) and managed.
4. MREL: To revisit strand-level ToCs and logframes to ensure that maximum impact is derived from activity that has been streamlined due to Official Development Assistance (ODA) prioritisation. Ensure all T2s and Accountable Grants are monitored through logframes with regular updates.
5. Finance: PFDU/ JFU to provide best practice guidance on the level of detail required from delivery partners to successfully monitor programme forecasts and budgets. To streamline processes where possible and ensure alignment to month-end reporting requirements at the centre.
6. Communication: Programme to refine proactive and reactive communication strategies to ensure that we are clearly explaining the impact of the programmes.
7. Programme Design and Stakeholder Management: All future programme design and contracting to give greater consideration to potential delays due to both internal factors (stakeholder identification during scoping, sub-contracting) and external (reliability or availability of stakeholders).
8. Formalise strand synergy: All programme teams to consider formation of internal working group so that potential areas of synergy can be identified to share learnings and deliver results sustainably and at scale as recommended in the May 2020 Readiness Review beyond monthly meetings.
Ease of Doing Business (EoDB):
1. Cross-HMG offer to India on EoDB to be streamlined to avoid overlap with global programmes, minimise conflicts among stakeholders and effectively use available resources. Alignment to be reflected through ToC narrative.
2. Other Government Departments (OGDs): Sign Memorandum of Understanding (MoU) with Regulatory Delivery (RD) to begin implementation of agreed work plan. Agree work plans with other identified OGDs.
Energy:
To ensure effective application of learning from other T1 programmes during design phase of Energy T1 programme.

Financial Services:
1. Maintain flexibility to deliver some aspects of the programme in-house if required.
2. More rigorous oversight by FCDO on financial management to ensure early detection of risks to the forecast and appropriate mitigation is taken by contractors.
3. Closer engagement with contractors on MREL to ensure that they understand FCDO requirements and have the required technical expertise and capacity to deliver work to our standard.
Skills for Jobs:
1. Consolidate the healthcare sector as a new priority and the established partnership with World Health Organisation (WHO) for select interventions in the context of coronavirus. Prioritisation review of the workplans, delivery approaches and new areas of focus to be done after discussions with partners and suppliers.
2. Provide prioritised support on digital content development, quality remote teaching, and online assessments.
3. Plan an appropriate mechanism to measure progress against impact and outcome level indicators using secondary data. Continued engagement with Ministry of Skill Development & Entrepreneurship (MSDE), National Skill Development Corporation (NSDC) and other institutions to promote India-UK institutional partnerships. Refresh project strategy to connect UK partners with the Indian vocational education market through e-knowledge sharing sessions, Business-to-Business (B2B) and Business-to-Government (B2G) engagements, and demonstrating expertise through innovative pilots.
Urban:
1. Tranche 1: Innovation Partnership themes and areas for capacity-building, coronavirus review report, and revised ranking of High Value Projects (HVP) to be considered in consultation with OGDs to ensure all original design. Phase outcomes have been assessed in context of coronavirus/ pandemic/ disaster management.
2. GESI Action Plan: Extended Design Phase to reconfigure stakeholder engagement on GESI, using PF network established by Mott MacDonald to troubleshoot GESI aspects and learn from other PF programmes.

Senior Responsible Officer (SRO) commentary:
I would like to thank the India Prosperity Fund team, the Government of India and our delivery partners for their commitment to delivering impact, through an exceptionally challenging period that saw the advent of the coronavirus crisis.
The programme has achieved a huge amount this year, from major deals on electric mobility, to training large numbers of India’s new insolvency professionals to building the capacity of India’s new Business Reform Secretariat, to working with frontline workers on covid-19 preparedness, to promoting sustainable change in waste management at a state level.

Two of our programmes remained in Design phase for much of the year, delayed first by the need to prioritise in the face of the coronavirus crisis, and then due to the UK Government’s ODA prioritisation exercise in response to that crisis. While the delay and spend reduction in the 2020 calendar year is unfortunate, it has allowed us to work with suppliers to ensure that the programmes are delivering maximum impact and value for money.
I am also grateful to the programme team for all of their work in responding to feedback from last year’s Annual Review and look forward to taking forward this year’s recommendations next year, when we will be in Tranche 1 delivery across all strands: delivering inclusive growth in India with secondary benefits for the UK.
JFU commentary:
The JFU is pleased to see the progress made by the programme – it has developed in lifecycle terms considerably since the previous annual review with almost all components now being in the implementation phase. We endorse the recommendations contained within this annual review and are pleased to see these reflected at appropriate levels across the programme portfolio and specific recommendations relating to each strand. The programme has taken a proactive approach to responding to the recommendations arising from the prior annual review Evaluation Readiness Review and despite the challenging contextual backdrop significant progress has been made across all five strands.
We support the important role that the programme has played in helping the UK-India partnership to address climate change, particularly in relation to some of the COP26 campaigns and initiatives. We look forward to the planned work in relation to the Energy Tranche 1 strand.
We are pleased to see the changes that have been made to programme logframes as approaches and assumptions have changed through contextual shifts.
The JFU really values the efforts that have been made to find synergies and value for money through collaboration with partners across HMG and more broadly as noted in this review.
We would like to thank the team responsible for the delivery of this programme.
List of Acronyms
ABB	Activity Based Budgeting	ITI	Industrial Training Institute
B2B	Business-to-Business	ITA	Integrated Transport Authority
BEIS	Department of Business, Energy and Industrial Strategy	JFU	Joint Funds Unit
BIM	Building Information Modelling	MCA	Ministry of Corporate Affairs
BRAP	Business Reform Action Plan	MoU	Memorandum of Understanding
BRE	Better Regulation Executive	MREL	Monitoring, Reporting, Evaluation, Learning
COP26	26th session Conference of Parties	MSDE	Ministry of Skill Development and Entrepreneurship
CBIC	Central Board of Indirect Taxes and Customs	MSME	Micro, Small and Medium Enterprises
CPWD	Central Public Works Department	NAPS	National Apprenticeship Promotion Scheme
CRESP	Climate Resilient Cities for Shared Prosperity	NGO	Non-Governmental Organisation
C&D	Construction and Demolition	ODA	Official Development Assistance
DFID	Department for International Development	OGD	Other Government Departments
DIT	Department for International Trade	PDSF	Project Delivery Skills Framework
DPIIT	Department for Promotion of Industry and Internal Trade	PFDU	Prosperity Fund Delivery Unit
EoDB	Ease of Doing Business	PFRDA	Pension Fund Regulatory and Development Authority
EL	Evaluation and Learning	PMRDA	Pune Metropolitan Region Development Authority
EV	Electric Vehicle	PWD	Persons with Disabilities
EY	Ernst & Young	PwC	PricewaterhouseCoopers
FCDO	Foreign Commonwealth and Development Office	QPs	Qualification Packs
FinTech	Financial Technology	RD	Regulatory Delivery
GESI	Gender Equality and Social Inclusion	RR	Readiness Review
GoI	Government of India	RS	Reform Secretariat
G&I	Gender and Inclusion	SB	Secondary Benefit
G2G	Government-to-Government	SEBI	Securities and Exchange Board of India
HMG	Her Majesty’s Government	SFJ	Skill for Jobs
HMRC	Her Majesty’s Revenue & Customs	SME	Small and Medium Sized Enterprises
HVP	High Value Project	SOP	Standard Operating Procedure
IBBI	Insolvency and Bankruptcy Board of India	SRO	Senior Responsible Officer
ICSI	Institute of Insolvency Professionals	SSC	Sector Skill Council
IEA	International Energy Agency	TA	Technical Assistance
IERP	India Economic Reform Programme	ToC	Theory of Change
IFC	International Finance Corporation	Tranche 1 (T1)	Refers to majority of programme spend and delivery under each strand
IPA	Insolvency Professionals Agency	Tranche 2 (T2)	Refers to smaller more flexible and adaptive programmes under each strand
IRDAI	Insurance Regulatory and Development Authority	VfM	Value for Money
IUKIFH	India UK Infrastructure Finance Hub	WHO	World Health Organisation

## A. INTRODUCTION AND CONTEXT

India’s economy has grown more than ten-fold since the 1990s. The opportunities for creating mutual prosperity for India and the UK by driving sustainable, inclusive economic growth are rising. However, there remain significant challenges. GDP per capita in India remains low at around $2000. India is the third largest emitter of greenhouse gases and is one of the country’s most vulnerable to the impacts of climate change. India can be a challenging place for businesses to set up and operate. How India continues to grow and develop impacts not only its 1.3 billion citizens, but how the planet responds to global challenges such as climate change and biodiversity threats.
The Economic Reform and Prosperity Programme in India provides technical assistance (TA) to address current market failures and weaknesses that impede India’s inclusive economic growth. It seeks to reduce poverty in India, address global challenges such as climate change, and unlock increased prosperity for both the UK and India. This has never been more important than now with the challenges of the coronavirus which has had a significant impact on India.
The India Economic Reform and Prosperity Fund, bilateral programme is now a £47.85 million five-year initiative, running from September 2017 – March 2023. The programme focuses on where the UK’s expertise and strengths match India’s reform priorities and development needs. These include climate and green growth (including working with India on taking a sustainable, low carbon approach to urbanisation) and advocating free and fair trade through work on ease of doing business, skills and financial services. The programme is implemented across eight states: Haryana, Karnataka, Tamil Nadu, Andhra Pradesh, Telangana, Gujarat, Delhi, and Maharashtra.
Structure
The five strands of the portfolio – Financial Services, Skills, Urban, Energy & Low Carbon, and Ease of Doing Business – each work in partnership with one main Private Sector Delivery Partner (PSDP). The majority of the programme activity is delivered through each strand’s ‘Tranche 1’ programme. The remainder is delivered via smaller and shorter ‘Tranche 2’ projects, which provide increased flexibility using a range of delivery mechanisms including working with multilateral organisations, awarding accountable grants, and issuing commercial tenders.
As of October 2020, Skills, Financial Services, Urban, and Ease of Doing Business strands have confirmed Tranche 1 contracts. The Energy Tranche 1 programme is out to market, with significant Tranche 2 work already underway.
Governance & MREL
The programmes are managed by strand leads and programme managers, alongside MREL, finance, and coordination functions. The team is overseen by a D7 Head of Prosperity who reports to the Programme SRO (Economic Counsellor). Weekly team meetings oversee day-to-day management, with monthly strategic meetings. A quarterly India PF Board, chaired by the SRO, brings together representatives from across the UK in India work and London. Each strand has additional individual governance, including regular meetings with suppliers, and a board at least every six months.
Strands’ progress into Tranche 1 contracts with PSDPs and delivery means that this review considers strand-level logframes and ToC. Each strand contributes an equal one-fifth to the overall assessment.

## B: PERFORMANCE AND CONCLUSIONS
Annual outcome assessment: IERP Programme has been rated ‘A’ (programme met expectation).
Ease of Doing Business: This programme aims to improve India’s business environment to unlock economic growth within India and open opportunities for UK and international companies. The T1programme, delivered in partnership with Pricewaterhouse Coopers (PwC), focuses on the promotion of regulatory transparency and making the Indian business environment more rules-based and transparent, through better regulation, tax administration, trade facilitation and standards. The programme largely concluded its design phase by March 2020.
The start of implementation was delayed due to the coronavirus outbreak and the subsequent prioritisation of the ODA budget. A larger than expected number of consultations throughout the design phase demonstrated stakeholder willingness and reinforced the programme’s objective. A revised workplan identified the economic impact of the pandemic on disadvantaged groups such as Micro, Small and Medium Enterprises (MSME) and women-led businesses, devising measures to support their revival. The programme moved into implementation on 29th October 2020.
In addition, our Tranche 2 programme with the International Finance Corporation (IFC) worked on the capacity-building of India’s Reform Secretariat (RS) to become the lead agency for business reforms in India, supporting Department for Promotion of Industry and Internal Trade (DPIIT) and the State Business Reform Action Plan (BRAP).
Work to share international best practices with Indian departments at the centre and states has drawn on other government departments (OGDs) in the UK. Two missions have been hosted, including experts from the UK’s Better Regulation Executive, Reform Directorate, and Her Majesty’s Revenue and Customs (HMRC). Strand assessment: A.

Energy & Low Carbon: We are working with India to address climate change and promote clean energy, supporting international efforts to as the hosts of COP26. This programme focuses on working with India to expand its use of renewable energy, increase energy efficiency and security, the use of electric vehicles (EV) and support green finance mobilisation.  Active stakeholder engagement has helped inform policy, raised awareness of energy sector opportunities in India in areas matched to UK capabilities, created commercial wins, and established a strong foundation for larger joint programmes.
At the September 2018 Energy Dialogue, the Government of India (GoI) agreed an Energy T1 programme to be joint funded with the GoI, the UK part of which was prepared for tender in January 2020, then placed on hold due to the coronavirus. A reformed programme, with a shorter time-frame, refined resource allocation, and a sharpened focus on COP26 priorities, and the green recovery from the pandemic was tendered on 5th October 2020.
There is continued support from the GoI to drive implementation, with strong engagement on UK COP26 campaigns (clean energy, energy efficiency, clean transport) that the programme will support. In the meantime, significant progress has continued on T2 elements, such as developing a business alliance to scale up renewable energy and energy efficiency adoption, knowledge exchanges on approaches for enhancing cleaner energy deployment, facilitating initiatives to accelerate the scale up of the electric mobility market in India and contributing towards the IEA Clean energy transition programme and energy resilience and security. These were drawn through a variety of relevant delivery mechanisms. Strand assessment: A.

Financial services: Well-functioning financial services are crucial for India’s growth and the UK is home to world-class financial services expertise. Working with delivery partner Ernst & Young (EY), the Tranche 1 programme this year progressed work on three pillars of the programme: financial market development (in particular insolvency), raising finance for infrastructure, and financial technology (FinTech). The programme’s work on insolvency has been especially impactful, working in close partnership with Indian government agencies to deliver capacity building for officials and professionals and supporting policy development in a number of areas.
While the programme has in place several achievements, aspects of programme delivery were delayed, as a result of capacity issues with the supplier as well as impact of the pandemic. The reasons are set out in Section C of the report.
The team worked hard to successfully resolve these issues and establish systems with agreed understandings on expectations. Due to the impact of coronavirus, the work-plan has been refocused to ensure momentum and relevance in the current context. Strand assessment: B

Skill for Jobs (SFJ): This strand is developing the skills market in priority sectors, providing TA for institutional capacity-building, promoting international standards and sustainable commercial models. Of the total budget of £12m, £4.7m comes from the PF, which supports an enhanced UK offer. The rest is provided by former Department for International Development (DFID) India. This year saw increased requests for policy level support. The onset of coronavirus has led to action to revisit and repurpose the programme. This was done by adapting our delivery mechanisms (a shift to online and e-sessions), and taking on new partners (the WHO for health work), and target recipients (e.g. health workers). The project is actively working on UK skilling institutions for potential partnerships with Indian agencies. Strand assessment: A.

Urban Development: This programme helps key Indian cities design major infrastructure projects to tackle the significant environmental and poverty challenges they face, reducing Co2 emissions and creating opportunities for UK and international companies. By focusing on cutting-edge projects in selected cities, we aim to create a demonstration effect for others. The programmes assist with the development, planning, and delivery of resilient urban projects while showcasing UKs strengths. As of 28th October 2020 the Tranche 1 programme has moved into delivery in partnership with Mott McDonald.
The conclusion of the programme’s initial design phase in March 2020 successfully identified five High Value Projects. Activities focused on identifying projects within the fields of transportation; urban services, and urban planning and the built environment. These will be developed throughout the programme lifecycle. Coronavirus and the subsequent nationwide lockdown impacted government priorities, and led to a modification in programme implementation, managed through an Extended Design Phase (EDP) from 15th June - 15th September 2020, which enabled prioritisation to ensure both pandemic and climate resilience. Strand assessment: A.
Building on the positive response of the portfolio to the recommendations of the previous Annual Review, and the progress made over the past 12 months, we are confident that the programme is in a strong position for the year ahead.

Key lessons
1. The impact of coronavirus, including ODA prioritisation, presented opportunities as well as risks for the programme. It was an opportunity to reassess projects and deliverables against changed landscapes, drawing on lessons learned, and improving effectiveness of delivery.
2. Effective financial management from FCDO to ensure forecasts are met in terms of overspends and underspends especially in the context of uncertainties such as COVID-19, prioritisation and any risks are mitigated effectively and on time.

Ease of Doing Business:
1. Adaptive programming: the programme was able to flex to provide immediate support to the governments of Tamil Nadu and Karnataka as a result of a revalidation exercise. In addition, the programme’s geographic spread was modified to prioritise work against levels of interest.
2. The programme continues to be GESI compliant. However, despite the team’s best efforts, mainstreaming gender is not always an active priority for GoI stakeholders, and therefore alternative means to consider gender inclusion in design and implementation are being explored.
Energy:
1. T2 scoping projects have significantly enriched the T1 project design, generating stakeholder feedback and inputs on key thematic priorities.
2. Sustaining and strengthening key stakeholder relationships through T2 projects has been critical in establishing a community of policy makers, think tank organisations and Government bodies that understand the benefits of UK-India technical assistance. Recommendations of T2 projects were key in designing T1 in joint collaboration with Ministry of Power and Ministry of New and Renewable Energy.
3. An adaptive approach to programme design and implementation was necessary to respond to the evolving context and to capitalise on spin-off opportunities.
4. Industry associations have demonstrated strong convening power for engaging with public and private sector stakeholders.
5. A structured involvement of FCDO and other HMG departments during implementation enables the impact to be amplified beyond the Prosperity Fund priority states.
6. Implementation through multilateral agencies like the International Energy Agency (IEA) requires careful collaboration during design and delivery to ensure the impact and outreach is jointly attributable.
Financial Services:
1. Clearer communication between FCDO and EY on the precise formulation of deliverables is crucial to ensure expectations are aligned early on.
2. It is crucial for delivery partner to have the right skills and expertise in place to ensure high quality and timely delivery of activities.
3. Greater focus on strong performing parts of the programme as a result of the prioritisation exercise, to maximise impact.
4. Ensure engagement with stakeholders at the appropriate level and at the right time to build support and enable effective decision making.

Skills for Jobs:
1. With the arrival of coronavirus, most of the planned activities were paused. With the changing economic landscape, supply and demand for skills is evolving, and the project’s priority sectors will need to be reviewed to make the programme relevant.
2. Coronavirus has amplified inequalities for persons with disabilities (PWDs), women, girls, and minorities. There is therefore a need to focus on developing adaptive skilling and employment approaches to be able to help poor populations of India who have been affected financially, physically, and mentally.
3. Several interesting ideas are emerging from discussions with government agencies who would like to work with FCDO, e.g. by learning from UK models such as e-assessments, greening of jobs for climate resilience, and use of Artificial Intelligence in skilling.
Urban:
1. The Government of India has signalled a clear drive on infrastructure projects, including the urban observatory and digital infrastructure, with buy-in from stakeholders. The Climate Resilient Cities for Shared Prosperity (CRESP) T1 programme is well-placed to grasp this opportunity. Whilst government stakeholders can sometimes be challenging to build engagement with, persistence has been effective.
2. The Theory of Change is a valuable tool to anchor activity, particularly when managing change. For example, a revised package offered to the GoI during the initial phase of coronavirus has now been reflected in Pillar 3 of CRESP (‘innovative collaboration’).
3. Building a base for future collaborations: Nearly 200 consultations were conducted to build the roadmap. These provide a good platform for wider Department for International Trade (DIT) teams to identify potential secondary benefits. The programme also shortlisted 50 projects during the selection process for the five HVPs, for which details were shared with DIT.
4. The Prosperity Fund’s presence across India through the network of Prosperity Advisors has been helpful for Mott McDonald’s team to deliver the programme across states.

Summary of changes to logframes since the last Annual Review
Logframes for all programmes have been revised as projects have moved from design to implementation and in the light of coronavirus. Further changes are to be expected, for example in the context of the Spending Review, and the impact of coronavirus and India’s response.

## C: DETAILED OUTPUT SCORING
Programme Title	Ease of Doing Business
Risk:	Moderate		Impact weighting (%):		20%
Risk revised since last AR?	No		Impact weighting % revised since last AR?		No

Project Title (T1): Facilitating sustainable reforms to India’s business regulatory environment.
Output 1: Policies and strategies developed for delivery of regulatory and service delivery reforms with necessary technical assistance, awareness and capacities developed in line with international good practices to help policymakers address barriers across the identified thematic areas with particular emphasis on MSMEs and women led businesses.
Indicator(s)		Milestones		Progress
Number of stakeholder consultations held with central government departments for identification of interventions.		11		30+ (DPIIT, Ministry of Corporate Affairs (MCA), Ministry of Law and Justice).
Number of stakeholder consultations / workshops held with businesses to assess the regulatory environment.		8		25+
Number of state specific intervention planning sessions conducted in PF target states to ensure relevance of identified interventions and ownership by respective state governments.		8		12+
Output 2: Strategies developed for strengthening taxpayer service delivery, risk assessment, data exchange and analytics capabilities in line with international good practices to promote voluntary compliance, reduce overall cost of compliance especially for MSMEs and women led businesses.
Indicator(s)		Milestones		Progress
Number of stakeholder consultations held with Government of India and HMG for identification and relevance of interventions and ownership by respective departments.		8		14+ consultations held with critical stakeholders in Central Board of Direct Taxes, Central Board of Indirect Taxes and Customs (CBIC), HMRC Tax and Goods and Services Tax (GST) secretariat.
Number of stakeholder consultations/ workshops held with businesses to assess the current landscape of paying taxes.		8		15+
Output 3: Capacity building sessions and action plans delivered for CBIC and other key trade related regulatory agencies, helping policymakers address trade barriers and the particular trading challenges faced by MSMEs and women entrepreneurs.
Indicator(s)		Milestones		Progress
Number of stakeholder consultations held with Government of India and HMG for identification and relevance of interventions and ownership by respective departments.		22		30+ consultations were held with CBIC, Department of Logistics, HMRC Customs and Standards’ bodies.
Number of stakeholder consultations/ workshops held with businesses to assess the current trade landscape.		8		10+
Project Title (T2): Advancing India’s regulatory reform agenda by harnessing global expertise, which will help develop stronger independent institutions working to improve the business environment (IFC).
Output 1: Sustaining business reforms in India by supporting the establishment of a Reform Secretariat (RS).
Indicator(s)		Milestones		Progress
Number of training manuals designed for the three year programme life cycle.		1		1
Number of training programmes delivered for the RS staff so that they are equipped and empowered to drive the reforms process.		5		5. Including one induction programme.
Output 2: Broadening and deepening the Business reform agenda in India by developing an inventory of regulatory bottlenecks and assistance on improvement on “Doing Business Report”
Indicator(s)		Milestones		Progress
Number of feedback sessions conducted with private sector to develop inventory of regulatory bottlenecks faced by investors.		3		3. Total members interviewed were 32 during feedback sessions
Number of ’doing business’ indicators identified for designing, implementing, monitoring and coordinating reforms.		4		4
Number of workshops conducted in newly included cities of Kolkata and Bengaluru to train them on ‘doing business’ methodology.		2		4
Number of discussions facilitated between GoI and World Bank’s Global Assessment Team for Doing Business Report.		1		2
Number of memos prepared in collaboration with Government implementation agencies in preparation for Doing Business Report 2021		10		10
Number of Assessment Reports prepared as part of State Business Reform Action Plan.		37		1 National Report and 36 State Reports
Project Title (T2): Knowledge and expertise sharing to develop regulatory capacity and best practice in India. OGD project.
Output: Improved awareness of UK best practices in regulatory delivery, tax administration and trade facilitation through a series of knowledge exchange workshops in UK and India.
Indicator(s)		Milestones		Progress
Number of HMG Departments (OGDs) identified.		5		5. Better Regulation Executive (BRE), RD, HMRC (Tax), HMRC (Customs), UK Land Registry.
Number of scoping visits conducted in India by identified OGDs to gauge the appetite of target GoI departments and identify specific work plans.		3		3. Experts from BRE delivered session at Cross-Border & Personal Insolvency training workshop for 29 senior officers
Number of MoUs signed with OGDs interested in delivering a knowledge-sharing programme in India.		1		MoU drafted but could not be signed due to limited OGD capacity (linked to Brexit and coronavirus). Currently in consideration for Year 2/3 uptake.

Key Points:
1. The EoDB programme spans three projects (with PWC, IFC, and OGDs). The programme works with six central government departments, up to nine state governments, and a minimum of three trade facilitation agencies through the Tranche 1 pillar alone. A further two state governments may be covered via IFC, while the OGD pillar potentially covers another three departments. The T1 design phase was essential in identifying an initial set of possible beneficiaries across all projects and the expertise needed from HMG.
2. ‘Facilitating sustainable reforms to India’s business regulatory environment’ is the Tranche 1 programme, due to run from October 2019 - March 2023. The delivery partner – PwC - was procured in October 2019 and the design phase successfully completed with the submission of the design report (including GESI action plan). The design phase was initially planned for three months, but was extended due to internal and external factors such as unavailability of key stakeholders due to state elections and sub-contracting delays. Design phase activities were largely concluded by March 2020, but the start of implementation was delayed due to the outbreak of the coronavirus. The programme was redesigned in June 2020 to respond to the coronavirus crisis. Then, due to the HMT ODA prioritisation exercise, activities were paused again, and the programme entered implementation in October 2020.
  1. Output 1 exceeded expectations against some milestones due to stakeholder interest expressed during the design phase. Some of these stakeholders were not initially envisaged but the interest maintained the programme’s momentum and has added Vfm. This saw the programme expand its scope to cover additional geographies like Haryana (Better Regulation pillar), additional departments including GST Council (Tax Pillar) and Department of Logistics (Trade pillar). New areas of priority continued to emerge through the design phase and the programme now aims to cover topics such as Regulatory Impact Assessment, Advanced analytics for tax fraud investigation, which were not originally planned. Further interest has been generated amongst the private sector through engagements with members of leading industry associations like Federation of Indian Chambers of Commerce and Industry (FICCI), UK India Business Council (UKIBC) and Confederation of British Industry (CBI), leading to a well-rounded programme approach, validated by business needs. It also improves our overall coverage of the programme, without any additional cost burden, while working towards the outcomes laid out in the business case.
  2. Multiple consultations were conducted in Tamil Nadu, Karnataka, Gujarat, Telangana, Delhi, Haryana, Andhra Pradesh, and Maharashtra during the design phase. Multiple consultations were conducted in Tamil Nadu, Karnataka, Gujarat, Telangana, Delhi, Haryana, Andhra Pradesh, and Maharashtra during the design phase. Adaptive programming allowed us to support the governments of Tamil Nadu and Karnataka during the design phase, through partial implementation of reform tools in the areas of Property Registration and Construction Permits. The recommendations flowed from IFC's advisory support to GoI through the other part of the EoDB programme. This demonstrated, to both State and Central governments, the end-to-end potential of the programme from central policy to state implementation level. It further allowed these two state governments meet their reform targets for 2019-20 well ahead of schedule, while other states were delayed owing to the COVID lockdown from March.
  3. The delivery teams conducted a baseline assessment involving consultations with the business community covering industry associations, large businesses (domestic and international – including from the UK), MSMEs, and women-led businesses.
  4. The interventions are yet to be finalised for the trade facilitation component (Output 3). Despite achievements against the milestones, Output 3 has suffered the most delays in overall delivery due to factors such as sub-contracting issues with consortium partners, overlap with the PF funded Global Trade Programme and resulting re-alignments to ToC. This pillar engages with a large number of stakeholders with varying remits but similar objectives and building consensus has proved challenging.
‘Advancing India’s regulatory reform agenda by harnessing global expertise, which will help develop stronger independent institutions working to improve the business environment, (IFC)’ is an on-going project from February 2019 to March 2023.
  1. Capacity Building: The capacity building programme was intended to begin in August 2019. However, due to elections in May 2019, an unsuccessful round of recruitment, and coronavirus, training began in April 2020. This meant the programme end date being revised to March 2023 (from June 2022). The original job description prepared by DPIIT were more aligned to GoI internal policies, leading to a tepid response from private sector. DPIIT, then, asked IFC to assist in defining the eligibility criteria and roles and responsibilities of key secretariat staff, in order to procure relevant expertise from the private sector. As of July 2020, recruitment of RS staff is partially complete. IFC has completed four virtual orientation sessions and has deployed a training manual to be used during the programme life-cycle.
  2. Private sector interaction: The IFC team has met investors and the private sector to get feedback on existing regulatory bottlenecks (sectoral, regulatory) across government in order to develop an inventory. The team also engaged with leading British industry associations based in India – the Confederation of British Industry (CBI) and UK India Business Council (UKIBC) – to identify feedback. The findings fed more into the state reform plan and helped identify areas of future intervention (e.g. compliance time and cost)
  3. State Reform Action Plan (BRAP 2019): The IFC team supported DPIIT in ranking of states on their implementation of 187 reform points across 12 business regulatory areas in the BRAP 2019. In line with global best practices, the IFC team developed a methodology for ranking states on reform implementation and private sector feedback, which was implemented by DPIIT states. Ranking of states based on BRAP 2019 was released following this methodology. Going forward, these activities will be taken over by the Reforms Secretariat team, as originally envisaged in Year 2 and 3 of the Programme.
‘Knowledge and expertise-sharing to develop regulatory capacity and best practice in India, OGD’ is an on-going Tranche 2 project due to run from April 2019 to March 2023. Delivery is dependent on the availability of UK experts which was challenging due to pressures on departments’ capacities linked to Brexit and coronavirus. This element is closely linked to and dependent on the T1 programme, so delays in signing off the T1 work plan contributed towards the delay in signing MoUs with OGDs. Implementation will therefore pick up along with T1 implementation.
  1. Despite the challenges, the programme was able to host two missions. Experts from BRE visited India in August 2019 on a scoping mission and delivered a half-day session at a Cross-Border & Personal Insolvency training workshop. Separately, experts from RD delivered a half- day ‘Introduction to Regulatory Delivery’ to senior GoI officials at an event attended by Lord Ahmad. HMRC (Customs) delivered a session on Post Clearance Audit and Risk Management Systems at a national training event of Indian customs officials.

Programme Title	Energy and Low Carbon
Risk:	Moderate	Risk:		Moderate
Risk revised since last AR?	No	Risk revised since last AR?		No

Project Title (T2): Voluntary contribution towards IEA Clean energy transition programme
Output(s)			Milestones		Progress
Number of high level exchanges with relevant stakeholders in India to foster political will.			4		16. Overachieved due to significant interest.
Number of partnerships/ MoUs between India and relevant international organisations including from the UK and IEA to foster sector interest (both formal and informal arrangements)			4		11. Overachieved due to stronger stakeholder buy-in.
Number of events and workshops.			6		4. Underachieved due to coronavirus.
Number of participants in events and workshops for capacity-building.			110		260 (data on 150 was captured, of whom 45 were women). In addition, the project also supported a partner event hosting 550 participants.
Number of analytical reports produced for stakeholders and relevant sector organisations (more focused on desk research now due to coronavirus).			7		2. Underachieved due to coronavirus.
Project Title (T2): Voluntary contribution towards IEA for Energy Resilience and Security.
Output(s)			Milestones		Progress
Number of events and workshops including training and online events to increase capacity through knowledge exchange.			2		1 (1 event remaining due to coronavirus).
Number of participants in capacity building/ thematic events			40		65
Project Title (T2): Facilitating state/ city led initiatives to accelerate scaling up of electric mobility market in India.
Output(s)			Milestones		Progress
Number of consultations and interviews with Indian and UK stakeholders to draft recommendations for technical assistance in electric mobility sector.			80		120
Number of workshops organised with state policy makers and stakeholders to draft recommendations.			6		8 (3 reported in first Annual Review).
Number of stakeholders engaged through state workshops and consultations.			600		700 (400 reported in first Annual Review).
Number of delegation visits to improve awareness and knowledge for building future partnerships on Electric Vehicles with GoI and states.			2		2 (2 reported in first Annual Review.)
Number of stakeholders and policy makers engaged in knowledge exchange visits in and from the UK.			16		16 (8 reported in first Annual Review).
Number of state approach papers and national strategy papers drafted based on workshop and delegation recommendations.			15		15
Project Title (T2): Knowledge exchange on approaches for enhancing cleaner energy deployment through consumer behaviour and smart grids
Output(s)			Milestones		Progress
Number of UK market players and companies identified which are interested in expansion to India in smart power.			100		87. Underachieved as many UK commercial organisations were uncomfortable sharing data.
Number of meetings/ consultations organised to prepare recommendations for work packages that deliver TA in demand-side management and smart grids.			20		51
Number of targeted knowledge exchange national and state consultations.			6		6
Number of state and national papers drafted.			16		16
Number of stakeholders and partner organisations participated in roundtable and consultation events.			150		191 (60 women). Indian government agencies partnered with the project to jointly delivery a national consultation. Doing so freed up capacity for additional activities and engagement
Number of policy makers and stakeholders participated in the knowledge exchange delegation visits to and from the UK.			20		13 (5 women). Milestone not completely met due to changes in funding agreements (from fully to partially self-funded) and state elections.
Project Title (T2): Developing a business alliance for scaling up renewable energy and energy efficiency adoption.
Output(s)			Milestones		Progress
Number of consultations / interviews conducted to identify sector needs and refine intervention areas for corporate green leadership.			75		88 (17 women)
Number of state consultations organised with policy makers, stakeholders and relevant organisations for gap analysis report.			5		5 (4 reported in first Annual Review)
Number of stakeholders consulted in states to draft gap analysis report and identify intervention areas.			100		130 (70 reported in first Annual Review)
Number of MoUs signed for alliance formation (core alliance members: Alliance for Energy Efficient Economy, Carbon Disclosure Project, Integrated Association of Micro Small & Medium Enterprises of India (IamSMEoflndia), The Climate Group, The Energy and Resource Institute, World Business Council for Sustainable Development, World Resource Institute India, and World Wide Fund).			1		1
Number of stakeholder meetings/ events for alliance formation including secretariat selection and launch.			5		6
Draft business case for the green leadership alliance.			1		1
Project Title (T2): Decommissioning of oil and gas assets and site restoration in India: Assessment of best practices relevant to India’s context and priorities.
Output(s)			Milestones		Progress
Number of interviews conducted to draft Knowledge Report.			5		18
Number of Knowledge Reports (including inventory analysis, mapping of best practices and framework development) submitted to FCDO.			1		1
Number of stakeholders reached to present findings of report.			6		4
Project Title (T2): Mapping of global best practice policies and regulations relevant to India’s energy security priorities.
Output(s)			Milestones		Progress
Number of interviews conducted for drafting knowledge report.			20		45 (7 women experts consulted)
Submission of knowledge product report.			1		1
Number of stakeholders/ contacts reached to present findings of report.			40		10. Underachieved due to strategic shift to focus on energy transition activities. The report was only shared with GoI officials.

Key Points:
1. The Energy & Low Carbon programme encompasses seven T2 projects implemented in the reporting cycle. Five of these were completed while two remain in implementation. Two T1 programmes will be contracted by early 2021.
2. ‘Voluntary contribution towards IEA Clean energy transition’ is an ongoing project from July 2019 to March 2022. Year 1 activities have strengthened our engagement with key Indian stakeholders and is continuing to create buy-in in the energy landscape.
  1. IEA were the Bureau of Energy Efficiency’s (BEE’s) preferred partner to organise a session on energy efficiency at their Foundation Day in March 2020. IEA mapped out ongoing and planned initiatives by bilateral/ multilaterals in energy efficiency.
  2. IEA in collaboration with Prayas organised a Maharashtra Power System Transformation workshop to discuss the state’s specific power system developments. The participation of Maharashtra’s Electricity Regulatory Commission, State Electricity Distribution Company, and State Electricity Transmission Company will result in the development of policies that facilitate clean energy transitions. The workshop also facilitated join-up with DFID Power Sector Reforms Programme by strengthening relationships with the Center for Energy Regulation.
  3. The project collaboration with IEA also helped accelerate progress in reducing cooling demand and improving energy efficiency. It also created awareness of UK expertise, models and practices with countries such as Australia, Brazil, USA, Sweden, Japan, and Korea.
‘Voluntary contribution towards IEA for Energy Resilience and Security’ is an ongoing project from January 2020 to December 2022. IEA-FCDO collaboration has resulted in multiple achievements:
- Invitation is extended to India to participate in the review of Canada’s emergency response system and participation of the Ministry of Petroleum & Natural Gas (MoPNG) at senior levels, and senior representation from leading energy companies in the forthcoming workshop providing a strong endorsement for the objectives of IEA India workshop series.
- India is the first country to become a strategic partner to IEA. Whilst this was initiated before PF, work on one of the IEA streams has become possible due to the energy resilience project.
‘Facilitating state/ city led initiatives to accelerate scaling up of electric mobility market in India’ was implemented for fifteen months from December 2018 (including a delay of nine months). The programme faced challenges in ground delivery of events and quality of state papers. These were overcome with significant intervention by FCDO staff on logistics and expert technical input.
  1. Project impact was scaled-up through coordinated efforts by the regional network and cross-HMG engagement (opening up new areas of working for Science and Innovation Network, DIT, and Department for International Development).
  2. The project successfully raised additional funding by involving external partners such as Indian Chamber of Commerce who sponsored a UK delegation to Hyderabad to engage with the State Government; and Haryana Government sponsoring the UK-India Electric Mobility Forum in Delhi.
  3. EO Charging, a Suffolk-based electric mobility company was one of the beneficiary of the programme, acknowledged the value of the delegation in terms of its design, networking opportunities, and support beyond the project life cycle. EO Charging, expects to deploy a minimum of 1,200 smart charging points across India, helping to bring healthier air and better urban environments, as well as create at least 250 local jobs.
1. ‘Knowledge exchange on approaches for enhancing cleaner energy deployment through consumer behaviour and smart grids’ was implemented for nine months from February 2019. There was delay of four months in project closure to accommodate the participation of Indian delegates in the Low Carbon & Innovation (LCNI) Conference and Expo in Glasgow in October 2019. The conference was one of the most important events in Europe, and built awareness of the latest technologies and commercial and policy approaches in demand side management (DSM) and Smart Grids. The consultations, roundtable conferences and outward delegation led to a focused knowledge exchange between Indian and UK entities and reached common ground on the way forward, in terms of collaboration opportunities in smart grid and demand side management themes.
2. ‘Developing a business Alliance for scaling up renewable energy and energy efficiency adoption’ was implemented for one year from December 2018 (including delay of six months in project closure). The goal for the proposed alliance to lead to emissions reduction from India’s industrial (leading corporates, supply chains and MSMEs) sector thereby contributing to climate change mitigation.
  1. The number of interviews and consultations with stakeholders moderately exceeded expectations, thereby adding VfM. This was primarily due to positive feedback from stakeholders and a willingness to contribute to the alliance formation.
  2. The alliance intervention areas and activities also sought inputs from women entrepreneurship organisations, such as FICCI Ladies Organisation (FLO), and Women Entrepreneur Cell – Association of Micro Small & Medium Enterprises of India (IamSMEoflndia). LNM Auto was one of the panel members for secretariat selection to bring in representation from MSMEs.
  3. The next step is to secure funding from organisations (including FCDO) to deliver on the business plan. A proposal to FCDO is under discussion and if successful, would likely be funded through an accountable grant.
1. ‘Decommissioning of oil and gas assets and site restoration in India: Assessment of best practices relevant to India’s context and priorities’ was implemented for nine months from February 2019(including delay of four months in project closure). The main output of the project is a knowledge report to inform the design of UK’s potential collaboration with India on decommissioning oil and gas assets and site restoration.
2. Mapping of global best practice policies and regulations relevant to India’s energy security priorities’ was implemented for eleven months from December 2018. The project identified options for further collaboration, but due to an agreed strategic shift, the focus of PF India programme is now focused on clean energy transition and building resilience. Therefore, no further activities are planned.
3. PF also initiated a new project which specifically supports the delivery of our objectives at COP26, through engagement with youth and civil society. In this reporting period, first Young Thinkers Conference was conducted, which reached out to the current and next generation of policy makers to understand challenges and opportunities. The conference helped connect with the current policymakers as part of this project in January 2020. Events since then have been largely virtual but we expect to initiate further events in 2020.
As mentioned above, five projects are now completed with achieved milestones and two IEA projects are on-going. Completed projects were delayed primarily due to external factors such as general elections leading to unavailability of government stakeholders.

Programme Title	Financial Services
Risk:	Moderate		Risk:		Moderate
Risk revised since last AR?	No		Risk revised since last AR?		No

Project Title (T1): Financial Services
Output: Highly rated, high impact and ongoing expert assistance/ strategic exchange for identified stakeholders on defined relevant topics for insurance, pensions and capital markets with impact on GESI.
Indicator(s)		Milestones		Progress
Number of strategic exchanges with targeted stakeholders including GESI focus topics.		1		Not achieved. The strategic exchange (IUFKP Symposium) has been postponed to Year 2 due to coronavirus.
Number of recommendations following strategic exchange.		Report with >2 recommendations		Not achieved. Dependent on the strategic exchanges mentioned above in 1a.
Output: Target group participation in highly rated capability-building and training for specific regulators of Securities and Exchange Board of India (SEBI), Insurance Regulatory and Development Authority (IRDAI), Pension Fund Regulatory and Development Authority (PFRDA) disaggregated by gender.
Indicator(s)		Milestones		Progress
Number of officials trained from SEBI (Capital Markets).		30		Not achieved. Postponed to Year 2 due to financial year end reporting priorities of the regulator.
Number of trainings held for training SEBI officials (Capital Markets).		1		Not achieved. The training has been postponed to year 2 due to financial year end reporting priorities of the regulator.
Percentage of participants reporting the training, post event, as relevant and having improved their capability.		70%
Output: Stewardship: Consensus on inter-regulatory Stewardship Code, drafting support for new code, implementation support for roll-out of new code which takes into consideration social responsibility.
Indicator(s)		Milestones		Progress
Number of events to develop an inter-regulator Stewardship Code which addresses gender, social, and environmental concerns.		1 Roundtable		Not achieved. The roundtable has been postponed to Year 2 due to coronavirus.
Number of recommendation papers.		1		Achieved
Output: Insolvency: Capability-building among practitioners, judiciary and regulators, creditors.
Indicator(s)		Milestones		Progress
Number of insolvency professionals (IPs), regulators and creditors trained under the programme.		IPs: 500 / Regulators: 30 officials / Financial creditors: 60 / 10% of the seats reserved for women		Moderately Achieved. 618 IPs and 36 Regulators trained. IPs trained in collaboration with Insolvency and Bankruptcy Board of India (IBBI) and Institute of Insolvency Professionals (ICSI) (of which over 10% participants were women). Attendance and feedback sheets pending from IBBI and ICSI. / Creditors: postponed to Year 2 due to coronavirus.
Percentage of participants reporting the training as relevant and having improved their capability		70%		Achieved: 73%
Output: Insolvency: Policy design & recommendations towards a more consistent insolvency framework which takes into consideration insolvency challenges that women and other socially excluded groups face in the Indian context.
Indicator(s)		Milestones		Progress
Number of policy recommendations provided to MCA/ IBBI towards consistent and transparent framework.		2		Achieved. 3 recommendation papers submitted to MCA: A review of role of Liquidators and the Official Liquidator in India (Jan 2020); Avoidance transactions regime in India (Feb 20); Pre-pack circular (Mar 20).
Output: RFI: Identified organisations supported to increase their attractiveness to domestic and international lenders/ investors, including from UK, based on an inclusive investment strategy for economic, social, and green infrastructure; progress on specific fund raising projects and increased access to international market infrastructure financing.
Indicator(s)		Milestones		Progress
Number of investors connected through India UK Infrastructure Finance Hub (IUKIFH) and/or roadshows to showcase opportunities in the Indian infrastructure sector.		5		Achieved. IUKIFH connected with 5 investors (HDFC Bank, Yes Bank, Axis Bank, NIIF Infrastructure Finance Ltd, and State Bank of India) as part of investor connect. Supported Pune Metropolitan Region Development Authority in discussions (2 meetings) with HDFC Bank to showcase the financing opportunity for a road project.
Number of organisations and/or projects supported in preparation of financial plans and guides in preparing for the process of fund-raising through IUKIFH.		2		Achieved: 2
Output: Innovation and Enablement: Support packages for 12-15 innovations and growth phase GESI compliant fintech projects aligned to financial inclusion and Small & Medium sized enterprise (SME) finance.
Indicator(s)		Milestones		Progress
Number of FinTech* projects (12 start-ups) provided support packages (mentorship, industry connect, fund raising support, tax, regulatory, strategy support).		6 new ideas identified to scale up. 1 Pitch event - 4 existing ideas identified.		Achieved. 2 Hackathons delivered identifying 6 new ideas for scale up. 1 Pitch event delivered identifying 4 existing ideas
Output: Connectivity – Observable growth in industry partnerships, collaborations stimulated by programme disaggregated by gender.
Indicator(s)		Milestones		Progress
Number of delegations facilitated by UK-India FinTech Hub.		1		Not achieved. The planned visit of 8 selected FinTech award delegation winners has been postponed to Year 2 due to coronavirus.
Number of international (including UK) India FinTech partnership discussions initiated as a result of delegations and bilateral meetings facilitated by UK-India FinTech Hub.		3		Not achieved. Dependent on the delegation visit above.
Output: Capability building and technical assistance. Workshops delivered to relevant senior officials across all 4 regulators on FinTech Reg and Reg Sandbox and prioritised states on enabling policy and promoting inclusion.
Indicator(s)		Milestones		Progress
Number of capability-building workshops delivered to relevant personnel regulators (on conducive FinTech regulation and reg sandbox operationalization).		Preparation of training themes and agenda (Aligned with the London FinTech week which due in July 2020).		Achieved. Agenda and training themes have been prepared. The capacity-building workshop was planned to be delivered on the sidelines of the India FinTech Festival (IFF). Both events have been postponed to Year 2 due to coronavirus.
Number of workshop on development of state FinTech ecosystem by International (including UK) experts.		Preparation of training themes and agenda.		Not achieved. The training has been postponed to year 2 due to coronavirus.
Project Title (T2): Strengthen India’s financial markets by scoping interlinkages between Indian and UK capital markets.
Indicator(s)		Milestones		Progress
Number of reports submitted.		1		Achieved
Number of roundtables organised to present the report to policy makers and market practitioners, both domestic and global.		1		Achieved
Project Title (T2): Chevening Financial Services Fellowship.
Indicator(s)		Milestones		Progress
Number of candidates selected for Chevening Financial Services Fellowship programme.		8		Achieved
Number of hours of classroom teaching attended in UK.		150 hrs		Achieved
Number of field visits attended in UK.		30		Achieved
Project Title (T2): Deliver Economic Outcomes for the Fintech Awards
Indicator(s)		Milestones		Progress
Number of applications received.		100		Achieved 62
Number of companies shortlisted.		20		Achieved 15
Number of companies selected.		10		Achieved 3

Key Points
1. Under Output 1 of our Tranche 1 programme – delivering by Ernst & Young - the programme provided expert assistance to financial regulators in India, including IBBI (insolvency), PFRDA (pensions), IRDAI (insurance) and SEBI (capital markets); as well as government departments (Ministry of Finance, MCA); industry players, and intermediaries.
2. To support SEBI’s regulatory purview, the programme presented a comparative study of Indian regulations on stewardship across various areas (Output 2). This study served as a key input to help SEBI draft the hugely important Stewardship Governance for Mutual Funds and Alternative Investment Funds, which were issued in December 2019. The implementation of the Stewardship Code will serve to significantly strengthen the corporate governance framework of listed companies in India, by enabling institutional investors to play an active role in the management of their investee companies.
3. Under Output 5, the programme took forward the long-standing UK-India cooperation on strengthening the insolvency regime in India, by enabling exchange of technical know-how through capacity building sessions and study visits. A strategic exchange programme was held, wherein a GoI delegation led by the former Secretary of the MCA, visited London in February 2020. Further, the programme also exceeded its milestone target for Output 5, training over 700 insolvency professionals on valuation and avoidance transactions. This included i) training on the UK valuation regime, ii) avoidance transactions training for Institute of Chartered Accountants of India (ICAI) members, iii) a webinar in collaboration with the Insolvency and Bankruptcy Board of India and ICSI Insolvency and Professionals Agency (IPA), and iv) a workshop on ‘Reviewing and Challenging Avoidable Transactions under IBC’. The programme also provided training to 29 officials from India’s insolvency regulator, IBBI, which was delivered by the UK’s Better Regulation.
4. The programme exceeded its Output 6 target of providing regulators with 3 recommendation papers on creating a consistent and transparent insolvency framework. The Insolvency Law Committee in India will draw upon these recommendations to draft updates and amendments to the Insolvency and Bankruptcy Code. The recommendations included: i) A draft report on ‘A review of role of Liquidators and the Official Liquidator in India’ was submitted to the MCA and presented during the Insolvency Knowledge Exchange Programme in London; ii) A technical paper on the avoidance transactions regime in India was submitted to MCA in February 2020 and has been received positively by the GoI; iii) A presentation on using technology for augmenting existing processes has resulted in the MCA requesting future programme support with the development of related legislation.
5. Under Output 7, the programme partnered with Indian organisations looking to raise private finance for India’s vital infrastructure sector, a key component of India’s economic growth story. The India-UK Infrastructure Finance Hub, set up under this programme, partnered with PMRDA by providing capacity support to prepare financing plans. THE IUKIFH also supported five organisations (HDFC Bank; Yes Bank; Axis Bank; NIIF Infrastructure Finance; State Bank of India) to increase their attractiveness to domestic and international lenders/investors. These were selected from a list of 100 organisation, based on objective criteria that included prior fundraising experience and location attractiveness.
6. The India-UK FinTech Hub, under Output 8, brings together world-class UK experts to mentor the next generation of cutting-edge FinTech start-ups to expand domestically and globally - transforming their ability to drive financial inclusion by providing credit and insurance products to marginalised groups. The programme also delivered two virtual hackathons on ‘India Finclusion Challenge’ to identify early-stage FinTech firms that focus on Small, and Medium Enterprises and financial inclusion. These hackathons helped identify six early stage ideas for innovative financial products or distribution solutions which will now be incubated under the Innovation and Enablement work stream. An apt example of the success of this programme is Onfido, a leading UK FinTech company providing e-KYC services that can dramatically reduce the cost of financial services delivery. Onfido participated in the FinTech Awards in 2018, and has recently signed a massive export win in March 2020. Today, India is Onfido’s third largest market in the world.
7. The programme has undertaken preparatory work to support a capability building workshop for Indian regulators to be delivered by the UK's Financial Conduct Authority (FCA) in support of Output 9 - – currently rescheduled due to coronavirus
8. Output 10. The programme drafted a report on ‘A review of the policies to build local currency bond markets for India’ analysing the recommendations and policy initiatives to develop bond markets in Indian and international markets. These reforms will enable: (1) Indian firms to raise finances using local currency bond markets in either domestic or international markets (such as the masala bond market in London), (2) domestic and foreign investors to be able to invest in these markets, and (3) for issuers and investors in these markets to manage the associated risks. It also delivered a roundtable featuring a panel of eminent experts to discuss and establish a way forward on issues associated with bond market development.
9. Tranche 2: ‘Deliver Economic Outcomes for the Fintech Awards’ is an ongoing project from March 2020 to December 2020, led by DIT and delivered by India Angel Network (IAN) Incubation and Mentoring Services. The purpose is to support the development of an open and inclusive financial services sector in India by facilitating exchange of global expertise through the delivery of Fintech Awards. This project is complementary to the T1 project's FinTech pillar. The shortlisted companies will be part of the India cohort. Due to coronavirus, synergies with various events conducted by EY, and the ODA prioritisation exercise, we have merged the India cohort to include companies selected from the shortlists by India Angel Network and EY.
10. While the programme has in place several achievements, aspects of programme delivery were delayed, as a result of capacity issues with the supplier as well as impact of the pandemic. The original draft design report, submitted by EY in June 2019, was missing crucial sections, including the ToC, logframe and ABB. Despite extensive engagement by the FCDO team, the design phase concluded in November 2019, with substantive changes to the programme management team agreed. The delay in closure of the design phase, as well as capacity issues in some parts of the EY technical team (FinTech pillar in particular) meant that there was only partial achievement of outputs planned for Year 1 of implementation. The delayed move into implementation also meant that several events were scheduled for March 2020 and were then delayed again due to COVID-19. The scope of the programme has been slimmed down on fewer priorities based on these experiences. The team worked hard to successfully resolve these issues and establish systems with agreed understandings on expectations. Due to the impact of coronavirus, the work-plan has been refocused to ensure momentum and relevance in the current context.
11. The success of the Insolvency and Raising Finance for Infrastructure pillars has provided the programme team an insight in to key components of successful programme delivery. The Insolvency pillar, in particular, has delivered high impact activities that have strengthened the insolvency regime in India – a key ease of doing business component, which has become increasingly crucial to India’s response and recovery to the economic impact of the pandemic. The FCDO team continues to work closely with EY to ensure that these learnings are suitably incorporated in to core programme delivery going forward. The programme team has also put in place robust monitoring and feedback mechanisms, including continuous dialogues between FCDO and all key government stakeholders, to ensure that the programme responds to emerging priorities of GoI and remains relevant and effective.

Programme Title		Skills for Jobs
Risk:		Moderate		Risk:	Moderate
Risk revised since last AR?		No		Risk revised since last AR?	No

Output 1: Strengthened Skills ecosystem for selected sectors.
Indicator(s)	Milestones		Progress
1.1. Numbers of trainees supported by formal assessments (Direct, Indirect).	40,000		Overachieved. Nearly 100,970 trainees assessed (directly and indirectly). These include apprentices, persons with disabilities, candidates who received training by pool of trainers using UK expertise.
1.2. Number Qualification Packs (QP) and transnational standards.	10		Achieved. Total of 11 QPs developed. Eight in the Electric Vehicle sector. Three in PWD sector.
1.3. Number of master trainers and assessors trained.	100		Achieved. 245 Master Assessors, Assessors and Trainers were trained in the identified sectors using UK experts in November 2019 and February 2020.
1.4. Pilots for sectoral partnerships.	8		Achieved. 6 sector partnerships: / New partnership with WHO to reach 11,000 frontline workers and laboratory staff to tackle coronavirus. / 3 pilots for training 94 people with Intellectual Disabilities (ID) and Visual Impairment (VI) with 3 partners. / Kick-started ‘Inclusion 100 Pilot Programme in India’ with Leonard Cheshire to promote inclusion of 1500 PWDs in apprenticeship ecosystem. / Partnership with NPTC Group of College and TISS[2] established.
1.5. Feedback from Sector Skills Councils.	Qualitative Indicator		Achieved. Feedback on the training of trainers and assessors programme is very positive.
Output 2: Expeditious & effective implementation of government skilling schemes
Indicator(s)	Milestones		Progress
2.1. Overarching mechanism for India-UK skills collaboration.	Bi-annual meetings of Joint Steering Committee.		Achieved. / Second meeting organised with a thematic focus on disability. Organised at Muskaan on 9th January 2020, alongside live trainings of youths with intellectual disability;
2.2. Policy and regulatory support to the Central Ministry/ State Skills Mission.	Support Government on Apprenticeships, Assessments, PwD, Standard Operating Procedure (SOP), Sector Skill Council (SSC), India International Skill Centre (IISC), Transnational Standards.		Overachieved. Organised a study tour to the UK for Indian delegation comprising of senior officials in March ’20 - received positive feedback. / Onsite dedicated TA to the leadership at MSDE for refining and strengthening policies for Apprenticeship in India including SOPs for operationalisation of training during and post COVID-19. / Support to ideate and design a ‘Skills Development Impact Bond. / Learning session conducted for the first batch of IES candidates (ISDS cadre) (28 participants) on UK best practices by People First, UK. / Ongoing policy support to NCVET[3] / Ongoing Policy support to Directorate General of Training / Progressed a pilot on Degree Apprenticeship for the Banking, Financial Services and Insurance Sector.
2.3. Qualitative indicators (feedback from State Govts/ GoI).	Strengthened capacity of State Skill Missions		Achieved. / Organised technical learning sessions and employer engagement workshops with Gujarat, Maharashtra, State Missions (in EV, PWD sectors).
Output 3 :Enhanced contributions to skilling in partnership with private sector including with UK businesses and institutions
Indicator(s)	Milestones		Progress
3.1. Number of corporates, including UK businesses, in India supported on apprenticeship and registered under National Apprenticeship Promotion Scheme (NAPS).	10		Achieved. / As a result of NAPS dissemination workshops, 10 new businesses registered on NAPS portal in the Renewable Energy and Aerospace & Aviation sector. / Conducted 2 Apprenticeship workshops, reaching out to 98 industry players in Aerospace & Aviation and Electric Vehicle sectors. / Direct support to corporates is no longer given in the programme. Indicators to be revised.
3.2. Number of Industry Partnerships in the identified States & Sectors through MoUs, CSR on Skilling.	100		Moderately achieved / Several forms of partnerships with Indian corporates ranging from co-hosting training and sharing of experts as trainers as in the case of Larsen and Toubro, Hindustan Aeronautics Limited (HAL), XRCVC Mumbai and Blind People Association, Ahmedabad and WIPRO, Bangalore. / Other partnerships include co-designing of new pilots / Corporate partnerships formed for securing employment opportunities from our pilots e.g. Big Bazar and Sarovar Portico. / Other forms include B2B meetings with UK providers like IIM Bangalore, Evoluer, Ashoka University.
3.3. UK-India Institutional partnerships.	8		Achieved / Developed a focused strategy to achieve secondary benefits. / Introduced Dudley College and Leonard Cheshire to Indian stakeholders through SFJ programme, / Facilitated 10 B2B meetings for National Star College UK with private Indian companies, / UK visit for Indian delegation, with help from UK Skills Federation (an association of UK training providers), / Designed India visit for 11 UK delegates to introduce them to Indian skills market in March 2020. The activity got halted due to coronavirus pandemic. Designing an e-session of UK providers.
3.4. Progress of partnership with Tata Trusts.	Indicators and baseline finalized.		Activity on hold.
Output 4: Skilling through innovation and piloting in up to 3 states, especially in the selected sectors
Indicator(s)	Milestones		Progress
4.1. Projects piloted in states	2		Achieved 2 projects have been piloted.
Output 5: Demonstrate / disseminate Good Practices / Lessons Learnt
Indicator(s)	Milestones		Progress
5.1. Sharing UK best practices.	10		Achieved
5.2. Communication products, lessons learnt and documentation of case studies (Living Bridge stories).	10		(Moderately achieved / Design communication collaterals for the promotion of NAPS like pamphlets and brochures. / Social media content development and management for NAPS promotion. Report on accessibility audit under Rajkot Industrial Training Institute (ITI) pilot. / Study on Assessing PWD ITI in Ahmedabad – Blind People’s Association. / Article on insight on ‘virtual training for PWDs in times of pandemic.’ / 10 pre-event, post-event communications to share on skills news portals and partners’ websites to share interventions and events
5.3. Knowledge products.	5 Knowledge products / 2 Quarterly Progress Reports		Achieved. Quarterly progress report prepared. 4 knowledge products were developed and disseminated: / Study on ‘Measuring productivity gains through apprenticeships’. / BFSI Industry – A future Skills Perspective. / Study to identify future job roles in the biomass sector. / Report on learnings of innovative PWD pilot.
[3] The National Council for Vocational Education and Training- A regulatory body for all long and short term vocational trainings

Key Points:
1. ‘Skills for Jobs’ (Joint Ex-DFID India and PF) is an on-going programme from September 2013 to March 2022. The programme is in the process of producing a dedicated Annual Review report (reference documents can be found here).
2. Skills development remains a GoI priority area as referenced in PM Modi’s speech on World Youth Skills Day in July. India wishes to learn from the international community, and partner with globally recognised UK institutions to get its workforce internationally recognised qualifications, aiming to make India the skills capital of the world.
3. As part of the India-UK Government-to-Government (G2G) MoU on Skills Development, the 2nd UK-India Joint Steering Committee Meeting was organised in January 2020. The meeting was hosted by Muskaan (a Non-Governmental Organisation (NGO) offering training facilities for people with disabilities), to showcase live training for youth supported by the programme – an area which has received limited attention in India before.
4. This year saw increased requests for policy level support as well as greater involvement from the MSDE, National Skill Development Corporation (NSDC), Directorate General of Training (DGT), National Council for Vocational Education and Training (NCVET), and Gujarat and Maharashtra State Governments. Dedicated policy level support is being provided for developing policy guidelines and frameworks, promotion of government skills scheme with industry engagement. These have been underpinned by the support on analytical studies, evidence, pilots and contextualisation of the UK best practices.
5. A 5-day UK study tour was organised in March 2020 to provide first-hand experience of the UK vocational education and training systems for Indian government officials. The visit helped in mutual learning and explored partnerships with the help of knowledge sessions to highlight the best of Britain e.g. a session on UK regulatory systems and apprenticeship model, visit to Wales to explore potential partnerships with GlobalWelsh and visits to training facilities.
6. The onset of coronavirus meant revisiting and repurposing the programme. This was done by adapting delivery mechanisms (shifting to online and e-sessions), taking on new partners (WHO for health work), and enhancing the scope of target recipients (e.g. health workers). Coronavirus has caused a temporary reduction in the pace of training activities due to restrictions on travel and onsite training. However, the project has continued to realign interventions and methods of delivery, making it as strategic and relevant as possible.
7. The project is actively working on UK skilling institutions for potential partnerships with Indian agencies. These will be in the form of India-UK partnerships (G2G, Government-to-Business (G2B), and B2B) to train youth to secure jobs domestically and globally as well as develop sustainable commercial models for UK providers to work in the Indian market. An inward delegation for UK skills providers was planned in March but was paused due to coronavirus. Smaller achievements are being made the form of interest for formal partnerships. For example, after the workshops on ‘Use of assistive technology to train PWDs’ by the UK’s National Star College (specialising in further education for PWDs), some Indian corporates, foundations, and training institutions have expressed interest in partnering more formally.
8. The programme works closely with teams across the British High Commission network in India and is well aligned with overall UK (and PF) priorities such as climate change, gender, financial inclusion, urban infrastructure, and the UK-India living bridge.

Programme Title	Urban Development
Risk:	Moderate			Risk:	Moderate
Risk revised since last AR?	No			Risk revised since last AR?	No

Project Title: Climate Resilience Cities for Shared Prosperity (CRESP)
Output 1: A set of large scale, high-value, exemplar city interventions (‘High Value Projects’ HVPs) with Invitations to Tender (ITTs) amounting to £500m developed and brought to the market that promote inclusive economic growth and poverty reduction.
Indicator(s)		Milestones	Progress
Project Finance Reports (Best Practices) for 2 HVPs.		2	2 reports submitted (June 2020). Bengaluru & Chennai prioritised for implementation. Delivery commenced.
Draft Information Gap Analysis reports submitted for 5 HVPs.		5	2 reports submitted (July 2020). Milestone for remaining 3 HVPs could not be delivered due to impact of coronavirus.
Procurement Strategy Reports prepared for each HVP issued. Contributing towards programme objectives including mainstreaming GESI and promoting inclusive economic growth.		5	1 report (Chennai) is delayed due to the pause of activities during ODA-prioritisation. It is under review and revision. Milestone for remaining 4 HVPs could not be delivered due to impact of coronavirus.
Draft GESI and Safeguarding reports submitted for 5 HVPs.		5	2 reports submitted, including revisions (July 2020). Milestone for remaining 3 HVPs delayed due to coronavirus.
Design Reports produced.		8	1 city selection report, 1 project selection report, 5 Strategic Outline Business Cases approved (March 2020), 1 coronavirus resilience study (methodology) submitted (July 2020).
Secondary Benefit Action Plan submitted.		1	Being jointly prepared by Mott McDonald, DIT, and FCDO.
Output 2: Senior officials, including women, are upskilled to address capacity gaps and new approaches to access project delivery skills.
Indicator(s)		Milestones	Progress
Draft Needs Assessment Reports submitted.		6	3 reports (Project Delivery Skills Framework (PDSF), Integrated Transport Authority (ITA), Building Information Modelling (BIM) submitted (July 2020) / In accordance with the finalised mini-Activity Based Budgeting (ABB) for the EDP. 3 reports delayed due to coronavirus.
Outline Plans and Detailed Plans submitted.		1 Outline plan / 1 Detailed plan	Finalised in March 2020.
Output 3: Major innovation partnerships announced publically in response to the prevailing requirements of the GoI that foster improved collaboration between urban actors; disseminate lessons from both domestic and international experience in inclusive and sustainable urbanization.
Indicator(s)		Milestones	Progress
Draft reports submitted on identification of Integrated Transport Authority model and Integrated Transport Platform.		2	1 report submitted (July 2020). In accordance with the finalised mini-ABB for EDP. Delivery of other report could not be taken up due to impact of coronavirus.
Outline Plans and Detailed Plans submitted.		1 Outline plan / 1 Detailed plan	Finalised March 2020.
Number of India BIM current state analysis reports and BIM implementation roadmaps		2	Roadmap and report will be developed after the workshop, which was delayed due to coronavirus. Approvals from Central Public Works Department (CPWD) have been received to conduct virtual workshop in September.
Tranche 2: Strengthen Tamil Nadu Government’s disaster risk reduction and mitigation response in cities with particular emphasis on restoration and protection of fragile ecosystems, prevention of salt water intrusion, along with best practices on rain water harvesting and general disaster risk reduction practice
Indicator(s)		Milestones	Progress
Number of policy papers, roadmaps, approach papers, reports (including inception reports) etc. produced. All including gender and inclusion considerations.		3	3 reports submitted: Inception workplan; Draft approach paper; Final approach paper.
Engagement/ consultations with Govt of Tamil Nadu officials (Dept of Disaster Management, etc.) with emphasis on restoration and protection of fragile ecosystems, prevention of salt water intrusion, and general disaster risk reduction.		Consultations held, interviews conducted with various stakeholders (GoI officials, departments, HMG officials, businesses, industry bodies).	Meetings held with numerous stakeholders to collect information and inputs on stress factors for each ecosystem, including: / 13 state and regional departments and agencies / 3 universities and research centres / 3 NGOs / As well as wider meetings with NGOs, researchers, members of civil society, local residents living near the ecosystems.
Number of workshops and Knowledge products delivered, with sufficient stakeholders attending, sharing best practices on inclusive and sustainable growth.		1	2 Knowledge Exchange workshops delivered. Conducted with stakeholder government departments (6), members of civil society (7), NGOs (10), and academia (7). / Knowledge product could not be completed due to restrictions on travel and engagements amid coronavirus.
Tranche 2: Support CPWD, Government of India to better recover, recycle/ treat and reuse/ utilise construction & demolition (C&D) waste generated in India, by drawing on international best practice, including from the UK, to effectively reduce environmental impact in terms of energy consumption, pollution, waste disposal and management.
Indicator(s)		Milestones	Progress
Number of policy papers, roadmaps, approach papers, reports (including inception reports) etc. produced that also include G&I considerations.		2	Inception Report submitted. / However, draft strategy report has not yet been delivered, in part due to coronavirus and the difficulty in scheduling stakeholder meetings.
Engagement/ consultations with officials from CPWD and C&D waste handling plants in select cities to identify areas to better recover, recycle and reuse C&D waste generated in India.		Consultation meetings, interviews with various stakeholders.	CPWD gave approval for 4 shortlisted cities to conduct research on C&D waste management. / Due to restrictions on travel and engagements, progress towards this activity is delayed.
Number of Knowledge Exchange workshops and knowledge products delivered.		2	Pending due to delay in above deliverables.

Key Points:
The main objective of Output 1 (T1) was to identify five high value urban interventions from the seven priority states, where the PF could capitalise on international and UK best practices to enhance the benefits of the HVPs and increase shared prosperity. Coronavirus will have a significant global impact in the way cities are planned and urban projects executed. The HVPs were therefore reviewed to assess their validity in this context, and Chennai Water Security and Bengaluru Sustainable Urban Transport, Visakhapatnam Environmental Improvement programme, Pune Flood, Waste protection project and Surat City Resilience project were selected. Selection drew on literature published by multilateral organisations and a rapid assessment Investment Sifting and Evaluation Tool (INSET) tool. The identified HVPs provide essential services required to manage disasters, climate change, epidemics, foster inclusivity, enhance economic activity, and improve the environment of the city. Resilience against climate impacts and environmental considerations were important criteria used for selection of HVPs in the Extended Design Phase. All shortlisted HVPs have potential to access green financing.

1. Six capacity-building thematic areas were recommended for delivery through Output 2 (T1). However, due to coronavirus the themes were reviewed in March 2020, based on their relevance and adaptability for pandemic/ disaster management. Three were prioritised: (i) setting up an Integrated Transport Authority (ITA)/ Urban Observatory, (ii) use of BIM, and (iii) use of PDSF to plan and implement resilient urban infrastructure projects. These themes will help in the management of disasters, fostering inclusivity, improving city governance, and contributing to economic rejuvenation.
2. The Innovation Plan of Output 3 (T1) defines an approach to improve collaboration between urban actors, and disseminate lessons from domestic and international experience towards inclusive and sustainable urbanisation. Five innovation themes and six potential areas of strategic partnerships were identified. Four partnerships are to be designed and established. However, due to coronavirus the themes were reviewed and the following were prioritised for the Extended Design Phase: (i) Setting up of an ITA in Bengaluru; and (ii) Integrated Transport Platform (ITP) (pilot for Urban Observatory).
3. All T2 outputs were achieved except one: a knowledge dissemination workshop and report could not be completed due to coronavirus – a no-cost extension to September 2020 was agreed.
4. The Tamil Nadu risk reduction project explicitly considers vulnerable sections of populations, focusing on areas of concerns, and framing recommendations and actions for the approach paper. Drafting of the C&D Waste project will take into account women-specific opportunities in the sector; addressing their particular health & safety issues; provision of health, childcare and education; and removing social stigma surrounding waste work.
5. Development of a draft strategy to guide planning on C&D waste management has slowed due to coronavirus restrictions, and it was agreed to extend the contract to September 2020. The Implementer’s performance has been adequate, however some challenges have required input and management by the programme team, including: budget management (variances on ABBs), not implementing GESI commitments, and not producing reports that meet our expectations.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE
1. Programme spend over the review period is £8,513,974, against a budget of £9,627,795 (Table 1). This covers 16 months including FY 19/20 and four months in FY 20/21. At the portfolio level, the £1,113,821 underspend is attributable to a combination of delays resulting from state and local elections, extended timeframes to clarify requirements, and the impact of coronavirus from March onwards.
2. The key cost drivers of the programme are programme delivery and admin, accounting for 87.5% and 9.8% of spend respectively (the remainder is costs paid to FCDO for use of the overseas platform). Admin costs are relatively high as a percentage of overall spend as only two out of five strands have reached full delivery and spend stage. If administration costs are maintained at the current level until 2022/23, they will account for just over 5% of total programme expenditure if measured against the original £60m allocation. The overall programme budget has since been revised to £47.85m. The budget reduction is due to reduced scope of Energy & Low Carbon program taking into account the reduced timescales available for delivery and Financial Services as a result of ODA prioritisation in July-August 2020. . The admin cost will be closely monitored with JFU to endeavour to keep within the target. The outcome of the current Spending Review process will provide more clarity on the programme’s projected proportion of Admin costs.
3. The Energy & Low Carbon T1 programme went to market with a reduced value (£7.7m) and more focused scope. Financial Services’ scope will be strategically reduced (by at least £1.65m) following the ODA prioritisation process, with spend being focused on the areas showing greatest initial impact. These budget adjustments will reduce programme impact, and the scope of the programmes have been revised accordingly.
4. The underspends shown in Table 1 for Energy and Low Carbon (69% of budget) and Ease of Doing Business (74%) are directly attributable to delays linked to coronavirus where limited spend occurred on programmes between April-July 2020. Coronavirus has also impacted on projects that are in delivery, resulting in changes to project plans and a shift to a hybrid delivery model with more online delivery and less face-to-face meetings (some activities have been postponed where e.g. Government of India stakeholders initially preferred face-to-face engagement – however virtual engagement is now the norm across all delivery).

Economy
1. All programme contracts have been procured through open tender processes which has ensured selection based on both technically sound and financially competitive bids. All programme strands follow Activity Based Budgeting (ABB), and payments are based on milestones and results upon completion of activity and quality review.
2. The programme team verifies documentation before payments are made, and undertakes random sampling to verify expenses. Programmes monitor average daily fees and Trust Fund administration fees, but we recommend that those costs are benchmarked against similar activities from other India development programmes to check that the costs remain competitive with the market and to assess where cost efficiencies may be realised. This will be done in consideration with the current difference in PF and former DFID operating framework. Additional support from Economics Unit will be required to coordinate with other PF programmes on finding suitable benchmarks and to obtain clear guidelines on sharing this information with delivery partners.
3. This review has found examples of strands renegotiating costs when a different delivery model has been required (Energy & Low Carbon), and robustly challenging delivery partners to ensure that deliverables meet programme team requirements (Financial Services). In the latter, the delivery partner provided inputs on a pro-bono basis during the Design Phase. Coronavirus has prompted programme strands to reconsider their approach and adopt virtual communication channels which has resulted in a reduction in travel and accommodation costs, savings which contributed to the ODA prioritisation exercise.

Efficiency
1. The programme has demonstrated adaptability and resilience in the face of coronavirus and all strands have delivered broadly in line with (and in some areas exceeded) milestone output indicators. The ODA prioritisation exercise has resulted in the shift of some milestones for future months. The programme remains on-track, and the overall impact of the programme is expected to be realised beyond 2023.
2. It is also clear that programme strands are using existing supplier and stakeholder relationships to deliver maximum impact. Examples include the Financial Services delivery partner’s links to key regulators in support of its Pillar 1 activity. The EoDB strand has benefitted from their main supplier’s familiarity with the business reform environment in India which has expedited stakeholder mapping and consultation exercises at the state and central government levels. The IFC Trust Fund (EoDB) has utilised its relationships with the GoI to speed implementation, particularly in the two cities added to the strand. State-based Prosperity Advisers have added value to the Energy & Low Carbon programme by providing programme management expertise and by strengthening local stakeholder engagement.
3. The programme team is working across strands to optimise synergies to deliver results sustainably and at scale as recommended in the May 2020 Readiness Review. This remains an on-going process and will be further formalised.
4. The programme team has made significant progress in developing its four strand-level ToCs and logframes in close collaboration with delivery partners. Work to further refine logframes is ongoing, particularly for the strands that have yet to reach full delivery for Tranche 1.

Effectiveness
1. The India programme is already delivering impact in a number of areas. For example the success of the electric mobility project has generated both policy and commercial outcomes, and the GoI is keen to initiate a joint programme on electric mobility with seed funding under the Energy & Low Carbon programme. Commercial wins include the UK-India joint venture ‘Yahhvi’ operation involving UK’s EO Charging to make and distribute smart charge-points in India. The EoDB strand was instrumental in designing and implementing reforms which have contributed to India featuring in the In Doing Business Report’s list of top 10 improvers for the third consecutive year – a reflection of industry and practices and feedback. Onfido (leading UK FinTech providing e-KYC services that could dramatically reduce the cost of financial services in India) from the 2018 FinTech Awards (Financial Services program) signed an export win in March 2020. The Annual Review has found evidence of Tranche 2 recommendations being integrated into the design of Tranche 1 programmes.
2. Further work is required within the programme team to assess how emerging results for the current year relate to the overall results trajectory, particularly given the coronavirus context. To this end, the programme should focus on outlining where it is on - and off- track to contribute to expected outcomes and impact, and what action/ course correction is planned in the year ahead as a result. We recommend that this activity occurs once the budget implications of the Spending Review become clear in November 2020.

Equity
1. The programme completed the GESI score card[4] and underwent a Gender & Inclusion (G&I) review by the Evaluation and Learning supplier during April-May 2020. Each programme is compliant with the PF G&I Policy and Guidance (receiving a score of 3) with Urban having the potential for Women and Girls ‘economic empowerment’ (i.e. received a score of 4). All programmes adhere to ‘Do no harm’ through a Gender Action Plan & Impact Assessment study.
  [4] GESI scorecard is used to rate programmes and projects against PF, Joint Funds Unit G&I Policy and Guidance. The scorecard rates programmes against five dimensions (programme design, internal capability and incentives, financial resources, accountability mechanisms, and partnerships)
2. As part of the initial interventions, major barriers to women led businesses, people with disabilities and MSME’s were identified and strategies were devised to address them.
3. All Tranche 1 suppliers have a G&I specialist in their team to maximise opportunities to deliver greater equality, including partner capacity building and implementation. The programme has ensured that most projects are tracking gender balance through collection of disaggregated data. GESI indicators have been included within logframes, ToCs and VfM processes.

Value for Money
1. We judge that the programme is on track to deliver good value for money despite the challenges of the past year (documented in the March 2020 VfM scorecard). Financial performance is improving, particularly as delivery partners have become attuned to monthly reporting requirements. Programmes have demonstrated agility and resilience in response to the coronavirus and have streamlined activities to reflect the new contextual realities and budget position post-ODA prioritisation. Work to refine logframes and the programme and strand level ToCs is still ongoing and the programme team will need to continue to act upon the recommendations provided within the Readiness Review to continue making improvements in this area. Dedicated VfM indicators will be prepared in the coming months and reflected in the annual score card exercise.
2. The main risks concern further delays, and the impact that this would have on benefits realisation. The Fund Level Evaluation Cycle 2 review has recommended “an extension of Prosperity Fund budgets beyond March 2023” adding that “While progress has been made in implementation, analysis of spend shows that this has been at a rate slower than originally intended. Programme delivery timescales should be reconsidered and extended to allow the Prosperity Fund to achieve its ambition”. This recommendation is also supported by this Annual Review. Significant output level results are already being achieved through the programme’s Tranche 1 and 2 interventions.

Quality of Financial Management
1. The programme has a finance team that oversees the forecasting and monitoring of programme expenditure and invoicing. Expenditure against forecast and budget is tracked and reported to the JFU and the FCDO central PF finance team monthly and to the India PF Board at Post quarterly. Suppliers are required to provide monthly finance and quarterly impact reports to the programme team – a contractual obligation for Tranche 1 delivery partners.
2. The programme delivered a financial outturn of £5.2m spend in FY 19/20, 81% against a revised post-Supplementary Estimates budget of £6.3m. The underspend was mainly attributable to a £0.8m credit adjustment being made by the centre in March 2020 to ensure that a Trust Fund payment had been correctly accounted for on a resource accounting basis. Final outturn would have been 95% aside from this issue. The programme are aware of how to avoid similar issues occurring in future and the FCDO central finance team has implemented a more robust approach to monitoring and approving prepayments in FY 20/21 which should also help.
3. Two delivery partners flagged in Annual Review interviews that they had underestimated the level of financial reporting (ABB) required by the programme team to track performance and expenditure. The ABB template was issued in November 2019 and shared with delivery partners, however challenges emerged in populating the subsequently issued template. Although both suppliers are now fully in step with requirements, it is recommended that central finance colleagues in London provide best practice guidance on the level of detail required from delivery partners. This would be helpful across the PF to explicitly set out the required financial data. This guidance should also aim to streamline processes where possible and be fully aligned with reporting requirements at the centre. Finance team at India post will take this up with JFU to commission guidelines as a standard document.

Date of last narrative financial report	June 2019

E: RISK
Overall risk rating: Moderate (same rating as Annual Review 2019)
Overview of programme risks
1. Lack of adequate resources committed by the participating central and state government agencies and delay in acceptance and implementation of suggested reforms to support programme activities by concerned stakeholders. This may impact programme delivery timelines, effectiveness and overall achievement of programme primary purpose and secondary benefits. All programmes are continuing to foster buy-in from the leadership on the counterpart support (government agencies)/ resources to be made available throughout the programme duration.
2. The period saw the outbreak of coronavirus, raising the risk of operational slow down and jeopardising achievement of overall programme impacts by 2023. Programmes quickly adapted by implementing business continuity plans, reprioritising activities and delivery models, and adopting adaptive programming.
3. Weakening of Indian economy amid coronavirus’s longer term impact might delay or slow down achievement of Secondary Benefits. The impact could lead India PF to fall short of high expectations on SB (business and political), especially in context of COVID-19. The programme is focusing on tracking soft wins in the initial phase of the programme with regular monitoring.
4. ODA prioritisation has impacted the programme not only financially but also in terms of programmes’ impact. This has led to a reduced financial year budget with an onward impact on the overall six-year allocation. Reduced budgets and changed priorities have required strands to reconsider projects and agree on contract variations with suppliers. In the context of the current spending review, the overall portfolio may change again, requiring the strands to realign projects.
5. Cross HMG offer through multiple projects has a risk of overlap/ duplication of efforts. To mitigate, joint initiatives are explored along with clear distinction of work and regular coordination with government departments (DIT, HMRC) and agencies, regulators, industry coalitions, think-tanks, funding agencies and other key stakeholders. Cross-mission fora such as the India PF Board brings together internal stakeholders.

F: COMMERCIAL CONSIDERATIONS
Delivery against planned timeframe. At the time of writing, Financial Services, Skills, EoDB, and Urban strands are in full Implementation. The main T1 elements of the EoDB and Urban programmes having been re-designed in response to coronavirus and went live in October 2020. T1 of the Energy and Low Carbon programme was due to go to tender in January 2020 but was also put on hold. The programme has now secured Ministerial approvals and will be delivered in a shorter timeframe with increased focus on climate change and COP26 priorities.
Performance of partnership(s). Delivery partners have performed in line with contractual agreements during the reporting period and have played an important role in managing the challenges raised by the pandemic and stakeholders’ changing priorities. Notable successes have included the support provided by various delivery partners on EoDB to embed Secondary Benefits into the programme design, and the close collaboration and coordination provided by the lead supplier on the Urban strand.
The Insolvency component of the Financial Services programme strand has performed particularly well, establishing successful partnerships with MCA and the insolvency regulator (IBBI), which have helped to strengthen the landmark Insolvency and Bankruptcy Code.
Some programme teams have advised that they have been required to undertake more coordination and monitoring of Tranche 2 projects than had been expected to ensure adherence to project plans, stakeholder engagement and on ground delivery of events as per FCDO standards. In these instances, issues have been resolved through verbal and written feedback and supplier performance reviews.
Changes in the Delivery Plan. Owing to delays due to the coronavirus, the implementation phase for both the Ease of Doing Business and Urban programme strands moved to October 2020. The Financial Services strand is re-prioritising its delivery plan in light of spending cuts and is focusing on Insolvency, Fintech, and capacity-building initiatives. Across all strands, interventions that require physical presence that cannot be delivered have replaced by virtual communication channels for the foreseeable future.
Commercial Management Systems and Service Level Agreements. Service Level Agreements formats and Service Credit mechanisms have been aligned across all contract strands to aide internal management standardisation. Contract Management plans are not complete and should be finalised in the calendar year so operational models are clearly understood by all stakeholders.
Asset monitoring and control. Programme strands are required to maintain asset registers although no assets have been identified thus far.

G: Business Environment
The programme has been instrumental in arranging consultations, dialogues, workshops and discussion groups to ensure alignment with India’s current business climate and to improve the potential to deliver secondary benefits for International (including UK) businesses. Notable successes:
- The EoDB programme responded to a GoI aspiration to adopt best practice in areas of Better Regulation, Tax Administration, and Trade Facilitation & Standards by facilitating knowledge exchanges with Department of Business, Energy and Industrial Strategy (BEIS), HMRC and HM Land Registry. These interactions have identified potential options for simplifying policies in the renewable energy, medical devices, and electronics sectors;
- Creating and using forums to support B2B knowledge-sharing and networking through the UK-India Tech Hub. World-class UK sector experts mentor the next generation of cutting-edge FinTech start-ups to expand domestically and globally.
- Delegation visits organised through the Energy strand have led to potential UK-Indian partnerships being established in projects on Electric Mobility, Demand Side Management, and Smart Grids. The programme also supported the launch of Yahhvi Enterprises as an activity partner of UK’s EO Charging to make and distribute smart charge points in India.
The Skills programme builds on HMG Agency work in the urban sector to build capacity in Building Information Management (BIM). The programme developed a strategic roadmap to institutionalise BIM training in India.

Non-ODA spend has been used to raise awareness of the programme in the private sector in the UK and to highlight UK specialist expertise with Indian stakeholders. The programme received £89k of Non-ODA budget in the 19/20 financial year and has used that to work with UK subject matter experts and regulatory bodies to provide direct support to the following state/ sector stakeholders:
- UK Businesses have supporting state officials in Karnataka in water management;
- Multiple UK regulatory bodies including the Pensions Regulator, Department of Work & Pensions, National Employment Savings Trust (NEST), private sector representatives (including FinTechs), retirement advisors, distributors, and informal sector associations shared their expertise and inputs to provide advice to Maharashtra officials in support of its bankruptcy code. The roadmap for the implementation of cross-border and personal insolvency laws was featured at the National Conference on Insolvency and Bankruptcy Code with over 200 attendees from GoI and industry. In addition, a 2-day workshop was delivered to train newly inducted Insolvency Resolution professionals on cross-border and personal insolvency.
- BEIS has facilitated knowledge-sharing meetings and delegations between the Government of India and UK businesses in order to submit recommendations on frameworks for policy design in India. A 3-day Red Tape Challenge workshop in India was attended by representatives from the programme’s priority state governments.

H: MONITORING & EVALUATION
Evidence and evaluation
Cycle 1 evaluation of the IERP programme has been deferred to April 2021 as a result of ODA prioritisation and the impact of coronavirus on programme implementation. In the absence of the evaluation, Evaluation & Learning suppliers conducted a Readiness Review (RR) during February-March 2020 to assess programme’s progress. Executive Summary:
‘Since the last Annual Review, the RR positively finds that the India programme team has worked closely with suppliers and made significant progress in developing the three strand-level ToCs and logframes. The India programme team have also strengthened approaches to gender, VfM, SB and learning in Tranche 1 project designs. The RR team finds that, with a few adjustments, all three strand-level ToCs and logframes can adequately serve as a framework for the upcoming Annual Review. The RR also positively notes that the India programme team and its suppliers are already adopting suggestions from the RR and starting to refine the MREL systems.’
The IERP’s ToC will be revised once each of the strands’ theories of change are finalised and approved (currently only Financial Services and Skills are finalised). Draft ToCs for the remaining programmes have been prepared with delivery partners, these will be finalised as each programme transitions from design to implementation phase.
Monitoring progress throughout the review period
The primary method of monitoring programme progress is via Programme Quarterly Reports, Risk Registers, the Prospero system, logframes, and the Annual Reviews. These reports are regularly submitted to PFDU. Learning from the programmes is generated through steering committees, regular catch ups within the portfolio team, knowledge sessions, cross HMG collaboration work, and the PF Learning platform. Due to the current travel restrictions, this year’s Annual Review is desk-based and has involved virtual interactions with all programme teams and delivery partners.