## Cover_sheet
Annex 1: Anglian RBD Flood Risk Management Plan (FRMP) – Summary of progress of implementing the first cycle measures
This Annex provides the implementation status of each measure published in the first cycle River Basin District Flood Risk Management Plan (FRMP) (2015–2021) as of 31 March 2021. The Annex also indicates if a measure has been transitioned to this second cycle FRMP, and whether this is as a ‘national’ or ‘local’ level measure.
Status of the measures
First cycle measures transitioned to this second cycle FRMP as ‘national’ level measures comprise the day-to-day work by the Environment Agency and Lead Local Flood Authorities (LLFAs). Measures transitioned as ‘local’ level measures are those ‘ongoing’ or ‘not started’ and which align with the approach of this second cycle FRMP. / Measures may have been transitioned as an individual measures or as part of a wider ‘aggregate’ measure. Aggregate measures comprise of several measures that are linked because of spatial proximity/outcome/efficiency/benefits. Measures may appear different compared to the first cycle. More information on the transitioned measures that appear in this second cycle FRMP can be found in Flood Plan Explorer. / Some first cycle measures that were ‘ongoing’ or ‘not started’ have not been transitioned to this second cycle FRMP. This is because they may not fit with the approach of this second cycle FRMP. These measures may still be considered for current or future programmes of work by the Environment Agency, LLFA or other Risk Management Authorities. The second cycle FRMP signposts to other plans and strategies that are likely to contain local measures. / Column D contains blank cells when a measure is 'completed' or 'ongoing' in FRMP cycle 1. / Column F contains blank cells when a measure is 'completed' or not transitioned to FRMP cycle 2.
Links to other FRMP resources
Flood Plan Explorer
Anglian river basin district flood risk management plan

## FRMP1_annex
Anglian FRMP 1 annex
This worksheet contains one table.
Measure ID	Measure Owner	Implementation Status	Reason for not progressing	Transitioned to FRMP2?	Transitioned Locally or Nationally?
ACT003	Environment Agency	Completed		N/A
ACT004	Northamptonshire County	Completed		N/A
ACT005	Northamptonshire County	Ongoing	It does not yet have funding	Yes	Local
ACT006	Northamptonshire County	Superseded	It has been included in another piece of work	N/A
ACT007	Northamptonshire County	Not started - proposed	It does not yet have funding	Yes	Local
ACT008	Northamptonshire County	Not started - proposed	It does not yet have funding	Yes	Local
ACT009	Northamptonshire County	Not started - proposed	It does not yet have funding	Yes	Local
ACT010	Northamptonshire County	Superseded	It has been included in another piece of work	N/A
ACT011	Northamptonshire County	Completed		N/A
ACT012	Northamptonshire County	Not started - proposed	It does not yet have funding	Yes	Local
ACT013	Northamptonshire County	Completed		N/A
ACT015	Northamptonshire County	Completed		N/A
ACT017	Rutland Unitary Authority	Completed		N/A
ACT018	Environment Agency	Completed		N/A
ACT019	Environment Agency	Ongoing		Yes	National
ACT020	Environment Agency	Ongoing		Yes	National
ACT021	Environment Agency	Ongoing		No
ACT022	Environment Agency	Ongoing		No
ACT023	Environment Agency	Ongoing		No
ACT024	Environment Agency	Completed		N/A
ACT025	Environment Agency	Ongoing		No
ACT026	Environment Agency	Ongoing		No
ACT027	Environment Agency	Ongoing		No
ACT028	Environment Agency	Ongoing		No
ACT029	Environment Agency	Ongoing		No
ACT030	Environment Agency	Completed		N/A
ACT031	Environment Agency	Ongoing		No
ACT032	Environment Agency	Ongoing		No
ACT033	Environment Agency	Ongoing		No
ACT034	Environment Agency	Ongoing		No
ACT035	Environment Agency	Completed		N/A
ACT036	Environment Agency	Ongoing		No
ACT037	Environment Agency	Ongoing		No
ACT038	Environment Agency	Ongoing		No
ACT039	Environment Agency	Ongoing		No
ACT040	Environment Agency	Ongoing		No
ACT041	Environment Agency	Ongoing		No
ACT042	Environment Agency	Ongoing		No
ACT043	Environment Agency	Ongoing		No
ACT044	Environment Agency	Ongoing		No
ACT045	Environment Agency	Ongoing		No
ACT046	Environment Agency	Ongoing		No
ACT047	Environment Agency	Ongoing		No
ACT048	Environment Agency	Ongoing		No
ACT049	Environment Agency	Ongoing		No
ACT050	Environment Agency	Ongoing		No
ACT051	Environment Agency	Ongoing		No
ACT052	Environment Agency	Ongoing		No
ACT053	Environment Agency	Ongoing		No
ACT054	Environment Agency	Ongoing		No
ACT055	Environment Agency	Ongoing		No
ACT056	Environment Agency	Ongoing		No
ACT057	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT058	Environment Agency	Ongoing		No
ACT059	Environment Agency	Ongoing		No
ACT060	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT061	Environment Agency	Completed		N/A
ACT062	Environment Agency	Ongoing		No
ACT063	Environment Agency	Ongoing		No
ACT064	Environment Agency	Ongoing		No
ACT065	Environment Agency	Ongoing		No
ACT066	Environment Agency	Ongoing		No
ACT067	Environment Agency	Completed		N/A
ACT068	Environment Agency	Completed		N/A
ACT070	Environment Agency	Ongoing		No
ACT071	Environment Agency	Ongoing		No
ACT072	Environment Agency	Completed		N/A
ACT074	Environment Agency	Ongoing		No
ACT075	Environment Agency	Ongoing		No
ACT076	Environment Agency	Ongoing		No
ACT077	Environment Agency	Ongoing		No
ACT078	Environment Agency	Ongoing		No
ACT079	Environment Agency	Completed		N/A
ACT081	Environment Agency	Ongoing		No
ACT082	Environment Agency	Ongoing		No
ACT083	Environment Agency	Ongoing		No
ACT084	Environment Agency	Completed		N/A
ACT085	Environment Agency	Completed		N/A
ACT086	Environment Agency	Ongoing		No
ACT087	Environment Agency	Completed		N/A
ACT088	Environment Agency	Ongoing		No
ACT089	Environment Agency	Ongoing		No
ACT090	Environment Agency	Ongoing		No
ACT091	Environment Agency	Ongoing		No
ACT092	Tendring District	Ongoing		No
ACT093	Environment Agency	Completed		N/A
ACT094	Environment Agency	Ongoing		No
ACT095	Environment Agency	Ongoing		No
ACT096	Environment Agency	Ongoing		No
ACT097	Environment Agency	Ongoing		No
ACT098	Environment Agency	Ongoing		No
ACT099	Environment Agency	Ongoing		No
ACT100	Environment Agency	Ongoing		No
ACT101	Environment Agency	Ongoing		No
ACT102	Environment Agency	Ongoing		No
ACT103	Environment Agency	Ongoing		No
ACT104	Environment Agency	Ongoing		No
ACT105	Environment Agency	Ongoing		No
ACT106	Environment Agency	Ongoing		No
ACT107	Environment Agency	Completed		N/A
ACT108	Environment Agency	Ongoing		No
ACT109	Environment Agency	Ongoing		No
ACT110	Environment Agency	Ongoing		No
ACT111	Environment Agency	Completed		N/A
ACT112	Environment Agency	Ongoing		No
ACT113	Environment Agency	Ongoing		No
ACT114	Environment Agency	Ongoing		No
ACT115	Environment Agency	Ongoing		No
ACT116	Environment Agency	Ongoing		No
ACT117	Environment Agency	Ongoing		No
ACT118	Environment Agency	Ongoing		No
ACT119	Environment Agency	Ongoing		No
ACT120	Environment Agency	Ongoing		No
ACT121	Environment Agency	Ongoing		No
ACT122	Environment Agency	Ongoing		No
ACT123	Environment Agency	Ongoing		No
ACT124	Environment Agency	Ongoing		No
ACT125	Environment Agency	Ongoing		No
ACT126	Environment Agency	Ongoing		No
ACT127	Environment Agency	Ongoing		No
ACT128	Environment Agency	Ongoing		No
ACT129	Environment Agency	Ongoing		No
ACT130	Environment Agency	Ongoing		No
ACT131	Environment Agency	Ongoing		No
ACT132	Environment Agency	Ongoing		No
ACT133	Environment Agency	Ongoing		No
ACT134	Environment Agency	Ongoing		No
ACT135	Environment Agency	Ongoing		No
ACT136	Environment Agency	Ongoing		No
ACT137	Environment Agency	Ongoing		No
ACT138	Environment Agency	Ongoing		No
ACT140	Environment Agency	Completed		N/A
ACT141	Environment Agency	Ongoing		No
ACT142	Environment Agency	Ongoing		No
ACT143	Environment Agency	Ongoing		No
ACT145	Environment Agency	Completed		N/A
ACT148	Environment Agency	Ongoing		No
ACT151	Environment Agency	Completed		N/A
ACT2213	Northamptonshire County	Ongoing	It has been included in another piece of work	Yes	Local
ACT2214	Northamptonshire County	Ongoing	Other - Ongoing as business as usual	Yes	National
ACT2215	Northamptonshire County	Ongoing	Other - Ongoing as business as usual	Yes	National
ACT2216	Northamptonshire County	Ongoing	Other - Ongoing as business as usual	Yes	National
ACT2217	Northamptonshire County	Ongoing	Other - Ongoing as business as usual	Yes	National
ACT2218	Northamptonshire County	Ongoing	Other - Ongoing as business as usual	Yes	National
ACT2219	Corby District (B)	Completed		N/A
ACT2220	Kettering District (B)	Completed		N/A
ACT2221	Northamptonshire County	Completed		N/A
ACT2222	Anglian Water	Completed		N/A
ACT2223	Northamptonshire County	Ongoing	Other - Ongoing as business as usual	Yes	National
ACT2224	Northamptonshire County	Completed		N/A
ACT2225	Northamptonshire County	Completed		N/A
ACT2226	Northamptonshire County	Ongoing	Other - Ongoing as business as usual	Yes	National
ACT2227	Northamptonshire County	Ongoing	Other - Ongoing as business as usual	Yes	Local
ACT2228	Northamptonshire	Completed		N/A
ACT2229	Northamptonshire County	Ongoing - construction	will be complete by Dec21	No
ACT2230	Northamptonshire County	Completed		N/A
ACT2231	Northampton District (B)	Superseded	Further work showed it was not viable	N/A
ACT2232	Northampton District (B)	Superseded	Further work showed it was not viable	N/A
ACT2233	North Northamptonshire Joint Planning Unit	Not started - proposed	It does not yet have funding	No
ACT2234	North Northamptonshire Joint Planning Unit	Not started - proposed	It does not yet have funding	No
ACT2235	Corby District (B)	Completed		N/A
ACT2236	Northampton District (B)	Ongoing	Other - To be delivered as part of development	Yes	National
ACT2237	Corby District (B)	Ongoing	Other - To be delivered as part of development	Yes	National
ACT2238	Northamptonshire County	Completed		N/A
ACT2241	Northamptonshire County	Not started - proposed	It does not yet have funding - Timescale still to be determined	Yes	Local
ACT2242	Northamptonshire County	Superseded	Further work showed it was not viable	N/A
ACT2244	Northamptonshire County	Ongoing - construction	Will be complete by Dec21	No
ACT2246	Northamptonshire County	Superseded	Further work showed it was not viable	N/A
ACT2247	Northamptonshire County	Ongoing - construction	Will be complete by Dec21	No
ACT2249	Northamptonshire County	Ongoing		Yes	Local
ACT2250	Northamptonshire County	Ongoing		Yes	Local
ACT2251	Northamptonshire County	Completed		N/A
ACT2252	Northamptonshire County	Completed		N/A
ACT2253	Northamptonshire County	Ongoing	Other - Ongoing as business as usual	Yes	National
ACT2254	Northamptonshire County	Ongoing	Other - Ongoing as business as usual	Yes	National
ACT2255	Northamptonshire County	Ongoing	Other - Ongoing as business as usual	Yes	National
ACT2286	Daventry District	Ongoing	Other - To be delivered as part of development	Yes	National
ACT2287	East Northamptonshire District	Ongoing	Other - To be delivered as part of development	Yes	National
ACT2288	Kettering District (B)	Ongoing	Other - To be delivered as part of development	Yes	National
ACT2289	Northampton District (B)	Ongoing	Other - To be delivered as part of development	Yes	National
ACT2290	South Northamptonshire District	Ongoing	Other - To be delivered as part of development	Yes	National
ACT2291	Wellingborough District (B)	Ongoing	Other - Ongoing as business as usual	Yes	National
ACT2834	Peterborough Unitary Authority	Ongoing		Yes	National
ACT2835	Peterborough Unitary Authority	Ongoing		Yes	National
ACT2836	Peterborough Unitary Authority	Ongoing		Yes	National
ACT2837	Peterborough Unitary Authority	Ongoing		Yes	National
ACT2838	Peterborough Unitary Authority	Ongoing		Yes	National
ACT2839	Peterborough Unitary Authority	Ongoing		Yes	National
ACT2840	Peterborough Unitary Authority	Ongoing		Yes	National
ACT2841	Peterborough Unitary Authority	Ongoing		Yes	National
ACT2842	Peterborough Unitary Authority	Ongoing		Yes	National
ACT2843	Peterborough Unitary Authority	Ongoing		Yes	National
ACT2844	Peterborough Unitary Authority	Ongoing		Yes	National
ACT2845	Peterborough Unitary Authority	Ongoing		Yes	National
ACT2847	Environment Agency	Completed		N/A
ACT2848	Environment Agency	Ongoing		Yes	National
ACT2849	Environment Agency	Ongoing		Yes	National
ACT2851	Environment Agency	Completed		N/A
ACT2852	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT2853	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT2854	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT2855	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT2856	Environment Agency	Ongoing		Yes	Local
ACT2857	Environment Agency	Completed		N/A
ACT2858	Environment Agency	Superseded	It does not yet have funding	N/A
ACT2859	Environment Agency	Completed		N/A
ACT2860	Environment Agency	Not started - proposed	It does not yet have funding	Yes	Local
ACT2861	Environment Agency	Completed		N/A
ACT2862	Environment Agency	Completed		N/A
ACT2863	Environment Agency	Ongoing		Yes	National
ACT2864	Environment Agency	Ongoing		Yes	National
ACT2865	Environment Agency	Ongoing		Yes	National
ACT2866	Environment Agency	Not started - agreed		Yes	National
ACT2867	Environment Agency	Ongoing		Yes	National
ACT2868	Environment Agency	Ongoing		Yes	National
ACT2869	Environment Agency	Ongoing		Yes	National
ACT2870	Environment Agency	Ongoing		Yes	Local
ACT2872	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT2873	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT2874	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT2875	Environment Agency	Ongoing		Yes	National
ACT2876	Environment Agency	Superseded	It does not yet have funding	N/A
ACT2877	Environment Agency	Ongoing		No
ACT2878	Environment Agency	Ongoing		Yes	National
ACT2879	Environment Agency	Ongoing		Yes	National
ACT2880	Environment Agency	Ongoing		Yes	National
ACT2881	Environment Agency	Ongoing		Yes	National
ACT2882	Environment Agency	Ongoing		Yes	National
ACT2883	Environment Agency	Ongoing		Yes	National
ACT2884	Environment Agency	Ongoing		Yes	National
ACT2885	Environment Agency	Ongoing		Yes	National
ACT2886	Environment Agency	Ongoing		Yes	National
ACT2887	Environment Agency	Ongoing		Yes	National
ACT2888	Environment Agency	Ongoing		Yes	National
ACT2889	Environment Agency	Ongoing		Yes	National
ACT2890	Environment Agency	Ongoing		Yes	National
ACT2891	Environment Agency	Ongoing		Yes	National
ACT2892	Environment Agency	Ongoing		Yes	National
ACT2893	Environment Agency	Ongoing		Yes	National
ACT2894	Environment Agency	Ongoing		Yes	National
ACT2895	Environment Agency	Ongoing		Yes	National
ACT2896	Environment Agency	Ongoing		Yes	National
ACT2897	Environment Agency	Ongoing		Yes	National
ACT2898	Environment Agency	Ongoing		Yes	National
ACT2899	Environment Agency	Ongoing		Yes	National
ACT2900	Environment Agency	Ongoing		Yes	National
ACT2901	Environment Agency	Ongoing		Yes	National
ACT2902	Environment Agency	Ongoing		Yes	National
ACT2903	Environment Agency	Ongoing		Yes	National
ACT2904	Environment Agency	Ongoing		Yes	National
ACT2905	Environment Agency	Ongoing		Yes	National
ACT2906	Environment Agency	Ongoing		Yes	National
ACT2907	Environment Agency	Ongoing		Yes	National
ACT2908	Environment Agency	Ongoing		Yes	National
ACT2909	Environment Agency	Ongoing		Yes	National
ACT2910	Environment Agency	Ongoing		Yes	National
ACT2911	Environment Agency	Ongoing		Yes	National
ACT2912	Environment Agency	Ongoing		Yes	National
ACT2913	Environment Agency	Ongoing		No	National
ACT2914	Environment Agency	Ongoing		Yes	National
ACT2915	Environment Agency	Ongoing		Yes	National
ACT2916	Environment Agency	Ongoing		Yes	National
ACT2917	Environment Agency	Ongoing		Yes	National
ACT2918	Environment Agency	Ongoing		Yes	National
ACT2919	Environment Agency	Ongoing		Yes	National
ACT2920	Environment Agency	Ongoing		Yes	National
ACT2921	Environment Agency	Ongoing		Yes	National
ACT2922	Environment Agency	Ongoing		Yes	Local
ACT2923	Environment Agency	Ongoing		Yes	Local
ACT2924	Environment Agency	Ongoing		Yes	Local
ACT2925	Environment Agency	Ongoing		Yes	National
ACT2926	Environment Agency	Ongoing		Yes	National
ACT2927	Environment Agency	Ongoing		Yes	National
ACT2928	Environment Agency	Ongoing		Yes	National
ACT2929	Environment Agency	Ongoing		Yes	National
ACT2930	Environment Agency	Ongoing		Yes	National
ACT2931	Environment Agency	Ongoing		Yes	National
ACT2933	Environment Agency	Ongoing		Yes	Local
ACT2934	Environment Agency	Ongoing		Yes	Local
ACT2935	Environment Agency	Ongoing		Yes	Local
ACT2936	Environment Agency	Ongoing		Yes	National
ACT2938	Environment Agency	Ongoing		Yes	Local
ACT2939	Environment Agency	Ongoing		Yes	Local
ACT2940	Environment Agency	Ongoing		Yes	National
ACT2941	Environment Agency	Superseded	It does not yet have funding	N/A
ACT3676	Environment Agency	Ongoing		Yes	Local
ACT3677	Environment Agency	Ongoing		Yes	Local
ACT3678	Environment Agency	Ongoing		Yes	Local
ACT3679	Environment Agency	Not started - agreed	It has been included in another piece of work	Yes	Local
ACT3680	Environment Agency	Not started - agreed	It has been included in another piece of work	Yes	Local
ACT3681	SBC	Ongoing		Yes	Local
ACT3682	SBC	Not started - agreed	It has been included in another piece of work	Yes	Local
ACT3683	SBC	Not started - agreed	It has been included in another piece of work	Yes	Local
ACT3684	SBC	Ongoing		Yes	Local
ACT3803	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3804	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT3805	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3808	Northamptonshire County	Not started - proposed		No
ACT3809	Northamptonshire County	Not started - proposed		No
ACT3810	Environment Agency	Ongoing		Yes	National
ACT3811	Environment Agency	Ongoing		Yes	Local
ACT3812	Cambridgeshire County	Superseded	Further work showed it was not viable	N/A
ACT3813	Cambridgeshire County	Completed		N/A
ACT3814	Cambridgeshire County	Superseded	Further work showed it was not viable	N/A
ACT3815	Cambridgeshire County	Superseded	It does not yet have funding	N/A
ACT3816	Cambridgeshire County	Ongoing	It has been replaced by another measure	No
ACT3817	Environment Agency	Ongoing		Yes	Local
ACT3818	Environment Agency	Completed		N/A
ACT3819	Environment Agency	Ongoing		Yes	Local
ACT3820	Environment Agency	Ongoing		Yes	Local
ACT3821	Environment Agency	Ongoing		Yes	Local
ACT3822	Environment Agency	Ongoing		Yes	Local
ACT3823	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3824	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3825	Environment Agency	Completed		N/A
ACT3826	Environment Agency	Ongoing	It has been replaced by another measure	No
ACT3827	Environment Agency	Completed		N/A
ACT3828	Environment Agency	Not started - proposed	It has been replaced by another measure	Yes	National
ACT3829	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT3830	Environment Agency	Completed		N/A
ACT3831	Environment Agency	Ongoing		Yes	Local
ACT3832	Environment Agency	Completed		N/A
ACT3833	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT3834	Environment Agency	Ongoing		Yes	National
ACT3835	Environment Agency	Ongoing		Yes	National
ACT3836	Environment Agency	Ongoing		Yes
ACT3837	Environment Agency	Ongoing		Yes
ACT3838	Environment Agency	Ongoing		Yes	National
ACT3839	Environment Agency	Ongoing		Yes
ACT3840	Environment Agency	Completed		N/A
ACT3841	Environment Agency	Completed		N/A
ACT4038	North Norfolk District	Superseded	Further work showed it was not viable	N/A
ACT4039	North Norfolk District	Ongoing		No
ACT4040	North Norfolk District	Ongoing		No
ACT4041	North Norfolk District	Ongoing		No
ACT4042	North Norfolk District	Superseded	Further work showed it was not viable	N/A
ACT4043	North Norfolk District	Superseded	Further work showed it was not viable	N/A
ACT4044	North Norfolk District	Ongoing		No
ACT4045	North Norfolk District	Ongoing		No
ACT4046	North Norfolk District	Ongoing		No
ACT4047	North Norfolk District	Ongoing		No
ACT4048	North Norfolk District	Ongoing		No
ACT4049	North Norfolk District	Ongoing		No
ACT4050	North Norfolk District	Superseded	It has been included in another piece of work	N/A
ACT4051	North Norfolk District	Ongoing		No
ACT4052	North Norfolk District	Ongoing		No
ACT4053	North Norfolk District	Ongoing		No
ACT4054	North Norfolk District	Ongoing		No
ACT4055	North Norfolk District	Ongoing		No
ACT4056	North Norfolk District	Ongoing		No
ACT4057	North Norfolk District	Ongoing		No
ACT4058	North Norfolk District	Ongoing		No
ACT4059	North Norfolk District	Ongoing		No
ACT4060	North Norfolk District	Ongoing		No
ACT4061	North Norfolk District	Ongoing		No
ACT4062	North Norfolk District	Ongoing		No
ACT4063	North Norfolk District	Completed		N/A
ACT4064	North Norfolk District	Completed		N/A
ACT4065	North Norfolk District	Completed		N/A
ACT4066	North Norfolk District	Ongoing		No
ACT4067	North Norfolk District	Ongoing		No
ACT4068	North Norfolk District	Ongoing		No
ACT4069	North Norfolk District	Completed		N/A
ACT4070	North Norfolk District	Completed		N/A
ACT4071	North Norfolk District	Ongoing		No
ACT4072	North Norfolk District	Ongoing		No
ACT4073	North Norfolk District	Ongoing
ACT4074	North Norfolk District	Ongoing
ACT4075	North Norfolk District	Completed		N/A
ACT4076	North Norfolk District	Ongoing
ACT4077	North Norfolk District	Completed		N/A
ACT4078	North Norfolk District	Ongoing		No
ACT4079	North Norfolk District	Ongoing		No
ACT4080	North Norfolk District	Superseded	It does not yet have funding	N/A
ACT4081	North Norfolk District	Ongoing		No
ACT4082	North Norfolk District	Ongoing		No
ACT4083	North Norfolk District	Ongoing		No
ACT4084	North Norfolk District	Superseded	It has been postponed	N/A
ACT4085	North Norfolk District	Ongoing
ACT4086	North Norfolk District	Ongoing		No
ACT4087	North Norfolk District	Completed		N/A
ACT4088	North Norfolk District	Ongoing		No
ACT4089	North Norfolk District	Superseded	It has been included in another piece of work	N/A
ACT4090	North Norfolk District	Completed		N/A
ACT4091	North Norfolk District	Superseded	It has been included in another piece of work	N/A
ACT4092	North Norfolk District	Ongoing		No
ACT4093	North Norfolk District	Superseded	Further work showed it was not viable	N/A
ACT4094	North Norfolk District	Ongoing		No
ACT4095	North Norfolk District	Superseded	It has been included in another piece of work	N/A
ACT4096	North Norfolk District	Superseded	It has been included in another piece of work	N/A
ACT4097	North Norfolk District	Ongoing
ACT4098	North Norfolk District	Superseded	It has been included in another piece of work	N/A
ACT4099	North Norfolk District	Completed		N/A
ACT4100	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4101	Environment Agency	Completed		N/A
ACT4102	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4103	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4104	Environment Agency	Completed		N/A
ACT4105	Environment Agency	Completed		N/A
ACT4106	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4107	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4108	Environment Agency	Completed		N/A
ACT4109	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4110	Environment Agency	Completed		N/A
ACT4111	Environment Agency	Completed		N/A
ACT4112	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4113	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4114	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4115	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4116	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4117	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4118	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4119	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT4120	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4121	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4122	Environment Agency	Completed		N/A
ACT4123	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4124	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4125	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4126	Environment Agency	Completed		N/A
ACT4127	Environment Agency	Completed		N/A
ACT4128	Environment Agency	Completed		N/A
ACT4129	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4130	Environment Agency	Completed		N/A
ACT4131	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4132	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4133	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4134	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4135	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4136	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4137	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4138	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4139	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4140	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4141	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT4142	Environment Agency	Completed		N/A
ACT4143	Environment Agency	Ongoing		No
ACT4144	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4145	Environment Agency	Completed		N/A
ACT4146	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4147	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4148	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4149	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4150	Environment Agency	Completed		N/A
ACT4151	Environment Agency	Ongoing		No
ACT4152	Environment Agency	Ongoing		No
ACT4153	Environment Agency	Completed		N/A
ACT4154	Environment Agency	Completed		N/A
ACT4155	Environment Agency	Completed		N/A
ACT4156	Environment Agency	Completed		N/A
ACT4157	Environment Agency	Ongoing		No
ACT4158	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4159	Environment Agency	Ongoing		No
ACT4160	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4161	Environment Agency	Ongoing		No
ACT4162	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4163	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4164	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4165	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4166	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4167	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT4168	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT4169	Environment Agency	Completed		N/A
ACT4170	Environment Agency	Ongoing		No
ACT4171	Environment Agency	Ongoing		No
ACT4172	Environment Agency	Ongoing		No
ACT4173	Environment Agency	Completed		N/A
ACT4174	Environment Agency	Completed		N/A
ACT4175	Environment Agency	Ongoing		No
ACT4176	Environment Agency	Ongoing		No
ACT4177	Environment Agency	Ongoing		No
ACT4178	Environment Agency	Ongoing		No
ACT4179	Environment Agency	Ongoing		No
ACT4180	Environment Agency	Ongoing		No
ACT4685	Environment Agency	Ongoing		No
ACT4778	Environment Agency	Ongoing		Yes	National
ACT4780	Environment Agency	Ongoing		Yes	National
ACT4788	Environment Agency	Ongoing		Yes	National
ACT4800	Environment Agency	Ongoing		Yes	National
ACT4801	Environment Agency	Ongoing		Yes
ACT4802	Environment Agency	Ongoing		No
ACT4813	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5013	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5014	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5015	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5016	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5017	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5019	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5020	Waveney District	Superseded	It has been included in another piece of work	N/A
ACT5021	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5022	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5023	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5024	Waveney District	Superseded	It has been included in another piece of work	N/A
ACT5025	Waveney District	Completed		N/A
ACT5026	Waveney District	Completed		N/A
ACT5027	Waveney District	Ongoing		No
ACT5028	Environment Agency	Completed		N/A
ACT5029	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5031	Suffolk County	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5032	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5033	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5034	Environment Agency	Completed		N/A
ACT5035	Environment Agency	Completed		N/A
ACT5036	Environment Agency	Completed		N/A
ACT5037	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5040	Suffolk County	Completed		N/A
ACT5041	Suffolk County	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5042	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5043	Environment Agency	Completed		N/A
ACT5044	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5045	Environment Agency	Completed		N/A
ACT5046	Waveney District	Completed		N/A
ACT5047	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5048	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5052	Waveney District	Completed		N/A
ACT5055	Environment Agency	Completed		N/A
ACT5057	Waveney District	Completed		N/A
ACT5058	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5059	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5060	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5061	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5062	Environment Agency	Completed		N/A
ACT5063	Essex and Suffolk Water	Completed		N/A
ACT5064	Environment Agency	Completed		N/A
ACT5066	Environment Agency	Completed		N/A
ACT5068	Environment Agency	Completed		N/A
ACT5069	Environment Agency	Completed		N/A
ACT5071	Environment Agency	Completed		N/A
ACT5072	Suffolk Coastal District	Completed		N/A
ACT5073	Suffolk Coastal District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5074	Environment Agency	Completed		N/A
ACT5075	Environment Agency	Completed		N/A
ACT5077	Environment Agency	Completed		N/A
ACT5078	Suffolk Coastal District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5080	Suffolk Coastal District	Completed		N/A
ACT5081	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5082	Environment Agency	Completed		N/A
ACT5083	Environment Agency	Completed		N/A
ACT5084	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5085	Environment Agency	Completed		N/A
ACT5086	Suffolk Coastal District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5087	Suffolk Coastal District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5088	Environment Agency	Completed		N/A
ACT5089	Environment Agency	Completed		N/A
ACT5090	Suffolk Coastal District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5091	Suffolk Coastal District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5092	Suffolk Coastal District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5093	Environment Agency	Completed		N/A
ACT5094	Environment Agency	Completed		N/A
ACT5095	Suffolk Coastal District	Completed		N/A
ACT5097	Suffolk Coastal District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5098	Suffolk Coastal District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5099	Suffolk Coastal District	Completed		N/A
ACT5100	Suffolk Coastal District	Completed		N/A
ACT5101	Suffolk Coastal District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5102	Suffolk Coastal District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5103	Suffolk Coastal District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5104	Environment Agency	Completed		N/A
ACT5105	Environment Agency	Completed		N/A
ACT5107	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5108	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5109	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5110	Environment Agency	Completed		N/A
ACT5111	Suffolk County	Completed		N/A
ACT5112	Suffolk Coastal District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5113	Environment Agency	Completed		N/A
ACT5114	Waveney District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5115	Environment Agency	Completed		N/A
ACT5116	Environment Agency	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5117	Suffolk County	Completed		N/A
ACT5118	Suffolk Coastal District	Ongoing	Duplicate measure from SMP action plan. Measure to signpost rather than duplicate	No
ACT5119	Environment Agency	Ongoing	It has been replaced by another measure	No
ACT5120	Environment Agency	Ongoing	It has been replaced by another measure	No
ACT5121	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5122	Environment Agency	Ongoing	It has been replaced by another measure	Yes	Local
ACT5123	Environment Agency	Completed		N/A
ACT5124	Environment Agency	Ongoing	It has been replaced by another measure	Yes	Local
ACT5125	Norfolk County	Completed		N/A
ACT5126	Norfolk County	Ongoing	It has been replaced by another measure for Lowestoft FRA	Yes	Local
ACT5127	The Broads	Ongoing	This is BAU Channel maintenance	Yes	National
ACT5128	Environment Agency	Ongoing	New measures Great Yarmouth FRA	No	Local
ACT5129	Environment Agency	Ongoing		Yes	National
ACT5130	Norwich District (B)	Ongoing		Yes	National
ACT5131	Environment Agency	Ongoing		Yes	National
ACT5132	Environment Agency	Ongoing		Yes	National
ACT5133	Environment Agency	Completed		N/A
ACT5134	Environment Agency	Ongoing		Yes	National
ACT5135	Environment Agency	Completed		N/A
ACT5136	Environment Agency	Completed		N/A
ACT5137	Environment Agency	Ongoing	It has been replaced by another measure	Yes	Local
ACT5138	Environment Agency	Ongoing	It has been replaced by another measure - lowestoft FRA	Yes	Local
ACT5139	Environment Agency	Not started - agreed	It has been included in another piece of work	No
ACT5140	Environment Agency	Ongoing	It has been replaced by another measure	No
ACT5141	Environment Agency	Completed		N/A
ACT5142	Environment Agency	Ongoing		Yes	National
ACT5143	Environment Agency	Ongoing	It has been replaced by another measure	No
ACT5144	The Broads	Completed		N/A
ACT5145	The Broads	Ongoing		Yes	National
ACT5146	The Broads	Completed		N/A
ACT5147	Norfolk Rivers IDD	Completed		N/A
ACT5148	Norfolk County	Ongoing	It has been replaced by another measure	No
ACT5149	Norfolk County	Completed		N/A
ACT5150	Environment Agency	Ongoing	It has been replaced by another measure	yes	National
ACT5151	Environment Agency	Ongoing		yes	National
ACT5152	Environment Agency	Ongoing		yes	National
ACT5153	Environment Agency	Ongoing		yes	National
ACT5154	Environment Agency	Ongoing		Yes	Local
ACT5155	Essex and Suffolk Water	Ongoing		No	National
ACT5156	Essex and Suffolk Water	Ongoing		No	National
ACT5157	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5158	Environment Agency	Completed		N/A
ACT5159	Environment Agency	Ongoing	It has been replaced by another measure	Yes	Local
ACT5160	Environment Agency	Ongoing	It has been replaced by another measure	Yes	Local
ACT5161	Environment Agency	Ongoing	It has been replaced by another measure	Yes	Local
ACT5162	Environment Agency	Ongoing	It has been replaced by another measure	No
ACT5163	Environment Agency	Ongoing		Yes	Local
ACT5164	Environment Agency	Ongoing		Yes	Local
ACT5165	Environment Agency	Completed		N/A
ACT5166	Environment Agency	Completed		N/A
ACT5167	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5168	Environment Agency	Ongoing	It has been replaced by another measure	Yes	National
ACT5169	Environment Agency	Not started - proposed	It has been postponed	No
ACT5170	Environment Agency	Completed		N/A
ACT5171	Environment Agency	Completed		N/A
ACT5172	Environment Agency	Completed		N/A
ACT5173	Environment Agency	Completed		N/A
ACT5174	Environment Agency	Completed		N/A
ACT5175	Environment Agency	Ongoing	It has been included in another piece of work	No
ACT5176	Environment Agency	Ongoing	It has been included in another piece of work	No
ACT5177	Environment Agency	Ongoing	It has been replaced by another measure	Yes	National
ACT5178	Environment Agency	Completed		N/A
ACT5179	Environment Agency	Completed		N/A
ACT5180	Environment Agency	Completed		N/A
ACT5181	Environment Agency	Ongoing		Yes	Local
ACT5182	Environment Agency	Completed		N/A
ACT5183	Environment Agency	Ongoing	Transitioned as aggregate measure for assessment and removal of redundant assets	Yes	Local
ACT5184	Environment Agency	Completed		N/A
ACT5185	Environment Agency	Ongoing	Prevention LLFA NOM	Yes	National
ACT5186	Environment Agency	Completed		N/A
ACT5187	Environment Agency	Ongoing		Yes	National
ACT5188	Environment Agency	Not started - agreed	It has been replaced by another measure	No
ACT5189	Environment Agency	Not started - agreed	It has been replaced by another measure	No
ACT5190	Suffolk County	Ongoing		Yes	Local
ACT5191	Suffolk County	Completed		N/A
ACT5192	Environment Agency	Completed		N/A
ACT5193	Environment Agency	Completed		N/A
ACT5194	Suffolk County	Completed		N/A
ACT5195	Suffolk County	Superseded	Further work showed it was not viable	N/A
ACT5196	Suffolk County	Completed		N/A
ACT5197	Suffolk County	Completed		N/A
ACT5198	Suffolk County	Completed		N/A
ACT5199	Suffolk County	Completed		N/A
ACT5200	Suffolk County	Completed		N/A
ACT5201	Suffolk County	Ongoing		Yes	National
ACT5202	Suffolk County	Completed		N/A
ACT5203	Suffolk County	Completed		N/A
ACT5204	Suffolk County	Completed		N/A
ACT5205	Environment Agency	Ongoing		Yes	National
ACT5206	Suffolk County	Completed		N/A
ACT5207	Suffolk County	Completed		N/A
ACT5208	Suffolk County	Completed		N/A
ACT5209	Suffolk	Ongoing		Yes	National
ACT5210	Suffolk	Ongoing		Yes	National
ACT5211	Suffolk	Ongoing		Yes	National
ACT5212	Suffolk	Superseded	Further work showed it was not viable	N/A
ACT5213	Cambridgeshire County	Ongoing		Yes	National
ACT5214	Suffolk County	Completed		N/A
ACT5215	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT5216	Suffolk Coastal District	Ongoing		No
ACT5217	Environment Agency	Completed		N/A
ACT5218	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5219	Suffolk County	Completed		N/A
ACT5220	Environment Agency	Completed		N/A
ACT5221	Environment Agency	Completed		N/A
ACT5222	East Suffolk IDB	Ongoing		Yes	Local
ACT5223	Waveney District	Completed		N/A
ACT5224	Suffolk County	Completed		N/A
ACT5225	Suffolk County	Completed		N/A
ACT5226	East Suffolk IDB	Ongoing		Yes	Local
ACT5227	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5228	Suffolk County	Completed		N/A
ACT5229	Environment Agency	Completed		N/A
ACT5230	Waveney District	Ongoing		Yes	Local
ACT5231	Waveney District	Ongoing		Yes	National
ACT5232	Suffolk County	Completed		N/A
ACT5233	Suffolk County	Completed		N/A
ACT5234	Waveney District	Superseded	It has been postponed	N/A
ACT5235	Suffolk County	Completed		N/A
ACT5236	Suffolk County	Completed		N/A
ACT5237	Environment Agency	Completed		N/A
ACT5238	Suffolk County	Completed		N/A
ACT5239	Waveney Lower Yare and Lothingland	Completed		N/A
ACT5240	Environment Agency	Ongoing		Yes	Local
ACT5241	Environment Agency	Ongoing		No
ACT5242	Suffolk County	Completed		N/A
ACT5243	Environment Agency	Ongoing		Yes	National
ACT5244	East Suffolk IDB	Completed		N/A
ACT5245	Environment Agency	Completed		N/A
ACT5246	Suffolk Coastal District	Completed		N/A
ACT5247	Environment Agency	Completed		N/A
ACT5248	Anglian Water	Completed		N/A
ACT5249	Suffolk County	Ongoing		Yes	National
ACT5250	Lakenheath	Completed		N/A
ACT5251	Lakenheath	Superseded	It has been postponed	N/A
ACT5252	Environment Agency	Completed		N/A
ACT5253	Mildenhall	Not started - agreed	It has been replaced by another measure	Yes	Local
ACT5254	Mildenhall	Superseded	Further work showed it was not viable	N/A
ACT5255	Environment Agency	Completed		N/A
ACT5256	East Suffolk IDB	Completed		N/A
ACT5257	Environment Agency	Ongoing		Yes	National
ACT5258	Suffolk County	Completed		N/A
ACT5259	Environment Agency	Ongoing		Yes	National
ACT5260	East Suffolk IDB	Ongoing		Yes	Local
ACT5261	Suffolk County	Completed		N/A
ACT5262	Suffolk Coastal District	Completed		N/A
ACT5263	Environment Agency	Completed		N/A
ACT5264	Environment Agency	Ongoing - construction		Yes	Local
ACT5265	Environment Agency	Ongoing		Yes	National
ACT5266	Environment Agency	Completed		N/A
ACT5267	Norfolk County	Ongoing		Yes	National
ACT5268	Norfolk County	Ongoing		Yes	National
ACT5269	Environment Agency	Ongoing		Yes	Local
ACT5270	Environment Agency	Ongoing		Yes	Local
ACT5271	Environment Agency	Not started - agreed	It has been postponed	Yes	Local
ACT5272	Environment Agency	Ongoing		Yes	National
ACT5273	Norfolk County	Superseded	Further work showed it was not viable	N/A
ACT5274	Norfolk County	Superseded	Further work showed it was not viable	N/A
ACT5275	Essex County	Completed		N/A
ACT5276	Essex County	Completed		No
ACT5277	Essex County	Ongoing		Yes	National
ACT5278	Essex County	Ongoing		Yes	National
ACT5279	Essex County	Ongoing		Yes	National
ACT5280	Essex County	Ongoing		Yes	National
ACT5281	Essex County	Ongoing		Yes	National
ACT5282	Essex County	Ongoing		Yes	National
ACT5283	Essex County	Ongoing		Yes	National
ACT5284	Essex County	Ongoing		Yes	National
ACT5285	Essex County	Ongoing		Yes	National
ACT5286	Essex County	Ongoing		Yes	National
ACT5287	Essex County	Ongoing		Yes	National
ACT5288	Essex County	Not started - agreed	It has been included in another piece of work	Yes	National
ACT5289	Essex County	Completed		N/A
ACT5290	Essex County	Superseded	Further work showed it was not viable	N/A
ACT5291	Essex County	Superseded	Further work showed it was not viable	N/A
ACT5292	Essex County	Superseded	Further work showed it was not viable	N/A
ACT5293	Essex County	Completed		N/A
ACT5294	Essex County	Superseded	Further work showed it was not viable	N/A
ACT5295	Essex County	Completed		N/A
ACT5296	Essex County	Completed		N/A
ACT5297	Essex County	Completed		N/A
ACT5298	Essex County	Completed		N/A
ACT5319	Environment Agency	Not started - proposed	It has been postponed	Yes	National
ACT5321	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT5322	Environment Agency	Ongoing	Transitioned in new measure 0200905131	Yes
ACT5323	Environment Agency	Completed		N/A
ACT5324	Environment Agency	Not started - proposed	It has been postponed	Yes	National
ACT5325	Environment Agency	Ongoing		Yes	National
ACT5326	Environment Agency	Ongoing		Yes	Local
ACT5327	Environment Agency	Ongoing	continued defence to harwich port is covered in essex and south suffolk smp	No
ACT5332	Environment Agency	Not started - proposed	It has been postponed	No
ACT5333	Environment Agency	Ongoing		Yes	National
ACT5335	Environment Agency	Completed		N/A
ACT5336	Environment Agency	Ongoing		No
ACT5338	Environment Agency	Not started - proposed	It has been postponed	Yes	Local
ACT5341	Environment Agency	Ongoing		Yes	Local
ACT5343	Environment Agency	Ongoing		No
ACT5345	Environment Agency	Ongoing		No
ACT5346	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5348	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5349	Environment Agency	Completed		N/A
ACT5350	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5351	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5352	Environment Agency	Not started - proposed	It has been postponed	Yes	Local
ACT5353	Environment Agency	Ongoing		Yes	Local
ACT5354	Environment Agency	Ongoing		Yes	Local
ACT5355	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5356	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5357	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5359	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5360	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5361	Environment Agency	Not started - proposed	It has been replaced by another measure	Yes	Local
ACT5385	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5400	Environment Agency	Ongoing		Yes	Local
ACT5407	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5440	Environment Agency	Superseded	It has been replaced by another measure	Yes	Local
ACT5453	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5454	Environment Agency	Not started - proposed	It has been replaced by another measure	Yes	Local
ACT5455	Environment Agency	Not started - proposed	It has been replaced by another measure	Yes	Local
ACT5456	Environment Agency	Ongoing		Yes	Local
ACT5457	Environment Agency	Ongoing		Yes	Local
ACT5458	Environment Agency	Completed		N/A
ACT5459	Environment Agency	Ongoing	Transitioned in new measure 0200605101	Yes
ACT5460	Environment Agency	Not started - proposed	It has been replaced by another measure	No	Will likely be BFI work
ACT5465	Environment Agency	Not started - proposed	It has been replaced by another measure - relevant smp measure	Yes
ACT5469	Environment Agency	Completed		N/A
ACT5471	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5472	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5476	Environment Agency	Completed		N/A
ACT5477	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5478	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5479	Environment Agency	Ongoing	Duplicate measure from FRMP 1 (ACT5513) Measure has been transitioned	Yes
ACT5480	Environment Agency	Completed		N/A
ACT5482	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5485	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5487	Environment Agency	Ongoing	Transitioned as measure 0216205003 (SoSBC- led	Yes
ACT5493	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5494	Environment Agency	Ongoing	Measure included to cover north norfolk rivers (including river glaven 0200605086	Yes
ACT5496	Environment Agency	Completed		N/A
ACT5509	Environment Agency	Completed	This is Great Yarmouth measure for Epoch 2 which is due to complete before frmp2 publication	No
ACT5510	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5511	Environment Agency	Ongoing	Transitioned as NFM measure	Yes
ACT5512	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5513	Environment Agency	Ongoing	Transitioned as measure 0200705066	Yes	Local
ACT5514	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5515	Environment Agency	Ongoing	Transitioned as NOM	Yes	National
ACT5516	Environment Agency	Ongoing		Yes	Local
ACT5517	Environment Agency	Ongoing		Yes	Local
ACT5518	Environment Agency	Ongoing		Yes	Local
ACT5519	Environment Agency	Ongoing		Yes	Local
ACT5520	Environment Agency	Completed		N/A
ACT5521	Environment Agency	Completed		N/A
ACT5522	Environment Agency	Completed		N/A
ACT5523	Environment Agency	Ongoing		Yes	Local
ACT5524	Environment Agency	Completed		N/A
ACT5525	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5528	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5541	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5542	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5543	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5544	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5545	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5546	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5547	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5548	Environment Agency	Completed		N/A
ACT5549	Environment Agency	Completed		N/A
ACT5550	Environment Agency	Completed		N/A
ACT5551	Environment Agency	Completed		N/A
ACT5552	Environment Agency	Ongoing		Yes	Local
ACT5553	Environment Agency	Ongoing	It has been replaced by another measure	Yes	Local
ACT5554	Environment Agency	Ongoing	It has been included in another piece of work	Yes	Local
ACT5555	Environment Agency	Ongoing		Yes	National
ACT5556	Environment Agency	Completed		N/A
ACT5557	Environment Agency	Completed	It has been replaced by another measure 0200705078	No	Local
ACT5558	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5559	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5560	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5561	Environment Agency	Ongoing	Transitioned as measure 0200705067	Yes	Local
ACT5562	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5563	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT5564	Environment Agency	Ongoing		Yes	National
ACT5565	Environment Agency	Ongoing		Yes	Local
ACT5566	Environment Agency	Ongoing		Yes	Local
ACT5580	Environment Agency	Not started - proposed	It has been postponed	Yes	Local
ACT5606	Environment Agency	Ongoing		Yes	National
ACT5614	Environment Agency	Ongoing		Yes	Local
ACT5618	Environment Agency	Ongoing		Yes	Local
ACT5619	Environment Agency	Ongoing		Yes	National
ACT5620	Environment Agency	Ongoing		Yes	Local
ACT5621	Environment Agency	Ongoing		Yes	Local
ACT5622	Environment Agency	Ongoing		Yes	Local
ACT5623	Environment Agency	Ongoing		Yes	National
ACT5626	Environment Agency	Ongoing		Yes	Local
ACT5627	Environment Agency	Ongoing		Yes	Local
ACT5628	Environment Agency	Ongoing		Yes	National
ACT5640	Environment Agency	Ongoing		Yes	Local
ACT5641	Environment Agency	Ongoing		Yes	Local
ACT5642	Environment Agency	Not started - proposed	It has been postponed	Yes	National
ACT5643	Environment Agency	Ongoing		Yes	Local
ACT5644	Environment Agency	Not started - proposed	It has been replaced by another measure	No
ACT5645	Environment Agency	Completed		N/A
ACT5647	Environment Agency	Ongoing		Yes	Local
ACT5648	Environment Agency	Ongoing		Yes	Local
ACT5649	Environment Agency	Ongoing		Yes	Local
ACT5654	Environment Agency	Ongoing		Yes	Local
ACT5656	Environment Agency	Ongoing		Yes	Local
ACT5657	Environment Agency	Ongoing		Yes	Local
ACT5658	Environment Agency	Ongoing		No
ACT5659	Environment Agency	Ongoing	Superseeded by more specfic NFM measures	Yes
ACT5661	Environment Agency	Completed		N/A
ACT5662	Anglian Water	Ongoing	transitioned as aggregate measure 0200905129	Yes
ACT5663	Anglian Water	Ongoing	transitioned as aggregate measure 0200905129	Yes
ACT5664	Anglian Water	Ongoing	transitioned as aggregate measure 0200905129	Yes
ACT5672	Environment Agency	Ongoing		Yes	Local
ACT5673	Anglian Water	Ongoing		Yes	National
ACT5681	Anglian Water	Ongoing	transitioned as aggregate measure 0200905129	Yes
ACT5682	Anglian Water	Ongoing	transitioned as aggregate measure 0200905129	Yes
ACT5683	Anglian Water	Ongoing	transitioned as aggregate measure 0200905129	Yes
ACT5684	Environment Agency	Ongoing		Yes	National
ACT5685	Environment Agency	Ongoing		Yes	Local
ACT5686	Environment Agency	Ongoing		Yes	Local
ACT5687	Environment Agency	Ongoing		Yes	Local
ACT5688	Environment Agency	Ongoing		Yes	Local
ACT5689	Environment Agency	Ongoing		Yes	Local
ACT5707	Environment Agency	Ongoing		Yes	Local
ACT5711	Environment Agency	Ongoing		Yes	Local
ACT5716	Environment Agency	Ongoing		Yes	Local
ACT5719	Environment Agency	Ongoing		Yes	Local
ACT5720	Essex County	Completed		N/A
ACT5721	Essex County	Ongoing		Yes	Local
ACT5722	Essex County	Ongoing		Yes	Local
ACT5723	Essex County	Completed		N/A
ACT5849	Southend-on-SeaUnitary Authority	Ongoing		Yes	National
ACT6055	Environment Agency	Ongoing		Yes	National
ACT6056	Environment Agency	Ongoing		Yes	National
ACT6287	Central Bedfordshire Unitary Authority	Ongoing		Yes
ACT6385	Central Bedfordshire Unitary Authority	Ongoing		Yes
ACT6388	Central Bedfordshire Unitary Authority	Ongoing		Yes
ACT6389	Central Bedfordshire Unitary Authority	Ongoing		Yes
ACT6391	Central Bedfordshire Unitary Authority	Ongoing		Yes
ACT6392	Central Bedfordshire Unitary Authority	Ongoing		Yes
ACT6988	Environment Agency	Ongoing		Yes	Local
ACT699	Environment Agency	Ongoing
ACT700	Environment Agency	Ongoing		Yes
ACT701	Environment Agency	Completed		N/A
ACT702	Environment Agency	Ongoing		Yes
ACT7023	Environment Agency	Ongoing		Yes	National
ACT703	Environment Agency	Ongoing		Yes
ACT704	Environment Agency	Ongoing		Yes
ACT705	Environment Agency	Ongoing		Yes
ACT706	Environment Agency	Ongoing		Yes
ACT707	Environment Agency	Ongoing		Yes
ACT708	Environment Agency	Ongoing		Yes
ACT7082	Southend-on-SeaUnitary Authority	Ongoing		Yes	National
ACT7083	Southend-on-SeaUnitary Authority	Ongoing		Yes	National
ACT7084	Southend-on-SeaUnitary Authority	Completed		N/A
ACT7085	Southend-on-SeaUnitary Authority	Ongoing		Yes	Local
ACT7086	Southend-on-SeaUnitary Authority	Ongoing		Yes	Local
ACT7087	Southend-on-SeaUnitary Authority	Ongoing		Yes	Local
ACT7088	Southend-on-SeaUnitary Authority	Ongoing		Yes	National
ACT7089	Southend-on-SeaUnitary Authority	Ongoing		Yes	National
ACT709	Environment Agency	Completed		N/A	National
ACT7090	Southend-on-SeaUnitary Authority	Ongoing		Yes	National
ACT7091	Southend-on-SeaUnitary Authority	Ongoing		Yes	National
ACT7092	Southend-on-SeaUnitary Authority	Ongoing		Yes	National
ACT7093	Southend-on-SeaUnitary Authority	Ongoing		Yes	National
ACT7094	Southend-on-SeaUnitary Authority	Ongoing		Yes	Local
ACT7095	Southend-on-SeaUnitary Authority	Ongoing		Yes	Local
ACT7096	Southend-on-SeaUnitary Authority	Ongoing		Yes	Local
ACT7097	Southend-on-SeaUnitary Authority	Ongoing		Yes	National
ACT7098	Southend-on-SeaUnitary Authority	Ongoing		Yes	National
ACT7099	Southend-on-SeaUnitary Authority	Ongoing		Yes	National
ACT710	Environment Agency	Completed		N/A
ACT7100	Southend-on-SeaUnitary Authority	Ongoing		Yes	National
ACT7101	Southend-on-SeaUnitary Authority	Ongoing		Yes	Local
ACT7102	Southend-on-SeaUnitary Authority	Ongoing		Yes	National
ACT7105	Norfolk County	Ongoing		Yes	National
ACT7106	Norfolk County	Completed		N/A
ACT7107	Norfolk County	Ongoing
ACT7108	Norfolk County	Ongoing		Yes	National
ACT7109	Norfolk County	Not started - agreed	It has been postponed	Yes	National
ACT711	Environment Agency	Ongoing		Yes
ACT7110	Norfolk County	Ongoing		Yes	National
ACT7111	Norfolk County	Ongoing		Yes	National
ACT7112	Norfolk County	Ongoing		Yes	National
ACT7113	Norfolk County	Superseded	Further work showed it was not viable	N/A
ACT7114	Norfolk County	Ongoing		Yes	National
ACT7115	Norfolk County	Ongoing		Yes	National
ACT7116	Norfolk County	Completed		N/A
ACT7117	Norfolk County	Ongoing		Yes	National
ACT7118	Norfolk County	Ongoing		Yes	National
ACT7119	Norfolk County	Ongoing		Yes	National
ACT712	Environment Agency	Ongoing		Yes
ACT7120	Norfolk County	Ongoing		Yes	National
ACT7121	Kings Lynn IDB	Ongoing		Yes	National
ACT7122	Norfolk County	Ongoing		Yes	National
ACT7123	Norfolk County	Not started - agreed	It has been postponed	Yes	National
ACT7124	Norfolk County	Ongoing		Yes	National
ACT7125	Norfolk County	Not started - agreed	It has been postponed	Yes	National
ACT7126	Norfolk County	Ongoing		Yes	National
ACT7127	Norfolk County	Ongoing		Yes	National
ACT7128	Environment Agency	Completed		N/A
ACT7129	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT713	Environment Agency	Ongoing		Yes	National
ACT7130	Environment Agency	Ongoing		Yes	National
ACT7132	Environment Agency	Ongoing		Yes	National
ACT7135	Environment Agency	Ongoing		Yes	National
ACT7137	Essex County	Completed		N/A
ACT714	Environment Agency	Ongoing		Yes
ACT7140	Milton Keynes Unitary Authority	Ongoing		Yes	National
ACT7141	Environment Agency	Ongoing		Yes
ACT715	Environment Agency	Ongoing		Yes
ACT716	Environment Agency	Ongoing		Yes
ACT717	Environment Agency	Ongoing		Yes
ACT718	Environment Agency	Ongoing		Yes	National
ACT7184	Southend-on-SeaUnitary Authority	Ongoing		Yes
ACT719	Environment Agency	Ongoing		Yes	National
ACT720	Environment Agency	Ongoing		Yes	Local
ACT721	Environment Agency	Ongoing		No
ACT722	Environment Agency	Ongoing		No
ACT723	Environment Agency	Ongoing		No
ACT724	Environment Agency	Ongoing		No
ACT725	Environment Agency	Ongoing		No
ACT726	Environment Agency	Ongoing		No
ACT727	Environment Agency	Ongoing		No
ACT728	Environment Agency	Ongoing		No
ACT729	Environment Agency	Ongoing		No
ACT730	Environment Agency	Ongoing		No
ACT731	Environment Agency	Ongoing		No
ACT732	Environment Agency	Ongoing		No
ACT733	Environment Agency	Ongoing		No
ACT734	Environment Agency	Ongoing		No
ACT735	Environment Agency	Ongoing		No
ACT736	Environment Agency	Ongoing		No
ACT737	Environment Agency	Ongoing		No
ACT738	Environment Agency	Ongoing		No
ACT739	Environment Agency	Ongoing		No
ACT740	Environment Agency	Ongoing		No
ACT741	Environment Agency	Completed		N/A
ACT742	Environment Agency	Completed		N/A
ACT743	Environment Agency	Completed		N/A
ACT744	Environment Agency	Ongoing		No
ACT745	Environment Agency	Ongoing		No
ACT746	Environment Agency	Ongoing		No
ACT747	Environment Agency	Ongoing		No
ACT748	Environment Agency	Ongoing		No
ACT749	Environment Agency	Ongoing		No
ACT7492	Southend-on-SeaUnitary Authority	Ongoing		Yes
ACT750	Environment Agency	Ongoing		No
ACT751	Environment Agency	Ongoing		No
ACT752	Environment Agency	Ongoing		No
ACT753	Environment Agency	Ongoing		No
ACT754	Environment Agency	Ongoing		No
ACT755	Environment Agency	Ongoing		No
ACT756	Environment Agency	Ongoing		No
ACT757	Environment Agency	Ongoing		No
ACT758	Environment Agency	Ongoing		No
ACT759	Environment Agency	Completed	Barrier operational by December 2020.	N/A
ACT760	Environment Agency	Completed		N/A
ACT761	Environment Agency	Ongoing - construction	Design complete and works on site sheduled for late 2020	Yes	Local
ACT762	Environment Agency	Completed		N/A
ACT763	Environment Agency	Superseded	It has been replaced by another measure - Consideration of PLP [now called PLR] handed to LLFA to consider.	N/A
ACT764	Environment Agency	Completed		N/A
ACT765	Environment Agency	Completed		N/A
ACT766	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT767	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT768	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT769	Environment Agency	Superseded	Further work showed it was not viable - Project outcomes will be sought through wider catchment tactical plan measures.	N/A
ACT770	Environment Agency	Superseded	Further work showed it was not viable - Project outcomes will be sought through wider catchment tactical plan measures.	N/A
ACT771	Environment Agency	Superseded	Further work showed it was not viable - Project outcomes will be sought through wider catchment tactical plan measures.	N/A
ACT772	Environment Agency	Superseded	Further work showed it was not viable - Project outcomes will be sought through wider catchment tactical plan measures.	N/A
ACT773	Environment Agency	Superseded	It has been replaced by another measure - Works on Bain superceded by Bain flood storage reservoir.	N/A
ACT774	Environment Agency	Not started - proposed	It has been postponed	No
ACT775	Environment Agency	Superseded	Further work showed it was not viable - Project outcomes will be sought through wider catchment tactical plan measures.	N/A
ACT776	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT777	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT778	Environment Agency	Ongoing		Yes	Local
ACT779	Environment Agency	Superseded	It has been included in another piece of work - Project outcomes will be sought through wider catchment tactical plan measures.	N/A
ACT780	Environment Agency	Not started - proposed	It has been postponed	No
ACT782	Environment Agency	Completed		N/A
ACT783	Environment Agency	Ongoing		Yes	Local
ACT784	Environment Agency	Not started - proposed	It has been replaced by another measure	No
ACT785	Environment Agency	Ongoing		Yes	Local
ACT786	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT787	Environment Agency	Completed		N/A
ACT791	Environment Agency	Ongoing		Yes	Local
ACT793	Environment Agency	Ongoing - construction		Yes	Local
ACT794	Environment Agency	Completed		N/A
ACT795	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT796	Environment Agency	Ongoing		Yes	National
ACT797	Environment Agency	Ongoing		Yes	National
ACT798	Environment Agency	Ongoing		Yes	National
ACT799	Environment Agency	Ongoing		Yes	National
ACT800	Environment Agency	Ongoing		Yes	National
ACT801	Environment Agency	Ongoing		Yes	National
ACT802	Environment Agency	Ongoing		Yes	National
ACT824	Environment Agency	Completed		N/A
ACT837	Environment Agency	Ongoing
ACT839	Environment Agency	Ongoing		Yes
ACT871	Environment Agency	Ongoing		Yes	National
ACT872	Environment Agency	Ongoing		Yes	National
ACT873	Environment Agency	Ongoing		Yes	National
ACT874	Environment Agency	Ongoing		Yes	National
ACT875	Environment Agency	Ongoing		Yes	National
ACT878	Environment Agency	Ongoing		Yes	National
ACT879	Environment Agency	Ongoing		Yes	National
ACT880	Environment Agency	Ongoing		Yes	National
ACT881	Environment Agency	Ongoing		Yes	National