## Cover_sheet
Northumbria flood risk management plan annex 1
This spreadsheet states the progress for the first cycle of the Flood risk management plan (FRMP) (2015-2021). The spreadsheet contains the status of each FRMP plan measure, the measure ID, the action owner, the implementation status as of the 31 March 2021. As well as reasons for not progressing if relevant.
Status of the measures
First cycle measures that comprise of the day-to-day work by the Environment Agency and Lead Local Flood Authorities (LLFAs) are transitioned to this second cycle FRMP as ongoing national-level measures. This may be as an individual measure or aggregated with other measures. More information on these measures can be found in Flood Plan Explorer. / Measures may appear differently in the second cycle compared with the first cycle, for example an individual measure in the first cycle may appear as part of a wider programme of work in the second cycle. / Measures that are not transitioned to the second cycle FRMP will continue to be developed or kept under review by the Environment Agency, LLFA and other risk management authorities. This will be done in accordance with the current Flood and Coastal Erosion Risk Management appraisal guidance and funding rules. / Column D contains blank cells when a measure is 'completed' or 'ongoing' in FRMP cycle 1. / Column F contains blank cells when a measure is 'completed' or not transitioned to FRMP cycle 2.
Links to other FRMP resources
Flood Plan Explorer
Northumbria river basin district flood risk management plan

## FRMP1_annex
Northumbria FRMP 1 annex
This worksheet contains one table.
Measure ID	Measure Owner	Implementation Status	Reason for not progressing	Transitioned to FRMP2?	Transitioned Locally or Nationally?
ACT2089	County Durham Unitary Authority	Completed		No
ACT2090	County Durham Unitary Authority	Completed		No
ACT2091	Sunderland Metropolitan District	Completed		No
ACT2092	Environment Agency	Completed		No
ACT2093	Environment Agency	Completed		No
ACT2094	Environment Agency	Completed		No
ACT2095	Environment Agency	Ongoing - construction		No
ACT2096	Environment Agency	Completed		No
ACT2097	Environment Agency	Superseded	It has been included in another piece of work	No
ACT2098	Environment Agency	Completed		No
ACT2099	Northumbrian Water	Completed		No
ACT2100	County Durham Unitary Authority	Completed		No
ACT2101	Environment Agency	Completed		No
ACT2102	Environment Agency	Completed		No
ACT2103	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT2104	Environment Agency	Completed		No
ACT2105	Environment Agency	Ongoing	It does not yet have funding	No
ACT2106	Environment Agency	Completed		No
ACT2107	Environment Agency	Completed		No
ACT2108	Environment Agency	Completed		No
ACT2109	Environment Agency	Not started - proposed	Other	No
ACT2110	Environment Agency	Completed		No
ACT2111	Environment Agency	Superseded	It has been postponed	No
ACT2112	Environment Agency	Completed	Further work showed it was not viable	No
ACT2113	Environment Agency	Completed		No
ACT2114	Environment Agency	Completed		No
ACT2115	Environment Agency	Superseded		No
ACT2116	Gateshead Metropolitan District	Completed		No
ACT2117	South Tyneside Metropolitan District	Completed		No
ACT2118	Newcastle upon Tyne Metropolitan District	Completed		No
ACT2119	North Tyneside Metropolitan District	Completed		No
ACT2120	Northumberland Unitary Authority	Completed		No
ACT2121	County Durham Unitary Authority	Completed		No
ACT2122	Environment Agency	Completed		No
ACT2123	Environment Agency	Completed		No
ACT2124	Environment Agency	Completed		No
ACT2125	Environment Agency	Not started - proposed	Other	No
ACT2126	Northumbrian Water	Completed		No
ACT2127	Environment Agency	Superseded	It has been included in another piece of work	No
ACT2128	Northumberland Unitary Authority	Completed		No
ACT2129	Environment Agency	Completed		No
ACT2130	Environment Agency	Superseded	Further work showed it was not viable	No
ACT2131	North Tyneside Metropolitan District	Completed		No
ACT2132	Newcastle upon Tyne Metropolitan District	Completed		No
ACT2133	Cumbria County	Completed		No
ACT2134	Environment Agency	Superseded	It has been included in another piece of work	No
ACT2135	Gateshead Metropolitan District	Completed		No
ACT2136	South Tyneside Metropolitan District	Completed		No
ACT2137	Environment Agency	Completed		No
ACT2138	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT2143	County Durham Unitary Authority	Completed		No
ACT2144	County Durham Unitary Authority	Completed		No
ACT2145	Darlington Unitary Authority	Completed		No
ACT2146	Darlington Unitary Authority	Completed		No
ACT2147	North Yorkshire County	Completed		No
ACT2148	North Yorkshire County	Completed		No
ACT2149	Stockton-on-Tees Unitary Authority	Completed		No
ACT2150	Stockton-on-Tees Unitary Authority	Completed		No
ACT2151	Middlesbrough Unitary Authority	Completed		No
ACT2152	Middlesbrough Unitary Authority	Completed		No
ACT2153	Hartlepool Unitary Authority	Completed		No
ACT2154	Hartlepool Unitary Authority	Completed		No
ACT2155	Redcar and Cleveland Unitary Authority	Completed		No
ACT2156	English Heritage	Completed		No
ACT2157	County Durham Unitary Authority	Superseded	Further work showed it was not viable	No
ACT2158	Darlington Unitary Authority	Superseded	Further work showed it was not viable	No
ACT2159	Redcar and Cleveland Unitary Authority	Superseded	Further work showed it was not viable	No
ACT2160	Environment Agency	Superseded	It has been included in another piece of work	No
ACT2161	Environment Agency	Completed		No
ACT2162	Environment Agency	Completed		No
ACT2163	Environment Agency	Superseded	Other	No
ACT2164	Environment Agency	Ongoing		No
ACT2165	Environment Agency	Completed		No
ACT2166	Environment Agency	Completed		No
ACT2167	Environment Agency	Ongoing		No
ACT2168	Environment Agency	Completed		No
ACT2169	County Durham Unitary Authority	Completed		No
ACT2170	Darlington Unitary Authority	Completed		No
ACT2171	Middlesbrough Unitary Authority	Completed		No
ACT2172	Hartlepool Unitary Authority	Completed		No
ACT2173	North Yorkshire County	Completed		No
ACT2174	Redcar and Cleveland Unitary Authority	Completed		No
ACT2175	Stockton-on-Tees Unitary Authority	Completed		No
ACT2176	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT2177	Environment Agency	Completed		No
ACT2178	Environment Agency	Completed		No
ACT2179	Northumberland Unitary Authority	Completed		No
ACT2180	Northumberland Unitary Authority	Completed		No
ACT2181	Northumberland Unitary Authority	Completed		No
ACT2182	Northumberland Unitary Authority	Completed		No
ACT2183	Environment Agency	Superseded	It has been included in another piece of work	No
ACT2184	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT2185	Environment Agency	Ongoing		No
ACT2186	Environment Agency	Superseded	Other	No
ACT2187	Environment Agency	Completed		No
ACT2188	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT2189	Environment Agency	Superseded	Other	No
ACT2190	Northumbrian Water	Completed		No
ACT2191	Newcastle upon Tyne Metropolitan District	Completed		No
ACT2192	North Tyneside Metropolitan District	Completed		No
ACT2193	Environment Agency	Completed		No
ACT2194	Environment Agency	Completed		No
ACT2195	Environment Agency	Completed		No
ACT2196	Environment Agency	Superseded	Other	No
ACT2197	Environment Agency	Not started - proposed	It has been postponed	No
ACT6072	Environment Agency	Completed		No
ACT6081	North Yorkshire County	Ongoing	It has been included in another piece of work	No
ACT6083	North Yorkshire County	Ongoing	It has been included in another piece of work	No
ACT6084	North Yorkshire County	Completed		No
ACT6085	North Yorkshire County	Completed		No
ACT6086	North Yorkshire County	Completed		No
ACT6087	Environment Agency	Completed		No
ACT6088	North Yorkshire County	Completed		No
ACT6089	North Yorkshire County	Ongoing	It has been included in another piece of work	No
ACT6090	North Yorkshire County	Ongoing	It has been included in another piece of work	No
ACT6091	Environment Agency	Superseded	It has been postponed	No
ACT6092	Environment Agency	Ongoing		No
ACT6093	Environment Agency	Completed		No
ACT6094	Environment Agency	Superseded	Further work showed it was not viable	No
ACT6095	Environment Agency	Completed		No
ACT7103	Environment Agency	Completed	It has been included in another piece of work	No
ACT7104	Environment Agency	Completed		No