## Cover_sheet
North West flood risk management plan annex 1
This spreadsheet states the progress for the first cycle of the Flood risk management plan (FRMP) (2015-2021). The spreadsheet contains the status of each FRMP plan measure, the measure ID, the action owner, the implementation status as of the 31 March 2021. As well as reasons for not progressing if relevant.
Status of the measures
First cycle measures that comprise of the day-to-day work by the Environment Agency and Lead Local Flood Authorities (LLFAs) are transitioned to this second cycle FRMP as ongoing national-level measures. This may be as an individual measure or aggregated with other measures. More information on these measures can be found in Flood Plan Explorer. / Measures may appear differently in the second cycle compared with the first cycle, for example an individual measure in the first cycle may appear as part of a wider programme of work in the second cycle. / Measures that are not transitioned to the second cycle FRMP will continue to be developed or kept under review by the Environment Agency, LLFA and other risk management authorities. This will be done in accordance with the current Flood and Coastal Erosion Risk Management appraisal guidance and funding rules. / Column D contains blank cells when a measure is 'completed' or 'ongoing' in FRMP cycle 1. / Column F contains blank cells when a measure is 'completed' or not transitioned to FRMP cycle 2.
Links to other FRMP resources
Flood Plan Explorer
North West river basin district flood risk management plan

## FRMP1_annex
North West FRMP 1 annex
This worksheet contains one table.
Measure ID	Measure Owner	Implementation Status	Reason for not progressing	Transitioned to FRMP2?	Transitioned Locally or Nationally?
ACT1259	United Utilities	Ongoing		No
ACT1262	Environment Agency	Completed		No
ACT1264	North Yorkshire County	Ongoing		No
ACT1265	Environment Agency	Ongoing		No
ACT1266	Environment Agency	Ongoing		No
ACT1267	Environment Agency	Ongoing		No
ACT1269	Lancashire County	Ongoing		No
ACT1270	Environment Agency	Ongoing		No
ACT1274	Environment Agency	Ongoing		No
ACT1275	Lancashire County	Ongoing		No
ACT1277	Environment Agency	Ongoing		No
ACT1279	Environment Agency	Ongoing		No
ACT1281	Lancashire County	Ongoing		No
ACT1282	Environment Agency	Completed		No
ACT1285	Environment Agency	Ongoing		No
ACT1288	Blackburn with Darwen Unitary Authority	Ongoing		No
ACT1289	Environment Agency	Completed		No
ACT1291	Environment Agency	Ongoing		No
ACT1294	Environment Agency	Completed		No
ACT1297	Environment Agency	Ongoing		No
ACT1298	Environment Agency	Ongoing		No
ACT1299	Environment Agency	Not started - agreed	Other - Dependent on partnership funding	No
ACT1300	Fylde District (B)	Ongoing		No
ACT1302	Environment Agency	Ongoing		No
ACT1304	Environment Agency	Completed		No
ACT1305	Environment Agency	Ongoing		No
ACT1306	Environment Agency	Completed		No
ACT1307	Environment Agency	Not started - proposed	It has been replaced by another measure	No
ACT1308	Environment Agency	Ongoing		No
ACT1309	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT1310	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT1311	Environment Agency	Not started - proposed	Other - Dependent on partnership funding	No
ACT1312	Environment Agency	Ongoing		No
ACT1313	Environment Agency	Ongoing		No
ACT1314	Environment Agency	Completed		No
ACT1315	Environment Agency	Ongoing		No
ACT1316	Environment Agency	Ongoing		No
ACT1317	Environment Agency	Ongoing		No
ACT1318	Environment Agency	Not started - proposed	Further work showed it was not viable	No
ACT1319	Environment Agency	Ongoing		No
ACT1320	Environment Agency	Ongoing		No
ACT1321	environment Agency	Ongoing		No
ACT1322	Environment Agency	Ongoing		No
ACT1323	Environment Agency	Ongoing		No
ACT1324	Environment Agency	Completed		No
ACT1325	Environment Agency	Ongoing		No
ACT1328	Environment Agency	Ongoing		No
ACT1329	United Utilities	Completed		No
ACT1330	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT1331	Environment Agency	Completed		No
ACT1332	Environment Agency	Ongoing		No
ACT1333	Lancaster District (B)	Ongoing		No
ACT1334	Environment Agency	Completed		No
ACT1335	Environment Agency	Ongoing		No
ACT1336	Environment Agency	Ongoing		No
ACT1338	Chorley District (B)	Ongoing		No
ACT1339	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT1340	Lancashire County	Ongoing		No
ACT1341	Lancashire County	Ongoing		No
ACT1342	Environment Agency	Superseded	Other - Communities at risk work has been carried out along with work on maintenance withdrawal. This measure is no longer relevant and has been superseded.	No
ACT1345	Environment Agency	Completed		No
ACT1347	Environment Agency	Completed		No
ACT1348	Adur District	Ongoing		No
ACT1350	Environment Agency	Ongoing		No
ACT1351	Environment Agency	Completed		No
ACT1353	Environment Agency	Ongoing		No
ACT1354	Environment Agency	Not started - proposed	It has been replaced by another measure	Yes	Local measure
ACT1355	Environment Agency	Ongoing		No
ACT1356	Wigan Metropolitan District	Ongoing		No
ACT1361	Environment Agency	Completed		No
ACT1362	Environment Agency	Ongoing		No
ACT1363	Lancashire County	Ongoing		No
ACT1365	Environment Agency	Ongoing		No
ACT1368	Adur District	Ongoing		No
ACT1369	Environment Agency	Ongoing		No
ACT1370	Environment Agency	Ongoing		No
ACT1372	Environment Agency	Superseded	Other - Communities at risk work has been carried out along with work on maintenance withdrawal. This measure is no longer relevant and has been superseded.	No
ACT1373	Environment Agency	Ongoing		No
ACT1374	Lancashire County	Ongoing		No
ACT1375	Chorley District (B)	Ongoing		No
ACT1377	Environment Agency	Ongoing		No
ACT1378	Lancashire County	Ongoing		No
ACT1379	Environment Agency	Ongoing		No
ACT1380	Lancashire County	Ongoing		No
ACT1381	Environment Agency	Completed		No
ACT1383	Environment Agency	Ongoing		No
ACT1384	Lancashire County	Ongoing		No
ACT1385	Environment Agency	Completed		No
ACT1386	South Ribble District (B)	Ongoing		No
ACT1387	Environment Agency	Ongoing		No
ACT1388	Lancashire County	Ongoing		No
ACT1390	Adur District	Ongoing		No
ACT1392	Environment Agency	Ongoing		No
ACT1393	Unknown	Ongoing		No
ACT1394	Environment Agency	Completed		No
ACT1396	Environment Agency	Ongoing	Other - Dependent on partnership funding	No
ACT1397	Environment Agency	Ongoing		No
ACT1399	Environment Agency	Not started - agreed	Other - To understand the interaction between river flow and tide.	No
ACT1400	Environment Agency	Completed		No
ACT1402	Lancashire County	Completed		No
ACT1403	Wyre District (B)	Ongoing		No
ACT1404	Environment Agency	Completed		No
ACT1406	Wirral Metropolitan District	Completed		No
ACT1408	Environment Agency	Ongoing		No
ACT1409	Environment Agency	Ongoing		No
ACT1410	Environment Agency	Ongoing		No
ACT1411	Environment Agency	Ongoing		No
ACT1414	Sefton Metropolitan District	Superseded	It has been included in another piece of work	No
ACT1415	Sefton Metropolitan District	Superseded	It has been included in another piece of work	No
ACT1417	Sefton Metropolitan District	Superseded	It has been included in another piece of work	No
ACT1418	Sefton Metropolitan District	Superseded	It has been included in another piece of work	No
ACT1419	Sefton Metropolitan District	Superseded	It has been included in another piece of work	No
ACT1423	Sefton Metropolitan District	Superseded	It has been included in another piece of work	No
ACT1426	Sefton Metropolitan District	Superseded	It has been included in another piece of work	No
ACT1427	Sefton Metropolitan District	Superseded	It has been included in another piece of work	No
ACT1428	Sefton Metropolitan District	Superseded	It has been included in another piece of work	No
ACT1430	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1431	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1432	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1433	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1434	Fylde District (B)	Superseded	It has been included in another piece of work	No
ACT1435	Fylde District (B)	Superseded	It has been included in another piece of work	No
ACT1436	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1441	Blackpool Unitary Authority	Superseded	It has been included in another piece of work	No
ACT1442	Blackpool Unitary Authority	Superseded	It has been included in another piece of work	No
ACT1443	Fylde District (B)	Superseded	It has been included in another piece of work	No
ACT1444	Blackpool Unitary Authority	Superseded	It has been included in another piece of work	No
ACT1445	Blackpool Unitary Authority	Superseded	It has been included in another piece of work	No
ACT1446	Blackpool Unitary Authority	Superseded	It has been included in another piece of work	No
ACT1448	Fylde District (B)	Superseded	It has been included in another piece of work	No
ACT1449	Fylde District (B)	Superseded	It has been included in another piece of work	No
ACT1450	Wyre District (B)	Superseded	It has been included in another piece of work	No
ACT1451	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1453	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1455	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1456	Wyre District (B)	Superseded	It has been included in another piece of work	No
ACT1458	Wyre District (B)	Superseded	It has been included in another piece of work	No
ACT1461	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1465	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1470	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1472	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1476	Lancashire County	Superseded	It has been included in another piece of work	No
ACT1477	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1480	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1481	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1482	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1483	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1486	Lancashire County	Superseded	It has been included in another piece of work	No
ACT1487	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1492	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1493	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1494	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1495	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1496	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1499	South Lakeland District	Superseded	It has been included in another piece of work	No
ACT1500	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1501	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1504	South Lakeland District	Superseded	It has been included in another piece of work	No
ACT1509	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1510	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1514	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1515	Highways Agency	Superseded	It has been included in another piece of work	No
ACT1516	Blackpool Unitary Authority	Superseded	It has been included in another piece of work	No
ACT1517	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1521	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1523	Barrow-in-Furness District (B)	Superseded	It has been included in another piece of work	No
ACT1524	Blackpool Unitary Authority	Superseded	It has been included in another piece of work	No
ACT1526	Barrow-in-Furness District (B)	Superseded	It has been included in another piece of work	No
ACT1527	Blackpool Unitary Authority	Superseded	It has been included in another piece of work	No
ACT1532	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1538	Copeland District (B)	Superseded	It has been included in another piece of work	No
ACT1539	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1542	Carlisle District (B)	Superseded	It has been included in another piece of work	No
ACT1547	Carlisle District (B)	Superseded	It has been included in another piece of work	No
ACT1553	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1554	Copeland District (B)	Superseded	It has been included in another piece of work	No
ACT1556	Carlisle District (B)	Superseded	It has been included in another piece of work	No
ACT1557	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1558	Carlisle District (B)	Superseded	It has been included in another piece of work	No
ACT1559	Cumbria County	Superseded	It has been included in another piece of work	No
ACT1562	Carlisle District (B)	Superseded	It has been included in another piece of work	No
ACT1563	Carlisle District (B)	Superseded	It has been included in another piece of work	No
ACT1571	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1573	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1575	Allerdale District (B)	Superseded	It has been included in another piece of work	No
ACT1576	Allerdale District (B)	Superseded	It has been included in another piece of work	No
ACT1577	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1580	Allerdale District (B)	Superseded	It has been included in another piece of work	No
ACT1581	Allerdale District (B)	Superseded	It has been included in another piece of work	No
ACT1583	Allerdale District (B)	Superseded	It has been included in another piece of work	No
ACT1739	Environment Agency	Completed		No
ACT1740	Environment Agency	Completed		No
ACT1741	Environment Agency	Ongoing		No
ACT1742	Environment Agency	Ongoing		No
ACT1744	Environment Agency	Completed		No
ACT1745	Environment Agency	Ongoing		No
ACT1747	Environment Agency	Ongoing		No
ACT1748	Environment Agency	Completed		No
ACT1749	Environment Agency	Ongoing		No
ACT1751	Environment Agency	Ongoing		No
ACT1752	Environment Agency	Ongoing		No
ACT1753	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1754	Environment Agency	Ongoing		No
ACT1755	Environment Agency	Not started - agreed	It has been replaced by another measure	No
ACT1757	Environment Agency	Ongoing		No
ACT1758	Environment Agency	Not started - agreed	It has been replaced by another measure	No
ACT1759	Environment Agency	Ongoing		No
ACT1760	Environment Agency	Ongoing		No
ACT1761	Environment Agency	Ongoing		No
ACT1764	Environment Agency	Ongoing		No
ACT1765	Environment Agency	Ongoing		No
ACT1766	Environment Agency	Ongoing		No
ACT1767	Environment Agency	Ongoing		No
ACT1768	Environment Agency	Ongoing		No
ACT1769	Environment Agency	Ongoing		No
ACT1770	Environment Agency	Completed		No
ACT1772	United Utilities	Ongoing		No
ACT1773	Environment Agency	Ongoing		No
ACT1774	Environment Agency	Completed		No
ACT1775	Cheshire East Unitary Authority	Ongoing		No
ACT1776	Cheshire East Unitary Authority	Ongoing		No
ACT1777	Environment Agency	Ongoing		No
ACT1778	Environment Agency	Ongoing		No
ACT1779	Cheshire East Unitary Authority	Ongoing		No
ACT1781	Environment Agency	Ongoing		No
ACT1782	Environment Agency	Ongoing		No
ACT1783	Environment Agency	Ongoing		No
ACT1784	Environment Agency	Ongoing		No
ACT1785	Bolton Metropolitan District	Completed		No
ACT1786	Environment Agency	Completed		No
ACT1788	Manchester Metropolitan District	Ongoing		No
ACT1789	Environment Agency	Ongoing		No
ACT1790	Manchester Metropolitan District	Ongoing		No
ACT1791	Oldham Metropolitan District	Ongoing		No
ACT1792	Environment Agency	Completed		No
ACT1794	Environment Agency	Ongoing		No
ACT1796	Environment Agency	Completed		No
ACT1797	Environment Agency	Completed		No
ACT1798	Environment Agency	Completed		No
ACT1799	Environment Agency	Completed		No
ACT1800	Environment Agency	Completed		No
ACT1801	Environment Agency	Completed		No
ACT1802	Environment Agency	Ongoing		No
ACT1803	St. Helens Metropolitan District	Ongoing		No
ACT1804	Warrington Unitary Authority	Ongoing		No
ACT1805	Wirral Metropolitan District	Ongoing		No
ACT1806	Environment Agency	Ongoing		No
ACT1807	Liverpool Metropolitan District	Ongoing		No
ACT4548	Environment Agency	Ongoing		No
ACT4552	Environment Agency	Not started - agreed	It has been replaced by another measure	Yes	Local measure
ACT4555	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT4557	Environment Agency	Completed		No
ACT4559	Environment Agency	Ongoing		No
ACT4561	Environment Agency	Ongoing		No
ACT4562	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT4563	Environment Agency	Completed		No
ACT4564	Environment Agency	Ongoing		Yes	Local measure
ACT4565	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT4566	Environment Agency	Completed		No
ACT4568	Sefton Metropolitan District	Ongoing		No
ACT4571	Environment Agency	Completed		No
ACT4574	Environment Agency	Ongoing		No
ACT4576	West Lancashire District (B)	Ongoing		No
ACT4578	Environment Agency	Completed		No
ACT4580	Environment Agency	Ongoing		No
ACT4581	Environment Agency	Completed		No
ACT4582	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT4584	Environment Agency	Ongoing		Yes	Local measure
ACT4585	Environment Agency	Completed		No
ACT4586	Environment Agency	Completed		No
ACT4587	West Lancashire District (B)	Not started - proposed	It does not yet have funding	No
ACT4588	environment Agency	Not started - proposed	It does not yet have funding	No
ACT4590	Environment Agency	Ongoing		Yes	Local measure
ACT4591	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT4592	Environment Agency	Ongoing		No
ACT4595	Environment Agency	Completed		No
ACT4597	Environment Agency	Completed		No
ACT4599	Environment Agency	Completed		No
ACT4600	Environment Agency	Completed		No
ACT4601	West Lancashire District (B)	Not started - proposed	It does not yet have funding	No
ACT4827	Manchester	Ongoing		No
ACT4846	Rochdale	Completed		No
ACT5008	Blackpool	Completed		No
ACT5740	Manchester Metropolitan District	Ongoing		No
ACT5742	Bolton	Completed		No
ACT5743	Bolton	Completed		No
ACT5744	Bolton	Completed		No
ACT5745	Bolton	Ongoing		No
ACT5746	Bury	Ongoing		No
ACT5747	Liverpool	Ongoing		No
ACT5748	Liverpool	Ongoing		No
ACT5749	Liverpool	Ongoing		No
ACT5750	Liverpool	Ongoing		No
ACT5751	Oldham	Completed		No
ACT5766	Rochdale Metropolitan District	Completed		No
ACT5767	Oldham Metropolitan District	Ongoing		No
ACT5768	Oldham	Completed		No
ACT5769	Oldham	Ongoing		No
ACT5771	Rochdale Metropolitan District	Ongoing		No
ACT5772	Environment Agency	Completed		No
ACT5773	Oldham	Ongoing		No
ACT5782	Environment Agency	Ongoing		No
ACT5783	Salford Metropolitan District	Ongoing		No
ACT5784	Oldham	Ongoing		No
ACT5785	Salford Metropolitan District	Ongoing		No
ACT5786	Oldham	Ongoing		No
ACT5787	Salford Metropolitan District	Completed		No
ACT5788	Oldham	Ongoing		No
ACT5789	Oldham	Completed		No
ACT5790	Oldham	Ongoing		No
ACT5791	Stockport Metropolitan District	Ongoing		No
ACT5792	Oldham	Ongoing		No
ACT5793	Stockport Metropolitan District	Completed		No
ACT5794	Stockport Metropolitan District	Ongoing		No
ACT5795	Stockport Metropolitan District	Ongoing		No
ACT5796	Stockport Metropolitan District	Ongoing		No
ACT5797	Environment Agency	Ongoing		No
ACT5826	Manchester	Ongoing		No
ACT5827	Manchester	Ongoing		No
ACT5828	Manchester	Ongoing		No
ACT5829	Manchester	Ongoing		No
ACT5830	Manchester	Ongoing		No
ACT5832	Manchester	Ongoing		No
ACT5833	Manchester	Ongoing		No
ACT5834	Manchester	Ongoing		No
ACT5835	Manchester	Ongoing		No
ACT5837	Environment Agency	Ongoing		No
ACT5838	Environment Agency	Ongoing		No
ACT5840	Environment Agency	Ongoing		No
ACT5841	Environment Agency	Ongoing		No
ACT5842	Environment Agency	Ongoing		No
ACT5843	Environment Agency	Ongoing		No
ACT5844	Environment Agency	Ongoing		No
ACT5845	Environment Agency	Ongoing		No
ACT5846	Environment Agency	Ongoing		No
ACT5847	Environment Agency	Ongoing		No
ACT5848	Environment Agency	Ongoing		No
ACT5850	Environment Agency	Ongoing		No
ACT5851	Environment Agency	Ongoing - construction		No
ACT5870	Environment Agency	Ongoing		No
ACT5871	Environment Agency	Ongoing		No
ACT5872	Environment Agency	Ongoing		No
ACT5873	Environment Agency	Ongoing		No
ACT5874	Environment Agency	Ongoing		No
ACT5875	Environment Agency	Ongoing		No
ACT5876	Environment Agency	Completed		No
ACT5877	Environment Agency	Completed		No
ACT5878	Environment Agency	Completed		No
ACT5880	Environment Agency	Completed		No
ACT5881	Environment Agency	Ongoing		No
ACT5882	Environment Agency	Completed		No
ACT5883	Environment Agency	Ongoing		No
ACT5884	Environment Agency	Ongoing		No
ACT5886	Environment Agency	Completed		No
ACT5888	Environment Agency	Completed		No
ACT5889	Environment Agency	Ongoing		No
ACT5890	Environment Agency	Completed		No
ACT5891	Environment Agency	Completed		No
ACT5892	Environment Agency	Completed		No
ACT5893	Environment Agency	Ongoing		No
ACT5894	Environment Agency	Completed		No
ACT5895	Environment Agency	Ongoing		Yes	Local measure
ACT5896	Environment Agency	Ongoing		No
ACT5897	Environment Agency	Ongoing - construction		No
ACT6058	Liverpool	Completed		No
ACT6059	Liverpool	Completed		No
ACT6438	Environment Agency	Completed		No
ACT6439	Environment Agency	Completed		No
ACT6441	Sefton	Ongoing		No
ACT6443	Sefton	Superseded	It has been included in another piece of work	No
ACT6444	Sefton	Ongoing		No
ACT6449	Sefton	Ongoing		No
ACT6450	Sefton	Ongoing		No
ACT6452	Sefton	Ongoing		No
ACT6453	Sefton	Completed		No
ACT6989	Environment Agency	Completed		No
ACT6990	Environment Agency	Completed		No
ACT6991	Environment Agency	Completed		No
ACT6992	Environment Agency	Ongoing		No
ACT6993	Environment Agency	Ongoing		No
ACT6994	Environment Agency	Ongoing		No
ACT6995	Environment Agency	Ongoing		No
ACT6996	Environment Agency	Not started - proposed	It has been replaced by another measure	No
ACT6997	Environment Agency	Ongoing		No
ACT6998	Environment Agency	Ongoing		No
ACT6999	Environment Agency	Completed		No
ACT7000	Environment Agency	Completed		No
ACT7001	Environment Agency	Ongoing		No
ACT7002	Cumbria	Ongoing		No
ACT7003	Lake District National Park Authority	Ongoing		No
ACT7004	Environment Agency	Ongoing		No
ACT7005	Environment Agency	Ongoing		No
ACT7006	Highways Agency	Ongoing		No
ACT7007	Environment Agency	Completed		No
ACT7008	Environment Agency	Ongoing		No
ACT7009	Environment Agency	Ongoing		No
ACT7010	Environment Agency	Ongoing		No
ACT7011	Environment Agency	Ongoing		No
ACT7013	Environment Agency	Ongoing		No
ACT7014	Environment Agency	Completed		No
ACT7015	Environment Agency	Ongoing		No
ACT7016	Environment Agency	Ongoing		No
ACT7017	Cumbria	Ongoing		No
ACT7018	Environment Agency	Ongoing		No
ACT7019	Environment Agency	Ongoing		Yes	Local measure
ACT7020	Environment Agency	Ongoing		Yes	Local measure
ACT7021	Environment Agency	Ongoing		No
ACT7022	Environment Agency	Ongoing		Yes	Local measure
ACT7024	Environment Agency	Ongoing		No
ACT7025	Environment Agency	Ongoing		No
ACT7026	Environment Agency	Ongoing		No
ACT7027	Environment Agency	Ongoing		Yes	Local measure
ACT7028	Environment Agency	Ongoing		Yes	Local measure
ACT7029	Environment Agency	Ongoing		No
ACT7030	Environment Agency	Ongoing		No
ACT7031	Environment Agency	Ongoing		No
ACT7032	Environment Agency	Ongoing		No
ACT7033	Environment Agency	Ongoing		No
ACT7034	Environment Agency	Ongoing		No
ACT7035	Environment Agency	Ongoing		No
ACT7036	Environment Agency	Ongoing		No
ACT7037	Environment Agency	Ongoing		No
ACT7038	Environment Agency	Completed		No
ACT7039	Environment Agency	Ongoing		No
ACT7040	Environment Agency	Ongoing		No
ACT7041	Environment Agency	Ongoing		No
ACT7042	Environment Agency	Superseded		No
ACT7043	Environment Agency	Ongoing		No
ACT7044	Environment Agency	Ongoing		No
ACT7045	Environment Agency	Ongoing		No
ACT7046	Environment Agency	Superseded	It has been replaced by another measure	No
ACT7047	Environment Agency	Ongoing		No
ACT7048	Environment Agency	Ongoing		No
ACT7049	Environment Agency	Ongoing		No
ACT7050	Environment Agency	Completed		No
ACT7051	Environment Agency	Ongoing		No
ACT7052	Environment Agency	Completed		No
ACT7053	Environment Agency	Completed		No
ACT7054	Environment Agency	Ongoing		No
ACT7055	Environment Agency	Ongoing		No
ACT7173	Environment Agency	Completed		No
ACT7174	Environment Agency	Ongoing - construction		No
ACT7177	Environment Agency	Ongoing - construction		No
ACT7178	Environment Agency	Completed		No
ACT7180	Environment Agency	Ongoing - construction		No
ACT7181	Blackpool Unitary Authority	Superseded	It has been included in another piece of work	No
ACT7489	Environment Agency	Ongoing		No
ACT7537	Environment Agency	Completed		No
ACT7538	Environment Agency	Completed		No
ACT7539	Environment Agency	Ongoing		No
ACT7540	Environment Agency	Ongoing		No
ACT7541	Environment Agency	Ongoing		No
ACT7542	Environment Agency	Ongoing		No
ACT882	Environment Agency	Ongoing		No
ACT883	Environment Agency	Completed		No
ACT884	Environment Agency	Completed		No
ACT886	Environment Agency	Ongoing		No
ACT888	Environment Agency	Completed		No
ACT889	Environment Agency	Ongoing		No
ACT891	Environment Agency	Ongoing		No
ACT893	Environment Agency	Ongoing		No
ACT894	Environment Agency	Completed		No
ACT895	Environment Agency	Ongoing		No
ACT896	Environment Agency	Ongoing		No
ACT900	Environment Agency	Ongoing		No
ACT901	Environment Agency	Ongoing		No
ACT902	Environment Agency	Ongoing		No
ACT904	Environment Agency	Ongoing		No
ACT907	Environment Agency	Completed		No
ACT909	Environment Agency	Completed		No
ACT910	Environment Agency	Ongoing		No
ACT911	Environment Agency	Ongoing		Yes	Local measure
ACT912	Environment Agency	Ongoing		Yes	Local measure
ACT913	Environment Agency	Completed		No
ACT915	Environment Agency	Completed		No
ACT917	Environment Agency	Ongoing		No
ACT918	Environment Agency	Ongoing		No
ACT919	Environment Agency	Completed		No
ACT920	Environment Agency	Ongoing		No
ACT921	Environment Agency	Ongoing		Yes	Local measure
ACT922	Environment Agency	Completed		Yes	Local measure
ACT923	Environment Agency	Ongoing		No
ACT924	Environment Agency	Ongoing		No
ACT925	Environment Agency	Ongoing		No
ACT926	Environment Agency	Completed		No
ACT927	Environment Agency	Ongoing		No
ACT928	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT929	Environment Agency	Ongoing		No
ACT930	Environment Agency	Completed		No
ACT931	Environment Agency	Ongoing		No