## Cover_sheet
South East flood risk management plan annex 1
This spreadsheet states the progress for the first cycle of the Flood risk management plan (FRMP) (2015-2021). The spreadsheet contains the status of each FRMP plan measure, the measure ID, the action owner, the implementation status as of the 31 March 2021. As well as reasons for not progressing if relevant.
Status of the measures
First cycle measures that comprise of the day-to-day work by the Environment Agency and Lead Local Flood Authorities (LLFAs) are transitioned to this second cycle FRMP as ongoing national-level measures. This may be as an individual measure or aggregated with other measures. More information on these measures can be found in Flood Plan Explorer. / Measures may appear differently in the second cycle compared with the first cycle, for example an individual measure in the first cycle may appear as part of a wider programme of work in the second cycle. / Measures that are not transitioned to the second cycle FRMP will continue to be developed or kept under review by the Environment Agency, LLFA and other risk management authorities. This will be done in accordance with the current Flood and Coastal Erosion Risk Management appraisal guidance and funding rules. / Column D contains blank cells when a measure is 'completed' or 'ongoing' in FRMP cycle 1. / Column F contains blank cells when a measure is 'completed' or not transitioned to FRMP cycle 2.
Links to other FRMP resources
Flood Plan Explorer
South East river basin district flood risk management plan

## FRMP1_annex
South East FRMP 1 annex
This worksheet contains one table.
Measure ID	Measure Owner	Implementation Status	Reason for not progressing	Transitioned to FRMP2?	Transitioned Locally or Nationally?
ACT2585	Environment Agency	Completed		N/A
ACT2587	Environment Agency	Not started - agreed	It does not yet have funding	No
ACT2588	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT2589	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT2590	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT2591	Environment Agency	Completed		N/A
ACT2592	Environment Agency	Ongoing - construction		No
ACT2593	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT2594	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT2596	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT2601	Environment Agency	Completed		N/A
ACT2604	Environment Agency	Completed		N/A
ACT2605	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT2606	Portsmouth Unitary Authority	Not started - proposed	It does not yet have funding	Yes	Locally
ACT2607	Environment Agency	Completed		N/A
ACT2609	Environment Agency	Ongoing - construction		No
ACT2611	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT2613	Environment Agency	Not started - proposed	It does not yet have funding	Yes	Locally
ACT2627	West Sussex County	Completed		N/A
ACT2638	Environment Agency	Completed		N/A
ACT2653	East Sussex County	Not started - proposed	It does not yet have funding	No
ACT2656	East Sussex County	Not started - proposed	It does not yet have funding	No
ACT2659	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT2660	East Sussex County	Not started - proposed	It does not yet have funding	No
ACT2661	Environment Agency	Not started - proposed	It has been postponed	Yes	Locally
ACT2666	Environment Agency	Ongoing		No
ACT2667	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT2669	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT2686	Brighton and Hove Unitary Authority	Completed		N/A
ACT2687	New Forest District	Completed		N/A
ACT2690	Environment Agency	Ongoing - construction		Yes	Locally
ACT2697	Hastings District (B)	Completed		N/A
ACT2701	Environment Agency	Ongoing - construction		Yes	Locally
ACT2709	East Sussex County	Ongoing		Yes	Locally
ACT2715	Lewes District	Completed		N/A
ACT2728	Environment Agency	Ongoing - construction		No
ACT2730	Arun District	Ongoing		No
ACT2732	Arun District	Completed		N/A
ACT2733	Environment Agency	Completed		N/A
ACT2734	Chichester District	Completed		N/A
ACT2749	Environment Agency	Ongoing		Yes	Locally
ACT2755	Eastbourne District (B)	Completed		N/A
ACT2762	Brighton and Hove Unitary Authority	Superseded	Further work showed it was not viable	N/A
ACT2763	Brighton and Hove Unitary Authority	Completed		N/A
ACT2764	Brighton and Hove Unitary Authority	Superseded	It has been included in another piece of work	N/A
ACT2766	Brighton and Hove Unitary Authority	Not started - proposed	It has been postponed	Yes	Locally
ACT2768	Portsmouth Unitary Authority	Completed		N/A
ACT2770	Portsmouth Unitary Authority	Completed		N/A
ACT2779	Portsmouth Unitary Authority	Ongoing		Yes	Locally
ACT2781	Portsmouth Unitary Authority	Ongoing - construction		Yes	Locally
ACT2785	Portsmouth Unitary Authority	Not started - proposed	It does not yet have funding	No
ACT2790	Portsmouth Unitary Authority	Superseded	It has been included in another piece of work	N/A
ACT2794	Environment Agency	Completed		N/A
ACT2795	Environment Agency	Completed		N/A
ACT2796	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT2797	Environment Agency	Completed		N/A
ACT2800	Environment Agency	Ongoing		No
ACT2801	Environment Agency	Completed		N/A
ACT2802	Environment Agency	Completed		N/A
ACT2803	Environment Agency	Ongoing		No
ACT2806	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT2807	Environment Agency	Completed		N/A
ACT2808	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT2809	Environment Agency	Not started - proposed	It has been postponed	No
ACT2810	Environment Agency	Completed		N/A
ACT2812	Environment Agency	Not started - proposed	It has been postponed	No
ACT2822	Arun District	Completed		N/A
ACT2823	Environment Agency	Ongoing		Yes	Nationally
ACT2824	West Sussex County	Completed		N/A
ACT2832	Arun District	Superseded	It has been included in another piece of work	N/A
ACT2833	Arun District	Completed		N/A
ACT5527	Southampton Unitary Authority	Ongoing		Yes	Nationally
ACT5529	Southampton Unitary Authority	Ongoing		Yes	Nationally
ACT5530	Southampton Unitary Authority	Ongoing		Yes	Nationally
ACT5532	Southampton Unitary Authority	Ongoing		Yes	Nationally
ACT5533	Southampton Unitary Authority	Ongoing		Yes	Nationally
ACT5534	Southampton Unitary Authority	Ongoing		Yes	Locally
ACT5536	Southampton Unitary Authority	Ongoing		Yes	Nationally
ACT5538	Southampton Unitary Authority	Completed		N/A
ACT5539	Southampton Unitary Authority	Completed		N/A
ACT5540	Southampton Unitary Authority	Ongoing		Yes	Nationally
ACT6035	Environment Agency	Ongoing		Yes	Nationally
ACT6036	Environment Agency	Ongoing		Yes	Nationally
ACT6037	Environment Agency	Ongoing		Yes	Nationally
ACT6041	Environment Agency	Not started - agreed	It does not yet have funding	No
ACT6042	Environment Agency	Not started - agreed	It does not yet have funding	No
ACT6043	Environment Agency	Not started - agreed	It does not yet have funding	No
ACT6096	Environment Agency	Ongoing		Yes	Nationally
ACT6097	Brighton and Hove Unitary Authority	Ongoing		Yes	Nationally
ACT6098	Mid Sussex District	Ongoing		Yes	Nationally
ACT6099	Lewes District	Ongoing		Yes	Nationally
ACT6100	Wealden District	Ongoing		Yes	Nationally
ACT6101	Environment Agency	Ongoing - construction		No
ACT6102	Environment Agency	Completed		N/A
ACT6103	New Forest District	Ongoing		Yes	Nationally
ACT6104	Environment Agency	Ongoing		Yes	Nationally
ACT6105	Environment Agency	Ongoing		Yes	Nationally
ACT6106	Environment Agency	Ongoing		Yes	Nationally
ACT6108	Environment Agency	Ongoing		Yes	Nationally
ACT6110	Environment Agency	Completed		N/A
ACT6112	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6113	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6114	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT6115	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6116	Environment Agency	Completed		N/A
ACT6118	Environment Agency	Ongoing		Yes	Nationally
ACT6119	Environment Agency	Not started - agreed	It does not yet have funding	No
ACT6120	Environment Agency	Ongoing		Yes	Nationally
ACT6121	West Sussex County	Ongoing		Yes	Nationally
ACT6122	Arun District	Ongoing		Yes	Nationally
ACT6123	Horsham District	Ongoing		Yes	Nationally
ACT6124	Environment Agency	Ongoing		Yes	Nationally
ACT6125	Environment Agency	Not started - agreed	It does not yet have funding	No
ACT6126	Environment Agency	Ongoing		Yes	Nationally
ACT6128	Environment Agency	Ongoing		Yes	Nationally
ACT6129	Environment Agency	Ongoing		Yes	Nationally
ACT6130	Lewes District	Superseded	It has been included in another piece of work	N/A
ACT6131	Environment Agency	Ongoing		No
ACT6160	Environment Agency	Ongoing		Yes	Locally
ACT6162	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT6163	Hastings District (B)	Completed		N/A
ACT6166	Environment Agency	Completed		N/A
ACT6168	Environment Agency	Completed		N/A
ACT6169	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6170	Environment Agency	Ongoing		No
ACT6186	Environment Agency	Ongoing		Yes	Nationally
ACT6187	Environment Agency	Completed		N/A
ACT6189	Brighton and Hove Unitary Authority	Completed		N/A
ACT6190	Brighton and Hove Unitary Authority	Ongoing - construction		No
ACT6191	Brighton and Hove Unitary Authority	Completed		N/A
ACT6192	Environment Agency	Ongoing		Yes	Nationally
ACT6193	Environment Agency	Ongoing		Yes	Nationally
ACT6194	Environment Agency	Ongoing		Yes	Nationally
ACT6195	East Sussex County	Ongoing		Yes	Nationally
ACT6196	Eastbourne District (B)	Ongoing		Yes	Nationally
ACT6197	Rother District	Ongoing		Yes	Nationally
ACT6198	Hastings District (B)	Ongoing		Yes	Nationally
ACT6199	Environment Agency	Completed		N/A
ACT6200	Environment Agency	Completed		N/A
ACT6220	Sussex	Ongoing		Yes	Nationally
ACT6221	West Sussex County	Completed		N/A
ACT6222	Worthing District (B)	Ongoing		No
ACT6223	West Sussex County	Completed		N/A
ACT6224	Worthing District (B)	Superseded	It has been included in another piece of work	N/A
ACT6228	Southampton Unitary Authority	Ongoing		Yes	Nationally
ACT6234	Southampton Unitary Authority	Ongoing		Yes	Nationally
ACT6238	Southampton Unitary Authority	Ongoing		Yes	Nationally
ACT6242	Environment Agency	Ongoing		Yes	Nationally
ACT6243	Environment Agency	Ongoing		Yes	Nationally
ACT6244	Environment Agency	Completed		N/A
ACT6245	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6246	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6247	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT6248	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6249	Environment Agency	Completed		N/A
ACT6251	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT6252	Environment Agency	Ongoing		Yes	Nationally
ACT6253	Environment Agency	Ongoing		No
ACT6254	Arun District	Completed		N/A
ACT6255	West Sussex County	Completed		N/A
ACT6458	Environment Agency	Ongoing		Yes	Nationally
ACT6459	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT6461	Environment Agency	Ongoing		Yes	Nationally
ACT6462	Environment Agency	Ongoing		No
ACT6464	Ashford District (B)	Ongoing		Yes	Nationally
ACT6466	Canterbury District (B)	Ongoing		Yes	Nationally
ACT6467	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT6468	Dover District	Ongoing		Yes	Nationally
ACT6469	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6470	Thanet District	Ongoing		Yes	Nationally
ACT6471	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6472	Environment Agency	Ongoing		Yes	Nationally
ACT6474	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT6476	Environment Agency	Not started - proposed	It has been postponed	No
ACT6484	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT6486	Environment Agency	Completed		N/A
ACT6487	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6488	Environment Agency	Completed		N/A
ACT6492	Environment Agency	Completed		N/A
ACT6493	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6494	Environment Agency	Completed		N/A
ACT6496	Canterbury District (B)	Completed		N/A
ACT6497	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT6501	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6502	Canterbury District (B)	Not started - proposed	It has been postponed	No
ACT6504	Environment Agency	Ongoing		Yes	Nationally
ACT6508	Environment Agency	Ongoing		Yes	Nationally
ACT6509	Canterbury District (B)	Superseded	It has been included in another piece of work	N/A
ACT6510	Environment Agency	Completed		N/A
ACT6512	Canterbury District (B)	Completed		N/A
ACT6513	Thanet District	Superseded	It has been included in another piece of work	N/A
ACT6514	Canterbury District (B)	Completed		N/A
ACT6516	Thanet District	Not started - proposed	It has been postponed	No
ACT6520	Dover District	Completed		N/A
ACT6521	Dover District	Ongoing		No
ACT6524	Thanet District	Completed		N/A
ACT6535	Environment Agency	Completed		N/A
ACT6538	Environment Agency	Completed		N/A
ACT6540	Environment Agency	Completed		N/A
ACT6541	Environment Agency	Ongoing		Yes	Nationally
ACT6543	Environment Agency	Ongoing		Yes	Nationally
ACT6545	Environment Agency	Ongoing		Yes	Nationally
ACT6553	Environment Agency	Completed		N/A
ACT6556	Thanet District	Not started - agreed	It has been postponed	No
ACT6559	Environment Agency	Ongoing		Yes	Nationally
ACT6561	Shepway District	Ongoing		Yes	Nationally
ACT6562	Environment Agency	Completed		N/A
ACT6564	Canterbury District (B)	Ongoing		Yes	Locally
ACT6565	Environment Agency	Completed		N/A
ACT6567	Canterbury District (B)	Completed		N/A
ACT6569	Environment Agency	Ongoing		Yes	Nationally
ACT6571	Canterbury District (B)	Completed		N/A
ACT6573	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6574	Dover District	Completed		N/A
ACT6576	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6577	Thanet District	Completed		N/A
ACT6578	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT6579	Thanet District	Completed		N/A
ACT6585	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT6588	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT6593	Kent County	Ongoing		No
ACT6594	Kent County	Superseded	Further work showed it was not viable	N/A
ACT6597	Kent County	Superseded	Further work showed it was not viable	N/A
ACT6598	Kent County	Superseded	Further work showed it was not viable	N/A
ACT6603	Environment Agency	Completed		N/A
ACT6696	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT6697	Environment Agency	Not started - proposed	It has been postponed	No
ACT6698	Environment Agency	Not started - proposed	It has been postponed	No
ACT6699	Environment Agency	Not started - proposed	It has been postponed	No
ACT6724	Environment Agency	Ongoing		Yes	Nationally
ACT6725	Environment Agency	Ongoing		Yes	Nationally
ACT6726	Environment Agency	Ongoing		Yes	Nationally
ACT6727	Environment Agency	Ongoing		Yes	Nationally
ACT6728	Environment Agency	Ongoing		Yes	Nationally
ACT6732	Environment Agency	Ongoing		Yes	Nationally
ACT6734	Environment Agency	Ongoing		Yes	Nationally
ACT6737	Environment Agency	Ongoing		No
ACT6743	Environment Agency	Ongoing		No
ACT6747	Environment Agency	Ongoing		No
ACT6754	Environment Agency	Completed		N/A
ACT6762	Environment Agency	Ongoing		No
ACT6764	Environment Agency	Ongoing		No
ACT6767	Environment Agency	Ongoing		No
ACT6771	Environment Agency	Ongoing		Yes	Nationally
ACT6778	Environment Agency	Ongoing		No
ACT6779	Environment Agency	Completed		N/A
ACT6782	Environment Agency	Completed		N/A
ACT6785	Rother District	Completed		N/A
ACT6788	Shepway District	Ongoing		Yes	Locally
ACT6803	Shepway District	Ongoing		Yes	Nationally
ACT6807	Shepway District	Completed		N/A
ACT6809	Environment Agency	Completed		N/A
ACT6812	Environment Agency	Completed		N/A
ACT6813	Environment Agency	Ongoing		Yes	Nationally
ACT6814	Environment Agency	Ongoing		Yes	Nationally
ACT6816	Environment Agency	Ongoing		Yes	Nationally
ACT6928	Environment Agency	Completed		N/A
ACT6929	Environment Agency	Ongoing - construction		No
ACT6932	Environment Agency	Ongoing		Yes	Nationally
ACT6933	Environment Agency	Ongoing		Yes	Nationally
ACT6937	Environment Agency	Ongoing		Yes	Nationally
ACT6938	Environment Agency	Ongoing		Yes	Nationally
ACT6939	Environment Agency	Ongoing		Yes	Nationally
ACT6941	Environment Agency	Ongoing		Yes	Nationally
ACT6942	Environment Agency	Ongoing		Yes	Nationally
ACT6944	Environment Agency	Ongoing		Yes	Nationally
ACT6945	Environment Agency	Ongoing		Yes	Nationally
ACT6946	Environment Agency	Ongoing		Yes	Nationally
ACT6947	Environment Agency	Ongoing		Yes	Nationally
ACT6950	Environment Agency	Ongoing		Yes	Nationally
ACT6952	Environment Agency	Ongoing		Yes	Nationally
ACT6953	Environment Agency	Ongoing		Yes	Nationally
ACT6954	Environment Agency	Ongoing		Yes	Nationally
ACT6955	Environment Agency	Ongoing		Yes	Nationally
ACT6956	Environment Agency	Ongoing		Yes	Nationally
ACT6957	Environment Agency	Ongoing		Yes	Nationally
ACT6958	Environment Agency	Ongoing		Yes	Nationally
ACT6961	Environment Agency	Ongoing		Yes	Nationally
ACT6965	Environment Agency	Ongoing		Yes	Nationally
ACT6966	Environment Agency	Ongoing		Yes	Nationally
ACT7155	Hampshire County	Ongoing		Yes	Nationally
ACT7156	Environment Agency	Ongoing		Yes	Nationally
ACT7157	Portsmouth Unitary Authority	Ongoing - construction		Yes	Locally
ACT7172	Southampton Unitary Authority	Superseded	Further work showed it was not viable	N/A