## Cover_sheet
South West Flood risk management plan 1 annex
This spreadsheet states the progress for the first cycle of the Flood risk management plan (FRMP) (2015-2021). The spreadsheet contains the status of each FRMP plan measure, the measure ID, the action owner, the implementation status as of the 31 March 2021. As well as reasons for not progressing if relevant.
Status of the measures
First cycle measures that comprise of the day-to-day work by the Environment Agency and Lead Local Flood Authorities (LLFAs) are transitioned to this second cycle FRMP as ongoing national-level measures. This may be as an individual measure or aggregated with other measures. More information on these measures can be found in Flood Plan Explorer. / Measures may appear differently in the second cycle compared with the first cycle, for example an individual measure in the first cycle may appear as part of a wider programme of work in the second cycle. / Measures that are not transitioned to the second cycle FRMP will continue to be developed or kept under review by the Environment Agency, LLFA and other risk management authorities. This will be done in accordance with the current Flood and Coastal Erosion Risk Management appraisal guidance and funding rules. / Column D contains blank cells when a measure is 'completed' or 'ongoing' in FRMP cycle 1. / Column F contains blank cells when a measure is 'completed' or not transitioned to FRMP cycle 2.
Links to other FRMP resources
Flood Plan Explorer
South West river basin district flood risk management plan

## FRMP1_annex
South West FRMP 1 annex
This worksheet contains one table.
Measure ID	Measure Owner	Implementation Status	Reason for not progressing	Transitioned to FRMP2?	Transitioned Locally or Nationally?
ACT1002	Environment Agency	Ongoing	n/a	Yes	Locally
ACT1003	Environment Agency	Completed	n/a	n/a
ACT1011	Environment Agency	Ongoing	n/a	Yes	Locally
ACT1013	Environment Agency	Completed	n/a	n/a
ACT1014	Environment Agency	Completed	n/a	n/a
ACT1015	Environment Agency	Superseded	It has been replaced by another measure	n/a
ACT1600	Environment Agency	Completed	n/a	n/a
ACT1601	Environment Agency	Ongoing	n/a	Yes	Locally
ACT1602	Environment Agency	Completed	n/a	n/a
ACT1603	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1604	Environment Agency	Superseded	It does not yet have funding	n/a
ACT1605	Environment Agency	Superseded	It has been replaced by another measure	n/a
ACT1606	Environment Agency	Ongoing - construction	n/a	Yes	Locally
ACT1607	Environment Agency	Completed	n/a	n/a
ACT1608	Environment Agency	Completed	n/a	n/a
ACT1609	Environment Agency	Not started - agreed	It has been replaced by another measure	Yes	Locally and nationally
ACT1610	Environment Agency	Completed	n/a	n/a
ACT1611	Environment Agency	Completed	n/a	n/a
ACT1612	Environment Agency	Superseded	It has been replaced by another measure	n/a
ACT1613	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1614	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1615	Environment Agency	Not started - agreed	It has been postponed	Yes	Nationally
ACT1616	Environment Agency	Not started - agreed	It has been postponed	Yes	Nationally
ACT1617	Environment Agency	Not started - agreed	It has been postponed	Yes	Nationally
ACT1618	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1619	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1620	Environment Agency	Ongoing	n/a	Yes	Locally and nationally
ACT1621	Environment Agency	Completed	n/a	n/a
ACT1622	Environment Agency	Not started - agreed	It has been postponed	Yes	Locally and nationally
ACT1623	Environment Agency	Ongoing	n/a	Yes	Locally and nationally
ACT1624	Environment Agency	Completed	n/a	n/a
ACT1625	Environment Agency	Completed	n/a	n/a
ACT1626	Environment Agency	Completed	n/a	n/a
ACT1627	Environment Agency	Not started - agreed	Other - Awaiting engagement to start	yes	Locally and nationally
ACT1628	Environment Agency	Completed	n/a	n/a
ACT1629	Environment Agency	Ongoing	n/a	Yes	Locally and nationally
ACT1630	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1631	Environment Agency	Completed	n/a	n/a
ACT1632	Environment Agency	Completed	n/a	n/a
ACT1633	Environment Agency	Superseded	It has been replaced by another measure	n/a
ACT1634	Environment Agency	Completed	n/a	n/a
ACT1635	Environment Agency	Not started - agreed	It has been postponed	Yes	Nationally
ACT1636	Environment Agency	Not started - agreed	It has been postponed	Yes	Nationally
ACT1637	Environment Agency	Superseded	It has been replaced by another measure	n/a
ACT1638	Environment Agency	Superseded	It has been replaced by another measure	n/a
ACT1639	Environment Agency	Superseded	It has been replaced by another measure	n/a
ACT1640	Environment Agency	Superseded	It has been replaced by another measure	n/a
ACT1641	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1642	Environment Agency	Superseded	It has been replaced by another measure	n/a
ACT1643	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1644	Environment Agency	Completed	n/a	n/a
ACT1645	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1646	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1647	Environment Agency	Not started - agreed	It has been postponed	Yes	Nationally
ACT1648	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1649	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1650	Environment Agency	Superseded	It has been included in another piece of work	n/a
ACT1651	Environment Agency	Superseded	It has been postponed	n/a
ACT1652	Environment Agency	Superseded	It has been included in another piece of work	n/a
ACT1653	Environment Agency	Superseded	It has been included in another piece of work	n/a
ACT1654	Somerset County	Completed	Other - Partnership has been established although there will be a need for ongoing partnership working with RMA's to ensure the success of the updated LFRMS.	n/a
ACT1655	Somerset County	Ongoing	n/a	Yes	Locally
ACT1656	Somerset County	Ongoing	n/a	Yes	Locally
ACT1657	Somerset County	Ongoing	n/a	Yes	Locally
ACT1658	Somerset County	Ongoing	n/a	Yes	Locally
ACT1659	Somerset County	Ongoing	n/a	Yes	Locally
ACT1660	Somerset County	Ongoing	n/a	Yes	Locally
ACT1661	Somerset County	Ongoing	n/a	Yes	Locally
ACT1662	Somerset County	Ongoing	n/a	Yes	Locally
ACT1663	Somerset County	Ongoing	n/a	Yes	Locally
ACT1664	Somerset County	Ongoing	n/a	Yes	Locally
ACT1665	Somerset County	Ongoing	n/a	Yes	Locally
ACT1666	South Somerset District	Ongoing	n/a	Yes	Locally
ACT1667	Environment Agency	Ongoing	n/a	Yes	Locally
ACT1668	Environment Agency	Ongoing - construction	n/a	Yes	Locally
ACT1669	Environment Agency	Ongoing	n/a	Yes	Locally
ACT1670	Environment Agency	Completed	n/a	n/a
ACT1671	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1672	Environment Agency	Completed	n/a	n/a
ACT1673	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1674	Environment Agency	Ongoing	n/a	Yes	Locally
ACT1675	Environment Agency	Ongoing	n/a	Yes	Locally
ACT1676	Environment Agency	Ongoing	n/a	No
ACT1677	Environment Agency	Ongoing	n/a	Yes	Locally
ACT1678	Environment Agency	Ongoing	n/a	No
ACT1679	Environment Agency	Completed	n/a	n/a
ACT1680	Environment Agency	Completed	n/a	n/a
ACT1681	Environment Agency	Completed	n/a	n/a
ACT1682	Environment Agency	Ongoing	n/a	No
ACT1683	Environment Agency	Superseded	Further work showed it was not viable	n/a
ACT1684	Environment Agency	Superseded	Further work showed it was not viable	n/a
ACT1685	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1686	Environment Agency	Superseded	Further work showed it was not viable	n/a
ACT1687	Environment Agency	Superseded	Further work showed it was not viable	n/a
ACT1688	Environment Agency	Superseded	Further work showed it was not viable	n/a
ACT1689	Environment Agency	Superseded	Further work showed it was not viable	n/a
ACT1690	Environment Agency	Superseded	Further work showed it was not viable	n/a
ACT1691	Environment Agency	Not started - proposed	It has been postponed	No
ACT1692	Environment Agency	Superseded	Further work showed it was not viable	n/a
ACT1693	Environment Agency	Completed	n/a	n/a
ACT1694	Environment Agency	Completed	n/a	n/a
ACT1695	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1696	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1697	Environment Agency	Not started - agreed	It has been postponed	Yes	Locally and nationally
ACT1698	Environment Agency	Completed	n/a	n/a
ACT1699	Environment Agency	Completed	n/a	n/a
ACT1700	Environment Agency	Ongoing	n/a	Yes	Locally and nationally
ACT1701	Environment Agency	Ongoing	n/a	Yes	Locally and nationally
ACT1702	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1703	Environment Agency	Superseded	Further work showed it was not viable	n/a
ACT1704	Environment Agency	Ongoing	n/a	Yes	Locally and nationally
ACT1705	Environment Agency	Ongoing	n/a	No
ACT1706	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1707	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1708	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1709	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1710	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1711	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1712	Environment Agency	Ongoing	n/a	Yes	Locally and nationally
ACT1713	Environment Agency	Ongoing	n/a	Yes	Locally and nationally
ACT1714	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1715	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1716	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1717	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1718	Environment Agency	Not started - proposed	It does not yet have funding	Yes	Locally
ACT1719	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1720	Environment Agency	Completed	n/a	n/a
ACT1721	Environment Agency	Ongoing	n/a	Yes	Locally and nationally
ACT1722	Environment Agency	Ongoing	n/a	No
ACT1723	Environment Agency	Ongoing	n/a	Yes	Locally
ACT1724	Environment Agency	Not started - proposed	It does not yet have funding	Yes	Locally
ACT1725	Environment Agency	Ongoing	n/a	Yes	Locally
ACT1726	Environment Agency	Ongoing	n/a	Yes	Locally
ACT1727	Environment Agency	Ongoing	n/a	Yes	Locally
ACT1728	Environment Agency	Not started - proposed	It has been postponed	Yes	Locally
ACT1729	Environment Agency	Not started - proposed	It has been postponed	No
ACT1730	Environment Agency	Not started - proposed	It has been postponed	No
ACT1731	Environment Agency	Ongoing		Yes	Locally
ACT1732	Environment Agency	Not started - proposed	It has been postponed	Yes	Locally
ACT1733	Environment Agency	Ongoing	n/a	Yes	Locally
ACT1734	Environment Agency	Completed	n/a	n/a
ACT1735	Environment Agency	Not started - proposed	It has been postponed	No
ACT1736	Environment Agency	Completed	n/a	n/a
ACT1737	Environment Agency	Completed	n/a	n/a
ACT1738	Environment Agency	Ongoing	n/a	Yes	Nationally
ACT1978	North Somerset Unitary Authority	Completed	n/a	n/a
ACT1982	North Somerset Unitary Authority	Not started - agreed	It does not yet have funding	Yes	Locally
ACT1983	North Somerset Unitary Authority	Not started - agreed	It does not yet have funding	Yes	Locally
ACT1984	North Somerset Unitary Authority	Not started - agreed	It does not yet have funding	Yes	Locally
ACT1985	North Somerset Unitary Authority	Ongoing	n/a	Yes	Locally
ACT1986	North Somerset Unitary Authority	Not started - agreed	It has been included in another piece of work	Yes	Locally
ACT2010	North Somerset Unitary Authority	Not started - agreed	It does not yet have funding	Yes	Locally
ACT2011	North Somerset Unitary Authority	Not started - agreed	It does not yet have funding	Yes	Locally
ACT2016	North Somerset Unitary Authority	Completed	n/a	n/a
ACT2018	North Somerset Unitary Authority	Completed	n/a	n/a
ACT2019	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Locally
ACT2021	North Somerset Unitary Authority	Ongoing	n/a	Yes	Locally
ACT2022	North Somerset Unitary Authority	Ongoing	n/a	Yes	Locally
ACT2023	North Somerset Unitary Authority	Ongoing	n/a	No	Locally
ACT2024	North Somerset Unitary Authority	Ongoing	n/a	No	Locally
ACT2027	North Somerset Unitary Authority	Ongoing	n/a	No	Locally
ACT2029	North Somerset Unitary Authority	Ongoing	n/a	No	Locally
ACT2031	North Somerset Unitary Authority	Not started - proposed	It has been postponed	no	Locally
ACT2034	Environment Agency	Ongoing	n/a	Yes	Locally
ACT2198	Bournemouth Unitary Authority	Ongoing		Yes
ACT2199	Bournemouth Unitary Authority	Ongoing		Yes
ACT2200	Bournemouth Unitary Authority	Superseded	It has been replaced by another measure	yes
ACT2944	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT2945	Environment Agency | Environment Agency	Completed		no
ACT2947	Environment Agency | Environment Agency	Not started - agreed	Other - Measure was originally planned for 2021-27	yes	Locally
ACT2948	Environment Agency | Environment Agency	Ongoing		no
ACT2949	Environment Agency | Environment Agency	Completed		no
ACT2951	Environment Agency | Environment Agency	Superseded	It has been replaced by another measure	no
ACT2952	Environment Agency | Environment Agency	Ongoing - construction		yes	Locally
ACT2953	Environment Agency | Environment Agency	Completed		no
ACT2954	Environment Agency | Environment Agency	Completed		no
ACT2955	Environment Agency | Environment Agency	Superseded	Further work showed it was not viable	no
ACT2956	Environment Agency | Environment Agency	Completed		no
ACT2957	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT2958	Environment Agency | Environment Agency	Completed		no
ACT2959	Environment Agency | Environment Agency	Not started - agreed	Other - Measure was originally planned for 2021-27	yes	Locally
ACT2960	Environment Agency | Environment Agency	Completed		no
ACT2961	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT2963	Environment Agency | Environment Agency	Completed		no
ACT2964	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT2966	Environment Agency | Environment Agency	Completed		no
ACT2967	Environment Agency | Environment Agency	Completed		no
ACT2968	Environment Agency | Environment Agency	Completed	It has been replaced by another measure	no
ACT2969	Environment Agency | Environment Agency	Completed		no
ACT2970	Environment Agency | Environment Agency	Superseded	Further work showed it was not viable	no
ACT2971	Environment Agency | Environment Agency	Superseded	Further work showed it was not viable	no
ACT2972	Environment Agency | Environment Agency	Completed		no
ACT2973	Environment Agency | Environment Agency	Completed		no
ACT2974	Environment Agency | Environment Agency	Completed		no
ACT2975	Environment Agency | Environment Agency	Completed		no
ACT2976	Environment Agency | Environment Agency	Completed		no
ACT2977	Environment Agency | Environment Agency	Superseded	Further work showed it was not viable	no
ACT2978	Environment Agency | Environment Agency	Superseded	Other - It is not a priority location	no
ACT2979	Environment Agency | Environment Agency	Superseded	It does not yet have funding	no
ACT2980	Environment Agency | Environment Agency	Not started - proposed	Other - Measure was originally planned for 2021-27	yes	Locally
ACT2982	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT2983	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT2984	Environment Agency | Environment Agency	Superseded	It has been replaced by another measure	no
ACT2985	Environment Agency | Environment Agency	Ongoing		no
ACT2986	Environment Agency | Environment Agency	Not started - agreed	It has been postponed	yes	Locally
ACT2988	Environment Agency | Environment Agency	Completed		no
ACT2992	Environment Agency | Environment Agency	Superseded	Other - Not a priority location	no
ACT2994	Environment Agency | Environment Agency	Not started - proposed	It has been replaced by another measure	no
ACT2997	Environment Agency | Environment Agency	Completed		no
ACT3000	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT3001	Environment Agency | Environment Agency	Superseded	Other - It is not a priority location	no
ACT3002	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT3004	Environment Agency | Environment Agency	Completed		no
ACT3005	Environment Agency | Environment Agency	Completed		no
ACT3012	Environment Agency | Environment Agency	Superseded	It has been postponed	no
ACT3015	Environment Agency | Environment Agency	Not started - proposed	It has been postponed	yes	Locally
ACT3017	Environment Agency | Environment Agency	Completed		no
ACT3019	Environment Agency | Environment Agency	Completed		no
ACT3021	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT3029	Environment Agency | Environment Agency	Completed		yes	Locally
ACT3042	Cornwall Unitary Authority | Environment Agency	Ongoing		yes	Locally
ACT3068	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT3071	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT3073	Environment Agency | Environment Agency	Completed		no
ACT3080	Environment Agency | Environment Agency	Superseded	Other - Not a priority location	no
ACT3083	Plymouth Unitary Authority | Environment Agency	Ongoing		yes	Locally
ACT3084	Environment Agency | Environment Agency	Completed		no
ACT3085	Cornwall Unitary Authority | Environment Agency	Ongoing		yes	Locally
ACT3089	Plymouth Unitary Authority | Environment Agency	Ongoing		yes	Locally
ACT3090	Environment Agency | Environment Agency	Superseded	It has been included in another piece of work	no
ACT3091	Environment Agency | Environment Agency	Ongoing		no
ACT3093	Environment Agency | Environment Agency	Completed		no
ACT3094	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT3095	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT3098	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT3099	Environment Agency | Environment Agency	Completed		yes	Locally
ACT3100	Environment Agency | Environment Agency	Completed		no
ACT3104	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT3109	Environment Agency | Environment Agency	Completed		no
ACT3113	Environment Agency | Environment Agency	Superseded	It has been replaced by another measure	no
ACT3114	Environment Agency | Environment Agency	Completed		no
ACT3115	Environment Agency | Environment Agency	Not started - proposed	It has been postponed	no
ACT3116	Environment Agency | Environment Agency	Completed		no
ACT3118	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT3119	Environment Agency | Environment Agency	Not started - proposed	It has been postponed	no
ACT3120	Environment Agency | Environment Agency	Ongoing		no
ACT3121	Cornwall Unitary Authority | Environment Agency	Completed		no
ACT3122	Environment Agency | Environment Agency	Completed		no
ACT3123	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT3124	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT3127	Environment Agency | Environment Agency	Not started - proposed	It has been postponed	yes	Locally
ACT3128	Environment Agency | Environment Agency	Superseded	It has been included in another piece of work	no
ACT3129	Environment Agency | Environment Agency	Ongoing		no
ACT3130	Environment Agency | Environment Agency	Superseded	Other - Not a priority location	no
ACT3136	Environment Agency | Environment Agency	Not started - proposed	It does not yet have funding	yes	Locally
ACT3137	Environment Agency | Environment Agency	Ongoing		yes	Locally
ACT3138	Environment Agency | Environment Agency	Completed		no
ACT3139	Environment Agency | Environment Agency	Not started - proposed	It has been postponed	no
ACT3142	Environment Agency | Environment Agency	Completed		no
ACT3145	Environment Agency | Environment Agency	Not started - proposed	Other - Postponed until scheme completed	no
ACT4815	Environment Agency	Ongoing		Yes	Nationally
ACT4817	Environment Agency	Ongoing		Yes	Nationally
ACT4818	Environment Agency	Ongoing		Yes	Nationally
ACT4819	Environment Agency	Ongoing		Yes	Nationally
ACT4949	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT4971	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT4972	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT4973	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT4974	Environment Agency	Superseded	Other - Not deemed strategic enough for FRMP2	N/A
ACT5364	Environment Agency	Ongoing		Yes	Nationally
ACT5365	Environment Agency	Ongoing		Yes	Nationally
ACT5366	Environment Agency	Ongoing		Yes	Nationally
ACT5367	Environment Agency	Ongoing		Yes	Nationally
ACT5368	Environment Agency	Ongoing		Yes	Nationally
ACT5369	Environment Agency	Ongoing		Yes	Nationally
ACT5370	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5371	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5372	Environment Agency	Ongoing		Yes	Nationally
ACT5373	Environment Agency	Ongoing		Yes	Locally
ACT5374	Environment Agency	Completed	Further work showed it was not viable	N/A
ACT5375	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5376	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5377	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT5378	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5379	Environment Agency	Completed		N/A
ACT5380	Environment Agency	Ongoing		Yes	Nationally
ACT5381	Environment Agency	Completed		N/A
ACT5382	Environment Agency	Ongoing		Yes	Nationally
ACT5383	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5384	Environment Agency	Ongoing		Yes	Nationally
ACT5386	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5387	Environment Agency	Ongoing		Yes	Nationally
ACT5388	Environment Agency	Completed		N/A
ACT5389	Environment Agency	Superseded	Other - Groundwater is managed by LPA	N/A
ACT5390	Environment Agency	Ongoing		Yes	Nationally
ACT5391	Environment Agency	Completed		N/A
ACT5392	Environment Agency	Ongoing		Yes	Nationally
ACT5393	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5394	Environment Agency	Ongoing		Yes	Nationally
ACT5395	Environment Agency	Completed		N/A
ACT5396	Environment Agency	Completed		N/A
ACT5398	Environment Agency	Completed		N/A
ACT5399	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5402	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5404	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5406	Environment Agency	Ongoing		Yes	Nationally
ACT5408	Environment Agency	Ongoing		Yes	Nationally
ACT5409	Environment Agency	Ongoing		Yes	Nationally
ACT5410	Environment Agency	Ongoing		Yes	Nationally
ACT5411	Environment Agency	Ongoing		Yes	Nationally
ACT5412	Environment Agency	Ongoing		Yes	Nationally
ACT5413	Environment Agency	Ongoing		Yes	Nationally
ACT5415	Environment Agency	Ongoing		Yes	Nationally
ACT5416	Environment Agency	Ongoing		Yes	Nationally
ACT5417	Environment Agency	Ongoing		Yes	Nationally
ACT5418	Environment Agency	Ongoing		Yes	Nationally
ACT5419	Environment Agency	Ongoing		Yes	Nationally
ACT5420	Environment Agency	Ongoing		Yes	Nationally
ACT5422	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5423	Environment Agency	Ongoing		Yes	Nationally
ACT5424	Environment Agency	Ongoing		Yes	Locally
ACT5430	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5431	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5432	Environment Agency	Completed		N/A
ACT5433	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5434	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5435	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5436	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT5437	Environment Agency	Ongoing		Yes	Nationally
ACT5438	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT6015	Environment Agency	Ongoing		Yes	Nationally
ACT6016	Environment Agency	Ongoing		Yes	Nationally
ACT6017	Environment Agency	Ongoing		yes	Nationally
ACT6018	Environment Agency	Ongoing		Yes	Nationally
ACT6019	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT6020	Environment Agency	Ongoing		Yes	Nationally
ACT6021	Environment Agency	Ongoing		yes	Nationally
ACT6022	Environment Agency	Ongoing		Yes	Nationally
ACT6023	Environment Agency	Ongoing		Yes	Nationally
ACT6024	Environment Agency	Ongoing		Yes	Nationally
ACT6025	Environment Agency	Ongoing - construction		Yes	Locally
ACT6026	Environment Agency	Ongoing		Yes	Nationally
ACT6027	Environment Agency	Ongoing		Yes	Nationally
ACT6028	Environment Agency	Ongoing		Yes	Nationally
ACT6029	Environment Agency	Ongoing		Yes	Nationally
ACT6030	Environment Agency	Ongoing		Yes	Nationally
ACT6031	Environment Agency	Ongoing		Yes	Nationally
ACT6032	Environment Agency	Ongoing		Yes	Nationally
ACT6033	Environment Agency	Ongoing		Yes	Nationally
ACT6034	Environment Agency	Ongoing		Yes	Nationally
ACT7056	Cornwall Unitary Authority | Cornwall Unitary Authority | Cornwall Council	Ongoing		yes	Locally
ACT7057	Environment Agency | Environment Agency | Cornwall Unitary Authority , Plymouth City Council , South West Water	Ongoing		yes	Locally
ACT7058	Environment Agency | Environment Agency | Cornwall Unitary Authority , Plymouth City Council , Network Rail	Ongoing		yes	locally
ACT7059	Environment Agency | Environment Agency | Cornwall Unitary Authority , Isles of Scilly , Teignbridge Council , Plymouth Coastal Observatory	Completed		no
ACT7060	Isles of Scilly Unitary Authority | Isles of Scilly Unitary Authority | Isles of Scilly , Teignbridge Council , Plymouth Coastal Observatory	Ongoing		no
ACT7061	Environment Agency | Environment Agency | Cornwall Unitary Authority , Isles of Scilly , Teignbridge Council , Plymouth Coastal Observatory	Completed		no
ACT7062	Cornwall Unitary Authority | Cornwall Unitary Authority | Cornwall Council , Plymouth City Council , Isles of Scilly , Teignbridge Council , Plymouth Coastal Observatory	Ongoing		yes	locally
ACT7063	Environment Agency | Environment Agency	Completed		no
ACT7064	Environment Agency | Environment Agency | Cornwall Council , Plymouth City Council , Isles of Scilly , Teignbridge Council , Plymouth Coastal Observatory	Ongoing		yes	locally
ACT7065	Cornwall Unitary Authority | Cornwall Unitary Authority | Cornwall Council	Ongoing		yes	locally
ACT7066	Cornwall Unitary Authority | Cornwall Unitary Authority | Cornwall Council , Isles of Scilly , Teignbridge Council , Plymouth Coastal Observatory , Environment Agency	Ongoing		yes	locally
ACT7067	Isles of Scilly | Isles of Scilly | Cornwall Council , Isles of Scilly , Teignbridge Council , Plymouth Coastal Observatory , Environment Agency	Ongoing		no
ACT7068	Environment Agency | Environment Agency | LLFA , Catchment Partnerships , Forestry Commission , Natural England	Completed		no
ACT7069	Environment Agency | Environment Agency | LLFA , Catchment Partnerships , Forestry Commission , Natural England	Completed		no
ACT7185	Environment Agency	Ongoing - construction		No
ACT7186	Environment Agency	Ongoing		No
ACT7187	Environment Agency	Not started - agreed	It does not yet have funding	No
ACT7188	Environment Agency	Completed		No
ACT7189	Environment Agency	Ongoing		No
ACT7190	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT7191	Environment Agency	Ongoing		No
ACT7192	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7193	Devon County	Completed		No
ACT7194	Environment Agency	Ongoing		No
ACT7195	Environment Agency	Ongoing		No
ACT7196	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7197	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7198	Environment Agency	Ongoing		No
ACT7199	Environment Agency	Ongoing		No
ACT7200	South Hams District	Completed		No
ACT7201	Environment Agency	Completed		No
ACT7202	Environment Agency	Not started - agreed	It does not yet have funding	No
ACT7203	Environment Agency	Superseded	It does not yet have funding	No
ACT7204	Environment Agency	Completed		No
ACT7205	Environment Agency	Not started - agreed	It does not yet have funding	No
ACT7206	Environment Agency	Completed		No
ACT7207	Environment Agency	Ongoing	It has been included in another piece of work	No
ACT7208	Environment Agency	Not started - agreed	It has been postponed	No
ACT7209	Environment Agency	Not started - agreed	It has been postponed	No
ACT7210	Environment Agency	Not started - agreed	It does not yet have funding	No
ACT7211	Environment Agency	Ongoing - construction		No
ACT7212	Environment Agency	Superseded	It has been replaced by another measure	No
ACT7213	Environment Agency	Ongoing		No
ACT7214	Devon County	Completed		No
ACT7215	Environment Agency	Completed		No
ACT7216	Environment Agency	Not started - proposed	It has been postponed	No
ACT7217	Environment Agency	Completed		No
ACT7218	Environment Agency	Ongoing		No
ACT7219	Devon County	Completed		No
ACT7220	Environment Agency	Ongoing		No
ACT7221	Torbay Unitary Authority	Not started - agreed	It has been postponed	No
ACT7222	Torbay Unitary Authority	Superseded	It has been postponed	No
ACT7223	Torbay Unitary Authority	Ongoing		No
ACT7224	Environment Agency	Ongoing		No
ACT7225	Torridge District	Superseded	It has been postponed	No
ACT7226	Torridge District	Superseded	It has been postponed	No
ACT7227	Environment Agency	Ongoing		No
ACT7228	Environment Agency	Completed		No
ACT7229	Environment Agency	Not started - proposed	It has been replaced by another measure	No
ACT7230	Teignbridge District	Not started - proposed	It has been postponed	No
ACT7231	Environment Agency	Ongoing - construction		No
ACT7232	Torbay Unitary Authority	Ongoing		No
ACT7233	Devon County	Not started - agreed	It has been postponed	No
ACT7234	Torbay Unitary Authority	Completed		No
ACT7235	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT7236	Environment Agency	Ongoing		No
ACT7237	Teignbridge District	Not started - agreed	It does not yet have funding	No
ACT7238	Environment Agency	Ongoing		No
ACT7239	Environment Agency	Ongoing		No
ACT7240	Environment Agency	Ongoing		No
ACT7241	Environment Agency	Ongoing		No
ACT7242	Environment Agency	Completed		No
ACT7243	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT7244	Devon County	Not started - proposed	It does not yet have funding	No
ACT7245	Environment Agency	Ongoing		No
ACT7246	Environment Agency	Completed		No
ACT7247	Environment Agency	Ongoing		No
ACT7248	Teignbridge District	Completed		No
ACT7249	Environment Agency	Completed		No
ACT7250	Teignbridge District	Ongoing		No
ACT7251	Teignbridge District	Not started - agreed	It does not yet have funding	No
ACT7252	Environment Agency	Superseded	It has been postponed	No
ACT7253	Environment Agency	Ongoing		No
ACT7254	Environment Agency	Not started - agreed	It has been replaced by another measure	No
ACT7255	Environment Agency	Ongoing - construction		No
ACT7256	Environment Agency	Ongoing		No
ACT7257	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7258	Devon County	Ongoing		No
ACT7259	Environment Agency	Ongoing		No
ACT7260	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7261	Environment Agency	Completed		No
ACT7262	Environment Agency	Superseded	It has been replaced by another measure	No
ACT7263	Environment Agency	Ongoing		No
ACT7264	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7265	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7266	Devon County	Ongoing - construction		No
ACT7267	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7268	East Devon District	Superseded	It has been included in another piece of work	No
ACT7269	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7270	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7271	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7272	Environment Agency	Ongoing		No
ACT7273	Environment Agency	Ongoing		No
ACT7274	Environment Agency	Completed		No
ACT7275	Environment Agency	Ongoing - construction		No
ACT7276	Environment Agency	Ongoing		No
ACT7277	Torbay Unitary Authority	Superseded	It has been included in another piece of work	No
ACT7278	Environment Agency	Ongoing		No
ACT7279	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7280	Environment Agency	Ongoing		No
ACT7281	Environment Agency	Not started - agreed	It does not yet have funding	No
ACT7282	Environment Agency	Superseded	It has been replaced by another measure	No
ACT7283	Environment Agency	Completed		No
ACT7284	Teignbridge District	Superseded	It has been included in another piece of work	No
ACT7285	Environment Agency	Completed		No
ACT7286	Environment Agency	Ongoing - construction		No
ACT7287	Exeter District (B)	Ongoing		No
ACT7288	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7289	Environment Agency	Ongoing		No
ACT7290	Devon County	Ongoing		No
ACT7291	Exeter District (B)	Not started - agreed	It has been included in another piece of work	No
ACT7292	Exeter District (B)	Not started - agreed	It does not yet have funding	No
ACT7293	Environment Agency	Ongoing		No
ACT7294	Environment Agency	Ongoing		No
ACT7295	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7296	Environment Agency	Ongoing		No
ACT7297	Environment Agency	Ongoing		No
ACT7298	Environment Agency	Completed		No
ACT7299	Environment Agency	Completed		No
ACT7300	Environment Agency	Ongoing		No
ACT7301	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7302	Environment Agency	Completed		No
ACT7303	East Devon District	Ongoing		No
ACT7304	Devon County	Ongoing		No
ACT7305	Environment Agency	Ongoing		No
ACT7306	Environment Agency	Completed		No
ACT7307	Environment Agency	Ongoing		No
ACT7308	Environment Agency	Completed		No
ACT7309	Environment Agency	Ongoing		No
ACT7310	Environment Agency	Ongoing		No
ACT7311	South Hams District	Not started - agreed	It does not yet have funding	No
ACT7312	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT7313	Environment Agency	Ongoing		No
ACT7314	Environment Agency	Ongoing		No
ACT7315	Environment Agency	Not started - agreed	It has been included in another piece of work	No
ACT7316	Environment Agency	Superseded	It has been postponed	No
ACT7317	Devon County	Completed		No
ACT7318	Devon County	Ongoing		No
ACT7319	Devon County	Ongoing		No
ACT7320	Environment Agency	Completed		No
ACT7321	Environment Agency	Ongoing		No
ACT7322	Devon County	Ongoing		No
ACT7323	Environment Agency	Completed		No
ACT7324	Environment Agency	Ongoing		No
ACT7325	Environment Agency	Not started - agreed	It has been postponed	No
ACT7326	Torbay Unitary Authority	Superseded	It has been included in another piece of work	No
ACT7327	Environment Agency	Completed		No
ACT7328	Devon County	Completed		No
ACT7329	Torbay Unitary Authority	Ongoing		No
ACT7330	Environment Agency	Completed		No
ACT7331	Environment Agency	Ongoing		No
ACT7332	Environment Agency	Completed		No
ACT7333	Environment Agency	Ongoing		No
ACT7334	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7335	Environment Agency	Completed		No
ACT7336	Environment Agency	Ongoing		No
ACT7337	Environment Agency	Ongoing		No
ACT7338	Torridge District	Superseded	It does not yet have funding	No
ACT7339	Environment Agency	Superseded	It has been postponed	No
ACT7340	Environment Agency	Not started - proposed	It has been postponed	No
ACT7341	Environment Agency	Not started - proposed	It has been postponed	No
ACT7342	Environment Agency	Superseded	It has been replaced by another measure	No
ACT7343	Environment Agency	Ongoing		No
ACT7344	Environment Agency	Ongoing		No
ACT7345	Environment Agency	Completed		No
ACT7346	Torbay Unitary Authority	Completed		No
ACT7347	Torbay Unitary Authority	Not started - agreed	It does not yet have funding	No
ACT7348	Torbay Unitary Authority	Not started - proposed	It does not yet have funding	No
ACT7349	Devon County	Ongoing		No
ACT7350	Devon County	Ongoing		No
ACT7351	Environment Agency	Ongoing		No
ACT7352	Environment Agency	Ongoing		No
ACT7353	Environment Agency	Ongoing		No
ACT7354	South Hams District	Superseded	It does not yet have funding	No
ACT7355	East Devon District	Superseded	It has been included in another piece of work	No
ACT7356	Environment Agency	Ongoing		No
ACT7357	Environment Agency	Completed		No
ACT7358	East Devon District	Ongoing		No
ACT7359	East Devon District	Completed		No
ACT7360	East Devon District	Superseded	It has been included in another piece of work	No
ACT7361	Devon County	Ongoing		No
ACT7362	East Devon District	Superseded	It has been included in another piece of work	No
ACT7363	East Devon District	Superseded	It has been included in another piece of work	No
ACT7364	Environment Agency	Ongoing		No
ACT7365	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7366	Environment Agency	Completed		No
ACT7367	Environment Agency	Ongoing		No
ACT7368	Environment Agency	Ongoing		No
ACT7369	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7370	Teignbridge District	Superseded	It has been included in another piece of work	No
ACT7371	Teignbridge District	Completed		No
ACT7372	Teignbridge District	Superseded	It has been included in another piece of work	No
ACT7373	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7374	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7375	Environment Agency	Ongoing		No
ACT7376	Environment Agency	Ongoing		No
ACT7377	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7378	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7379	Environment Agency	Superseded	Other	No
ACT7380	Environment Agency	Ongoing		No
ACT7381	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7382	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7383	Devon County	Superseded	Other	No
ACT7384	Environment Agency	Superseded	Other	No
ACT7385	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7386	Environment Agency	Superseded	Other	No
ACT7387	Environment Agency	Superseded	Other	No
ACT7388	Environment Agency	Superseded	Other	No
ACT7389	Environment Agency	Superseded	Other	No
ACT7390	Environment Agency	Superseded	Other	No
ACT7391	Environment Agency	Superseded	Other	No
ACT7392	Environment Agency	Superseded	Other	No
ACT7393	Environment Agency	Superseded	Other	No
ACT7394	Environment Agency	Ongoing		No
ACT7395	Environment Agency	Superseded	Other	No
ACT7396	Environment Agency	Superseded	Other	No
ACT7397	Devon County	Superseded	Other	No
ACT7398	Teignbridge District	Superseded	Other	No
ACT7399	Environment Agency	Superseded	Other	No
ACT7400	Environment Agency	Superseded	Other	No
ACT7401	Environment Agency	Superseded	Other	No
ACT7402	Environment Agency	Ongoing		No
ACT7403	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7404	Environment Agency	Superseded	Other	No
ACT7405	Environment Agency	Superseded	Other	No
ACT7406	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7407	Environment Agency	Superseded	Other	No
ACT7408	Environment Agency	Superseded	Other	No
ACT7409	Environment Agency	Superseded	Other	No
ACT7410	Environment Agency	Superseded	Other	No
ACT7411	Environment Agency	Superseded	Other	No
ACT7412	Environment Agency	Superseded	Other	No
ACT7413	Environment Agency	Superseded	Other	No
ACT7414	Environment Agency	Superseded	Other	No
ACT7415	Environment Agency	Superseded	Other	No
ACT7416	Environment Agency	Superseded	Other	No
ACT7417	Environment Agency	Superseded	Other	No
ACT7418	Environment Agency	Superseded	Other	No
ACT7419	Environment Agency	Superseded	Other	No
ACT7420	Environment Agency	Superseded	Other	No
ACT7421	Environment Agency	Superseded	Other	No
ACT7422	Environment Agency	Superseded	Other	No
ACT7423	Environment Agency	Superseded	Other	No
ACT7424	Environment Agency	Superseded	Other	No
ACT7425	Environment Agency	Superseded	Other	No
ACT7426	Environment Agency	Ongoing		No
ACT7427	Environment Agency	Superseded	Other	No
ACT7428	Environment Agency	Superseded	Other	No
ACT7429	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7430	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7431	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7432	Environment Agency	Superseded	Other	No
ACT7433	Environment Agency	Superseded	Other	No
ACT7434	Environment Agency	Superseded	Other	No
ACT7435	Environment Agency	Superseded	Other	No
ACT7436	Environment Agency	Superseded	Other	No
ACT7437	Torbay Unitary Authority	Superseded	Other	No
ACT7438	Teignbridge District	Superseded	Other	No
ACT7439	Environment Agency	Ongoing		No
ACT7440	Environment Agency	Completed		No
ACT7441	Environment Agency	Completed		No
ACT7442	Environment Agency	Completed		No
ACT7443	Devon County	Ongoing		No
ACT7444	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7445	Environment Agency	Completed		No
ACT7446	Environment Agency	Ongoing		No
ACT7447	Environment Agency	Completed		No
ACT7448	Teignbridge District	Ongoing		No
ACT7449	Environment Agency	Superseded	Further work showed it was not viable	No
ACT7450	Environment Agency	Completed		No
ACT7451	Teignbridge District	Superseded	It has been included in another piece of work	No
ACT7452	Environment Agency	Ongoing		No
ACT7453	Environment Agency	Ongoing		No
ACT7454	Environment Agency	Completed		No
ACT7455	Environment Agency	Completed		No
ACT7456	Mid Devon District	Completed		No
ACT7457	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7458	Environment Agency	Ongoing		No
ACT7459	Environment Agency	Ongoing		No
ACT7460	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7461	Environment Agency	Ongoing		No
ACT7462	Environment Agency	Completed		No
ACT7463	Environment Agency	Ongoing		No
ACT7464	Environment Agency	Ongoing		No
ACT7465	Torbay Unitary Authority	Superseded	It has been included in another piece of work	No
ACT7466	Torbay Unitary Authority	Superseded	It has been included in another piece of work	No
ACT7467	Environment Agency	Ongoing		No
ACT7468	Torbay Unitary Authority	Superseded	It has been included in another piece of work	No
ACT7469	Torbay Unitary Authority	Superseded	It has been included in another piece of work	No
ACT7470	Torbay Unitary Authority	Completed		No
ACT7471	Torbay Unitary Authority	Ongoing		No
ACT7472	Torbay Unitary Authority	Superseded	It has been postponed	No
ACT7473	Torbay Unitary Authority	Superseded	It has been postponed	No
ACT7474	Environment Agency	Ongoing		No
ACT7475	Torbay Unitary Authority	Superseded	It does not yet have funding	No
ACT7476	Environment Agency	Completed		No
ACT7477	Environment Agency	Completed		No
ACT7478	Environment Agency	Ongoing		No
ACT7479	Environment Agency	Ongoing		No
ACT7480	Devon County	Ongoing		No
ACT7481	Torridge District	Ongoing - construction		No
ACT7482	Torridge District	Superseded	It has been included in another piece of work	No
ACT7483	Environment Agency	Ongoing		No
ACT7484	Environment Agency	Superseded	It has been postponed	No
ACT7485	Environment Agency	Not started - agreed	It does not yet have funding	No
ACT7486	Environment Agency	Superseded	It has been included in another piece of work	No
ACT7487	West Devon District (B)	Not started - proposed	It has been included in another piece of work	No
ACT7488	Devon County	Superseded	Other	No