## Cover_sheet
Solway Tweed flood risk management plan annex 1
This spreadsheet states the progress for the first cycle of the Flood risk management plan (FRMP) (2015-2021). The spreadsheet contains the status of each FRMP plan measure, the measure ID, the action owner, the implementation status as of the 31 March 2021. As well as reasons for not progressing if relevant.
Status of the measures
First cycle measures that comprise of the day-to-day work by the Environment Agency and Lead Local Flood Authorities (LLFAs) are transitioned to this second cycle FRMP as ongoing national-level measures. This may be as an individual measure or aggregated with other measures. More information on these measures can be found in Flood Plan Explorer. / Measures may appear differently in the second cycle compared with the first cycle, for example an individual measure in the first cycle may appear as part of a wider programme of work in the second cycle. / Measures that are not transitioned to the second cycle FRMP will continue to be developed or kept under review by the Environment Agency, LLFA and other risk management authorities. This will be done in accordance with the current Flood and Coastal Erosion Risk Management appraisal guidance and funding rules. / Column D contains blank cells when a measure is 'completed' or 'ongoing' in FRMP cycle 1. / Column F contains blank cells when a measure is 'completed' or not transitioned to FRMP cycle 2.
Links to other FRMP resources
Flood Plan Explorer
Solway Tweed river basin district flood risk management plan

## FRMP1_annex
Solway Tweed FRMP 1 annex
This worksheet contains one table.
Measure ID	Measure Owner	Implementation Status	Reason for not progressing	Transitioned to FRMP2?	Transitioned Locally or Nationally?
ACT1584	Blackpool Unitary Authority	Superseded	It has been included in another piece of work	No
ACT1585	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1586	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1587	Carlisle District (B)	Superseded	It has been included in another piece of work	No
ACT1588	Allerdale District (B)	Superseded	It has been included in another piece of work	No
ACT1589	Blackpool Unitary Authority	Superseded	It has been included in another piece of work	No
ACT1590	Allerdale District (B)	Superseded	It has been included in another piece of work	No
ACT1591	Environment Agency	Superseded	It has been included in another piece of work	No
ACT1592	Blackpool Unitary Authority	Superseded	It has been included in another piece of work	No
ACT1593	Allerdale District (B)	Superseded	It has been included in another piece of work	No
ACT2139	Northumberland Unitary Authority	Ongoing		No
ACT2140	Environment Agency	Ongoing		N/A
ACT2141	Environment Agency	Ongoing		No
ACT2142	Environment Agency	Ongoing		No
ACT5800	Environment Agency	Ongoing		N/A
ACT5804	Environment Agency	Ongoing		No
ACT5806	Environment Agency	Completed		No
ACT5809	Environment Agency	Ongoing		No
ACT5811	Environment Agency	Ongoing		No
ACT5813	Environment Agency	Completed		No
ACT7182	Allerdale District (B)	Superseded	It has been included in another piece of work	No
ACT7183	Environment Agency	Ongoing		No
ACT7543	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT932	Eden District	Ongoing		No
ACT933	Environment Agency	Ongoing		No
ACT934	Environment Agency	Ongoing		No
ACT935	Environment Agency	Ongoing		No
ACT936	Environment Agency	Ongoing		No
ACT937	Environment Agency	Ongoing		No
ACT938	Environment Agency	Ongoing		No
ACT939	Environment Agency	Ongoing		No
ACT940	Environment Agency	Ongoing		No
ACT941	Environment Agency	Ongoing		No
ACT942	Environment Agency	Ongoing		No
ACT943	Environment Agency	Ongoing		No
ACT944	Environment Agency	Ongoing		No
ACT945	Environment Agency	Ongoing		No
ACT946	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT947	Environment Agency	Not started - proposed	It has been postponed	No
ACT948	Environment Agency	Completed		No
ACT949	Environment Agency	Not started - proposed	Other - At the present time MoD are fully operating the site and the chance of withdrawal is currently unlikely. This action will be pursued in the future if withdrawal becomes a reality.	No
ACT950	Environment Agency	Ongoing		No
ACT951	Environment Agency	Completed		No
ACT952	Environment Agency	Not started - proposed	It does not yet have funding	No
ACT953	Environment Agency	Ongoing		No