Evaluation of the Voluntary and Community Sector Emergencies Partnership:
Transition from COVID-19 response to wider emergency preparedness
June 2022

JACKIE GALLAGHER AND MARK FORSYTH

Contents

# Executive summary
## Introduction

The Voluntary and Community Sector Emergencies Partnership (the Partnership) is a network of approximately 240 voluntary and community sector (VCS) organisations working together with local and national statutory partners to ensure support for all who most need it in an emergency. The Partnership was formed in the aftermath of the 2017 national emergencies including the Grenfell Tower fire and terrorist attacks in Manchester and London. It aims to achieve system-level change by bridging the gaps between the emergency response specialist and community-based voluntary sector and between the sector and national government, to build a better-connected, more collaborative and therefore more effective voluntary and community sector contribution to national resilience.

Appendix 1 provides more information on the roles and responsibilities of partners and the Partnership central team.

This report presents findings from a process evaluation of the Partnership’s transition from emergency response to COVID-19 to a more general emergency preparedness model. The Partnership commissioned an independent evaluation by Jackie Gallagher, supported by Mark Forsyth who led on conducting an online survey.

The Partnership’s work has been funded by the department for Digital, Culture Media and Sport (DCMS) over the last two years:

DCMS funding phase	Grant received
April 2020 – March 2021: COVID response	£4,654,112
April 2021 – June 2021: COVID extension	£1,153,123
July 2021 – March 2022: Transition	£696,058
July 2021 – March 2022 (Home Office transferred funds - Afghan response)	£23,000

This report focuses on the transition period between July 2021 to March 2022. The Partnership’s COVID response has been evaluated previously[1] so this evaluation focuses specifically on the lessons learned from the transition period only, and also considers the value of DCMS’s investment and early indicators of impact, whilst not undertaking a formal value for money or impact assessment.
[1] Previous evaluation reports are available from info@vcsep.org.uk

The evaluation used mixed methods to ensure its findings were based on robust evidence and to test the validity and consistency of the key findings across a range of data sources. Methods included an online survey, qualitative one-to-one interviews, participant observation, document review and review of performance metrics.

The Partnership has set three objectives drawn from its Theory of Change (see Appendix 2) as indicators of progress towards longer term impact:
- Strong local and national relationships are built on trust and improved and sustained collaboration and support.
- Communities and organisations work together before, during and after a crisis to maximise expertise and resources for the benefit of the people impacted.
- Shared ongoing insight and understanding of changing threats, needs and activity.

Three lines of enquiry were explored to evaluate the Partnership’s progress towards meeting these objectives during the transition period: building community and national resilience; capability building and skills development; and enabling better insight and information flow.

## Headline findings

The evaluation found that the Partnership has made strong and consistent progress against each of its objectives though the transition period.

A number of points for both learning and action were identified, although there were no areas found where urgent or remedial action was required. These action points are all critical development areas for the Partnership’s ambitions as it moves into preparedness mode. Progress and action points from each key line of enquiry are summarised below, with a bulleted list of all progress and action points for each key line of enquiry in the main report. (Hyperlinked below in paragraph headers).

KLE1: Building community and national resilience

There was sustained progress under this objective with a significant and positive step-change achieved in building trusted connections, increasing collaboration, and in embedding partner VCS organisations within Local Resilience Forums[2] (LRFs) during the transition period. A large part of this is due to success in facilitating and enabling self-agency in the relationships between partners and early work during the COVID-19 response appears to have delivered a sustained effect which is continuing despite reduced resources. However, much of this is based on individual relationships which have been forged through working together during extreme adversity, so working structures will need to be sustained as individuals move on over time.
[2] Multi-agency partnerships of representatives from local public services, including emergency services, local authorities, NHS, Environment Agency and others. LRFs plan and prepare for localised incidents and catastrophic emergencies to prevent or mitigate the impact of any incident on their local communities.

Areas for further action included:
- Continuing relationship building with LRFs, including developing more systematic ways of sharing learning between LRFs and supporting replication and adaptation of models to suit local contexts.
- Ensuring relationships are consistently strong at regional level between the Partnership and national specialist organisations.
- Developing an inclusion roadmap which sets out the steps the Partnership will take to reach its goal of reaching and supporting those disproportionately impacted during an emergency.

KLE2: Capability building and skills development

There was good progress against this objective. Three capability building events were well received, and there has been learning from each event which has helped to improve the next. Other activities which have contributed to the successful implementation of this objective have included the development of a Slack communication channel which has been an increasingly valuable mechanism for sharing information, expertise and practical resources. As with objective 1, an important strength has been enabling peer-to-peer support rather than depending only on outputs from the central staff team.

Areas for further action were:
- Working proactively with a wider range of organisations with relevant experiences who can share their expertise, including those who can contribute direct experience from within communities.
- Contributing to a new inclusion roadmap by accessing hyper-local health inequalities data being generated through Integrated Care Systems[3] health inequalities impact assessments.
  [3] Partnerships which plan and deliver joined up health and care services to improve the lives of people in their area. Following several years of locally led development, the Health and Care Act 2022 is establishing 42 ICSs across England on a statutory basis from 1 July 2022.

KLE3: Insight and information flow

During the transition period the Partnership reviewed its insight strategy, conducted user research and developed a three-year plan for the period 2022 – 2025. Although this is just beginning to be rolled out, the unexpected volume of emergencies which presented over the transition period (the Omicron wave, the winter storms, the Afghanistan evacuation and the war in Ukraine) meant that the Partnership had to step up in real time to each of these and was successful in delivering reliable and timely information and insight, as well as facilitating peer-to-peer information sharing which largely met partners’ needs. This demonstrated early success in its aim to make a strategic shift from ‘pure’ data-driven and technology-led approaches to a ‘networked knowledge’ approach, based on sharing knowledge and improving information flow between partners and others. There were also early indicators that some partners are now using Partnership data to identify vulnerable communities at risk and better target or redirect resources.

There had also been a significant improvement in the use of VCS insight during emergency response by government, with the Department for Levelling Up, Housing and Communities (DLUHC) incorporating Partnership feedback provided during the transition period in its guidance on the Ukraine refugee response published shortly after the transition period.

The evaluation highlighted one area for further action in this key line of enquiry - further developing and testing capability profiling which takes account of the different vulnerabilities and needs of different groups in different areas to contribute to emergency preparedness.

Priorities for action

The two most significant areas across the three lines of enquiry which the evaluation suggests should be prioritised for action are:
- Tackling the next level of building relationships with the Local Resilience Forum.
- Addressing the challenge of increasing reach to disproportionately impacted groups and achieving more inclusive response in emergencies.

These are both major and longer term workstreams for the Partnership and have been key areas of focus in previous evaluations. Good progress has been made against previous recommendations in both these areas, but these will continue to be primary strategic areas where the Partnership will need to focus a sustained and high degree of effort and resources over time.

## Value for Money

Funding from DCMS during the transition period was decreased to less than a fifth of the initial annual COVID-19 response grant, taking account of the changing operating environment and the transition from COVID-19 emergency response to preparedness for other future emergencies. In their joint grant agreement for the transition period the Partnership and DCMS recognised that this would reduce the operating model to “a skeleton, contingency model rather than a full activation status.”[4] The evaluation therefore considered indicators of value within this context of reduced resources and contingency operating model.
[4] Grant variation agreement DCMS/VCSEP: Voluntary and Community Sector Emergencies Partnership (VCSEP) coordination of the voluntary sector’s COVID-19 response and preparedness for other emergencies, 3 August 2021

The evaluation did not include a formal economic analysis and reviewed value for money in general terms only, through two lenses. First, by applying the National Audit Office’s key criteria of economy, efficiency, effectiveness and equity, and second, by considering how far the Partnership had met DCMS’ expectations set out in its Value for Money rationale within the grant agreement.

Relevance and effectiveness

The survey tested via a ranking approach how well the Partnership’s objectives continued to align with the relative priorities of partners, and how effective partners perceived Partnership work had been in the areas which matter most to them. This demonstrated that overall, the Partnership was generally perceived as most effective in areas of higher relative priority for partners with one significant exception – more inclusive response in an emergency ranked highest in importance for partners but was viewed as the second least effective area of work. (See Figure 1: relevance and effectiveness).

Economy, efficiency, effectiveness and equity

The evaluation found that DCMS’ rationale for continued public investment had largely been met against the National Audit Office criteria – fully met against the criteria of economy, efficient and effectiveness, and partly met against the criterion of equity. (See Value for Money evidence table).
## Conclusions

Overall, the evaluators consider that Partnership has delivered against the objectives for the transition period, as evidenced by the analysis across the key lines of enquiry. The evaluation has identified good qualitative and quantitative evidence from the survey, interviews and supplementary evidence sources, that DCMS’ value for money rationale for public investment in the transition from COVID-19 response has largely been met. The evaluators suggest that the Partnership should use this evidence to support its future work towards sustainable funding from more diverse sources.

Ensuring more inclusive response which ensures reach and support to those disproportionately impacted in an emergency is part of a much wider challenge for both the VCS and the statutory sector. This is the least well-developed of the Partnership’s activities but the Partnership is already considering new approaches to embedding inclusion more centrally in its work. Finding ways to set clear targets and measure progress towards this goal will be essential to demonstrating future value.

# 1 Introduction

## 1.1 The Voluntary and Community Sector Emergencies Partnership

The Voluntary and Community Sector Emergencies Partnership (the Partnership) is a network of approximately 240 voluntary and community sector (VCS) organisations working together with local and national statutory partners. Its mission is to act as a mobilising force bringing organisations across the VCS together with its partners in local and national government to deliver a more coordinated and person-centred response to emergencies.

Formed in the aftermath of the 2017 national emergencies including the Grenfell Tower fire and terrorist attacks in Manchester and London, the Partnership seeks to build greater national resilience and a better experience for people adversely impacted by emergencies, especially those disproportionately impacted, by helping to make best use of the resources across the voluntary and community sector. The Partnership aims to achieve system-level change by bridging the gaps between the emergency response specialist and community-based voluntary sector and between the sector and national government, to build a better-connected, more collaborative and therefore more effective voluntary and community sector contribution to national resilience. The Partnership is a collective of organisations working together – rather than creating a new legal entity it works through its partners to achieve change. Its governance structure is co-chaired by NAVCA (the National Association for Voluntary and Community Action) and the British Red Cross, and its central staff team is hosted by the British Red Cross.

Appendix 1 provides more information on the Partnership structure, staffing, roles and responsibilities.

The Partnership was initially funded by in-kind contributions from the founding national partners, with partner cash contributions of £75,000 made during the period July 2021 - March 2022. Its first major public funding was from the Department for Digital, Culture Media and Sport (DCMS) in Spring 2020 to respond to the first wave of the COVID-19 pandemic, with subsequent grant extensions to continue the COVID emergency response to June 2021. DCMS then funded a further nine-month transition period from July 2021 to March 2022 at reduced funding levels to enable a transition from a COVID-19 response model to a preparedness model for all future emergencies.

DCMS has thus played a strategic role in the formation of the Partnership as both the core funding partner, and in continuing to financially support its evolution. DCMS has also played a key convening role in helping the Partnership build and strengthen its cross-government connections with other government departments including the Home Office; the Department of Health and Social Care; the Cabinet Office; the Department for Levelling Up, Housing and Communities; the Department for Education and the Department for Transport.

## 1.2 Purpose of this report

This report provides a process evaluation of the Partnership’s work over the nine-month transition period from July 2021 to March 2022. It is intended to inform the next phase of the Partnership’s development. Whilst not undertaking a formal value for money or impact evaluation, the evaluation does consider the value of DCMS’s investment and early indicators of impact.

## 1.3 Partnership objectives

The objectives for the Partnership’s transition period were drawn directly from its Theory of Change (Appendix 2) which the Partnership reviewed and updated in autumn 2021. These objectives are indicators of progress towards longer term impact:

  - Strong local and national relationships are built on trust and improved and sustained collaboration and support.
  - Communities and organisations work together before, during and after a crisis to maximise expertise and resources for the benefit of the people impacted.
  - Shared ongoing insight and understanding of changing threats, needs and activity.

## 1.4 Key lines of enquiry (KLEs)

The Partnership and DCMS agreed key lines of enquiry (KLEs) to evaluate how work over the last nine months has contributed towards achieving these objectives:

KLE1	Building community and national resilience

1.1	How far has the Partnership helped to better connect local VCS with Local Resilience Forums (LRFs – see Glossary at Appendix 4) and use those connections to improve community and national resilience?
1.2	How far has the Partnership tackled inequalities in emergency response and enabled, facilitated and promoted more inclusive response practice?
1.3	How far has the Partnership enabled improved use of insight to strengthen resilience at local and national levels?

KLE2	Capability building and skills development

2.1	How far do partners feel more enabled to make a more effective and humane intervention?
2.2	How far has capability and capacity changed so that more people know what to do in an emergency?
2.3	How far has capability changed so that those people most at risk during an emergency are reached and supported?

KLE3	Insight and information flow

3.1	How far has the Partnership enabled the VCS to access more and/or better insight?
3.2	How far has the Partnership enabled the VCS to use insight more effectively?
3.3	How far has the Partnership enabled national and local government to access and use more effectively VCS insight that was previously unavailable to them?

## 1.5 Emergencies during the evaluation period

During the transition period there were four major emergencies which required a response at the community or national level. These were:

- winter storms, such as storms Arwen and Eunice
- the Omicron variant wave of COVID-19 infection during the winter and early spring
- the emergency evacuation of refugees from Afghanistan
- the escalation of war in Ukraine causing mass refugee migration.

## 1.6 Evaluation approach and methods

The evaluation used a mixed methods approach to ensure its findings were based on robust evidence and to test the validity and consistency of the key findings across a range of data sources.

Primary data was drawn from two main sources. Firstly, a largely quantitative online survey of VCS partners which achieved a 29% (67 responses) broadly representative response rate. The survey ran from 1st April to 25th April 2022 and it took approximately 14 minutes to complete, on average.

Survey bias: The evaluators consider there was little or no response bias from the VCS organisations surveyed. Early non-response was addressed through two reminders and a deadline extension. The population of VCS organisations surveyed was stratified by size, type and location and the final response was representative across these variables. The survey was anonymous to remove social desirability bias. Any acquiescence bias was minimal as only 12% of respondents answered the same response to every scaled question.

The survey sample of 235 organisations comprised individuals from the 187 VCS signatories to the Partnership’s Working Together agreement, plus individuals from other organisations actively engaged with the Partnership through its network or regional structures and on its e-mailing list. This included a small number of statutory organisations (from national or local government or from other public bodies such as NHS England or the Police) although no responses were received from statutory organisations.

Secondly, qualitative one-to-one interviews were conducted with 43 individuals from a sample of community-based and specialist national VCS organisations and local and national statutory partners. The sample was constructed purposively to include a range of representatives reflecting key characteristics of the Partnership:

Qualitative interviews with Partnership representatives	Number
Local Leads (see Glossary, Appendix 4) from all five of the Partnership regions	7
Other community-based orgnaisations	2
Emergency response specialist organisations	9
Other specialist organisations	10
Faith-based organisations	3
National government departments/agencies	4
Statutory organisation representatives from local government/ LRFs	3
Partnership central team	5
Total	43

Interviews were conducted online between 17th April and 16 May 2022, with an interview time of between 30 – 90 minutes with most taking approximately 60 minutes.

Ethical considerations and confidentiality: The evaluation research methods and tools were developed in accordance with the Social Research Association's Research Ethics Guidance[5]. Evaluation research participants understood that their examples and comments might be quoted in the evaluation report but would not be identifiable as attributable to them or their organisation except where explicitly agreed, and that their personal data would be protected.
[5] See: https://the-sra.org.uk/SRA/SRA/Ethics/Research-Ethics-Guidance.aspx

Limitations of the primary data: The main limitation was the relatively low participation from representatives of the statutory sector at local level. The Partnership’s connection with the 38 LRFs in England is through VCS partners who represent the sector within their local Forum, therefore few statutory LRF representatives are actively involved themselves in the Partnership. This is why the survey sample included only a small number of statutory organisations and the response comprised only VCS organisations. Following survey response analysis, the evaluation team sought to supplement the data with additional qualitative interviews with statutory LRF representatives but these were not possible within the timeframe due to lack of LRF staff availability.

Findings were tested and validated through supplementary methods including:

- Participant observation (all online) – including meetings of the national Network and the five regional hubs; an evaluation workshop with Local Leads; and a half day workshop with the Equalities Steering Group.
- Document review - review of Partnership documents including the Insight Strategy review documentation; activity review and analysis reports such as those for the Afghanistan response; documentation on the sector response to the National Resilience Review; and documentation and participation feedback from capability training and development activities and events.
- Review of key performance metrics – Measuring Success measures agreed with DCMS as part of the grant monitoring framework.

## 1.7 Navigating this report

The transition objectives and the three KLEs for each provide a framework for the evaluation findings and for considering early indications of the value provided over the transition period, summarised in the following sections:

- Section 2 – Building community and national resilience
- Section 3 – Capability building and skills development
- Section 4 – Insight and information flow
Section 5 – Value for Money

A summary of the headline findings is provided for each of the KLE sections which uses a colour-blind friendly colour rating system:

Blue	Positive progress
Amber	Action needed

The headings “Positive progress” and Action needed” are also used for readers not using the colour rating system.

Appendices
These provide more detail on the Partnership’s organisational structure, its Theory of Change, its Value Proposition and a Glossary of terms and acronyms used in the report.

# 2 KLE1: Building community and national resilience

Objective: strong local and national relationships are built on trust and improved and sustained collaboration and support.
KLE 1.1 - How far has the Partnership helped to better connect local VCS with Local Resilience Forums and use those connections to improve local and national resilience? / KLE 1.2 - How far has the Partnership tackled inequalities in emergency response and enabled, facilitated and promoted more inclusive response practice? / KLE 1.3 - How far has the Partnership enabled improved use of insight to strengthen resilience at local and national levels?

Positive progress: / KLE 1.1 / Sustained progress in embedding partners within Local Resilience Forum (LRF) structures. / Sustained progress in building trusted relationships across the Partnership and with LRFs, with a step-change improvement during the transition period in effective responses to new emergencies. / Improved collaboration and support, including new collaboration across county boundaries at regional level. / Increasing openness and collaboration between emergency response specialist and community-based organisations. / KLE 1.2 / Limited progress in promoting more inclusive responses. / KLE 1.3 / Early positive perceived impact on community resilience from improved flow of information and insight.
Action needed: / KLE 1.1 / Build partner VCS organisations’ ability to play a representative and connector role in LRFs where this is not yet mature. / Develop more systematic ways of sharing learning between LRFs and support replication and adaptation of models to suit local contexts – this could include working with collectives such as the National Consortium for Societal Resilience+. / Investigate barriers to engagement within the 11 LRFs without an embedded partner. / Develop advice to help organisations address barriers to effective collaboration. / Strengthen and target engagement and communication on the benefits of ongoing preparedness activity for partners where Partnership relevance may be reducing. / Ensure relationships are consistently strong at a regional level between the Partnership and national specialist organisations. / KLE 1.2 / Develop and set an inclusion roadmap with clear (SMARTER)[6] short- and long-term targets.
[6] Specific, Measurable, Achievable, Realistic/relevant, Timely, Evaluated, Reviewed/revised

## 2.1 Introduction

Background
The Partnership’s primary mechanism for achieving the overarching objective for this key line of enquiry - strong local and national relationships are built on trust and improved and sustained collaboration and support – is relationship-based, working largely through the regional and national hubs where partners come together. It has developed its regional and national hubs to allow for variation in need across the country. The hubs now meet generally on a monthly basis, supplemented by an online platform to enable networks to exchange insights, resources and ideas. The frequency of hub meetings increases as threats or emergencies arise.

Key activities for this KLE during the transition period

- Contributing to a public consultation on the government’s post-implementation review of the Civil Contingencies Act 2004.
- Contributing to the National Preparedness Commission’s independent review of the Act.
- Stepping up the use of the hubs, drawing on strengthened relationships and trust, to respond to the Afghanistan evacuation and the potential effects of the Ukraine war.
- Running a half day workshop with the Equalities Steering Group to plan and prioritise activities for promoting and achieving more inclusive emergency response.
- Launching a new communications App, the Slack channel, intended to improve use of information and insight sharing, before during and after and emergency.

The following sections evaluate the effectiveness of these activities and any lessons and action needed moving forward.

## 2.2 KLE 1.1: How far has the Partnership helped to better connect local VCS with Local Resilience Forums (LRFs) and use those connections to improve local and national resilience?
The survey[7] found that 81% of respondents felt the Partnership had a very positive (24%) or slightly positive (57%) impact on helping their organisation connect better to the local VCS resilience structures. Where smaller numbers of survey respondents reported no impact, this was primarily because there were already good connections in place and most solutions were found locally.
[7] Survey findings here and throughout refer to a total number of 67 responses from a survey of 235 organisations (see section 1.6 for more detail).

The interviews produced a more mixed and complex picture across the country. Consistent with the survey findings though, this was partially dependent on whether the LRF already worked in a closely connected way with the VCS, in which case there was less need felt for Partnership support.

Partner roles within LRF resilience structures

Partnership performance monitoring data shows that by March 2022 one or more partner organisations were embedded within the operational structures in 71% of the 38 LRFs in England demonstrating a steady increase from 45% by January 2021 and 65% by March 2021[8].
[8] Mid-term process evaluation, Report to the Voluntary and Community Sector Emergencies Partnership, January 2021 and Outcomes evaluation: COVID-19 Programme, Report to the Voluntary and Community Sector Emergencies Partnership, April 2021

The Partnership’s aim is to have partner organisations around each LRF table, empowered to speak on behalf of and to connect other partners and VCS organisations in that locality and region as needed. This role is now working well within some LRFs:

“The Partnership representative I’ve got is great and working together we’ve got a consolidated group of voluntary sector individuals far beyond the normal which has opened things up much more for us in understanding…we’ve managed to pull in groups that wouldn’t normally have thought they would be involved in supporting us during an incident. So, we can stand up and everyone knows what they have to do and how it works.”
(LRF Statutory Lead)

Improving collaboration locally and cross-regionally

Where the partner representative role is working as envisaged, it is proving valuable in improving collaboration and facilitating shared learning cross-regionally.

Better collaboration within and across regions: / New dedicated VCS cells within LRF resilience structures
Working collaboratively with partner organisations, LRF A set up a dedicated VCS cell co-chaired by a Partnership representative. It was created during the COVID response but has continued as a permanent structure. In LRF B in another area, a permanent VCS cell is being established with support from the Partnership, using the documentation and terms of reference shared by the Partnership from the LRF A cell as a template. / “There are real benefits to having a dedicated VCS cell – being able to relay information to a whole group at once; we can brief and update on changes to a particular plan; look at learning from previous incidents; training, for example on Resilience Direct. The VCS has been ‘poor cousins’ of the LRF and we want to change that.” (LRF Statutory Lead)

Although there has been continued progress during the transition period with partner organisations now embedded in 27 of the 38 LRFs, in many areas this representation, in the view of the evaluators, has not yet matured into the kind of empowered, connective and representative role envisioned by the Partnership.

Supporting the development of this role more systematically across all LRFs by building on existing strengths and sharing learning from LRFs where the role is already working well and as envisaged will be the key next step towards achieving this long-term goal.

The case example above also highlights both the benefits of having a dedicated VCS cell within an LRF structure and the role the Partnership is already playing in sharing learning between LRFs and supporting replication and adaptation of learning and models to suit local contexts. Another example of effective Partnership knowledge sharing is its contribution to a full day Voluntary Sector Teams webinar hosted by the Emergency Planning Society for LRFs in early April 2022, attended by approximately 68 participants. Partners and central team staff shared recent learning and information on how they could support a future major flood response in dialogue with LRFs who also shared good practice from their engagement with the voluntary sector.

Evaluator reflection - Developing the approach for sharing effective working models with LRFs more systematically should now be a priority for the Partnership moving forward.

Partnership reach

There are a smaller number (11 of the 38 LRFs have no embedded partner within their structures) of areas in the country where both the VCS and the statutory resilience sector are either not engaged with the Partnership or remain at arm’s length. In some cases, this appears to be because these areas have well-established structures and relationships so feel less need for support and engagement with the Partnership. One of the limitations of the evaluation is that interviews have not been conducted with these organisations so there is little evidence so far on the barriers to engagement. The Partnership now needs to address this issue, initially by investigating and understanding better the barriers to engagement, as there may be new opportunities for improving the reach into these areas given the move towards whole-of-society[9] resilience in the emergency response sector.
[9] See: https://nationalpreparednesscommission.uk/2022/03/independent-review-of-the-2004-civil-contingencies-act/

Contributing towards future national resilience strategy

Interview participants from central government departments appreciated the Partnership’s contribution since Spring 2020 in supporting national resilience, during COVID-19 (particularly the mass mobilisation of volunteers nationally) and the more recent emergencies during the transition period. Joint work has continued with various government departments at senior operational levels. During COVID, these working relationships were via the Partnership’s National Volunteering Coordination Cell with: DCMS, the Department of Health and Social Care, Department for Education, and Department of Transport. During the transition period these relationships were with: DCMS, the Home Office and the Department for Levelling Up, Housing and Communities on an emergency-by-emergency basis.

There appears to be a strong commitment to working with the VCS in the strategic shift to a whole-of-society emergency response, but as yet there is no clear picture of how this might translate into systemic and sustainable operational arrangements that are based on more than establishing strong individual working relationships with senior civil servants who are regularly moved on. Interview participants reflected that the scale and nature of change implicit in moving to whole-of-society resilience will realistically be a long-term process. In the meantime, the Partnership might therefore make best use of its finite resources by building on its existing strengths and taking a “bottom-up” approach to achieving incremental change.

As noted above, the evaluators suggest that the Partnership should extend its approach of sharing best practice and operating models to its work with LRFs in a more systemic way. This might involve working with other collectives such as the National Consortium for Societal Resilience [UK+] to bring LRFs together to share practical examples of how the Partnership’s networking and approach adds value to national resilience. This could begin to create the environment for practical change and improvement on the ground.

LRF need for more awareness-raising communications

One LRF statutory representative fed back that although they were working closely with the local voluntary and community sector including partners, they did not really understand the Partnership’s aims and that it would be useful to produce written materials such as leaflets and presentations which set out clearly for LRF members how the Partnership’s local coordinating and connecting role is intended to work.

“Despite a great working relationship, if you asked me exactly what the Partnership was trying to achieve, I wouldn’t be able to answer.” (LRF Statutory Lead).

Sustained progress in building trusted relationships

Interview participants described steady and significant progress in building trust across the Partnership during the transition period. These participants also identified a step-change during the transition period, as stronger and more trusted relationships have kept people better connected or able to re-connect rapidly and so are able to respond more effectively to crises and gaps.

However, participants also noted that building and sustaining strong and trusted relationships should be seen as a long-term objective that will not be realised quickly. Participants felt that in Spring 2020 trust within the sector was at a relatively low base level, particularly between specialist organisations working at the national level and community-based organisations. Interview participants saw this in the context of tensions and challenges across the English voluntary and community sector resulting from several decades of having to meet increased need with reduced resources.

Increased trust in the Partnership collective

Interview participants commented on the increased confidence in the Partnership demonstrated by new organisations now approaching the Partnership directly and actively seeking to take part, compared to the earlier days when proactive work was needed to engage partners. There appears to be increased trust in the overall collective of partner organisations as well as in the structural support from and increased effectiveness of the central team.

“The team is working differently; it’s about how it’s interacting with different sorts of partners and the expectations it’s setting. Where there’s good coordination locally and good relationships they’ve not needed to be involved. Where there’s not, they’ve served a function to bring people together and build some of those bridges in an emergency.” (National Specialist Organisation)

Improved collaboration and mutual support

For participants this better connectedness enabled their organisation or others to respond more effectively and quickly to incidents without having to call for additional support or ending up with unforeseen gaps in response.

“I think there’s better joining-up between the community-focused and the specialist thinking where the local infrastructure convenes different organisations to come together to meet needs.” (National Specialist Organisation)

Trusted relationships during the Omicron wave: / Faster, targeted volunteer recruitment to tackle gaps in vaccine booster programme
During the Omicron wave, one of the specialist emergency response partners had a volunteer shortage in certain local areas during its booster programme. Organisation A is one of the Local Lead organisations for the Emergencies Partnership in the city. It also provides coordination for the city-wide Volunteer Centres Forum as their trusted partner, so was able to rapidly link the partner with volunteer centres in those areas where there were volunteer shortages. / “Because [Organisation A] already had a trusted relationship with the emergency response organisation and was also already trusted by local volunteer centres it really speeded things up and that loop happened much more quickly than it would otherwise have done, within a couple of days.” (Local Lead)

Improved working structures

Participants from both community and specialist organisations described improved structures for working together which have helped to widen participation and increase the sense of parity between partners, including:
- Opening up the network meeting (which usually meets monthly) of national strategic leaders to include active participation from community organisations, smaller specialist organisations representing minoritised communities, and faith-based organisations.
- Sustaining representation of community organisations despite funding reductions by creating 11 Local Leads to liaise with and represent other infrastructure and community organisations within their respective regions. Local Leads cover five broad regions (North; Midlands & East; London; South East, and South West) with two Leads in each region except Midland & East which has three.
- Creating a Local Reference Group of the Local Leads which provides a channel for two-way information flow and feedback between community organisations and the Partnership’s central support team.
- Including two representative Local Leads in the Strategy Steering group, creating a direct route for community organisations’ input to Partnership strategy-making.

“The Partnership has really shifted where it’s at. We’ve shifted away from talking about local and national to talking about community-focused and specialist, which seems to bring a different stance, recognising we have different specialisms makes it less confrontational – it does seem to be better.” (National Specialist Organisation)

New collaboration and support across county boundaries

Local Leads reported a strong legacy from the regional structures introduced during the COVID response enabling collaboration and support across a much wider geographical range within their regions. There had previously been well-established VCS collaborative relationships within counties or other local government and NHS trust boundaries, but the Partnership has enabled and facilitated a much broader engagement across these ‘natural’ boundaries which Local Leads considered a major benefit of the Partnership. This engagement has facilitated regular and extensive knowledge transfer and sharing of learning across the region and built new trusted relationships with peers in other parts of the region who would not otherwise have been known. The benefit was not just for Local Leads themselves but for a much broader group of Chief Executive Officers of community infrastructure organisations within the regions who had provided positive feedback to the Local Leads.

This has been an unforeseen benefit of the Partnership’s geographical structure which has previously been questioned on occasion because it does not map directly to traditional boundaries.

Whilst national specialist organisations sought to ensure they were represented at the main regional meetings, there was significant variation between regions in the extent of day-to-day contact between Local Leads and the regional representatives of national specialist organisations. The frequency and consistency of contact appeared to be determined by whether national organisations had a local emergency response presence. Whilst the above was not flagged as a problem it suggests that there is work required to strengthen the consistency of regional engagement with national specialist organisations.

Improved collaboration with communities

The evaluators consider that the Partnership has delivered a significant step-change in facilitating effective and timely joint working between national emergency response specialist organisations and community organisations (one of the key drivers for establishing the Partnership in the aftermath of the 2017 Grenfell fire and other 2017 national terrorist and climate emergencies).

Specialist emergency response organisations and other large specialist organisations increasingly welcome the opportunity to work more closely with local communities created by the Partnership. The experience of collaboration has demonstrated to them that community organisations bring perspectives and knowledge that enable a more comprehensive and effective response to emergencies.

“Around that table were organisations I’ve never worked with before and they’ve never worked with us, but we were all asking the same questions and sharing the insight that we had and building a more effective picture.” (Emergency Response Specialist Organisation)

However, emergency response specialists also commented on the challenges their organisations faced working with smaller and less institutionalised organisations.

“They worked in a fundamentally different way than we did. We work in a very structured way to crisis response as we’ve learned over the years that you get better and safer outcomes and you can manage the situation more effectively – and many other Partnership organisations work the same way. The new organisations, faith groups and others, weren’t used to working in our way, and actually probably found it a bit stifling – this was a real and helpful challenge to things we just took for granted.” (Emergency Response Specialist Organisation)

With increased collaboration across a wider range of diverse organisations these challenges to working culture and practice are likely to increase in parallel. The Partnership might wish to collate the experiences so far to develop advice to help organisations address barriers to effective collaboration.

Getting the balance right

Participants welcomed the changes to working arrangements and valued the increased sharing of different perspectives and experiences which they felt were happening more naturally as a result. However, there was also a view that that the balance was not yet quite right, with different reasons for this. Some considered that the Partnership still needed to work on ensuring a stronger voice for community level organisations. Others acknowledged the value of aggregating and understanding the diversity of local issues at a strategic level but highlighted a risk of over-focus on the detail of local issues, which might lose engagement from some of the larger specialist organisations.

Sustaining relevance

Participants who had reduced their contact with the Partnership during the transition period reported that this was because they had not been directly affected by any of the emergencies occurring over the last nine months, combined with the pressure of the return to business-as-usual activities post-COVID. This was a particular issue for specialist organisations with a single focus – if the current emergency or other capability building activity was not clearly relevant to their mission, they were less likely to prioritise Partnership engagement.

This suggests that these organisations were primarily relating to the Partnership in its emergency response mode and were not yet convinced of the value of the Partnership’s community preparedness activity to their own missions. These participants all confirmed that they still felt part of the Partnership and that they could easily step back into more active participation whenever needed. However, there is clearly a risk here of drift away over time.

Evaluator reflection - The Partnership should now work to strengthen and target engagement and communication to such organisations on the benefits of ongoing preparedness activity.

## 2.3 KLE 1.2: How far has the Partnership tackled inequalities in emergency response and enabled, facilitated and promoted more inclusive response practice?

The survey identified this as the least developed area of the Partnership’s recent work with 32% identifying no impact, 46% identifying a slight positive impact, and 18% identifying a very positive impact. Survey respondents also ranked this issue as the most important of the Partnership’s intended outcomes.

This perspective was also reflected in the interviews. There were a range of responses from participants, including those who felt the Partnership had made a good start to its work on inclusion, but that this has not yet translated into systemic action that effectively reduces the disproportionate impact of emergencies on vulnerable individuals. Participants also acknowledged that this is not just a Partnership challenge, but one being grappled with by the VCS and statutory sector more widely.

“Despite the caveats I think one of the big value-adds is that where equality was completely off the radar it absolutely isn’t now. It is central to Partnership thinking and functioning and the relationships are there and the trust is there and we’re finding our way to making things more concrete.” (Specialist Organisation)
Seeding inclusive practice

Participants commented that the Partnership is working hard to sow the seeds of more inclusive emergency response – for example, during COVID Partnership members were instrumental in getting key messaging and support to the most disproportionately-impacted communities and improving vaccination take-up.

Increasing confidence to act

Widening the Partnership to bring different voices and experiences into the network has helped develop a better understanding of the factors that contribute to the unintended exclusion of some groups and increased the Partnership’s confidence to act to promote more inclusive practice. Several participants commented that previously some organisations had not felt confident in conversations about promoting inclusion or asking questions such as “Is this a faith issue?”

“They’re not used to having those conversations. Bringing different voices in was helpful because I think it has resulted in, going forward, more focus on the needs of vulnerable groups through different emergencies.” (Local Lead)

Those who had taken part in recent capability building events welcomed the focus on potential impacts for vulnerable groups as a step forward.

Some participants highlighted the value of the work of the Equalities Steering Group in helping to foreground inclusion and suggested that a proposed joint project with Equally Ours, the UK-wide pan-equality and human rights network of over 80 members and associates, to build capacity to prepare for and respond to climate emergencies and to inform policy advocacy would help deliver more inclusive practice for the future.

Need to prepare more systematically for inclusive response irrespective of emergency

Participants also noted that the Partnership needs to go beyond efforts to understand which groups will be disproportionately affected in particular types of crises, which was described as essential but only one building block towards achieving effective and inclusive emergency response. The Partnership also needs to put in place systems that can be used whatever the nature of an emergency - even when that emergency has not been foreseen - to quickly identify those who might be most impacted, and how they can best be reached and supported.

Evaluator reflection - This is a major and long-term work strand for the Partnership, and there is more work to be done to map out the steps which will enable it to reach this goal. In March 2022 the Equalities Steering Group held a workshop to review equality, diversity and inclusion priorities within the context of the Partnership’s operational objectives for financial year 2022/23. The workshop outputs should now be used to develop this roadmap. Section 3.4 of this report suggests that drawing on the data developed by Integrated Care Systems (now legally constituted by the Health and Social Care Act 2022) through place-based health inequalities impact assessments might contribute to such a roadmap.

## 2.4 KLE 1.3: How far has the Partnership enabled improved use of insight to strengthen resilience at local and national levels?

Section 4 of the report evaluates insight and information flow overall and in greater depth, whereas this KLE question considers the use of information and insight specifically in relation to strengthening community resilience. Survey respondents viewed this as the most successful aspect of the Partnership’s work on building community resilience, with 35% identifying a very positive impact, 53% identifying a slight positive impact and only 2% identifying no impact.

This resonated strongly with interview findings. Participants reported that the flow of information and insight was impacting positively on community resilience. Information, good practice and practical tools shared on the Partnership’s Slack channel, through email bulletins, or via regional and national calls have enabled organisations to plan better and to consider things and do things differently.

Information flow as an LRF connector

Local Leads and other interview participants reported that the Partnership has helped connect organisations by supporting the flow of relevant information, which was working well across all five regions, most recently during the Ukraine war. At the beginning of the Ukraine crisis the Partnership directly connected to national government, working closely with the Department for Levelling Up, Housing and Communities (DLUHC), creating frequent national engagement opportunities and launching the #Ukraine channel on its Slack App. These gave partners and LRFs new channels for reliable and timely information.

Local Leads reported that LRFs appreciated the direct flow of information from central government channelled rapidly by the Partnership, also evidenced by a sharp increase in LRF direct engagement in Partnership activities such as network calls, capability building events and regional briefing calls. For example, in one area, the Partnership has an active relationship with the LRF and the County Council, with the wider VCS supporting extensively in relation to the border pressures faced in this area. During the Ukraine crisis, both LRF and County Council representatives joined the Partnership’s Slack channel as active partners sharing and receiving information.

In another area the information flow from the Partnership also helped to support VCS connectedness into the LRF.

“I am sharing lots of intelligence and information that we’re getting through the Partnership - even colleagues that are upper tier local authority leading the Ukraine response don’t always receive the same information that we are able to share. So, we’re really valued as a member that can bring national information from our networks.” (Local Lead)

Similarly in other areas the flow of information related to the Ukraine response has been a lever to connect with the LRFs who have appreciated national level information from the Partnership.

“Our local LRF has started to see the benefit of the Partnership. This is where the Partnership really helps because we’re able to hear it from the horse’s mouth, DCMS or DLUHC, what’s going on, and able to share that locally and wider across the Partnership.” (Local Lead)

Improved information flow has also helped to build dialogue and increase connectedness at regional levels between the VCS and the statutory sector who can easily contribute information which may help others and can also access the information they need themselves.

“Information flow is one of the big things that has improved as a direct result of the Partnership. We weren’t talking outside our boundaries before – we do now. Its helped information flows across the voluntary sector in a wider geographical area, its helped information flows vertically to the public sector locally. We are now more engaged at regional levels so the Local Government Association East of England region is now talking to the voluntary sector across the region – they weren’t doing that a year ago.” (Local Lead)

## 2.5 Summary of key findings

The key lines of enquiry show sustained progress under this objective with a significant and positive step-change achieved in building trusted connections during the transition period. A large part of this is due to success in facilitating and enabling self-agency in the relationships between partners – early work during the COVID-19 response appears to have delivered a sustained effect which is continuing despite reduced resources. However, much of this is based on individual relationships which have been forged through working together during extreme adversity, so working structures will need to be sustained as individuals move on over time.

# 3 KLE2: Capability building and skills development

Objective: communities and organisations work together before, during and after a crisis to maximise expertise and resources for the benefit of the people impacted.
KLE 2.1 - How far do partners feel more enabled to make a more effective and humane intervention? / KLE 2.2 - How far has capability and capacity changed so that more people know what to do in an emergency? / KLE 2.3 - How far has capability changed so that those people most at risk during an emergency are reached and supported?

Positive progress: / KLE 2.1 / 64% of survey respondents felt more enabled by Partnership activities and events to intervene effectively in an emergency. / KLE 2.2 / Significant progress through sharing information, good practice, tools and resources. / The Slack communications channel is a successful new mechanism for sharing expertise and resources, with steadily increasing take-up. / Capability building events were well attended and highly rated with 92% satisfaction rates by April[10]. / There is now an opportunity to better integrate Partnership capability building events with those being offered by LRFs and other bodies. / 93% of those providing feedback from the April event reported enhanced subject knowledge[11]. / 75% of survey respondents thought Partnership activities and events would help people in their communities to know how to respond appropriately in an emergency. / KLE 2.3 / 78% of survey respondents thought Partnership activities and events would help ensure that the most vulnerable receive the support they require in an emergency.
Action needed: / KLE 2.1 / Explore scope to work more proactively with a wider range of organisations with relevant experiences and processes to share their expertise with others, including those who can contribute direct experience from communities themselves. / KLE 2.3 / Contribute to a new inclusion roadmap (suggested in section 2.3) by seeking access to hyper-local health inequalities data via local infrastructure organisations’ engagement with Integrated Care Systems health inequalities impact assessments.
[10] Although delivered in April, the work to plan and develop the content and to engage partners for this event took place during the transition period.
[11] Source: Event feedback questionnaire – see table on event engagement and feedback in section 3.2 for more detail.

## 3.1 Introduction

Background

During the early months of the transition period the Partnership reviewed the support partners need to make the most of the Partnership’s expertise and resources (see Section 4.1 for more detail). One key finding was that partners wanted help to learn and implement lessons from previous emergencies. The Partnership therefore increased its focus on skills sharing and capability-building activities and events, widening participation to include more non-emergency response organisations and more organisations working at a community level.

Key activities for this KLE during the transition period

- Capability building and skill sharing events delivered in October 2021 (flooding); January 2022 (spontaneous volunteer management) and April 2022 (heatwave).
- Launching new tool – Slack online communications and collaboration App.
- Sharing good practice and resources via the Slack channel, website and other mechanisms such as regional and network calls.

The following sections evaluate the effectiveness of these activities and any lessons and action needed moving forward.

## 3.2 KLE 2.1: How far do partners feel more enabled to make a more effective and humane intervention?

The survey[12] found that 64% of respondents expected that the activities and events offered by the Partnership would help ensure that their organisation or other organisations that they support would intervene effectively in an emergency, with 16% identifying very positive impact and 48% identifying a slight impact. Where no impact was noted, for this and for the other two line of enquiry questions discussed in this section, typically this was because respondents already had relevant experiences and processes or they had not yet taken up this part of the Partnership offer.
[12] Survey findings here and throughout refer to a total number of 67 responses from a survey of 235 organisations (see section 1.6 for more detail).

Evaluator reflection - It may be helpful for the Partnership to explore how to work more proactively with a wider range of organisations with relevant experience and processes to share their expertise with others.

One example from the interviews of this type of expertise came from an area where there are well-established community response plans so the community often responds more rapidly than even the local formal emergency responders. There are local people in the area who could contribute directly to sharing this expertise and support national emergency responders to develop their approach to working with what is already in place when helping out in a new location.

Capability and skills sharing events

During the transition period two skills-sharing capability building events were delivered, one on flooding in October 2021 and one on spontaneous volunteer management in January 2022. These events provided a platform for experts by experience to share and discuss their skills in an open forum with a broad range of partners. A third event on heatwaves was planned and developed during the transition period and delivered in April. This event was run as a scenario-based Tabletop Exercise (TTX), allowing organisations to explore their roles, responses and how they would work together in a heatwave specific emergency situation. The aim of these events was to build capability and connections as well as to increase emergency preparedness.

Although the delivery date for the heatwave event falls just outside the formal transition period, the work to plan and develop the content and to engage partners took place during the transition period itself. The evaluators have therefore included event feedback within the evaluation because this is helpful to show trends, because it indicates the early impact of work undertaken during the period and because during interviews participants could offer fresh and recent reflections of value to this overall line of enquiry.

Event engagement

Events were well attended with a well-balanced mix of local community-based, emergency response specialist, local authority and LRF representatives.

 The following table provides more information on participation, feedback levels and satisfaction rates.

Event engagement and feedback

Event	Total # participants	# participants statutory organisations	Total # feedback	% would recommend / event	% satisfied
Flooding / October 2021	31	9	1	N/A	N/A
Volunteer management January 2022	90	9	28	100%	N/A
Heatwave / April 2022	78	22	31	96%	92%

For the heatwave event, 93% of event feedback respondents reported enhanced knowledge of the subject. For the volunteer management event, most feedback respondents identified new learning points that they intended to act on or share with others. Respondents for both events provided comments which suggested they felt enabled to make more effective interventions:

“Some things I hadn't thought of before, such as homeless as a vulnerable group in heat (not just cold weather events).” (Event feedback)

Several of the event feedback respondents for both events commented on the value of learning more about what other organisations might offer in a particular scenario and intended to do more to explore this further within their own operating environments, with an “…increased awareness of the need to build contacts in peacetime” (event feedback). Event feedback respondents also highlighted the value of sharing and learning from other organisations’ experience.

Making more of expertise and resources

Interview participants felt that the Partnership had made a significant difference during COVID-19 in enabling organisations to make use of the expertise and resources available, and that this had continued during the transition period. Interview participants reported that this was achieved primarily through sharing, information, good practice, tools and resources, and also commented that this aspect of the work overlaps significantly with building community resilience (see Section 2 above).

New learning and thinking differently

Interview participants welcomed the increased focus on running capability building and skill sharing events and suggested that these should continue to be a priority for the Partnership.

Those interview participants who had attended events described the ways in which it had stimulated their thinking and enabled them to think differently about risks and the future actions they might take that they had not considered previously. They also described taking away new learning which they anticipated putting into practice.

Participants highlighted the importance of the process of the events, the specificity of the scenario being used for the exercise and the opportunity to work together on that topic; working through the scenario together helped to bring people together to make connections in advance of an emergency.

“More of the community organisations are coming to things like the capability building events, and this is building the understanding of community assets and the knowledge and intelligence that different organisations bring to the table.” (National Specialist Organisation)

Need for better integration with LRF capability building

Interview participants pointed to the need for greater integration of the Partnership’s capability building events with those being delivered by LRFs and other bodies. LRFs are not yet inviting broader civil society representatives into their training and exercises, although this is a key aspect of moving towards a whole-of-society resilience approach, so there is an immediate opportunity for the Partnership here.

“We are now reaching out to people like the Emergency Planning Society to build links with them because they are running sessions for local authorities on a regular basis – we could be part of that and start to make the links.” (Central team member)

## 3.3 KLE 2.2: How far has capability and capacity changed so that more people know what to do in an emergency?

The survey found that 75% respondents expected that the activities and events offered by the Partnership would help people in their communities to know how to respond appropriately in an emergency, with 21% indicating a very positive impact and 54% indicating a slight positive impact.

Event questionnaire respondents indicated that they would be building wider links and connections with other organisations as a result of the event to help prepare better for a future heatwave scenario. Event questionnaire respondents also referred to feeding back to colleagues and reviewing practice and protocols as a result.

“[I] learnt to be more confident to let spontaneous volunteers 'step over the ribbon'. I will develop a toolkit to enable us to take advantage of spontaneous volunteers in future situations.” (Event feedback)

Slack channel
Interview participants cited the Partnership Slack channel as a key mechanism for sharing expertise and resources which had become increasingly valuable since its launch in early 2022. Analysis of usage data shows that by the end of the transition period, there were 319 individual Slack members, with an average of 60-90 active members per week reading and sending messages or posting resources across the different sub-channels, with the Ukraine channel most widely used during the period. By April, membership had increased by 10% to 351 members with activity levels remaining steady.

Good practice examples and experiences have been shared widely, both by the Partnership’s central team and by other partners (such as London Plus capability mapping at the beginning of the Ukraine war). This sharing of information, good practice and other tools and resources has enabled many partners to work differently and more effectively, for example, one survey respondent commented:

“During COVID-19, regular meetings and information sharing between sub-regional VCSE partners was particularly useful. During the Ukraine refugee crisis, the VCSEP structure has learnt from the experience during COVID-19 and information sharing from national to local partners is much improved. Through Slack, we have been able to identify and connect with local VCSEP partners from further afield who are working in similar ways, sharing ideas and information such as template data sharing agreements, volunteer role descriptions, and proposals for developing new local capacity-building projects.” (Survey respondent)

## 3.4 KLE 2.3: How far has capability changed so that those people most at risk during an emergency are reached and supported?

The survey found that 78% of respondents expected that the activities and events offered by the Partnership would help ensure that the most vulnerable will receive the support they require in an emergency, with 24% indicating a very positive perceived impact and 54% indicating a slight positive perceived impact.

From the event feedback, one respondent from a specialist organisation working nationally fed back that they were now thinking differently about how to better integrate and collaborate with grassroots responses such as mutual aid groups and spontaneous volunteers in an emergency to increase reach and support:

“I learnt that LRFs should have a strategy in place for dealing with spontaneous volunteers and local mutual aid groups and this has provided food for thought on how [my organisation] integrates/collaborates with such groups.” (Event feedback)

From the interviews, participants who had taken part in a capability event commented on the efforts of the Partnership central team to design the events so that reaching and supporting those most at risk during an emergency was central to the activities and scenario planning:

“In our session on heatwaves, it was really key that it was not what is the general impact of a heatwave, but who is particularly vulnerable: pregnant women, homeless people, people who don’t have English as a first language, older people with conditions. That was part of the analysis.” (Local Lead)

As noted at 2.3 above, interview participants commented that the Partnership had made a good start in ensuring that more inclusive response is now central to its agenda, but also suggested that this has not yet translated into practice which consistently makes a difference by reducing disproportionate impacts.

Collaborating with place-based Integrated Care Systems to reduce inequalities

During the interviews two of the Local Leads highlighted the work to address health inequalities being undertaken nationally within the health and social care sector through local place-based Integrated Care Systems (ICSs). All ICSs nationally are undertaking health inequalities impact assessments and developing strategies and as many community infrastructure organisations will be actively involved in this, they suggested that the Partnership could collaborate through Local Leads and other community infrastructure partners to help improve reach in an emergency to those groups likely to be most adversely impacted through health inequalities, which are often driven by wider social determinants.

“If you’ve got a really good local ICS impact assessment and that data is good that data can be used to identify our vulnerable groups, communities, communities of interest that we need to approach and communicate with and in a different way. There is a connection there because if that data is good enough you can use it in an emergency response.” (Local Lead)

## 3.5 Summary of key findings

The key lines of enquiry show good progress against this objective. The three capability building events delivered during the transition were well received, and there has been learning from each event which has helped to improve the next. Other activities which have contributed to the successful implementation of this objective have included the development of the Slack communication channel which has been an increasingly valuable mechanism for sharing information, expertise and practical resources. As with objective 1, an important strength has been enabling peer to peer support rather than depending only on outputs from the central team.

# 4 KLE3: Insight and information flow

Objective: Shared ongoing insight and understanding of changing threats, needs and activities.
KLE 3.1 - How far has the Partnership enabled the VCS to access more and/or better insight? / KLE 3.2 - How far has the Partnership enabled the VCS to use insight more effectively? / KLE 3.3 - How far has the Partnership enabled national and local government to access and use more effectively VCS insight that was previously unavailable to them?

Positive progress: / KLE 3.1 / 65% of survey respondents thought the Partnership had enabled the VCS in their community to access more and/or better emergency response information and insight. / Successful strategic shift away from “pure” data-driven and technology-led approach to “networked knowledge” based on sharing knowledge and improving information flow. / Afghanistan evacuation - Partnership provision of reliable information flow and exchange played a crucial role in supporting partners across all regions to mobilise rapidly and coordinate effectively. / Ukraine crisis – the Partnership learnt from the Afghanistan response and made rapid gains in in making better insight and information more accessible and timelier. / Early capability profiling has met identified need successfully, and further development and testing should be a priority. / KLE 3.2 / 73% of survey respondents thought the Partnership had enabled the VCS in their community to use emergency response information and insight more effectively. / Targeting vulnerability – those survey respondents using the Emergencies Toolkit had used it to identify vulnerable communities at risk and better target or redirect resources. / 88% of survey respondents thought the Partnership had enabled local government to access and/or use more effectively emergency response information and insight that was previously unavailable to them. / KLE 3.3 / Government departments have developed a better situational understanding of local issues and improved access to information from community level during the Afghanistan and Ukraine responses. / Partnership feedback during the transition period was directly incorporated by DLUHC in subsequent guidance on the Ukraine refugee response which is a significant improvement in the use of VCS insight by government during an emergency response.
Action needed: / KLE 3.1 / Prioritise further development and testing of capability profiling as part of improving preparedness as part of a whole-of-society approach, taking account of the different vulnerabilities and needs of different groups in each area.

## 4.1 Introduction

Background

During COVID-19 the Partnership developed an online insight platform hosting a series of insight tools (some COVID-19-specific and some potentially of longer-term value). This strategy sought to test and understand what features might be of most value in an emergency.

Activities for this KLE during the transition period

Simplifying data infrastructure

In summer 2021, the Partnership decommissioned COVID-19-specific tools and put the complex data infrastructure it had built into ‘hibernation’ until needed as the sector moves forward in data use in alignment with the Government’s national data strategy[13]. The Emergencies Toolkit, which can be found at https://insight.vcsep.org.uk/ was retained for further development.
[13] National Data Strategy Mission 1 Policy Framework: Unlocking the value of data across the economy, DCMS, 2021

Insight strategy review

The Partnership undertook user research, working with Microsoft, FutureGov and the National Preparedness Commission to review its understanding of the insights that partners need and want, identifying three challenges:

- The initial insight strategy was very broad, the approaches and pilots undertaken had been overly ambitious and the technology solutions had been overly complex and resource intensive.
- It had attempted to service a too-broad range of audiences resulting in fewer audiences getting precisely what they needed.
- The insight offer was insufficiently focused on the Partnership’s existing strengths of increasingly trusted networks and potential to build on this foundation.

Move towards “networked knowledge”

In many areas the user research demonstrated that the Partnership was on the right track. The user research also confirmed that the focus on network building and skills and best practice sharing is crucial for partners whose immediate need is for knowledge and information flow rather than pure data. There was a consistent demand for better understanding of capabilities and for learning from and implementing lessons from previous emergencies. Trust, networks and connections mattered most for the majority of partners, rather than using data or searching for new tools to drive action in an emergency. The Partnership now simplified its knowledge and insight strategy, moving away from its complex online platform and data infrastructure, instead developing ‘networked knowledge’ by building on its trusted networks.

Future strategy

The Partnership recognised that partners themselves are the priority audience, and that insight should be generated from the network as well as the central team, showcasing and connecting knowledge and insight created by partners or of value to partners, including knowledge from partner, government and open sources. It prioritised continued learning, iteration and revision to develop the ways in which knowledge and insight can improve emergency planning and response by supporting partners to use these with increasing skills and confidence. This was set out in a three-year plan for 2022 – 2225, with the current year (2022/23) consolidating and refining what is already in place. This approach was tested during the transition period during three primary emergencies - the winter storms, the Afghanistan refugee evacuation and the response to war in Ukraine.

The following sections evaluate the effectiveness of these activities and any lessons and action needed moving forward.

4.2	KLE 3.1: How far has the Partnership enabled the VCS to access more and/or better insight?
The survey[14] found that 65% of respondents thought that the Partnership had enabled the VCS in their community to access more and/or better emergency response information and insight, with 24% identifying a very positive impact and 41% identifying a slight positive impact. Where no impact was identified in the survey, this was typically because the information being disseminated was not relevant to organisational activity or because good connections to local LRF structures already enabled useful and detailed local information. One respondent commented:
[14] Survey findings here and throughout refer to a total number of 67 responses from a survey of 235 organisations (see section 1.6 for more detail).

“The main advantage has been sharing of resources, (such as a user-friendly vaccine leaflet from a CVS, and BRC translated materials), produced by another VCS organisation that has avoided the need to start from scratch. And similarly, the ability to rapidly track down someone useful to speak to (such as a VCS asylum worker based in an asylum hotel when we had a week or so’s notice of a hotel opening locally.” (Survey respondent)

During the interviews as noted in section 2.4 above participants fed back that the flow of both information and insight was impacting positively on community resilience, often linked to their experience of the Partnership as an increasingly trustworthy provider of accurate and up-to-date information. Participants also highlighted the value of the facilitating role the Partnership had played in enabling partner-to-partner communication, particularly through the Slack channel (see section 3.3).

Afghanistan evacuation

During the Afghanistan evacuation information was being shared at rapid pace and there was initially a great deal of uncertainty, followed by the need to mobilise very fast. Partnership information was highly valued by those involved in the response, and participants not involved also commented on the value they observed as a result of transparent and clear communication of information as it became available.

There were many situational challenges during the evacuation crisis including the lack of and inconsistency of needs assessments and significant data sharing constraints due to security and data protection concerns. The Partnership central team also faced internal challenges at this time as it was a period of limited staff capacity due to reorganisation and reduced funding, and it had not yet developed its new communications channel. Nevertheless, participants considered that the Partnership had played a crucial role in supporting partners across all regions to mobilise rapidly and coordinate effectively, and that the reliable information flow and information exchange that facilitated this was key.

Ukraine crisis
Interview participants were clear that the Partnership had learnt much from the Afghanistan evacuation and made rapid gains in making better insight and information more accessible and timelier during the Ukraine crisis. In the early weeks, the Slack channel was a core conduit for information which was welcomed and widely taken up by the Partnership at regional and national levels.

Participants also highlighted the importance of the well-established structure of monthly network calls and regional meetings which were activated to meet more frequently with weekly network calls and weekly regional calls focused specifically on the Ukraine situation.

These calls provided key functions which included providing early access to information directly from central government which was not being shared as rapidly with local government in their operational areas, and where there was little or no information yet available, getting reassurance that government activity was underway and some indication of timelines, even if these had to be frequently updated. This was very effective in building confidence amongst partners on what they should or should not be doing.

“People were saying, ‘we’re standing up to respond’ and then changing that to ‘okay, now what we’re thinking about is how to prepare, and these are the connections we’ll try and make so that if and when refugees arrive, we’re joined-up in our response’.” (Central team member)

Capability profiling
Participants highlighted the value of the granular capability profiling matrix London Plus had created. This was developed at a regional rather than national level and was ground-breaking, bringing together knowledge and information from a wide range of networks including the Partnership about grassroots community organisations, including very small specialist groups, for example offering local translations.

Coordinating support in London during the Ukraine crisis: / Creating a live online tool to signpost support across the city
London Plus created a live online tool with a list of organisations to signpost support for those affected by the crisis in Ukraine. This included charities and community groups, with a particular focus on London-based organisations, and was regularly updated by the London Plus team as new information came in. It also included ways to support those in Ukraine via emergency appeals for donations and funding. / The Ukrainian support document[15] helped to support the coordination of London's voluntary and community organisations during the early weeks of the crisis. By late March this page had 10,856 unique views and 23,157 impressions on Twitter. The document drew on knowledge and information from organisations in London Plus’s networks, social media, and new connections being made through London Plus’s role as a VCSEP Local Lead for London.
[15] https://londonplus.org/news/support-for-ukraine-crisis-london

Interview participants also found very useful the Ukraine-specific capability mapping matrix that the Partnership put together rapidly by using the London Plus matrix as a model and extrapolating it nationally, although not at such granular level (see: VCS EP Potential Offers of Support for the UK Response to the Ukraine Crisis) .

The insight user research conducted by the Partnership during the insight strategy review identified capability profiling as a key need from partners. The positive engagement with these Ukraine-specific tools has demonstrated the value of situational capability profiling as a rapid response to an individual emergency. This approach allowed for each organisation’s offer and connection mechanism to vary depending on the nature of the emergency and the role it might play. This was very different to developing and maintaining a national directory of organisational capabilities which was challenging to keep up to date, less able to achieve the reach and inclusion to grassroots level of a more local or regional model, and less able to flex for different emergencies.

The Partnership had begun developmental work on a national capability matrix before the Ukraine crisis, so now has early experience of capability profiling in both preparedness and response mode and given the thirst for this type of resource, this should now be taken forward as a priority area of work. There may also be scope for working with the National Preparedness Commission on this as a future preparedness resource as it aligns closely with its requirement for “…clarity about which VCS organisations will provide which skills and capabilities in what circumstances, and confidence that those skills and capabilities can be mobilised quickly and effectively.”[16]
[16] Independent Review of the Civil Contingencies Act 2004 and its Supporting Arrangements, (2022) Bruce Mann, Kathy Settle, Andy Towler, National Preparedness Commission
## 4.3 KLE 3.2: How far has the Partnership enabled the VCS to use insight more effectively?

The survey found that 73% of respondents thought that the Partnership had enabled the VCS in their community to use emergency response information and insight more effectively, with 31% perceiving a very positive impact and 42% perceiving a slight positive impact.

Using information to convene rapidly and effectively
Interview participants commented that identifying and bringing in new partners, particularly those supporting groups most impacted by the crisis, demonstrated ways in which the Partnership was now using information and insight more effectively to bring the right people together in an emergency. Participants also reflected that there was notably improved collaboration across the VCS and that the Partnership had made a significant contribution to this through better information-sharing to support rapid convening and response.

“Those early conversations were so reassuring, particularly with the central team, there was a real confidence – that was incredibly valuable that there was someone offering a helping hand to these evacuees straight out of Afghanistan into a hotel.” (National government representative)

Targeting vulnerability
Although the survey found that only 10% of respondents had used the online Emergencies Toolkit, two respondents reported that they had used the risk indicator tool (which maps vulnerabilities by post code) to identify vulnerable communities at risk and to help target or redirect resources. Similarly, interview participants who had used the toolkit commented that the risk indicator mapping had provided new insight which had helped them focus their work more effectively.

“Their insight, resources and toolkits, overlaying datasets, that’s another thing that needs commendation because that’s really good. I have shared that locally and people love it, incredibly useful.” (Local Lead)

One interview participant suggested that there is scope to enrich and develop the toolkit by feeding in regional open-source data sets, with input from local public health intelligence colleagues.

Using insight and information to develop a more effective response
Interview participants working at local level had found the information shared by the Partnership was enabling them to develop more effective local responses.

“Those meetings we had specifically around support networks for Afghan refugees, support services, issues around post-arrival support, that was very helpful – when we’re looking at something we’re practically facing in real time, that’s where the value is at its most positive. Those focused, live meetings have been most productive and most helpful – seeing ‘they’re doing that – maybe we can do something like that too.’” (Local Lead)
## 4.4 KLE 3.3: How far has the Partnership enabled national and local government to access and use more effectively VCS insight that was previously unavailable to them?

Local government

There was limited data available from local government representatives as none responded to the survey and only three interview participants were local government or local statutory LRF representatives. However, many of the VCS survey respondents were working closely with their local authority, and in several cases had formally contracted responsibilities for coordinating and/or delivering local emergency response activities on behalf of their authority. The survey found that 88% of respondents thought that the Partnership had enabled local government to access and/or use more effectively emergency response information and insight that was previously unavailable to them, with 39% perceiving a very positive impact and 49% perceiving a slight positive impact. Interview participants expressed similar views.

During the winter storms and Omicron variant wave of COVID-19 infections which had more localised than national impacts, communities typically mobilised and acted via their LRF at a local or regional level based on the relationships already established either through previous experience in areas regularly affected badly by storms and flooding, or relationships more recently built during the COVID-19 response, so there was no need for the Partnership to undertake any convening activities. Nevertheless, a number of VCS participants actively involved in the LRF-led responses commented that the information shared on the Partnership website and through bulletins, including winter preparedness; Omicron and COVID-19 insights; flooding plan/respond/recover insights; information on storms Dudley and Eunice; partner updates, and British Red Cross insights documents had helped to support these local responses.

As noted in section 2.4, some LRFs had appreciated the direct flow of information from central government channelled rapidly by the Partnership, evidenced by the increase in LRF direct engagement in Partnership activities such as network calls, capability building events and regional calls.

“I do think they have really added something to the conversations which have been going on between local government, migration boards, central government, that none of us could have contributed to…they have a type of authority which VCS organisations by themselves don’t have. It’s that convening power, which is really, really helpful, and the Partnership is the sensible route to do that.” (Local government representative)

National government

During both the Afghanistan evacuation and the Ukraine crisis interview participants considered that the Partnership had significantly improved government’s understanding of the situation at local and grassroots levels, and that government officers were developing a more rounded understanding. Departments such as the Home Office and the Department for Levelling Up, Housing and Communities have had access to a more collective view of what is happening in the wider voluntary sector and within the communities the sector supports.

“It's made a massive difference to us, 100%. So, when any big question that the government is asking whether that’s ‘have we got enough vaccine volunteers?’ or ‘how are we going to engage the voluntary sector on any particular emergency response?’, it’s immensely valuable to have somebody we can go to and talk to and who can convene others who are keen to be involved. Especially, whenever there’s a crisis you get outpourings of support – having a place as government (which is a very blunt instrument) which can do that join up between the very national level priorities and the local is hugely helpful.” (National government representative)

Participants from the VCS commented that they now have a direct route into government, that their voice and feedback was being escalated to government and that their concerns are beginning to be heard. Nevertheless, there remained a strong sense that this is not yet effecting significant change or impacting on policy.

However, an early example of the Partnership beginning to gain traction on more effective government use of VCS insight was during the Ukraine crisis towards the end of the transition period, where the Partnership collated partner feedback on specialist areas and shared this with central government departments. The Department for Levelling Up, Housing and Communities subsequently launched guidance on the Ukraine refugee response incorporating a great deal of this Partnership feedback. Although the guidance was published shortly after the end of the transition period, it drew on the information and insight shared during that time, and so demonstrates important progress during the transition. This is a significant improvement in the use of VCS insight by the government during an emergency response.

## 4.5 Summary of key findings

Although the formal insight strategy developed over the transition period is yet to be rolled out, the unexpected volume of emergencies which have presented over the transition period (the Omicron wave, the winter storms, the Afghanistan evacuation and the war in Ukraine) meant that the Partnership had to step up in real time to each of these and was successful in delivering reliable and timely information and insight, as well as facilitating peer to peer information sharing which largely met partners’ needs.

# 5 Value for Money

## 5.1 Introduction

In summer 2021 DCMS identified a clear rationale for continuing to fund the Partnership. This acknowledged that VCS organisations were still facing significant demands on their services both for continued COVID-19 support and more generally, as the communities they served continued to face significant social and financial pressures, particularly the disproportionately impacted groups who were hardest hit by the pandemic. Recognising the changing nature and frequency of major emergencies and consequently the importance of whole-of-society resilience, DCMS also envisaged growing value from the Partnership’s role in enabling VCS participation in whole-of-society response.

DCMS recognised that in many cases VCS income and fundraising were still below the pre-COVID-19 levels. However, in line with the reduced demand for COVID-19 specific volunteering and the approach then being taken across national government, such as ending the shielding arrangements for the clinically extremely vulnerable, the funding for the work of the Partnership was reduced to recognise the shift from COVID-19 emergency response and recovery mode to preparedness for other future emergencies.

DCMS funding phase	Grant received
April 2020 – March 2021: COVID-19 response	£4,654,112
April 2021 – June 2021: COVID-19 extension	£1,153,123
July 2021 – March 2022: Transition	£696,058
July 2021 – March 2022 (Home Office transferred funds - Afghan response)	£23,000

The funding was therefore decreased to less than a fifth of the initial annual COVID-19 response grant, as a jointly planned downshift by DCMS and the Partnership, recognising in their grant agreement for the transition period that, “this grant variation would reduce the VCSEP to a skeleton, contingency model rather than a full activation status”[17].
[17] Grant variation agreement DCMS/VCSEP: Voluntary and Community Sector Emergencies Partnership (VCSEP) coordination of the voluntary sector’s COVID-19 response and preparedness for other emergencies, 3 August 2021

It is therefore important to consider the indicators of value within this context of the reduced Partnership resources during the transition period of July 2021 – March 2022.

Value for Money rationale for DCMS continued investment

In the grant agreement[18] DCMS set out its Value for Money rationale for continued investment in the Partnership:
[18] Grant variation agreement DCMS/VCSEP – as above.

“By supporting the sector to continue to respond to COVID-19 through the recovery stage, and
enabling coordination, insights and continuous learning (through shared experience and
development of data intelligence) the VCSEP will help ensure we are able to continue to respond to the current issues and respond quickly and efficiently to any future wave of COVID-19. Concurrently, there will be strengthening of the evidence-based systems leadership behind responding to an emergency which can be re-used for a wider emergency preparedness model. All of this optimises value for money regarding this work.” (DCMS, grant agreement)

This evaluation does not include a formal evaluation of the value for money from DCMS public funding investment during this period for two main reasons:

- Although the Partnership has collected expenditure data by activity, the changing and cross-cutting nature of emergency response and the relationships involved makes it difficult to relate activities to outcomes discretely, to identify genuinely meaningful unit costs or to monetise the benefits which could be attributed, and so derive a cost-benefit analysis.
- There is no proxy counterfactual[19] available against which to compare any attempted cost-benefit analysis and designing an experimental counterfactual able to take account of the national scale and complexity of the Partnership’s programme of work would be costly, impractical and potentially unreliable given the many variables involved.
  [19] A ‘counterfactual’ enables comparison between what actually happened and what would have happened in the absence of the intervention, for example by creating a control group with the same key features but no intervention or by using an existing group with comparable key features but no intervention.

Instead, the evaluation applied a lighter touch approach and considered value for money in general terms only without undertaking a formal economic analysis, through two lenses - first, the National Audit Office’s (NAO) key criteria for assessing value for money of economy, efficiency, effectiveness and equity, and second, considering how far the Partnership has met DCMS expectations of value for money outlined in the grant agreement.

The assessment data was drawn from the survey and interviews which included specific questions to stakeholders on early impact and value. It does not draw on any numeric analysis of costs or activity data.

## 5.2 Making a difference to the national emergency response eco-system

Within its Theory of Change the Partnership mission is as “a mobilising force bringing organisations across the VCS together, with its partners in local and national government, to deliver a more coordinated and person-centred response to emergencies” (see Theory of Change, Appendix 2).

The ambition is to achieve systemic improvement to the national emergency response eco-system. The three transition programme objectives drawn from the Theory of Change are indicators of the Partnership’s impact in achieving sustained change. Achieving this systemic and long-term difference relies on ensuring the continued relevance of the Partnership’s work for all partners.

Relevance and effectiveness

The survey therefore sought to test via a ranking approach how well the Partnership’s objectives continue to be aligned with the relative priorities of partners responding to the survey. It also used the ranking exercise to examine how effective its work has been in the areas which matter most to partners. Figure 1 overleaf demonstrates that overall, the Partnership has generally been most effective in the areas which are of higher relative priority for partners with one significant exception – more inclusive response in an emergency ranked highest in importance for partners but was viewed as the second least effective area of work.

This key finding underscores the learning and action point in section 2.3 which suggests that the Partnership should develop, set and review clear targets with tangible outcomes on achieving more inclusive response in an emergency, for the shorter and longer term so that it can both better understand and demonstrate progress in this area moving forward.

### Figure 1: Relevance and effectiveness

## 5.3 Economy, efficiency, effectiveness and equity

The KLEs discussed in previous sections have demonstrated how the Partnership has met each of the transition objectives which underpin the value for money rationale for investment in the grant agreement.

The table below provides a summary of the key evidence from the transition data against each of the National Audit Office’s criteria for assessing value for money. The third column within the table then applies the evidence to consider how far DCMS’s Value for Money (VfM) rationale in the grant agreement for the period has been met.

### Value for Money evidence table

VfM criteria	Evidence from transition data	DCMS VfM rationale
Economy / Minimising the cost of resources used while having regard to quality (inputs) – spending less.	Overall reduction of resources (central team, Local Lead convenors with local infrastructure organisations) costing less than one fifth of previous annual funding but continuing to deliver, successfully drawing on learning from the original bigger team. / Despite running as a “contingency model rather than a full activation status” the Partnership was able to stand up and respond effectively across several emergencies during the period. / Review of investment in insight and shift away from tech and “pure” data has reduced costs significantly whilst better meeting partner needs. / Operating structure – move to a more streamlined operating model including standing down regional hubs and network meetings during steady state non-emergency time.	Fully met
Efficiency / Relationship between the output from goods or services and the resources to produce them – spending well.	More coordinated sector with single point of access for varying government departments depending on emergency. / Improved VCS collaboration and support including new cross-regional collaboration. / Insight - move to focus on content delivered at much more rapid pace is a better use of reduced resource and more responsive to partners’ “live” information needs. / Slack channel – introduction of new and cost-efficient communication App has enabled efficient knowledge share between partners and optimised the information outputs from the central team. / For government – investment has enabled clear and direct communication channel and better connectedness to sector. / Diverting insight spend away from pure data and into human knowledge exchange to meet user priority needs. / Capability events well attended and highly rated as effective.	Fully met
Effectiveness / Relationship between the intended and actual results (impact) of public spending (outcomes) – spending wisely.	Contribution of the volunteering sector over last two years has been sustained during the transition period at local levels responding to Omicron wave and winter storms. / Increasing effectiveness of the VCS response, evidenced by Afghanistan evacuation, and contribution to development of DLUHC Ukraine response guidance. / Sustained progress in embedding VCS partners within LRF structures. / Increasing practical, operational conversations with different parts of government. / Early impact of increasing community capability and sharing of expertise/resources as evidenced by event feedback.	Fully met
Equity / Extent to which services are available to and reach all people that they are intended to – spending fairly.	Afghanistan response – VCS made a major contribution at pace in supporting a group in extreme and urgent need, comprehensively addressing their welfare and safeguarding needs. / Increased participation in the Partnership by faith groups and others representing less-heard communities. / Continued rollout of messaging and support to promote vaccination take-up in at-risk communities. / Capability events placed promoting inclusivity as a central element. / Emergency toolkit – early indications that this may help target resources to the most vulnerable and at-risk. / Progress is viewed as less well developed and less effective than other Partnership work by partners.	Partially met

## 5.4 Sustainability

The evidence table above demonstrates that DCMS’ value for money rationale for continued public investment in the Partnership’s transition has largely been met. The Partnership has built on its legacy from earlier funding to continue to achieve strong results despite sharply tapering resources. Nevertheless, if the Partnership is to achieve the impact and sustained change outlined in section 5.2 it will need to achieve a greater diversification and amount of funding.

DCMS has committed a sustained level of funding (up to £750k) for the current year 2022/23, then tapering off in 2023/24 (up to £500k) and further in 2024/25 (up to £250K) which will provide crucial core funding. A three-year funding commitment, even with a steep taper will also facilitate greater efficiency by avoiding the “drag” factor of higher staff turnover that is inevitable with short term grants. In 2021/22 partners also contributed £75k in cash, with British Red Cross also contributing resources to the value of £20k in addition to its cash donation. Partners may continue to contribute but the amount is unlikely to increase while VCS income and fundraising remains below pre-COVID-19 levels. The Partnership is also preparing funding applications to charitable and private donors, but these are likely to be project-specific and therefore fixed-term restricted funds.

The success noted in peer-to-peer facilitation is an important green shoot for the longer term. One of the challenges moving forward will be how to continue to grow and expand the work of the Partnership with a very limited central resource, relying less on fielding the Director or other central team members during crises. As trust increases and the partner representative role matures it should be possible for staff to take more of a background role, as different partners can deploy on behalf of the Partnership playing to their organisation’s expertise and strengths.

To achieve sustainability, and to scale up and grow, the Partnership now needs to work with DCMS as its main funding department to better demonstrate to other government departments such as the Cabinet Office and the Department for Levelling Up, Housing and Communities not just how the Partnership’s activities and mission align with their own work to support national resilience but why these activities also merit broader government investment.

# Appendix 1 – Partnership organisation

# Appendix 2 – Theory of Change

# Appendix 3 – Value Proposition

# Appendix 4 – Glossary of terms and acronyms

Term	Definition
DCMS	Department for Digital, Culture, Media and Sport
DLUHC	Department for Levelling Up, Housing and Communities
Equalities Steering Group	A Partnership committee within its governance structure which works on ensuring equality, inclusion and diversity across the Partnership’s activities. The Chair of the Equalities Steering Group also sits on the Partnership Board.
ICS	Integrated Care Systems - partnerships of organisations that come together to plan and deliver joined up health and care services, and to improve the lives of people who live and work in their area. Following several years of locally led development, the Health and Care Act 2022 is establishing 42 ICSs across England on a statutory basis from 1 July 2022.
KLE	Key line of enquiry for the evaluation.
Local Lead	The Partnership has 11 Local Leads from local infrastructure organisations who liaise with and represent other infrastructure and community organisations within their respective regions. Local Leads cover five broad regions (North; Midlands & East; London; South East, and South West) with two Leads in each region except Midlands & East which has three.
LRFs	Local Resilience Forums - multi-agency partnerships made up of representatives from local public services, including the emergency services, local authorities, the NHS, the Environment Agency and others. LRFs plan and prepare for localised incidents and catastrophic emergencies to prevent or mitigate the impact of any incident on their local communities.
LIO	Local infrastructure organisation
Network	A network of sector leaders and statutory partners with a shared understanding of the challenges faced and action needed in a crisis.
Slack channel	An online communications and collaboration app introduced by the Partnership during the transition period.
Partnership or VCSEP	The Voluntary and Community Sector Emergencies Partnership.
VCS	The Voluntary and community sector
VfM	Value for money
Working Together Agreement	The signed agreement in place between 187 of the partners – other partners collaborate and are engaged with the Partnership but have not formally signed the agreement – a total of approximately 240 partners.