## Annual Review

ASEAN Economic Reform Programme (AERP)
Programme Value £ (full life): £19.7million / (with the addition of Indonesia Regulatory Reform Programme in January 2021)		Review date: / December 2021
Programme Code: / GB-GOV-50-PF-18-ASEANER	Start date: / April 2018	End date: / March 2022

Summary of Programme Performance
Year	04/2018-08/2019	08/2019-10/2020	09/2020-09/2021
Overall Output Score	B	A	A
Risk Rating	Moderate/Major	Moderate	Moderate

Link to Business Case:
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/810873/Business_case_for_ASEAN_Economic_Reform_PF_Programme.odt
Link to results framework:	N/A

A. SUMMARY AND OVERVIEW

This is the third annual review of the ASEAN Economic Reform Programme (AERP), covering the period September 2020 to September 2021.
AERP aims to achieve inclusive economic growth and poverty reduction in ASEAN, particularly focused on Indonesia, Malaysia, Myanmar, the Philippines, Thailand and Vietnam, by enabling a fairer business environment and deepening financial markets. The programme includes project level components on financial services, financial technology (fintech), intellectual property (IP), competition and business regulation, business integrity and anti-corruption. With the on-going pandemic, consideration was given as to whether the programme should pivot towards activities targeted at alleviating the effects of COVID-19. However, it was concluded that the programme was already meeting this challenge in pursuing the existing objectives and contributing towards economic recovery in the region.
The military coup in Myanmar resulted in the suspension of all programme activity there. This was, and continues to be, a hugely challenging time, particularly for programme staff in country. Significant progress, particularly regarding the Anti-Money Laundering (AML) work, has been lost. Changes to the Official Development Assistance (ODA) budget of the Foreign, Commonwealth and Development Office (FCDO) for 2021/22 also led to changes to the AERP allocation. This required scenario planning for each aspect of the programme and ultimately a reduction to the Financial Services Intellectual Property (FSIP) pillar. Despite this, this review period was the most significant year to date for delivery. UK expertise is highly regarded in this region and has been well-received by country partners.
Summary supporting narrative for the overall score in this review
The overall score awarded (A) reflects the positive contribution of this programme to changing the mind-sets, policies and practices of entities and organisations that can collectively progress inclusive economic reform in the ASEAN region. Despite large-scale disruption caused by the COVID-19 pandemic, travel restrictions, and significant changes in political contexts, the programme partners were able to adapt and continue delivering activities. A score was not given for the secondary benefits despite its inclusion in the log frame. Future programme log frames should only include what will be measured and what the programmes will be directly accountable for, and secondary benefits can be captured in a regional secondary-benefit tracker.
Major lessons and recommendations for the year ahead
AERP is entering its final year of delivery. Therefore, these lessons and recommendations place particular emphasis on actions that could help to inform the design of any future economic reform programming in the ASEAN region.

Stakeholder engagement and coordination:
- Under AERP, there was some interaction between implementers before COVID-19, which they found to be useful for understanding the wider work of AERP. However, facilitation of this engagement was not sustained, mainly due to the pandemic. There could have been benefits in continuing this to help implementers navigate shared challenges, share lessons learned and report successes, as well as providing an opportunity for the programme team to keep implementers informed of the latest FCDO thinking and hold them accountable for delivery.
- There are a number of departments supporting delivery of AERP, including the Department for Business, Energy, and Industrial Strategy (BEIS), Department for International Trade (DIT), Cabinet Office. This is a positive indicator of the programme working to deliver shared UK policy priorities with departmental leads at Posts coordinating activity where relevant. Any future programme should continue to draw on a wide range of expertise from across Government and make links to any relevant cross-cutting initiatives, like Build Back Better World (B3W).
Recommendation: that the programme team involves multiple government departments with a potential interest in the economic reform in the design of any future economic programme to solicit views, ideas and support on priorities. During mobilisation and implementation phases in particular, there could be regular meetings bringing all implementing partners together to support delivery and ensure the portfolio or programme is greater than the sum of its parts.
Monitoring, Evaluation and Learning (MEL):
The output indicators in the programme logframe could have been more rigorous and specific in some cases to help fully quantify progress. In addition, the outputs recorded in the logframe were not always consistent with those recorded in the original Theory of Change (TOC). It will be important for the final year and in any new programme that the TOC and logframe are both reviewed and kept up to date to reflect changing circumstances, track progress and provide better data for decision making.
Recommendation: that a MEL adviser is recruited for any successor programme to help design, implement and improve methods of data capture and reporting. Throughout the programme an adviser can ensure consistency between project and programme level results, and relay monitoring of programme data in a targeted way to the Senior Responsible Owner (SRO) to inform decision making. A MEL adviser could also help the programme team to better quantify secondary benefits.
Adaptive Programming:
Adaptive delivery enables programmes to be flexible and build in testing, learning and iteration to respond to changing circumstances, whilst staying aligned to their overall outcomes.​ AERP has multiple work streams, often operating in complex environments. For any future programme, an adaptive approach could be used to test and scale innovative interventions more systematically. There was some evidence of AERP testing and piloting new interventions. This work could be expanded under a new programme.
Recommendation: for any new programme, evaluate with a MEL adviser whether an adaptive programming approach would be a more suitable approach for delivery. This would require the onus to be placed on learning and adjusting during implementation rather than determining all courses of action in the programme design phase. Testing and scaling new interventions could be delivered alongside work to continue existing AERP projects.
Gender Equality and Social Inclusion (GESI):
Efforts to address accessibility of programme activities for women gained traction over time, including through partnerships with specialist organisations and creation of dedicated platforms. However, it has been broadly acknowledged that the programme would have benefited from clearer strategic intent with regard to GESI from the outset. AERP could have articulated more clearly how gender inequality is a cause and consequence of uneven economic policy and development, and what this means for poverty in the region.
Recommendation: ensure that any future business case is gendered and includes a broader focus on social exclusion. Conduct research to identify specific barriers to gender equality and inclusion in the thematic areas of the programme. In the design phase, prioritise and set GESI objectives and outcomes to clearly define the change sought. Engage technical expertise and specialist delivery partners where possible, and set clear expectations with all delivery partners on GESI policies and objectives.
Sustainability:
The programme should focus on sustainability in the final year and how progress could be preserved once AERP funding ends. For any work that may be carried over into future programming, it will be important for FCDO to maintain relationships with key stakeholders. For example, the recently launched Vietnam Business Integrity Network is a promising initiative to improve corporate governance. However, a funding model needs to be developed to maintain it in the medium-to-long term.
Recommendation: Implementing partners and programme managers should focus on building sustainability considerations into all workstreams in the final year of delivery. If a successor programme is confirmed, FCDO should conduct research, analysis and wide consultation as early as possible to determine which, if any, of the AERP workstreams may be continued, and which will need to find other means of delivering a sustainable impact after AERP closes.
Programme Structure:
Conditions for AERP delivery have been challenging this year but progress has been made with intermediate outcomes reached across the programme work streams that show potential for further, targeted investment. One of the issues that the programme seems to have grappled with is the programme delivery structure with many layers of delivery at country and regional levels. A regional approach was seen as important by stakeholders and complementary to bilateral support, but both types of intervention have different advantages and it will be important to be clear about these when considering the aims of any successor programme.
Recommendation: In the short term, the AERP programme team should review its staffing requirements to ensure it is able to manage the completion of AERP, given the complexity of the current delivery model and the number of different implementing partners. In the longer term, the team should ensure that any future programme seeks to streamline and simplify the delivery model where possible, learning from the AERP experience, and finding the right balance between regional and bilateral activities.

B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
Theory of Change (TOC)
The intended impact of this programme is to generate more ‘inclusive economic growth and poverty reduction by enabling a fairer business environment and broadening and deepening financial markets’. The programme seeks to do that by delivering three outcomes. These outcomes are then subdivided into a series of more specific ‘intermediary outcomes’ (IO), as summarised below:
Outcome 1: Strengthened and harmonised business environment frameworks.
- Regulators implement Intellectual Property legal, regulatory or policy changes.
- Improved policy and regulatory frameworks to streamline business processes.
- Actions identified to make logistics sector regulations more pro-competitive.
Outcome 2: Improved business practices adopted and corruption risks minimised.
- Improved transparency and integrity policies and practices by government and businesses.
- Strengthened legislation and application of judicial mechanisms to decrease corruption.
Outcome 3: More inclusive, efficient and diversified financial markets.
- Regulators implement improved capital market policies, regulations and development plans.
- Improved regulatory environment to expand the fintech sector and access to financial services.
- Enhanced ability of Myanmar government to tackle financial crime.[1]
  [1] Written before the military coup. All programme activity was suspended in Myanmar after the coup.
The AERP impact statement is broad, and may have benefited from being separated into multiple impact statements (possibly multiple TOCs). For instance, ‘inclusive economic growth’ could be a standalone impact given the complex nature of the initial problem of uneven/unequal economic growth. A more specific definition of inclusive economic growth could also have created a stronger shared understanding of the end goal throughout the span of the programme.
Likewise, ‘fairer business environment’ and ‘broadened, deepened financial markets’ may have fared better either as standalone impacts or as long-term outcomes. At present they are framed as means of achieving the impact, but are also contained within the impact statement itself. Some outputs, such as ‘improved transparency in government contracts’, could also have been listed as outcomes, because they are not direct outputs of the programme.
In any future programme, the conceptual links, such as between economic reform and poverty reduction, could be strengthened with reference to a broader evidence base. Future programmes could also conduct more political economy analysis to understand how and why decisions on economic policy are made.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Most stakeholders reflected that good progress against outputs has been achieved, though the time taken to set up the programme and changes in context, not least the pandemic, has slowed some progress at intermediate outcome level. Even within a three to four year programme, it is not typical to see impacts being fully delivered and completed, but rather indications that programme activity is contributing to the desired impact. Remaining activities are primarily final workshops and capacity building sessions and consolidating gains, such as supporting new legislation or regulations.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The AERP Board have approved in principle an extension to the programme, from April to December 2022. This involved a review of all programme streams and assessment against agreed criteria, noting that extensions could only be granted where the work was demonstrating impact, deliverables could be achieved within a nine-month period and would continue to meet UK priorities. The findings of this review indicate that prioritising the most effective activities with a view to creating the foundations for a successor programme is the right course of action. There are aspects of AERP which demonstrate real potential and fit well with UK priorities for the region, as covered in other sections of this review.
Gender Equality and Social Inclusion (GESI)
The approach to GESI within this programme has shown improvement but has had to compensate for a lack of strategic direction set at the design stage. There are pockets of good practice and achievements. For instance, United Nations Development Programme (UNDP) integrated a work strand focused on diversity and inclusion, exploring the connection between business integrity, corruption and gender in order to make more meaningful their efforts on women’s participation in programme activities. They published a report on this topic in March 2021 having conducted research into businesses in the region on their approach to diversity and inclusion under the banner of business integrity.
However, implementing partners and programme staff have broadly agreed that the programme’s contribution to gender equality and social inclusion was hindered by a lack of strategic objective setting that better defines the problem and the change needed, and how this contributes to achieving the overall programme impact. The AERP was one of the first Prosperity Fund Programmes to go into implementation and as such, it did not benefit from the guidance and tools on GESI that were developed at a later stage. This has led to some difficulties, with the team trying to use the new tools to measure GESI progress in a programme which was designed before those frameworks existed.
This could be addressed in a future programme by ensuring that research and analysis on GESI is conducted at the business case stage, guided by a social development adviser or gender adviser, to ensure that the business case clearly articulates how and why gender inequality and other forms of exclusion may be both drivers and consequences of the problem being addressed. Any future business case should also set more specific objectives on gender and inclusion that better define the change needed. These objectives can then be translated to each country context/thematic area of programming and factored into the theory of change (TOC) and results frameworks.
During the review period, programme staff participated in workshops in March 2021 focusing on disability inclusion and broader GESI objectives facilitated by social development advisers. This provided an opportunity to consider the AERP’s contribution to GESI through its delivery partners, results and accountability mechanisms. Furthermore the Work and Opportunities for Women (WoW) Helpdesk undertook a review of AERP in September-October 2021. The review found:
- The AERP lacked a strategic approach linking GESI and Women Economic Empowerment (WEE) interventions to the programme’s overall TOC. The delivery partners responded to FCDO ambition by meeting minimum standards in their designs, identifying entry points in their on-going programmes, and including more gender skills in their teams.
- All delivery partners had created opportunities for women to participate in project activities, however the focus had been on numbers of women in capacity building in order to comply with minimum standards. Only UNDP had carried out post-training follow up to assess the impact on participants. Delivery partners had also integrated GESI into training materials and seminars, but there was no evidence as to how this had influenced the participants.
- Delivery partners are still raising awareness of GESI within their own organisations. This affected their ability to advocate for a greater integration of GESI among ASEAN Member State (AMS) economic reform processes. All partners consulted with women’s organisations in each country they were operating in, but the quality of engagement varied considerably.
- Scoping analysis carried out by delivery partners at the country level on GESI/WEE issues and situation tended to be broad and general but influenced design in some cases. A lack of specific and technical information on GESI barriers and issues in the thematic areas of the programme, and how these could be addressed, was a key gap across the strands.
Secondary Benefits
The approach to Secondary Benefits has been developing and improving this year. There is now a Secondary Benefit Adviser Network with a Secondary Benefit Lead in all target countries, an FCDO Secondary Benefits Tracker has been launched and workshops have been held. PwC have also developed a separate secondary benefits tracker for their work, which became fully operational in 2021-2022 and is shared with FCDO as part of the quarterly and annual reporting process. There were also early signs of progress on exports, with £10m generated from non-ODA activity.
However, despite this progress, challenges were highlighted in a number of areas:
- More technical support and resources could have been dedicated to tracking secondary benefits at an earlier stage. Secondary benefits advisers were appointed at a late stage, which also affected the suitability of some secondary benefits indicators.
- Delivery partners could have done more to highlight secondary benefit opportunities and capture and share evidence with the secondary benefits advisers. There is also the question, as illustrated in the business case, that the benefits would continue to accrue after the programme has completed and how that evidence would be captured.
- The new secondary benefits tracker has the potential to streamline the flow of information, but the process of collecting and analysing the data could still be improved, including to avoid duplication with existing quarterly reporting. In addition, the recording of secondary benefits appears uneven with only information for the Philippines currently recorded.
Going forward, the team should review the system for recording data in the tracker, so that everyone is clear on the type of information that needs to be provided and to whom. This should include looking at ways to improve the template and how data can most usefully be analysed and extracted to inform decision making. For any future programme, the team should consider how best to assess secondary benefits and ensure they are fully reflected in the logframe with outcome and impact indicators.
C. DETAILED OUTPUT SCORING

Output Title	FSIP: Inclusive Intellectual Property (IP) capacity building through knowledge sharing and technical assistance to improve IP and related legal/policy frameworks, regulation and practices
Output number:		1A	Output Score:	A
Impact weighting (%):		5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
No. of new or improved IP policies, standards and regulations including targets, mandates, incentives and roadmaps that have benefitted from FSIP’s support	2020 – 7 achieved (planned 0) / 2021 – 0 achieved (planned 0) / 2022 – (15 planned)	Progress is ahead of schedule against log frame targets.

At the regional level, the programme launched the Digital IP tool to help small and medium-sized enterprises (SMEs) identify their IP and held an Enforcement Coordination Webinar for IP promotion in creative industries with numerous business associations. In Vietnam, the IP Law was reviewed, and a report was delivered on draft provisions; work was completed on IP enforcement coordination with other countries, including a workshop and a research report; and a focus group discussion was held on the IP of the financial ecosystem and how this might be developed. In the Philippines, the programme secured a MoU on IP and delivered a report on financial system IP and how to develop the ecosystem locally, as well guidance on IP promotion in the creative industries. In Indonesia, reports were submitted on the e-commerce regulatory regime and the finance ecosystem IP.
The relevance of IP work on e-commerce and the creative industries has grown in the advent of the pandemic, and there is strong demand for support on financial system IP. In response, the Programme has set the aim of steering ASEAN towards the adoption of a regional MoU on e-commerce. The programme extension period will be used to pave the way by building consensus across the region for this initiative. As a secondary benefit much of this work also generated positive exposure for the UK, most notably the launch of the MoU in the Philippines and public acknowledgement of support from the Copyright Office Vietnam. It is worth noting that separate work is being done by the ASEAN Secretariat Working Group on IP to harmonise aspects of IP in the region. It is anticipated this will take a number of years with some areas progressing quicker than others.
Assess the Value for Money (VfM) of this output compared to the proposition in the Business Case, based on performance over the past year
The proposition for this output in the Business Case focused on improvements to IP policy frameworks and implementation through improved regulatory efficiency, transparency, predictability and harmonisation in ASEAN. This was potentially too ambitious in the given timeframe, although delivery is currently ahead of logframe targets. There was also some evidence of increased efficiency following the switch to virtual events which enabled increased participation and audience reach.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
A change request was agreed to narrow the scope of this output, removing a digital services component.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
No specific recommendations were made about this output in the previous AR. No specific lessons learned or recommendations for this output.
Output Title	In-House IP: Inclusive IP capacity building through knowledge sharing and technical assistance to improve IP and related legal/policy frameworks, regulation and practices
Output number:		1B	Output Score:	A+
Impact weighting (%):		5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of delegates reporting having used learning from the capacity building activities after 6 months	2018: 14 achieved (10 planned) / 2019: 35 achieved (30 planned) / 2020: 54 achieved (35 planned) / 2021: 90 achieved (45 planned)	90 achieved
Number of non-PF funded industry speakers delivering sessions at each capacity building seminar.	2018: 4 achieved (5 planned) / 2019: 13 achieved (10 planned) / 2020: 10 achieved (15 planned) / 2021: 2 achieved (2 planned)	2 achieved

The IP in house project is delivered by FCDO and overseen by the UK Intellectual Property Office (IPO) (which co-funds this work in Singapore and Brunei). The majority of activity is capacity building through training across two strands: IP enforcement and IP innovation. The priority markets are Vietnam, Indonesia, the Philippines and Myanmar although all ASEAN Member States are within scope. The training sessions were originally delivered in person but the use of webinars continued throughout the annual review period due to travel restrictions. These trainings also increasingly focused on e-commerce IP capacity given the sharp rise in usage of e-commerce platforms due to the pandemic.
In this AR period, the following sessions were delivered:
- UK-ASEAN IP commerce Webinar (August 2021) covering the latest developments in E-commerce policy, regulation, consumer behaviour trends and how policy makers can leverage the growing E-commerce sector to build back better with IP. Total participants: 161, including 76 women (47%) and representing 8 ASEAN Member States (AMS).
- UK-ASEAN IP Enforcement Webinar Series (September 2021) covering transparency and governance in Free Trade Zones, protecting supply chains and the environmental impact of IP infringing goods. Total participants for part 1: 195 (including 10 ASEAN Member States), part 2: 169 including 9 AMS.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The Business Case set out the objective to ‘progress implementing ASEAN IP action plan, especially on enforcement including online trademark infringement and engage regional online intermediary platforms on their IP policy.’ Through this activity, there has been demonstrable progress to the intermediate outcomes in the TOC as the delivery partner reported participants have actively used the learning and knowledge gained from the training activities in their work. This activity represented a small proportion of spend and aligned well with both the OECD work on competition policy and with the commercial IP work delivered by the PwC consortium. This output added further secondary benefits by highlighting the UK’s expertise and assistance on IP enforcement and innovation, thereby improving relationships and consolidating the UK’s position as ASEAN’s partner of choice on IP enforcement. This was particularly important to demonstrate the UK’s ongoing commitment in the region as an ASEAN dialogue partner.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The main changes came about as a result of the pandemic and continued restrictions to gathering and travel. Delivery continued online which increased the reach in terms of participants, though the cost in quality of relationships from face-to-face interactions was recognised.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
No specific recommendations were made about this output in the previous AR. No specific recommendations for this output.
Output Title	RD BEIS: Increased capacity building and collaboration for government stakeholders to improve regulatory practices
Output number:		2	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of recommendations proposed for adoption by GoPh, GoV or GoI to implement/revise laws, regulations, rules and/or administrative practices to improve business environment (Cumulative)	2019: 3 achieved (2 planned) / 2020: 4 achieved (5 planned) / 2021: 7 achieved (9 planned) / 2022: (9 planned)	2021: 7 achieved
Number of officials trained (gender disaggregated)	2019:128 achieved (50 planned) / 2020:128 achieved (200 planned / 2021: 349 achieved (350 planned) / 2022: 450 planned)	2021: 349 achieved
% of positive feedback from selected domestic and international business organisations on reform plans and processes and views about future improvement	2019: (50% planned) / 2020: (75% planned) / 2021: (80% planned) / 2022: (80% planned)

This output has experienced delivery challenges due to the pandemic that has led to it being extended until Quarter 4 and most likely will be extended again for a further six months into the next financial year. Nevertheless, progress against output targets was in line with expectations and positive feedback from beneficiaries was high.
In Indonesia, the focus has been on continuing to support the step change improvement in business licensing and inspection across government, which the programme has supported through its inclusion in the 2020 Omnibus Law on Job Creation to simplify processes and avoid duplication and improve regulatory outcomes. Contracting local consultants, with expert support from London, has enabled delivery through the pandemic restrictions. The delivery team continues to support the government in policy development, secondary regulation and implementation processes. In addition, expertise was shared through a webinar series, including workshops on oversight of inspectorates, attended by 2000 people, and over 650 people logged into a webinar on the risk-based reform agenda.
In Vietnam, work continues in collaboration with the Ministry of Justice (MOJ) on a Policy Impact Assessment Scrutiny Manual, promoting UK best practice. On regulatory reform UK experts visited and presented on the UK’s administration burden reduction programme. Subsequently, UK experts presented at a workshop offering further ideas for improvements. The Programme also supported the Government of Vietnam to develop Resolution 68 on simplification and streamlining of business conditions in Vietnam during 2020-2025, which was modelled on the UK’s administrative burden reduction programme. Subsequently, UK experts continued to further support the implementation of the Resolution, including the digitalisation transformation efforts of the government.
In the Philippines, there were two main outputs. Work on the Whole of Government Re-engineering Manual was completed to help improve service delivery by government agencies and improve ease of doing business. In addition, the programme supported the development and implementation of the Philippine Good Regulatory Principles, which was launched in July, supported by webinars and videos to promote it to national and local government agencies. The principles were modelled on the UK’s Regulator Code, and contain a principle on engagement which requires policy makers to undertake inclusive stakeholder engagement throughout the regulatory lifecycle, including maximising different channels to engage hard-to-reach and under-represented groups.
Outputs were also delivered at the regional level, in partnership with OECD, with a contribution from BEIS to the final session of ASEAN-OECD Good Regulatory Practices Network in October, covering international regulatory cooperation from a UK perspective.
In addition, the first milestone indicator of seven recommendations is arguably an underestimate because this only counts work on the Indonesia omnibus law as one recommendation. In reality this work is multi-faceted, with a number of clearly-defined and separate work streams, all of which could be considered as separate recommendations. For example, this included:

- Working with the Indonesia Investment Coordinating Board (BKPM) to support the implementation of risk-based licensing within Online Single Submission (OSS) process.
- Conducting a policy review of current licensing regime and supporting a policy proposal to resolve inter-Ministerial conflicts, rationalise regulation and clarify regulator responsibilities. This policy was adopted and BEIS are now supporting implementation.
- Proposing a new framework for a risk-based inspection regime. This was incorporated into the Omnibus Law and provides a framework for the frequency and content of inspection and reporting methods. Further work in 2022 will develop techniques and training.
If these recommendations were each counted separately, this would bring the milestone indicator to 10, exceeding the target of 9.
Regarding the percentage of positive feedback indicator, BEIS are still in the process of developing the methodology to measure this across all three countries – Indonesia, the Philippines, and Vietnam.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Evidence of effectiveness is visible and the switch to virtual delivery increased economy and efficiency by extending the number of people who could access the workshops. The switch to remote delivery stimulated thinking in the project team about alternative means of delivery to re-balance the need for face-to-face engagement to build relationships. The deployment of local consultants, supported by UK technical experts, has achieved this, keeping costs below the pre-pandemic approach while maintaining effectiveness. This is a model that has proven to be effective in other FCDO programmes.
In addition, as a secondary benefit, the programme has been able to create a number of UK engagement opportunities through its activities, which improved the VfM further. For example in Vietnam, the project has created opportunities for meetings with the Chair of the Office of Government. In Indonesia, the project supported the negotiation and launch of the Indonesian Joint Economic and Trade Committee (JETCO) which will help promote and develop trade, investment and economic cooperation ties and address market access barriers affecting UK businesses trading with Indonesia.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
In January 2021, the Indonesia Regulatory Reform Programme (IRRP), formerly an independent programme, merged with this programme strand and became part of AERP. The merger was approved by the Programme Board, and resulted in an increase in the over-all programme budget to £19.7m. The MoU governing the project was amended, and both the project and portfolio level log frames were adjusted accordingly.
In addition to this change, as part of a new funding allocation in July 2021 an additional £50,000 was added to this project in order to facilitate some additional work through OECD. The Regulatory Development International under BEIS (RD BEIS) signed an MoU with OECD for them to promote the standardisation of better regulatory and enforcement practices adopted by Member States due to the COVID-19 pandemic.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Previous recommendations:
Future in-country consultation processes should be targeted and adapted to relevant local stakeholders, taking time to provide them with necessary background information and relevant details or skills to engage in a meaningful way.
As can be seen from the output activities this year, engagement and cooperation with stakeholders locally was effective within the timeframe of this review and tailored to local requirements.
Lessons Learned:
Regulatory reform takes time, and it can take a number of years before the impact and benefits of any reform starts to be realised. It is important to be mindful of this in any future programme design.
Leveraging UK expertise by facilitating visits had a catalytic effect. For example, in 2019, the director general of Anti-Red Tape Authority visited the Philippines and discussed the UK Regulators Code. The Philippines authorities were drawn to this and subsequently launched a similar initiative in July. This was not originally an envisaged output for the project. However, collaboration on the Code enabled the UK to promote best practice. It would be useful to assess the impact of this during the remaining term of the programme.
Recommendations for the year ahead:
Future work – The project will not reach its full potential and VfM if it ceases at the end of the current programme. Considerable investment has been made into building relationships and trust with beneficiaries and there is an appetite to continue working with BEIS on regulatory reform. There are other international donors operating in this field, but the UK is recognised for its thought leadership and experience on regulatory systems. This is a strong, niche position which is recognised by beneficiaries. The programme team should give serious consideration to continuing and expanding this project in future, noting progress to date and alignment with UK’s economic and foreign policy priorities.
Regulatory diplomacy - The Integrated Review (IR) sets out the importance of regulatory diplomacy. Regulatory diplomacy is important to the UK’s long-term competitiveness, prosperity and national security. For any future programming, the Programme team should consider how this project might link with and support the IR focus on regulatory diplomacy as a secondary benefit.
Cross-Government coordination – The project team are well connected to the Better Regulation Executive, under BEIS, and relevant cross-Government groups. However, coordination is most easily achieved at Posts where links across Departmental priorities can be identified. If a successor programme is developed, the team should look at international priorities on regulation across Government and identify areas for inter-departmental collaboration where appropriate.
Output Title	OECD: Increased adoption of recommendations on use / misuse of competition assessments and special rights and privileges of SOE’s
Output number:		3	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of Competition Authorities reporting increased knowledge and usage of competition assessment	2021: 10 achieved (6 planned)	2021: 10 achieved, 100%
Number of recommendations Competition Authorities or other Government regulators say they support for implementation, have implemented or may recommend for implementation	2021: 30% achieved significantly above the 5% planned. A new project is also being discussed which would involve providing more technical support to translate the report recommendations into implementation. This further supports this indicator.	2021: 30% achieved / Two countries have already implemented key recommendations (Singapore and Indonesia) and two additional countries have expressed their intentions to consider them (Philippines and Vietnam).
Policymakers reached via stakeholder meetings, launch events and workshops as a % of key stakeholders that attended the launch events	2021: 100% achieved (80% planned)	100% / All key stakeholders were involved, as well as senior political leaders (economic ministers of all 10 countries) that were also involved, which was beyond expectations.

Briefly describe the output’s activities, and provide supporting narrative for the score.
The ASEAN Member States (AMS) have agreed to implement significant advances in competition policy as part of the ASEAN Competition Action Plan 2016-2025 (ACAP 2016-2025). This project contributed to the ACAP 2016-2025 by reviewing regulatory constraints on competition in all ten ASEAN Member States to identify regulations that hinder the efficient functioning of markets and/or create an un-level playing field for business.
The OECD conducted competition assessments which involved evaluating laws and regulations though the lens of competition: assessing their purpose, suitability, effectiveness and efficiencies. The ASEAN Secretariat and ASEAN Experts Group on Competition (AEGC), together with the OECD, chose the logistics sector to be the focus of the research as it can play a significant role in increasing ASEAN’s economic development. Alongside this, the OECD undertook competitive neutrality reviews in order to assess the extent of a level playing field between state-owned entities and private competitors. These in-depth studies required wide consultation with 280 stakeholders across 10 countries, and assessed approximately 700 regulations. Twenty-two reports were published (10 country reports and one regional report per assessment type) and launched at country level (apart from Myanmar and Laos) throughout 2021 and at an ASEAN ministerial meeting in September 2021.
The work delivered under this output has been received beyond expectations and achieved buy-in at the highest political levels in ASEAN countries. It is the only time a non-ASEAN report has been launched at an ASEAN Ministerial meeting, indicating its strategic relevance at a political and working level. It was launched with all 10 economic Ministers of ASEAN, as well as the UK Minister for Trade Policy and the Secretary Generals of ASEAN and of the OECD. Furthermore, the country reports were launched in almost all countries in ASEAN, most of the time with very senior political attendance and high-level policymakers of the relevant ministries and regulators. The regional workshops for policymakers achieved further awareness and understanding at a more technical level about the recommendations. Wide media coverage also supported the OECD’s objective to create more public dialogue on competition in order to improve the chances of recommendations being implemented.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The objective in the Business Case was to ‘level the playing field in ASEAN by strengthening the competition policy frameworks and their enforcement’. This activity delivered by OECD shows strong potential in achieving the output, which would subsequently contribute to achieving the outcome level change set out in the Business Case. The evidence of this is the interest shown by Member States in the report recommendations and in receiving assistance to implement the recommendations. The Indonesian government used the Omnibus Law on foreign investment to integrate some key OECD recommendations. The governments of Cambodia, Singapore, the Philippines and Vietnam have also cited the assessments as the basis for regulatory and/or legislative changes needed.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Delays caused by the COVID-19 pandemic meant more time was needed to complete agreed activities and an extension was granted from March to September 2021. As activities were suspended in Myanmar, no launch event was held for the country report. There was also no report launch in Laos.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Previous Recommendation: Collect and document information on how adoption of recommendations is proceeding, what the barriers are and how to address these moving forward.
The project completion report summarised what interest exists and what progress had been made to date per country. The possibility of a next phase to the project was being discussed at the time of the review which would open up the opportunity for further monitoring of the adoption of OECD’s recommendations.
Previous Recommendation: Encourage diverse representation, including Civil Society Organisations (CSOs), in the launch of the reports, providing background information on its purpose and goals before the event. Monitor the response to the recommendations and assess the extent to which women may be affected/positively or negatively by the adoption of these recommendations.
OECD relayed that this was beyond the scope of their deliverables. The engagement of a wider, more representative group of stakeholders involved in the monitoring of OECD recommendations and assessing their effectiveness – including the extent to which women benefit from a level playing field – should be actively explored in any plans for a future project phase.
Output Title	UNDP: Strengthened partnerships between civil society and public and private sectors to implement and monitor integrity policy, opening participation for women and underrepresented groups.
Output number:		4a	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4a (a): Number of learning & knowledge platforms for Government – private sector and civil society policy dialogue (UNDP Output Indicator 1.1)	2019: 1 achieved (1 planned) / 2020: 5 achieved (3 planned) / 2021: (5 planned)	6 achieved
4a (b): % of involved stakeholders reporting feeling more comfortable on dialogue on integrity and transparency with counterparts following participation in the platforms (disaggregated by gender) - referring to the ability of understand and trust each other and work for common goals	2019: 84%achieved (0 planned) / 2020: 88% achieved (70% planned) / 2021: 98% achieved 80% planned	98% achieved
4a (c)# stakeholders engaged through the regional platforms (sex- disaggregated and sector-disaggregated: public sector, private sector, CSO...)	2019: (this indicator was only introduced in March 2020) / 2020: 602 achieved (300 planned) / 2021: 3652 achieved (500 planned)	3,652 achieved

Output Title	UNDP: Improved transparency in government contracts and increased compliance with international procedures and trade standards
Output number:		4b	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4b (a) # of countries that have established open and innovative service delivery mechanisms	2019: 1 achieved (1 planned) / 2020: 2(cumulative) achieved (2 planned) / 2021: 3 (cumulative) achieved (3 planned)	3 (cumulative) achieved
4b (b) # of new infrastructure projects where data is disclosed by governments of Thailand and Indonesia following CoST methodology	2019: 52 achieved (123 planned) / 2020: 306 achieved (260 planned) / 2021: 1413 achieved (400 planned)	1,413 achieved
4b (c) CoST West Lombok and CoST Thailand uses the guidance developed by the CoST IS to promote and increase the participation of women	2021: (2 planned)	0 achieved

Output Title	UNDP: Adoption of responsible business practices & good corporate governance including gender and diversity by private companies & SOEs
Output number:		4c	Output Score:	A+
Impact weighting (%):		5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4c (a): # of business integrity instruments adopted (trainings and/or tools on code of conduct, internal control mechanisms or whistleblowing mechanisms developed for business sector)	2019: 6 achieved / 2020: 20 achieved 20: 6 achieved (2 planned) / 2021: 21 achieved, cumulative (4 planned, cumulative)	21 achieved
4c (b) # of companies in ASEAN that have joined responsible business conduct initiatives by project	2019: 0 achieved (0 planned) 2020: 12 achieved (2 planned) / 2021:147 achieved (4 planned)	147 achieved

Output Title	UNDP: Strengthened anti-corruption policies, plans and strategies and improved redress mechanisms
Output number:		5	Output Score:	A
Impact weighting (%):		5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5a: # countries supported to develop or update preventive anti-corruption policies, plans or strategies	2019: 2 achieved (1 planned) / 2020: 3 achieved, cumulative (2 planned) / 2021: 4 achieved (3 planned)	4 achieved
5b: # of new in-country judicial initiatives initiated following regional peer to peer exchanges (targeted countries)	2019: 2 achieved (1 planned) / 2020: 2 achieved, cumulative (2 planned) / 2021: 3 achieved, cumulative (3 planned)	3 achieved

NB: the UNDP outputs have been grouped and assessed together
Output 4a. All UNDP-led indicators come under the FairBiz project. The project works both regionally and in the six target countries to improve business practices and minimise corruption risks, creating a fairer business environment. One aspect was to enhance public procurement processes. The project aimed to bring together governments and regulators with the private sector and civil society to improve business integrity and eradicate corruption. During the review period, UNDP established a series of thematic platforms through which to engage regional stakeholders in strategic dialogue. These platforms are: global supply chains; procurement; environment, social and governance; diversity and inclusion; youth and entrepreneurship; integrity in government institutions. They are directed by the FairBiz Integrity Hub’s Private Sector Advisory Group, with an online repository of resources.
Output 4b. The ‘CoST – the Infrastructure Transparency Initiative’ approach to measuring levels of transparency and the quality of processes related to public infrastructure at both national and sub-national levels is premised on four core features: disclosure, assurance, multi-stakeholder working and social accountability. In Thailand, FairBiz worked with the UNDP Country Office and the UK Government Digital Service to review the public procurement process in full in Thailand. This included a comparative analysis of different procurement systems and bespoke technical advice on subordinate legislation related to the legislation on procurement. The project has also supported the Anti-Corruption Organisation of Thailand (ACT) – a civil society organisation monitoring transparency in public procurement of infrastructure construction.
This output was also delivered in Indonesia. The support included direct engagement with Indonesia’s National Public Procurement Agency (LKPP). That work started with a study and comparative analysis as to how the system could be improved to reflect international best practices and standards. It also included the development and operationalisation of a mass online course for suppliers on public procurement that went live in 2021. CoST also worked in Indonesia and established a relationship with the sub-national government in West Lombok, which agreed to pursue alignment of its procurement system with the CoST methodology. At the end of October 2021, FairBiz convened regional stakeholders for a major workshop on public procurement with the intention of expanding lessons from Thailand to other ASEAN member states.
Output 4c. UNDP commissioned and published a research report reviewing circumstances in five ASEAN countries to identify key interventions that have promoted gender, diversity and inclusion in business. They also developed guidance on mainstreaming gender equality into infrastructure projects. Several AERP partners have contacted the project team to receive guidance and advice on how to more effectively integrate gender equality in their projects.
In Indonesia, through a close collaboration with Alliance for Integrity and LKPP, FairBiz conducted a pilot training with a selected group of women-led enterprises aimed at enhancing female participation in public tenders throughout improving business standards.
In Malaysia UNDP partnered with Deloitte to pilot training with two large multi-national corporations with the aim of promoting more robust corporate governance and internal controls throughout their supply chains. The target audience were SME’s from the supply chain, who received training on local and international law, corporate governance and management techniques to promote a sustainable and equitable business environment. Based on what was learned, all SMEs were asked to return for an Action Day where they would report on their progress in implementing the action items that were identified during the training for each company.
In Vietnam, UNDP and Deloitte piloted risk assessments in three large corporations by conducting internal audits of their risk management systems. This included training for corporate staff and the development of a template manual for staff that has since been adapted and applied by the companies. UNDP also partnered with the Vietnam Chamber of Commerce and Industry (VCCI) on trainings for VCCI members. The partnership with VCCI also allowed for the development, with the Vietnam National University, of a Handbook on Fundamental Auditing which has been piloted with university classes earlier in 2021. FairBiz also supported VCCI in establishing the Vietnam Business Integrity Network, which is a national network of private sector and state-owned enterprises that provides awareness raising, technical advice and conducts research and analysis on improving corporate governance in Vietnam.
Output 5. Four countries were the focus of this output – Vietnam, Myanmar (not as of 2021), Indonesia and Malaysia.
- Indonesia: UNDP developed partnerships with the newly-established National Agency for the Prevention of Corruption. They commissioned three corruption risk assessments related to key sectors that are notoriously drivers of corruption. These allowed the agency to identify drivers of corruption in each sector and the entry points to promote prevention of corruption.
- Malaysia: UNDP continued their work with the Malaysian National Centre for Governance, Integrity and Anti-Corruption (GIACC). Knowledge products developed under the project regarding anti-corruption were printed and distributed among Ministries, Government and public universities, reaching a broad and diverse targeted audience.
- Vietnam: Here the project worked with the Supreme People’s Court to improve its ability to interpret and implement foreign arbitration decisions. In 2021 officials approved a study on mechanisms for ensuring judicial integrity to promote business environment. The study aimed to promote the need for judicial integrity if Vietnam is to increase investor confidence.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The FairBiz project brought together different actors to promote fair business in the ASEAN region, based on the recognition that each actor has a stake and a role in bringing about this improvement. To a degree, this project piloted an approach of cooperation between different entities and coordinating offices - in this case UNDP country offices. This required adaptability in finding optimal ways of working and communication in order to appeal to the range of stakeholders and beneficiaries.
The use of the platforms created a stable and long-term basis for the project to operate across related, yet not fully integrated, issues linked to business integrity and the broader anti-corruption agenda in the region. The platforms have been leveraged to build active networks in select countries. For example, the diversity and inclusion platform was utilised to support a network of Thai women business leaders where new skills and knowledge are shared with key private sector actors in the country.
UNDP took a tailored approach to training and communication in each country. UNDP’s choice of partner (CoST) with well-established networks in country also enabled a targeted approach. There is certainly evidence that investing in country-based solutions - such as the work with multinational companies in Malaysia - was effective as there was dedicated capacity, sufficient stakeholder management, and evidence of policy and practice change in the target SMEs in their supply chains.
Furthermore, by requiring training participants to return in one month with signs of action, it instilled in the SMEs the need to leave the training with an agenda for action and change. Not all SMEs returned with a plan and those that did were likely already committed to combating corruption, but the concrete measures outlined in the training and the link to the multinational companies allowed for deeper penetration than otherwise would have been possible.
UNDP also saw advantages in taking a regional approach. The value add came from being able to connect regionally to share lessons on what has worked, pitfalls, influencing and promoting exchanges. The potential to implement changes regionally is particularly prominent given the project’s partnerships with multinational corporations, for instance one company is now interested in expanding the project with their offices in Thailand and Vietnam.
UNDP recently conducted an independent evaluation of the FairBiz programme from inception to date. The report concluded that the project has achieved significant results in response to all four key outputs. It noted that the project has shown results at national levels which could be replicated regionally. The review cited the transformation of the public procurement process in Thailand as being the most impactful work of the project, with the project able to claim some attribution for the on-going reforms that continue with the Comptroller-General’s Department of the Ministry of Finance. In addition, the adoption by the Government of Thailand of the sub-regulation that now requires all procurement entities to report data and information in accordance with CoST standards and the recognition of CoST and its multi-stakeholder group has allowed for a strong, trusted relationship between the partner and the Government. The fact that CoST standards for data are now the legal standards for the Government of Thailand is a significant and impactful change. The evaluation also suggests that in Malaysia and Vietnam there are clear signs of strong relationships being built with the private sector and civil society which can be leveraged to achieve more outcome level changes.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The pandemic and lockdown rules continued to affect the target countries, meaning in-person activities had to be moved online. Activities in Myanmar were suspended due to the military coup. The results framework was updated accordingly.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Capture learning and innovative techniques on digital learning and share with other programme implementers and the Prosperity Fund network.

The team have captured these lessons and shared with other delivery partners.

Encourage UNDP to engage more meaningfully with local partners, particularly women-led coalitions and associations, in its roll out of remaining activities.

UNDP have done this where possible, most recently evidenced by their work with a Thai Women’s Business Association.

Review sustainability options with UNDP for the remaining time of implementation including the possibility of flexible funds for targeted activities.

The Programme Team have worked with the FairBiz programme Team regarding sustainability, particularly in respect of monitoring and evaluation, moving towards reporting at the outcome level.

Strengthen links and maintain connection between UK embassies and UNDP in country for closer relationship building, promotion of activities, accountability and monitoring purposes.

The Programme Team have raised this issue with the FairBiz Team on a number of occasions. Monitoring through FCDO Programme Managers indicates that the situation has much improved.

Keep a close eye on impact of staff turnover and raise concerns early if gaps are not being filled and activities are delayed.

This is still a concern and this issue was also separately identified in the UNDP evaluation. Reassurances have been sought regarding the stability of the team.

The UNDP independent project evaluation also highlighted that:
- There were some inconsistencies between project and programme level outputs and outcomes.
- Project indicators included in the design phase were not necessarily relevant throughout the entire programme period.
- The project was slow to develop and establish the platforms, and suggested a more strategic approach to delivery.
- Demonstrable political buy in on anti-corruption (such as passing of legislation) enabled better engagement with the private sector.
Output Title	PwC: Positive influence on market regulation through ASEAN Capital Markets Forum (ACMF) and promotion of international standards in FS / (Logframe: Capital markets’ development plans, policies and regulations developed or improved)
Output number:		6		Output Score:		B
Impact weighting (%):		10		Weighting revised since last AR?		No
Indicator(s)			Milestone(s) for this review		Progress
6(a) No of strategic recommendations reports developed			2020: 0 achieved (0 planned) / 2021: 1 achieved (3 planned) / 2022: (3 planned)		1 achieved

Output Title	PwC: Improved capacity and frameworks within key financial institutions and markets / (Logframe: Policies and regulatory issuances updated or developed, and industry provided the platform to develop or enhance responsible Fintech products or services)
Output number:		7		Output Score:		A
Impact weighting (%):		10		Weighting revised since last AR?		No
Indicator(s)			Milestone(s) for this review		Progress
7 (a): No. of new frameworks or systems developed			2020: 4 achieved (4 planned) / 2021: 1 achieved (2 planned) / 2022: (0 planned)		1 achieved
7 (b): No of strategic recommendations reports developed			2020: 1 achieved (1 planned) / 2021: 7 achieved (6 planned) / 2022: (2 planned)		7 achieved

Output Title	PwC: Capacity building and knowledge sharing to tackle financial crime and money laundering / (Logframe: Training and frameworks delivered across Myanmar’s government agencies to improve institutional standards of anti-money laundering and countering the financing of terrorism)
Output number:		8	Output Score:	N/A
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
8 (a) No of strategic recommendations reports developed	2020: 6 achieved (6 planned) / 2021: 0 achieved (0 planned) / 2022: (1 planned)	0 achieved
8 (b) 'No. of new frameworks or systems developed	2020: 4 achieved (4 planned) / 2021: 0 achieved (0 planned) / 2022: (0 planned)	The coup d'etat in Myanmar affected the project's progress, bringing it to a halt.

Output Title	PwC: Facilitate increased selling of international funds including UK funds in ASEAN and vice-versa; Improved links between international business, including UK and SEA
Output number:		9	Output Score:	N/A
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Output 9: Number of working relationships established between UK organisations & target FSIP stakeholders	2020: (3 planned) / 2021: (5 planned) / 2022: (7 planned)	0 achieved

NB: The PwC outputs have been grouped and assessed together. Some of the output titles here are different to the logframe outputs because FSIP outputs were nested into the AERP level logframe and therefore required some adaptation. Taken together, these four outputs delivered by PwC alongside output 1a above, are known collectively as the Financial Services Intellectual Property (FSIP) project.
Output 6. Only one strategic recommendation report has been delivered against output 6. The planned work on capital markets in Vietnam did not materialise due to a lack of stakeholder engagement, and the targets were subsequently cancelled. In the Philippines, one strategic recommendation plan and associated action plan was approved by the Securities and Exchange Commission (SEC) and the Central Bank of the Philippines (BSP). PwC have reached an agreement with the SEC and revised the action plan based on the feedback. The delivery in Year 3 will now focus on strengthening the SEC’s efforts for inspections of Risk Based Capital Requirement (RBCA) supervision.
Output 7. Several activities in the Philippines contributed to this output. This included the public launch of the Philippines Fintech Industry Sandbox, together with the British Embassy and other national and regional stakeholders; a co-hosted workshop with the International Labour Organisation (ILO) designed to improve women’s soft and technical skills related to Science, Technology, Energy, and Mathematics (STEM), and exploring work opportunities in the FinTech Industry; publication of the Open Finance Circular on the BSP website; and 313 regulators were trained, 68 per cent were female.
In Indonesia, the programme engaged and assisted Otoritas Jasa Keuangan (OJK; Financial Services Authority of Indonesia) to improve the draft revision of Peraturan Otoritas Jasa Keuangan (POJK; Financial Services Authority Regulation) 77/2016 through a series of meetings, email exchanges, presentations and consultations. The updated regulations were circulated by OJK to key industry stakeholders for consultation. Based on OJK’s recommendations, the Ministry of Finance (MOF) also asked FCDO for technical support in the drafting of the Financial Sector Omnibus Law. Regular discussion with MOF took place where the different policy options and their implications highlighting international best practice were discussed. Draft recommendations relating to the Fintech provisions of the Omnibus Law on Financial Services was presented to MOF. After the milestones have been completed and the work package closed, MOF is still currently drafting the Financial Services Omnibus Law and so have asked for additional support going forward. This also reflects the success of the technical assistance programme.
In Thailand, an International Financial Reporting Standards (IFRS) 9 virtual roundtable was delivered to 197 participants with an aim to strengthen the capacity of Bank of Thailand (BOT) to monitor and supervise IFRS 9 compliance for financial institutions. The session covered regulation of state owned financial institutions. A virtual digital assets session was held for 260 participants from the Securities and Exchange Commission (SEC), the BOT and the Thailand Federation of Accounting Professions (TFAC) and 46 external auditors to promote financial and economic stability. A separate GESI focused session was also hosted to introduce the GESI concept to participants.
For Malaysia, the programme received approval from the Board of Trustees (13 State representatives) for the establishment of the Emergency Waqf Fund programme which is a key milestone achievement towards establishing new Islamic Finance services. Recommendations were also included in two reports on mobilising an Emergency Fund to mitigate losses due to flood events.
An International Financial Reporting Standards (IFRS) gap assessment and implementation roadmap were delivered in Vietnam, focusing on the roadmap to IFRS implementation that will enable the Ministry of Finance (MOF) and the other Vietnamese authorities and stakeholders to develop and implement their individual policies and plans in a coordinated manner.
A number of new or improved policies and regulations benefited from the programmes support. BSP in the Philippines incorporated advice on COVID-19 relief measures by issuing amendments to the Credit-Related Regulatory Relief Measures for BSP Supervise Financial Institutions (BSFIs); in Thailand, the SEC proposed new rules for digital asset custodians; and, in Vietnam, the MOF approved the introduction of IFRS on a voluntary basis from 2022, with mandatory application after 2025.
Output 8. Prior to the cessation of programme activities in Myanmar, because of the coup, the delivery team completed a comprehensive review of the Standard Operating Procedures (SOP) for the Financial Intelligence Unit. A virtual training session on Basic Intelligence, Use of Intelligence and Operational Analysis was delivered with a majority of participants reporting that they will implement learnings into their day-to-day operations. In addition, training was provided to help implement the processes and procedures provided in the Risk Management Manual delivered previously. A remedial training plan was created for the Union Attorney General's Office, covering legal and regulatory technical gaps and operational issues. Skills gaps were identified as part of this work and recommendations made for training requirements.
Output 9. This output was intended to be a secondary benefit of the programme, which would be achieved indirectly through the other eight outputs. As such there was no specific activity designed to deliver this output directly. As set out on page 1, future programme logframes should only include what the programme will be directly accountable for and any secondary benefits can be captured in a regional secondary-benefit tracker.
Assess the VfM of these outputs compared to the proposition in the Business Case, based on performance over the past year
Evidence of the project’s effectiveness is visible and, as with other output activity, the switch to virtual delivery has increased economy and efficiency by extending the number of people who were able to access workshops and training than would have been possible in a face-to-face format. There was a suggestion that the delivery and payment structure for the outputs may have hindered VfM in some areas, because it incentivised a focus on overly-rigid, pre-set milestones, rather than practical delivery. While this may have been a distraction, it is difficult to judge whether this would have had an impact on securing VfM.
Describe any changes to these outputs during the past year, and any planned changes as a result of this review.
The PwC budget was reduced by around a third (£0.86m) in May 2021 following a review of all project activity. The review looked across the FSIP programme, identifying areas which were under-performing, and reaching consensus on those activities which should be removed from the programme. The corresponding outputs were removed as a result. In addition, following the cessation of activities in Myanmar, output 8 was no longer reported on. No changes planned as a result of this review, as the contract with PwC will end in March 2022.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Previous AR Recommendations:
The programme team should work together with PwC to reduce 388 milestones to a manageable level – whilst the current operating model works, it requires a lot of time and resource on the part of both programme teams. It is also suggested that the programme undertake a lessons learned exercise on this particular delivery model, and share the findings across other PF programmes.
A detailed programme review was conducted as part of Year 3 planning and the number of milestones was reduced to 343 milestones. A lessons learned exercise is planned for end of January 2022.
The review team recommends that the programme should use the relevant contract clause to carry out a Satisfaction Survey of the commercial contract to capture satisfaction levels.
A survey was carried out in March 2021 and another was being implemented in December 2021. Headlines of the March survey:
- The relationship between stakeholders and the FSIP regional team had improved, and their timely responses and availability was appreciated.
- Communications could still be more clear and concise.
- The milestone management process was still difficult to manage, both externally and internally at Post, and with the Regional Programme Team.
- On secondary benefits, the FSIP Regional Team could work more closely with colleagues in the UK to have a more coordinated approach
- PwC Country Coordinators should be more empowered to engage on FSIP work streams, and provide support to the FSIP regional team to better understand the local context.
- Work stream leads for IP, FinTech, Capital Markets and Accounting Standards have strong working relationships with key external stakeholders and Post. However, more attention could be given to ensuring that the work is appropriate to the local context. Communication between work stream leads and stakeholders could have been more diplomatic on occasion.
Governance – an immediate and robust review and stabilisation of governance is required. It is good practice to review this annually. Once agreed this should not change without express board, contract or SRO approval.
Governance procedures have been reviewed and are evolving in line with the regional approach. There is a new focus on the extent to which the programme will match the strategic impact intended originally.
Rapid assessment is required to understand what is deliverable within the commercial terms, noting delays and risk related to nugatory work.
This assessment was undertaken as part of the Year 3 review.
Ensure local strategic partnerships are made and that community-based stakeholder consultation takes place in a meaningful way.
The FSIP Programme Team have encouraged stakeholder consultation, though this has sometimes proved challenging. Local partnership coordinators were recruited. Over the past year, PwC has increased the seniority of these interlocutors, which has led to some improvement in relationships with local stakeholders. However, through various routes of monitoring and reporting stakeholder management was still raised as an issue during this review, particularly in Vietnam and Thailand. The FSIP team should continue to improve stakeholder consultation in the final year of delivery.
The Programme Team should closely monitor the impact of the Quality Panel to ensure the quality of deliverables is as expected.
Monitoring continues. The Programme Team requested the FSIP Project Management Office (PMO) to add to the FSIP Annual Report some assessment of the role of the Quality Panel, which has been actioned. In their year 2 Annual Report the following analysis is given: “Through [the Quality Panel’s] role to oversee the delivery of the programme from a technical perspective, ensuring delivery of results and value for money, we have initially observed that it reduced feedback/clarifications from the FCDO for revision of outputs from 16% to 14% (comparative analysis between Y3Q2 and Y2Q2) of the MCRs. On top of that, it helped to bring down the average approval length by 10% (sample analysis from Y3Q2 MCR approvals). Throughout Y2, 98% of the milestone completion reports delivered were approved on time and with minimal clarification (114 out of 116 milestones); only one AML and one FT milestone required additional time for revision.”
Financial and commercial audit – It is recommended under agreed terms of reference that there is an independent auditor and a commercial specialist assessment of PwC contract performance and finances prior to completion of the contract.
This recommendation has been discussed internally with Commercial Department, internal assurance department and the Programme Management Office. Current audit practices have been reviewed and have been found to be compliant. A robust system has been put in place to review PwC invoicing and financial reporting. Additional spot checks have been introduced. Both the programme team and Commercial Department have agreed that these measures fulfil programme requirements. An additional full independent external audit would not represent VfM at this point in the programme.
Closely monitor PwC at country level to ensure that ongoing analysis of risks and opportunities takes place and that partners meet minimum standards on G&I in implementation.
This recommendation has been met though the formal reporting process and informal regular meetings with the local teams.
Ensure local strategic partnerships are made and that community-based stakeholder consultation takes place in a meaningful way.
The hallmark of PwC’s more successful interventions was strong relationships with local stakeholders. This was the case in Malaysia, Philippines and Indonesia. However, the performance in Thailand and Vietnam was more challenging, because the relationships were not as strong. The issue appears to have particularly pronounced in Thailand. The importance of building strong stakeholder relationships and strategic partnerships should be prioritised from the outset in any future programme.
There is a need for FSIP to focus its efforts on strengthening implementing partners, to ensure they are able to deliver on GESI deliverables. It is noted that developing local strategic partnerships will be a priority for the coming year and this should be closely monitored.
FSIP has introduced additional monitoring and the GESI lead has worked closely with work streams to try and ensure both compliance and the identification of opportunities for empowerment. However, the level of ambition remains relatively low. Targets in the log frame have been met, but those targets reflect levels of minimum compliance rather than anything more ambitious. FSIP did run a successful workshop in partnership with International Labour Organisation (ILO) to encourage women in the Philippines in the FinTech sector. A second workshop was planned in Thailand to promote women in business, but tapping into the right networks has proved challenging and FSIP were unable to identify a partner to collaborate with. Instead it was agreed that the GESI lead would produce a short research paper to explore women’s financial inclusion in Thailand which would conclude with some considerations for future programming. This report is due for submission in January 2022.
Encourage FSIP to expand its level of GESI ambition to build assets, capabilities and opportunities for women and excluded groups over the next year.
This has been attempted (see activity listed above) but with limited success, partly due to the lack of budget to resource additional activity.
Closely monitor FSIP at country level to ensure that ongoing analysis of risks and opportunities takes place and that partners meet minimum standards on GESI in implementation.
Monitoring continues. In their Annual Report (Year 2) FSIP note that:
- Out of the strategic recommendation reports produced, 50% included recommendations to improve gender quality and social inclusion.
- Across Accounting Standards, FinTech and Intellectual Property work streams, FSIP say that they successfully prioritised and advocated for women’s inclusion.
- Women have represented 65% of participants across all FSIP programmes in year 2. FSIP ensured women’s participation at the FinTech sandbox in the Philippines.
- FSIP have successfully sought out women speakers, for example for the IP training for the design sector in the Philippines in September 2021, where 2 out of 3 speakers were women.
- FSIP have sought to integrate GESI considerations in the design of activities to increase the impact. For example, improving outcomes for socially marginalised groups has been integral to the design of the Emergency Waqf Fund under the Islamic Finance work stream.
- Women in FinTech session co-hosted with ILO.
Lessons Learned:
Stakeholder engagement: as referenced, above, PwC’s ability to establish and maintain effective relationships with local stakeholders was mixed. This is recognised within the Programme Team, as is the need to conduct a more thorough assessment of delivery partners’ in-country knowledge and networks. This may require putting in place appropriate mitigations before commencing future projects.
GESI: over the last year, better gender-disaggregated data was gathered on events. This was particularly the case where PwC had strong local relationships with stakeholders. However, there was less focus on social inclusion. This is symptomatic of the wider approach to GESI across the programme where GESI did not appear to be integral to the design of the programme at the outset. This will need to be considered for future programming.
Recommendations for the year ahead:
Adaptive Programming – FSIP’s latest Annual Report suggested a switch to an adaptive programme that would go beyond the pre-set milestones to look for opportunities to grow the work packages: integrating learnings and synergies across countries, work streams and outcomes in an adaptive way as the programme progressed. However, this was not pursued. It appears that the constraints of reporting against fixed milestones made this impractical. The decision not to take an adaptive approach was probably the right one in the circumstances. However, it raises an interesting question as to whether this type of approach would have been more effective if implemented from the start. PwC has responsibility as a leading delivery partner with multiple work streams in areas that had not previously been invested in before, operating in complex environments without pre-established stakeholder networks. For future programme design, an adaptive programme approach could be used to test and scale innovative interventions, alongside building on the work done under this project.
Stakeholder management – despite the challenges, this project has led to the establishment of important relationships with regional stakeholders. Since this project is scheduled to end in March 2022, the Programme Team should plan how it will maintain those relationships and maximise the sustainability of their investment, bearing in mind any implications for future programme plans.
Future programme work – in the immediate term, the Programme Team should consider how it could adapt its project activity to support Indonesia’s G20 Presidency. This is a good opportunity to increase influence and raise the profile for the UK in the ASEAN region and beyond. Financial access, SMEs, women and youth appear to be prominent issues for the Presidency, which the programme could support. With regard to any successor programme, the Islamic Finance work stream seems to show promise. The Programme Team should consider whether it can be extended, using an adaptive programming approach, together with the sandbox pilot currently being tested in the Philippines.
D: RISK

Overview of risk management
Risk management was reported through the quarterly reports and the AERP Dashboard for the Programme Board. Risks and issues were grouped at the project level or as cross-cutting risks (e.g. COVID, and corporate). However, there is scope to improve existing risk management processes in line with FCDO best practice on risk management. With this in mind, the following actions could improve risk management further, in line with the (Programme Operating Framework) PrOF:
- The Programme Board reviews the level of risk it is willing to tolerate in order to achieve its goals and outcomes, mindful of the threats and opportunities that it is likely to encounter.
- There should be a systematic approach to risk identification and assessment that quantifies the likelihood and impact. This will assist with prioritisation, monitoring and appropriate mitigation.
- Risks and issues should be separated in reporting so that what might happen is differentiated from what has already happened, as this will inform the programme response.
- When planning future programmes, it will be important to consider risk as part of the development of the theory of change, linked to planned outcomes.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Implementing Partners
Overall the implementing partners have worked well with country stakeholders and FCDO programme managers. There is clear appreciation for the work being delivered with the work of OECD and UNDP for instance being directly credited by stakeholders. There are variations in experience between countries and programme themes. For instance in Vietnam it was felt that UNDP added clear value, was responsive to the needs of stakeholders and programme managers, was able to recruit suitable staff in country and partnered with local organisations. Beneficiaries and local delivery partners in Malaysia, the Philippines and Indonesia also found PwC to be an effective supplier.
The use of different modes of delivery – in-house, multilateral (with sub-grants to CSOs) and commercial – required multiple layers of management in order to deliver and oversee the programme on a regional basis and at country level. This meant PwC and UNDP had regional teams, country teams and country-based consultants respectively requiring a significant amount of staff time to manage the various components of the programme. Considering most outputs were achieved at country level as opposed to a whole-of-region basis, the programme team may wish to consider whether this level of staff capacity at multiple levels provides maximum VfM.
Commercial
There was a notable shift in commercial issues experienced earlier on in the Programme, partly due to the reduced scope of work being delivered by the commercial partners following reductions to the budget. Oversight of the FSIP component from commercial advisers ensured that any concerns on performance were escalated promptly, resulting in fewer issues and smoother delivery during this year. In closing this part of the AERP, there are no foreseen problems, particularly given the good working relationship between the programme manager and commercial lead.
In considering future commercial procurement processes, the Programme team are encouraged to engage a commercial adviser from the outset and clearly define the aims or services needed in a Statement of Requirements, ensuring the parameters of delivery, payment, governance, accountability and performance are clearly defined before a contract is awarded.
Finance
There have been a number of key changes to AERP finances since November 2020:
- In November 2020, the UK Government reduced its ODA spending from 0.7% to 0.5%. This led to a financial adjustment in the FSIP commercial contract in May 2021, whose allocation was reduced by £860,000 or 35% of its contract value.
- In January 2021, FCDO and RD/ BEIS revised their MoU to merge the Indonesian Regulatory Reform Project (IRRP) to RD BEIS’s work in the region. This increased the Programme’s allocation by £700,000.
- In April 2021, the Programme received an additional budget of £170,000 from another FCDO funding mechanism. The allocation has been spread across project strands.
- Beginning FY 2021-2022, programme-funded staff were moved onto their respective Posts’ budgets. As a result, the programme saw a £380,000 underspend which was originally allocated for staff costs during the financial period.
- Within FY 2021-2022, AERP started three new projects and signed new agreements with Cyber Capacity Unit (CCU), Government Digital Service (GDS), and United Nations Office on Drugs and Crime (UNODC).
Following the ODA review exercise in November 2020, the Programme Team returned £921,000 as underspend. The amount included an administration line covering salaries, enabling funds, accruals from the last financial year and savings on UNDP funding due to exchange range fluctuations. It also included underspends across OECD, and RD BEIS lines.
For the remainder of the FY 2021-2022, the Programme Team expects to return an additional £241,000. The amount is comprised of underspends from RD BEIS, OECD, In-House IP, and remainder of the Enabling Fund. The worsened restrictions due to the new COVID-19 omicron variant had pushed the delivery partners to cancel their planned in-person activities and re-profile their budget.
Overall, for FY 2021-2022, the Programme expects an underspend of £1,161,592 against the total budget of £4,070,000. This could be reallocated to FY 2022-2023 if an extension phase of the Programme was designed and agreed.
The changes in the political and economic landscape of the region impacted the programme’s financial management and project delivery. Throughout this period the COVID-19 pandemic remained a key challenge. With the spread of more transmissible variants, Southeast Asia saw a surge of cases that caused a string of lockdowns and shifts of priorities which resulted in project delays to all delivery partners. In February 2021, the coup in Myanmar meant that all Myanmar activity was stopped.
The Programme’s total budget is £19.7 million. Since 2018, the budget has funded the delivery of strategic multi-year projects with eight delivery partners – PwC, CCU, GDS, RD BEIS, OECD, UK IPO, UNDP, and UNODC. By the end of March 2022, the Programme is expected to spend 91% of its total allocation leaving a balance of approximate £1.7 million. This may be requested for an extension phase. The decision on an extension phase was approved in principle by the SRO and the Programme Board in November 2021, pending the availability and allocation of the necessary funding.
Date of last narrative financial report	9 November 2021	Date of last audited annual statement	N/A