## Cover_sheet
Social Housing Decarbonisation Fund (SHDF) Wave 1 Statistics
This spreadsheet contains a selection of data tables to provide an overview of the progression of the SHDF scheme.
The Government launched Wave 1 of the SHDF in August 2021. It has awarded around £179m of grant funding for delivery from 2022 into 2023, and will see energy performance improvements to up to 20,000 social housing properties.
Publication dates
The data tables in this spreadsheet were published at 09:30am Thursday 20th April 2023.
Data Coverage
Data covered in this release is for Wave 1 delivery to the end of February 2023.
Data covered in this release is for England only, as the scheme only operated in England.
Units, notes and no data
Some cells in the tables refer to notes which can be found beneath the tables on each worksheet. Note markers are presented in square brackets, for example: [n1]. Some cells have no data, when this is the case cell is left blank. An explanation of why there is no data is given at the top of the worksheet. Some column headings give units, when this is the case the units are presented in round brackets to differentiate them from note markers.
Contact Details
Press Enquiries to the Press Officer: 020 7215 5975; or the news desk: 020 7215 1000
Responsible Statisticians: Isi Avbulimen and Christine Cheung
EnergyEfficiency.Stats@beis.gov.uk
07927 579551
This workbook was updated on: | 2023-04-20
The next update for these statistics is: | 2023-05-18

## Contents
Table of contents
Publication date: | 2023-04-20
Data Period | 1 March 2022 to 28 February 2023
Geographical Coverage | England only
All figures are provisional and subject to revision.
These table numbers are subject to change in future releases, as additional and more detailed analysis are included.
Worksheet number | Worksheet Title | Date the data was last updated | Next publication date
Summary | Summary | 2023-04-20 | 2023-05-18
T1 | Table 1 - Number of Measures Installed by month | 2023-04-20 | 2023-05-18
T2 | Table 2 - Number of Households Upgraded by Month | 2023-04-20 | 2023-05-18
T3 | Table 3 - Number of Measures Installed and Average Measure Cost by Measure Type | 2023-04-20 | 2023-05-18
T4 | Table 4 - Number of Households upgraded and Measures installed by signed-up LA | 2023-04-20 | 2023-05-18
T5 | Table 5 - Number of Households Upgraded and Measures installed by English geographic region | 2023-04-20 | 2023-05-18
T6 | Table 6 - Number of Measures Installed and Households Upgraded by Parliamentary Constituency | 2023-04-20 | 2023-05-18
T7 | Table 7 - Number of Measures Installed by Measure Group and Property Type | 2023-04-20 | 2023-05-18

## Summary
Summary of Key Trends
This worksheet summarises the key trends presented in the tables within this release.
Introduction
This release presents the latest statistics on the Social Housing Decarbonisation Scheme (SHDF) Wave 1.
This release of statistics contains a selection of tables covering key metrics to monitor the scheme. In future releases, additional analysis tables will be included, so the table numbers will change.
The data contained in the analysis is based on returns submitted by mid March 2023, covering measure installations to the end of February 2023.
The data is based on returns from 66 Local Authorities, with completed installations reported by 25 Local Authorities.
An extension has been made available to all Local Authorities to allow them to spend their Grant Funding to the end of June 2023, with delivery end dates in 2023 agreed on a project-by-project basis.
The scheme is only available in England. For more information on the scheme, please see the
Social Housing Decarbonisation Fund Scheme Wave 1 (opens in new window).
Key points
• Over the first year of SHDF Wave 1 delivery to the end of February 2023, there were 3,958 measures installed in 2,546 households. Measure delivery increased by 63 per cent in the last rolling 3 month period, up from 1,240 measures delivered in September through to November 2022 to 2,027 in the three months to February 2023.
• Of the 3,958 measures, the majority were Insulation measures (2,550 measures, 64 per cent), with Electricity Related measures accounting for 21 per cent (834 measures) and Windows and Doors measures accounting for 13 percent (503 measures) of measures installed. (Table 3).
• The most common measure installed was Loft Insulation (1,229 measures, 31 per cent), with 899 Cavity Wall Insulation measures (23 per cent) and 577 Energy Efficient Lighting measures (15 per cent) also installed. (Table 3).
• The overall average cost per measure was £4,400. The highest average measure cost was for External Solid Wall Insulation at an average of £22,900 per measure, with the lowest average cost being for Energy Efficient Lighting at £300 per measure (Table 3).
• Of the 3,958 measures installed, the majority were installed in the North East region (1,745 measures, 44 per cent), with 831 measures installed in Yorkshire and The Humber (21 per cent) and 621 measures in North West (16 per cent). (Table 5).
• To the end of February 2023, 2,546 households have been upgraded under the scheme, meaning they have had at least one measure installed. Of these, 1,014 households were upgraded in the North East (40 per cent), 711 in Yorkshire and the Humber (28 per cent), and 291 in North West (11 per cent). (Table 5).
• The majority of measures were installed in Houses (2,701 measures, 68 per cent), followed by Bungalows (892 measures, 23 per cent) (Table 7).
• An additional 797 ventilation measures have been installed over the period, which includes measures installed to allow other installations to reach PAS standards.

## Charts
Charts visualising key statistics
This worksheet contains six charts. The charts visualise some of the key statistics within the release.
This worksheet contains blank rows and columns to aid the presentation of the charts.
Chart 1: Number of Measures Installed by Installation Month | Chart 2: Number of Households Upgraded by First Installation Month
Chart 3: Number of Measures Installed by Measure Type | Chart 4: Proportion of Measures Installed by English Region
Chart 5: Proportion of Households Upgraded by English Region | Chart 6: Number of Measures Installed by Property Type

## T1
Table 1: Number of Measures Installed by month
This worksheet contains one table. The table presents the number of measures installed by installation month.
Some cells refer to notes, which can be found below the table.
Tables may contain blank cells. These indicate that there is no data but are kept to allow easy comparisons between tables.
Freeze panes are used in this table. To turn them off, go to View, Freeze Panes, Unfreeze panes.
Installation Month | Number of Measures Installed [n1] [n2]
March 2022 | 53
April 2022 | 93
May 2022 | 138
June 2022 | 98
July 2022 | 162
August 2022 | 147
September 2022 | 161
October 2022 | 254
November 2022 | 825
December 2022 | 457
January 2023 | 807
February 2023 | 763
Total | 3958
[n1] Number of measures installed is a count of the number of energy efficiency measures installed in a household under the SHDF scheme. It includes measures where a date of completed installation is provided.
Installation month is based on the Date of Completed Installation.
[n2] 797 ventilation related measures have been installed but are not included in these tables while we consider their treatment in the statistics.
Last updated | 2023-04-20
Next update | 2023-05-18

## T2
Table 2: Number of Households Upgraded by Month
This worksheet contains one table. The table presents the number of households upgraded by first installation month.
Some cells refer to notes, which can be found below the table.
Tables may contain blank cells. These indicate that there is no data but are kept to allow easy comparisons between tables.
Freeze panes are used in this table. To turn them off, go to View, Freeze Panes, Unfreeze panes.
First Installation Month | Number of Households Upgraded [n1]
March 2022 | 53
April 2022 | 92
May 2022 | 132
June 2022 | 91
July 2022 | 144
August 2022 | 104
September 2022 | 98
October 2022 | 180
November 2022 | 502
December 2022 | 277
January 2023 | 462
February 2023 | 411
Total | 2546
[n1] Number of households upgraded is a count of the number of households where at least one energy efficiency measures has been installed.
The date that the household is upgraded is taken as the completed installation of the first measure installed. For example, if a household had a measure installed in March 2022 and May 2022 then the date that the household is upgraded would be March 2022.
Last updated | 2023-04-20
Next update | 2023-05-18

## T3
Table 3: Number of Measures Installed and Average Measure Cost by Measure Type
This worksheet contains one table. The table presents the number of measures installed and average measure cost by measure type.
Some cells refer to notes, which can be found below the table.
Tables may contain blank cells. These indicate that there is no data but are kept to allow easy comparisons between tables.
Freeze panes are used in this table. To turn them off, go to View, Freeze Panes, Unfreeze panes.
Measure Group | Measure Type [n1] | Number of Measures Installed | Percentage of Total Measures Installed | Average (Mean) Measure Cost (£) [n2][n3]
Insulation | All Insulation Measures | 2550 | 64.43% | 4500
Insulation | Cavity Wall Insulation | 899 | 22.71% | 2300
Insulation | External Solid Wall Insulation | 330 | 8.34% | 22900
Insulation | Internal Solid Wall Insulation | 32 | 0.81% | 3900
Insulation | Loft Insulation | 1229 | 31.05% | 700
Insulation | Pitched Roof Insulation | 0 | 0% | 0
Insulation | Flat Roof Insulation | 2 | 0.05% | #
Insulation | Bay Roof Insulation | 1 | 0.03% | #
Insulation | Room in Roof Insulation | 14 | 0.35% | 17400
Insulation | Solid Floor Insulation | 0 | 0% | 0
Insulation | Suspended Floor Insulation | 28 | 0.71% | 5200
Insulation | Under Floor Insulation | 15 | 0.38%
Insulation | Park Home Insulation | 0 | 0% | 0
Low Carbon Heat | All Low Carbon Heat Measures | 68 | 1.72% | 6800
Low Carbon Heat | Air Source Heat Pump | 4 | 0.1% | #
Low Carbon Heat | Ground Source Heat Pump | 0 | 0% | 0
Low Carbon Heat | Hybrid Heat Pump | 0 | 0% | 0
Low Carbon Heat | Biomass Boiler | 0 | 0% | 0
Low Carbon Heat | Solar Thermal | 1 | 0.03% | #
Low Carbon Heat | Electric Storage Heating | 63 | 1.59% | 6500
Heating Controls | All Heating Control Measures | 3 | 0.08% | 0
Heating Controls | Heating Controls | 3 | 0.08%
Heating Controls | Hot Water Tank Insulation | 0 | 0% | 0
Heating Controls | Hot Water Tank Thermostat | 0 | 0% | 0
Windows and Doors | All Window and Door Measures | 503 | 12.71% | 6200
Windows and Doors | Double or Triple Glazing | 383 | 9.68% | 7700
Windows and Doors | Draught Proofing | 0 | 0% | 0
Windows and Doors | Energy Efficient Windows and Doors | 120 | 3.03% | 3600
Windows and Doors | Secondary Glazing | 0 | 0% | 0
Electricity Related | All Electricity Related Measures | 834 | 21.07% | 2700
Electricity Related | Solar PV | 257 | 6.49% | 6800
Electricity Related | Energy Efficient Lighting | 577 | 14.58% | 300
Total | All Measures | 3958 | 100% | 4400
[n1] 797 ventilation related measures have been installed but are not included in these tables while we consider their treatment in the statistics.
[n2] The average measure cost is based on measures where the cost has been reported by the local authority.
[n3] # refers to values between 1 and 4 inclusive which have been supressed to prevent disclosure.
Last updated | 2023-04-20
Next update | 2023-05-18

## T4
Table 4: Number of Households upgraded and Measures installed by signed-up LA
This worksheet contains one table. The table presents the number of households upgraded and measures installed by signed-up LA.
Some cells refer to notes, which can be found below the table.
Tables may contain blank cells. These indicate that there is no data but are kept to allow easy comparisons between tables.
Freeze panes are used in this table. To turn them off, go to View, Freeze Panes, Unfreeze panes.
Area Code | LA [n1] | Number of Measures Installed [n2][n3] | Number of Households Upgraded [n2][n3]
E06000009 | Blackpool Borough Council | 73 | 73
E06000010 | Hull City Council | 35 | 35
E06000047 | Durham County Council | 1515 | 805
E06000050 | Cheshire West and Chester Borough Council | 102 | 55
E06000057 | Northumberland County Council | 51 | 44
E06000062 | West Northamptonshire Council | 39 | 13
E07000026 | Allerdale Borough Council | 220 | 83
E07000096 | Dacorum Borough Council | ^ | ^
E07000109 | Gravesham Borough Council | 138 | 124
E07000240 | St Albans City & District | 103 | 54
E07000243 | Stevenage Borough Council | 44 | 36
E07000245 | West Suffolk Council | # | #
E08000003 | Greater Manchester Combined Authority | 114 | 28
E08000017 | Doncaster Council | 82 | 66
E08000018 | Rotherham Metropolitan Borough Council | 143 | 106
E08000024 | Sunderland City Council | 159 | 158
E08000026 | Coventry City Council | 149 | 93
E09000019 | Islington Council | # | #
E09000022 | London Borough of Lambeth | 108 | 97
E09000031 | London Borough of Waltham Forest | 92 | 44
E09000033 | Westminster Council | # | #
E10000012 | Essex County Council | 56 | 37
E47000003 | West Yorkshire Combined Authority | 571 | 504
E47000004 | Liverpool City Region Combined Authority | 112 | 52
E47000006 | Tees Valley Combined Authority | 20 | 7
[n1] Only areas where completed installations have been reported are included.
[n2] # refers to values between 1 and 4 inclusive which have been supressed to prevent disclosure.
[n3] ^ refers to values of 5 or more which have been supressed where another value within the group was suppressed to prevent disclosure.
Last updated | 2023-04-20
Next update | 2023-05-18

## T5
Table 5: Number of Households Upgraded and Measures installed by English geographic region
This worksheet contains one table. The table presents the number of households upgraded and measures installed across the whole scheme by English geographic region.
Some cells refer to notes, which can be found below the table.
Tables may contain blank cells. These indicate that there is no data but are kept to allow easy comparisons between tables.
Freeze panes are used in this table. To turn them off, go to View, Freeze Panes, Unfreeze panes.
Geographic Region Code | Region Name [n1] | Number of Measures Installed | Percentage of Total Measures Installed | Number of Households Upgraded | Percentage of Total Households Upgraded
E12000001 | North East | 1745 | 44.09% | 1014 | 39.83%
E12000002 | North West | 621 | 15.69% | 291 | 11.43%
E12000003 | Yorkshire and The Humber | 831 | 21% | 711 | 27.93%
E12000004 | East Midlands | 40 | 1.01% | 14 | 0.55%
E12000005 | West Midlands | 149 | 3.76% | 93 | 3.65%
E12000006 | East | 228 | 5.76% | 152 | 5.97%
E12000007 | London | 206 | 5.2% | 147 | 5.77%
E12000008 | South East | 138 | 3.49% | 124 | 4.87%
E12000009 | South West | 0 | 0% | 0 | 0%
E92000001 | England Total | 3958 | 100% | 2546 | 100%
[n1] There have been no reported completed installations in South West.
Last updated | 2023-04-20
Next update | 2023-05-18

## T6
Table 6: Number of Measures Installed and Households Upgraded by Parliamentary Constituency
This worksheet contains one table. The table presents the number of households upgraded and measures installed across the whole scheme by parliamentary constituency.
Some cells refer to notes, which can be found below the table.
Tables may contain blank cells. These indicate that there is no data but are kept to allow easy comparisons between tables.
Freeze panes are used in this table. To turn them off, go to View, Freeze Panes, Unfreeze panes.
Area Code | Parliamentary Constituency Name [n1] | Number of Measures Installed [n2][n3] | Number of Households Upgraded [n2][n3]
E14000548 | Batley and Spen | 130 | 63
E14000581 | Bootle | 47 | 13
E14000590 | Braintree | ^ | ^
E14000611 | Bury North | 114 | 28
E14000624 | Central Suffolk and North Ipswich | # | #
E14000634 | Chingford and Woodford Green | 32 | ^
E14000640 | City of Chester | 102 | 55
E14000641 | City of Durham | 550 | 304
E14000650 | Coventry North West | 149 | 93
E14000658 | Darlington | ^ | ^
E14000668 | Doncaster Central | 82 | 66
E14000673 | Dulwich and West Norwood | 107 | 96
E14000677 | Easington | 965 | 501
E14000715 | Gravesham | 138 | 124
E14000723 | Halifax | 49 | 49
E14000733 | Hartlepool | # | #
E14000739 | Hemel Hempstead | 24 | 24
E14000740 | Hemsworth | 42 | 42
E14000746 | Hexham | 23 | 16
E14000749 | Hitchin and Harpenden | 27 | 16
E14000754 | Houghton and Sunderland South | 44 | 43
E14000763 | Islington North | # | #
E14000771 | Kingston upon Hull East | 35 | 35
E14000776 | Lancaster and Fleetwood | 73 | 73
E14000790 | Leyton and Wanstead | 11 | #
E14000795 | Liverpool, Wavertree | 34 | 8
E14000826 | Morley and Outwood | 73 | 73
E14000829 | Newark | # | #
E14000836 | Normanton, Pontefract and Castleford | 245 | 245
E14000861 | Northampton North | ^ | #
E14000862 | Northampton South | ^ | ^
E14000899 | Rochford and Southend East | # | #
E14000903 | Rother Valley | 143 | 106
E14000960 | St Albans | 76 | 38
E14000968 | Stevenage | 44 | 36
E14000982 | Sunderland Central | 14 | 14
E14001009 | Wakefield | 32 | 32
E14001013 | Walthamstow | 49 | 24
E14001014 | Wansbeck | 28 | 28
E14001020 | Washington and Sunderland West | 101 | 101
E14001036 | Westminster North | # | #
E14001044 | Wirral West | 31 | 31
E14001045 | Witham | 45 | 28
E14001053 | Workington | 220 | 83
[n1] Only areas where completed installations have been reported are included.
[n2] # refers to values between 1 and 4 inclusive which have been supressed to prevent disclosure.
[n3] ^ refers to values of 5 or more which have been supressed where another value within the group was suppressed to prevent disclosure.
Last updated | 2023-04-20
Next update | 2023-05-18

## T7
Table 7: Number of Measures Installed by Measure Group and Property Type
This worksheet contains one table. The table presents the number of measures installed across the whole scheme by measure type and property type.
Some cells refer to notes, which can be found below the table.
Tables may contain blank cells. These indicate that there is no data but are kept to allow easy comparisons between tables.
Freeze panes are used in this table. To turn them off, go to View, Freeze Panes, Unfreeze panes.
Property Type
Measure Group | Measure Type [n1] | Bungalow | House | Flat | Maisonette | Unknown | Total Measures Installed | Percentage Measures Installed
Insulation | All Insulation Measures | 574 | 1738 | 230 | 7 | 1 | 2550 | 64.43%
Insulation | Cavity Wall Insulation | 134 | 639 | 122 | 4 | 0 | 899 | 22.71%
Insulation | External Solid Wall Insulation | 36 | 206 | 88 | 0 | 0 | 330 | 8.34%
Insulation | Internal Solid Wall Insulation | 0 | 25 | 7 | 0 | 0 | 32 | 0.81%
Insulation | Loft Insulation | 370 | 842 | 13 | 3 | 1 | 1229 | 31.05%
Insulation | Pitched Roof Insulation | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Insulation | Flat Roof Insulation | 0 | 2 | 0 | 0 | 0 | 2 | 0.05%
Insulation | Bay Roof Insulation | 0 | 1 | 0 | 0 | 0 | 1 | 0.03%
Insulation | Room in Roof Insulation | 13 | 1 | 0 | 0 | 0 | 14 | 0.35%
Insulation | Solid Floor Insulation | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Insulation | Suspended Floor Insulation | 11 | 17 | 0 | 0 | 0 | 28 | 0.71%
Insulation | Under Floor Insulation | 10 | 5 | 0 | 0 | 0 | 15 | 0.38%
Insulation | Park Home Insulation | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Low Carbon Heat | All Low Carbon Heat Measures | 2 | 3 | 63 | 0 | 0 | 68 | 1.72%
Low Carbon Heat | Air Source Heat Pump | 2 | 2 | 0 | 0 | 0 | 4 | 0.1%
Low Carbon Heat | Ground Source Heat Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Low Carbon Heat | Hybrid Heat Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Low Carbon Heat | Biomass Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Low Carbon Heat | Solar Thermal | 0 | 1 | 0 | 0 | 0 | 1 | 0.03%
Low Carbon Heat | Electric Storage Heating | 0 | 0 | 63 | 0 | 0 | 63 | 1.59%
Heating Controls | All Heating Control Measures | 0 | 3 | 0 | 0 | 0 | 3 | 0.08%
Heating Controls | Heating Controls | 0 | 3 | 0 | 0 | 0 | 3 | 0.08%
Heating Controls | Hot Water Tank Insulation | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Heating Controls | Hot Water Tank Thermostat | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Windows and Doors | All Window and Door Measures | 67 | 391 | 45 | 0 | 0 | 503 | 12.71%
Windows and Doors | Double or Triple Glazing | 55 | 310 | 18 | 0 | 0 | 383 | 9.68%
Windows and Doors | Draught Proofing | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Windows and Doors | Energy Efficient Windows and Doors | 12 | 81 | 27 | 0 | 0 | 120 | 3.03%
Windows and Doors | Secondary Glazing | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Electricity Related | All Electricity Related Measures | 249 | 566 | 19 | 0 | 0 | 834 | 21.07%
Electricity Related | Solar PV | 32 | 217 | 8 | 0 | 0 | 257 | 6.49%
Electricity Related | Energy Efficient Lighting | 217 | 349 | 11 | 0 | 0 | 577 | 14.58%
Total | All Measures | 892 | 2701 | 357 | 7 | 1 | 3958 | 100%
[n1] 797 ventilation related measures have been installed but are not included in these tables while we consider their treatment in the statistics.
Last updated | 2023-04-20
Next update | 2023-05-18

## SHDF LA List
SHDF LA List - LAs that have signed up to the scheme
Local Authorities [n1] | LA Code | Region Code | Region Name
Blackpool Borough Council | E06000009 | E12000002 | North West
Hull City Council | E06000010 | E12000003 | Yorkshire and The Humber
City of York Council | E06000014 | E12000003 | Yorkshire and The Humber
Leicester City Council | E06000016 | E12000004 | East Midlands
Nottingham City Council | E06000018 | E12000004 | East Midlands
Stoke-on-Trent City Council | E06000021 | E12000005 | West Midlands
Plymouth City Council | E06000026 | E12000009 | South West
Thurrock Council | E06000034 | E12000006 | East of England
Milton Keynes | E06000042 | E12000008 | South East
Durham County Council | E06000047 | E12000001 | North East
Cheshire East Borough Council | E06000049 | E12000002 | North West
Cheshire West and Chester Borough Council | E06000050 | E12000002 | North West
Shropshire Council | E06000051 | E12000005 | West Midlands
Bedford Borough Council | E06000055 | E12000006 | East of England
Northumberland County Council | E06000057 | E12000001 | North East
West Northamptonshire Council | E06000062 | E12000004 | East Midlands
Fenland District Council | E07000010 | E12000006 | East of England
Allerdale Borough Council | E07000026 | E12000002 | North West
South Derbyshire District Council | E07000039 | E12000004 | East Midlands
East Devon District Council | E07000040 | E12000009 | South West
Stroud District Council | E07000082 | E12000009 | South West
Dacorum Borough Council | E07000096 | E12000006 | East of England
Three Rivers District Council | E07000102 | E12000006 | East of England
Gravesham Borough Council | E07000109 | E12000008 | South East
Folkestone & Hythe District Council | E07000112 | E12000008 | South East
Broadland District Council | E07000144 | E12000006 | East of England
Great Yarmouth | E07000145 | E12000006 | East of England
Norwich | E07000148 | E12000006 | East of England
Ashfield District Council | E07000170 | E12000004 | East Midlands
Newcastle under Lyme Borough Council | E07000195 | E12000005 | West Midlands
Stafford Borough Council | E07000197 | E12000005 | West Midlands
Tamworth Borough Council | E07000199 | E12000005 | West Midlands
Reigate and Banstead Borough Council | E07000211 | E12000008 | South East
Stratford-on-Avon District Council | E07000221 | E12000005 | West Midlands
Crawley Borough Council | E07000226 | E12000008 | South East
St Albans City & District | E07000240 | E12000006 | East of England
Stevenage Borough Council | E07000243 | E12000006 | East of England
West Suffolk Council | E07000245 | E12000006 | East of England
Greater Manchester Combined Authority | E08000003 | E12000002 | North West
Barnsley Council | E08000016 | E12000003 | Yorkshire and The Humber
Doncaster Council | E08000017 | E12000003 | Yorkshire and The Humber
Rotherham Metropolitan Borough Council | E08000018 | E12000003 | Yorkshire and The Humber
Newcastle City Council | E08000021 | E12000001 | North East
Sunderland City Council | E08000024 | E12000001 | North East
Coventry City Council | E08000026 | E12000005 | West Midlands
Walsall Metropolitan Borough | E08000030 | E12000005 | West Midlands
Leeds City Council | E08000035 | E12000003 | Yorkshire and The Humber
City of London | E09000001 | E12000007 | London
London Borough of Camden | E09000007 | E12000007 | London
Enfield Council | E09000010 | E12000007 | London
London Borough of Havering | E09000016 | E12000007 | London
London Borough of Hillingdon | E09000017 | E12000007 | London
London Borough of Hounslow | E09000018 | E12000007 | London
Islington Council | E09000019 | E12000007 | London
Royal Borough of Kensington & Chelsea | E09000020 | E12000007 | London
London Borough of Lambeth | E09000022 | E12000007 | London
London Borough of Sutton | E09000029 | E12000007 | London
London Borough of Waltham Forest | E09000031 | E12000007 | London
Westminster Council | E09000033 | E12000007 | London
Essex County Council | E10000012 | E12000006 | East of England
Nottinghamshire County Council | E10000024 | E12000004 | East Midlands
West Yorkshire Combined Authority | E47000003 | E12000003 | Yorkshire and The Humber
Liverpool City Region Combined Authority | E47000004 | E47000004 | North West
Tees Valley Combined Authority | E47000006 | E47000006 | North East
West Midlands Combined Authority | E47000007 | E47000007 | West Midlands
West of England Combined Authority | E47000009 | E47000009 | South West
[n1] Each local authority is leading one project except for Leeds City Council, Islington Council and London Borough of Hounslow that are leading two projects.