Annual Review (20/21 Ver.) - Summary Sheet

Programme Title			Preventing and Countering Violent Extremism (P/CVE) Programme
Programme ID			C-AFR-0006
Country and Region			East Africa – Kenya, Uganda, Tanzania, Ethiopia, and Mozambique
IATI Unique ID			CSSF-03-000018
HMG Partners / (Lead in bold)			FCDO, CTEN, Home Office
Total Budget			ODA: £ 13.5m				Non-ODA: -
Budget this FY			ODA: £ 4.155m				Non-ODA: -
Spend this FY			ODA: £ 4.194m				Non-ODA: £ 0.059m
Time Frame			Start Date: August 2019				End Date: July 2022
Outputs								Scale of Delivery
1.1 Intervention packages for at-risk individuals in violent extremism (VE) hotspots and hotbeds which (i) identify; (ii) refer (iii) advise/mentor; and (iv) safeguard to reduce risks of radicalisation and recruitment into violent extremism groups, are tested								4
1.2 Greater understanding of the risks of radicalisation and recruitment and VE dynamics, through research and analysis, to inform future policy and programming								4
2.1 Key non-state actors are provided with skills to support at-risk individuals that identify, refer, advise/mentor and safeguard them from radicalisation and recruitment into violent extremist groups.								3
2.2 Key non-state actors are provided with skills to investigate VE dynamics and better identify those at-risk of radicalisation and recruitment and make P/CVE policy and programme recommendations.								3
2.3 Key non-state actors are provided with skills and opportunities to engage government on P/CVE action.								2
3.1 Context-appropriate methodologies to improve government knowledge of radicalisation and recruitment, and of good P/CVE practice are developed.								3
3.2 Support to the development and implementation of P/CVE policy frameworks.								4
3.3 Interventions to improve relationships and interactions between national and sub-national governments, and state and non-state actors on P/CVE, are provided								3
4.1 Knowledge and learning utilised internally to inform adaptive management and shared externally with targeted P/CVE actors.								4
5.1 Programming is gender aware and conflict sensitive								4
Overall Scale of Output Delivery								3
Outcome Assessment	Over the last financial year, the programme made significant progress across all outcomes, with Collective Resilience Against Extremism (CREATE) firmly moving into the implementation phase. However, a three-month inception period, followed by limitations imposed by the C-19 outbreak and the subsequent decision to end activities in Ethiopia and Mozambique, meant CREATE’s geographical reach was more limited than originally intended. This assessment also takes into account the fact that the programme was originally set up with an unrealistic timeframe. While progress has been made, achieving lasting change in the P/CVE space requires a longer commitment than three years.
Overall Outcome Progress Rating:								Amber
Overall Risk Rating:								Medium
Summary of Programme Performance
Year		2016/17a		2017/18b		2018/19b				2019/20b		2020/21c
Programme Rating		B		B	A	A		A		B	B	Amber	3
Risk Rating		Medium		Medium		Medium				High		Medium
Programme changes during this period				Towards the end of the FY the programme agreed not to pursue further work in Ethiopia.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
- Funding of the Collective Resilience Against Extremism (CREATE) that seeks to reduce drivers, enablers and narratives of Violent Extremism (VE) by providing mentorship, referrals and psychosocial support to understand and assist individuals at risk of radicalisation or recruitment. It also builds the capacity of non-state actors, and state actors on PVE (Preventing Violent Extremism).
- The UK supported United Nations Office on Drugs and Crime (UNODC) to deliver training and technical assistance to Kenya Prison Services (KPS) to manage threats of radicalisation.

Key Results for FY 20/21:
- 274 (187 male, 87 female) at-risk individuals received support to increase their resilience and reduce their vulnerability to radicalisation and recruitment.
- 18 non-state actors were able to use knowledge and skills offered by the programme to engage state actors on matters relating to the prevention of violent extremism and to identify, mentor, refer, and safeguard at-risk men and women.
- Government bodies in three Kenyan counties took concrete steps mainstream prevention of violent extremism into their wider activities and budgets, and 977 government officials were able to strengthen their knowledge and skills on the prevention of violent extremism.

Key Lessons
- While having a single major implementer brings many advantages (such as consistency of approach and depth of relationships), this kind of programme should retain some flexibility with funding so that it can respond to changing circumstances and pursue different approaches.
- While the programme has a regional remit and structures, overall, it has demonstrated the difficulties of pursuing a genuinely transnational approach, given that the circumstances and organisations are particular to each country.
- Given the pioneering nature of some of the work and focus on behaviour change, demonstrating impact and learning lessons in the P/CVE space requires long-term programming – a more realistic time frame would be 5-10 years.

Key Recommendations for FY 21/22

There is an urgent need to implement a sustainable and responsible exit strategy – to preserve the impact of the programme, maintain relationships and ensure against leaving organisations or individuals in a vulnerable position. Discussions should take into account the fact that CREATE’s contract had a three-month inception period followed by disruptions due to COVID-19, which has meant that it has only recently begun to show tangible results. There is a risk that these could be lost or diminished without a sustainable exit.

Leverage diplomatic engagement to build political will and support within countries, enabling CREATE’s work to be done in a safe way, and multiplying the impact that CREATE has in terms of its government engagement and facilitating non-state actor engagement. Ensure work on CREATE is included in briefings for diplomatic engagements with key stakeholders.

More systematic knowledge sharing and lesson learning across the programme between Mercy Corps and downstream partners. In some cases, partners were hugely positive about the engagement, collaboration and willingness of Mercy Corps/Wasafiri of sharing lessons to help with their work, but in other cases it was suggested they could be more proactive in this engagement.