Programme Completion Review
Programme Title:	EAST AFRICA SECURITY PROGRAMME
Programme ID:	C-AFR-0007
Country and Region:	East Africa
IATI Unique ID:	CSSF-03-000021
HMG Partners (Lead in bold):	Ministry of Defence; BPST; FCDO
Total Budget:	£9.695m	ODA: £1.639m	Non-ODA: £8.056m
Total Spend:	£9.544m	ODA: £1.516m	Non-ODA: £8.027m
Time Frame:	Start Date: April 2015	End Date: March 2021

Outputs	Score
Strengthened Kenyan led internal governance and management of the counter- improvised explosive device (C-IED) capability.	4
C-IED training delivered by a more capable and functional UK mentored Kenyan and EA staffed training cadre.	4
UK political and policy engagement in support of Kenyan, regional and international engagement in regional C-IED capability development.	3
Increasingly regional and relevant force elements acquire the knowledge and skills to operate in a high threat IED environments through receiving training by the wing.	3
Final Overall Scale of Output Delivery	4

Outcome Assessment: significant achievement in building Kenyan led, Counter-IED capability, supported by a functional training institution. There is less evidence of this being sustainable and regionally supported as a centre of excellence for C-IED training in East Africa. Enhanced capability and effectiveness of C-IED trained EA forces deployed in high-threat IED environments has been strongly achieved in respect of Kenyan forces (including border police); and partially achieved in relation to other Troop Contributing Countries (TCCs)/ countries requiring a C-IED capability.
Final Overall Scale of Outcome Achievement:					3
Overall Risk Rating:					Medium
Summary of programme performance
Year	2016/17		2017/18			2018/19		2019/20		2020/21 (PCR)
Programme Score		B	A/B	B		A	A	A	A	4	3
Risk Rating	Low		Low			Low	Low	Low	Medium	Medium

What support did the UK provide?
- The programme evolved from the CSSF Enhancing Regional Capacity against Insecurity and Organised Crime programme in FY2015-16, which included C-IED capacity-building support to the Humanitarian Peace Support School (HPSS) in Embakasi (Nairobi) through the British Peace Support Team (BPST).
- In FY2016-17, the CSSF EA Security programme focused on continued support to C-IED through BPST together with Peace Support Operations (PSO) capacity, and a continued focus on Small Arms and Light Weapons (SALW) and Tackling Illegal Wildlife Trade (IWT).
- In FY2017-18, the programme focus narrowed exclusively on the C-IED component. Since 2017, BPST(A) has been the sole implementing partner providing support to the HPSS CIED Wing to develop this into a regional centre of excellence and expand technical training to security forces across Kenya and the region. This support includes financing a Threat Mitigation Adviser (TMA), seconding two British military officers and sponsoring courses. Quality assurance has been provided by the Defence Explosive Ordinance Disposal Munitions and Search (DEMS) Training Regiment. A Training & Development Cell (TDC) has also been established within HPSS.

What Results Did the Programme Deliver?
This PCR covers the period April 2016 to end March 2021. The main focus of the PCR is on the BPST-managed CIED-focused component from April 2017 onwards, and for the purposes of programme scoring, the PCR has used the period of programme implementation covered by the current programme document (PD) and results framework (RF), from April 2018 to present.
- There has been a significant achievement in building a Kenyan led, Counter-IED capability supported by a functional training institution. There has been less evidence of this being sustainable and regionally supported as a centre of excellence for C-IED training in East Africa. Enhanced capability and effectiveness of C-IED trained EA forces deployed in high-threat IED environments has been strongly achieved in respect of Kenyan forces (including border police); partially achieved in relation to other TCCs/ countries requiring a CIED capability.
- Limited attention has been paid to assessing the impact level (in terms of the enhanced ability of those trained to save lives in the field). Anecdotally, C-IED training has helped to reduce both PSO and civilian casualties. Impact is mainly in one country (Somalia), within Sector 2 of AMISOM’s operations (supported by Kenyan forces).
- The programme performed strongly in building a Kenyan-led and managed centre of expertise. Good progress was also made in developing an increasingly competent cadre of expert trainers from the region, although these remain mainly Kenyans and to a lesser extent Ugandans). Other outputs intended to support UK regional political engagement to promote C-IED training and the development of supportive national policies and institutions. While there was limited systematic assessment of what was achieved, there was evidence of excellent progress with the Government of Kenya, but much less so with other Troop Contributing Countries (TCCs) and the African Union (AU).

Will Results be Sustained?
Sustainability was built into the developing a Kenyan-led and regionally supported C-IED capability strand, supported by a functional training institution centre. However, as highlighted as an issue of concern in previous ARs, sustainability remains a concern, with many of the levers required to deliver this sustainability out of BPST(A)’s control or influence.
Efforts were made to engage with other international partners providing support in this area (Germany, US etc.) to look at future support. However, the Government of Kenya asked HMG for continued funding of the C-IED Wing and this has reportedly been agreed at a political level.

What Lessons Have Been Learnt?
CIED approaches
- More work is needed to embed C-IED policies and capacity within the AU, its member states and institutions.
- National and country level C-IED frameworks, legislation, policies, inter-agency strategies and institutional structures are critical and should be a priority for future support/capacity building. In order for the AU, PSOs and member states to be able to counter IED threats and for the CIED wing to contribute to these capacities, future support must also be provided to assist Eastern African states to develop national structures in CIED. Other priorities include strengthening of forensic capacities and to work to build the capacity and equipping of border police.
- Good coordination with other donors and training providers is essential to ensure coherence.
- Communities can play a key role to raise their CIED awareness and willingness to work with the authorities in detecting threats, in a context/culturally sensitive and gender-sensitive way.
Institutional development
- The institutional development focus was essential to ensure the CIED-wing functions independently within HPSS/IPSTC.
- Building a more regionally-oriented centre of excellence will require a different governance structure, training delivery and financial model, as well as greater political cooperation between TCCs, supported by stronger involvement by AMISOM and political support from the AU Commission and key Member States.
- A strong and functional lessons learned capacity is essential to inform training and institutional governance.
- The language barrier is a critical factor in the accessibility of training. Provision needs to be made for this to build greater participation from around the region.
- Full accreditation by both the UN/AU is essential for HPSS CIED to be a centre of excellence for PSO training which directly develops the capacity of UN and AU missions.