Programme Completion Review (20/21 Ver.) - Summary Sheet

Programme Title:		Niger Delta and Maritime Security Programme
Programme ID:				C-AFR-0016
Country and Region:				Nigeria, West Africa
IATI Unique ID:				CSSF-03-000022
HMG Partners (Lead in bold)				FCDO, MOD (BRITISH MILITARY ADVISORY TRAINING TEAM)
Total Budget 18-21		ODA: £1.800m					Non-ODA: £1.65m
Total Spend 18-21		ODA: £1.993m					Non-ODA: £1.407m
Time Frame		Start Date: 01/04/2018					End Date: 31/03/2021
Total Budget 20-21		ODA: £0					Non-ODA: £0.45m
Total Spend 20-21		ODA: £0					Non-ODA: £0.157m
Outputs 2020-21							Score
1. Increased understanding of the nature and scale of maritime insecurity and piracy in the Gulf of Guinea (GoG) and the costs to UK, International Community and Nigeria/other coastal states.							4
2. Increased capacity of Western Naval Command to conduct maritime interdiction operations.							4
3. Increased capacity of the Nigerian Navy (NN) Special Boat Service to conduct maritime interdiction operations.							4
Final Overall Scale of Output Delivery							4
Outcome Assessment: There is evidence of all outcomes being achieved. The Nigeria Navy’s Western Naval Command and Special Boat Service are conducting maritime interdiction operations at an increased level of effectiveness. The UK is engaging with G7++ Friends of the Gulf of Guinea (FOGG) through the co-chair role for 2021, and that this is set to continue through Dec 2021.
Final Overall Scale of Outcome Achievement:							4
Overall Risk Rating:							Medium-High
Summary of Programme Performance
Year	2016/17a		2017/18b			2018/19b				2019/20b		2020/21c
Programme Rating	B / (BMATT) / A / (Niger Delta Stabilisation - NDS)		B (BMATT) / A / (NDS)		B (BMATT) / A / (NDS)	Output / B		Outcome / B		Output / A	Outcome / A	Output / 4	Outcome / 4
Risk Rating	Medium (BMATT) / Medium (NDS)		Medium (BMATT) / High (NDS)			Medium/High				Medium		Medium-High
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide? The FY 20/21 programme had a reduced focus from the original programme conception. The Annual Review of the 19/20 programme captured earlier delivery across three streams of activity: Security and Governance; Economic Development; and Political Analysis. For FY 20/21 only activity on Security continued, including:
- Training to three boarding teams (24 personnel) of the Nigerian Navy Special Boat Service on non-compliant boarding techniques, in a manner compliant with International Humanitarian Law (IHL) and Human Rights Law. This was delivered via the Intermediate Operators Course: Vessel Board, Search and Seizure (IOC VBSS), delivered in Lagos. This tactical course is aimed at increasing Nigerian capacity to conduct maritime interdiction operations.
- Two Nigerian Navy officers from the Western Naval Command were sent to the UK for attendance on the International Lieutenants’ Course on Surface Warfare as a gradual method of increasing the capacity of Western Naval Command to conduct maritime interdiction operations.
- The support enabled the production of a GoG Maritime Security Research report, a resource for HMG intended to inform decision-making in FY 20-21 and beyond.

The global COVID-19 pandemic and the pause in engagement and training for Nigerian Defence and Security actors following the “End Special Anti-Robbery Squad (SARS)” protests disrupted delivery significantly.

What Results Did the Programme Deliver? Will they be Sustained?
- Nigerian Navy (NN) interdictions against maritime crime, including arrests in the Gulf of Guinea, are increasing.
- Enabled support that helped ensure the introduction of the Suppression of Piracy and Other Maritime Offences Act 2019.
- Brokered agreement between Nigerian Government departments and maritime law enforcement agencies of a protocol for evidence collection on Arrest, Detention and Prosecution of Vessels and Persons in Nigeria’s Maritime Environment.
- The launch by the Ministry of Niger Delta Affairs of a website for citizens to monitor the delivery of the Stakeholder Implementation Work Plan (SIWP) – a framework for the coordination of investments in development and stabilisation interventions in the Niger Delta Region.
- The GoG Maritime Research Report, published January 2021. Prepared for HMG, the report provided a detailed description and analysis of the maritime insecurity context and issues in the GoG, and a range of approaches and options to inform decision-making in FY 20-21 and beyond by the UK.

There are early signs that the Suppression of Piracy Law will have lasting impact well beyond the programme and that it may well encourage regional states to pass Acts of their own. The SIWP may have lasting impact, though needs championing. Training to the Nigerian Navy has not yet delivered behavioural shifts which would require longer term engagement. The GoG Maritime Research report could inform longer term HMG thinking and programming.

What Lessons Have Been Learnt?

- Project design and inclusive, and explicit, decision-making around prioritisation and change: The NDMS Programme was reduced but without clear reasoning behind the new prioritisation. This is essential so all involved in the programme (from implementing partners to project sponsors) understand ambition levels, plans and their roles.
- Tactical delivery for strategic effect: The “End SARS” protests in Nigeria highlighted the potential for instability as a result of security actors' non-adherence to IHL and Human Rights Laws. Whilst very tactical in nature, the programme’s training of front-line forces in HRs-compliant approaches can help catalyse more Nigerian-led, training mechanisms. Evidence gleaned from interviews indicated that, should tactical training be built upon and invested in, this is a realistic possibility.
- Programmes benefit when there is sustained diplomatic engagement: the programme aimed to inform high-level UK and partner political engagement. When the UK has engaged well within G7++, it has been when those involved had awareness of strong regional dynamics and sensitivities and were able to navigate them. This sort of engagement needs routine championing.
- Programmes need to focus on scale-up, local ownership and sustainability from the outset: This should be embedded in programme design and based upon a realistic assessment of what is possible. More concrete attention is required on how this will happen, rather than assuming a demonstration of effect will be sufficient.
- Conflict Sensitivity, Gender and Human Rights: The gender and human rights impacts of disinvesting in programming in the Niger Delta should be captured. A gender analysis of dynamics in the Niger Delta, as recommended in the Gulf of Guinea Maritime Research report, should be conducted.