Programme Completion Review (20/21 Ver.) - Summary Sheet

Programme Title	Nigeria - Covid-19 Direct Response Programme
Programme ID	C-AFR-0014
Country and Region	Nigeria, West Africa
IATI Unique ID	CSSF-03-000034
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office
Total Budget	ODA: £1.116m	Non-ODA: £0.0m
Total Spend	ODA: £1.242m	Non-ODA: £0.0m
Time Frame	Start Date: April 2020	End Date: March 2021

Outputs	Scale of Delivery
1. Informed and improved messaging content on Covid-19	3
2. Capacity of key programme beneficiaries built and enhanced	3
3. Key audiences engaged	3
4. Quality and timely information dissemination and flows to the public and within the Federal Government of Nigeria (FGN)	3
Final Overall Scale of Output Delivery	3

Outcome Assessment	The programme was designed in less than a month to respond to the emerging pandemic. The initial programme document is very short and did not contain an overarching outcome statement, theory of change or results framework to assess progress against. A retrospective theory of change was developed once the programme started. The initial projects were expected to be completed within 5 to 9 months, although there were some no-cost extensions resulting in some projects lasting up to 3 months longer than this. The short duration of projects has given little time for outcomes to be seen. Also, during emergency response programmes, the focus is on more immediate results rather than on longer-term outcomes. For these reasons, this Programme Completion Report scores outputs but does not score outcomes (although an indicative Red-Amber-Green rating is applied to each outcome).
Final Overall Scale of Outcome Achievement:		Not scored (but can be given an overall amber/green rating – the programme is mainly on track to deliver the outcomes)
Overall Risk Rating:		Medium-Low

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A		N/A	N/A	N/A	N/A	3	N/A
Risk Rating	N/A	N/A		N/A		N/A		Medium-Low
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
- Support to the Risk Communications pillar of the Presidential Task Force (PTF) leading Nigeria’s response to the pandemic, including through technical assistance and funding targeted at polling to inform future communications - implemented by the UK’s Government Communications Service International (GCSI).
- Targeted media and communications to increase audiences’ awareness of and adherence to coronavirus prevention and management measures and creation of space for discussion of related social and governance issues – implemented by BBC Media Action (BBC-MA).
- Sensitisation of at-risk communities about threats of Covid-19 and contribution to the mitigation of the impact on security and stability – implemented by the Policy and Legal Advocacy Centre (PLAC) working through the Kukah Centre.
- Capacity building for the Nigerian Police Force to improve their interaction with the public and monitoring of the conduct of security forces enforcing implementation of Covid-19 protocols – implemented by the CLEEN Foundation.
What Results Did the Programme Deliver? Will they be Sustained?
- GCSI provided strategic communications training and rapid Covid-19 polling data on citizen attitudes and behaviour to the Risk Communications pillar of the PTF. 15 polls were funded by HMG. This helped the FGN to provide more effective Covid-19 messaging to the public and helped increase confidence within the government. Efforts were made to engage on communications at the State level through the Governors Forum but with limited results in communications support at this level.
- BBC-MA trained 130 journalists in 50 radio stations on communicating Covid-19 messages, delivered through 228 radio programmes in Hausa and Pidgin English languages with an estimated national reach of 40.6 million. Data from GCSI polling and Kukah engagement with vulnerable communities was used to make messaging more effective. Facebook messaging platforms had 13.8 million views over 6 months and helped to counter misinformation surrounding Covid-19. Communications material was also used to support virtual town hall meetings which discussed Covid-19 issues and were streamed live. Handbooks were produced on reporting on emergencies for use of FCDO and local radio.
- Kukah worked with 144 field officers in 72 local government areas to get data on Covid-19 related behaviour and perceptions. This data was used by Kukah and by BBC-MA for more effective communications. Kukah reached an estimated 1.8 million people on social media and 5 million via radio and TV jingles with Covid-19 messaging. Information on instability was provided to the National Peace Commission which helped to strengthen links and future working relationships. The 144 field officers gained data collection and communication skills but would require more funding to continue their work at the community level.
- CLEEN Foundation improved an App which was used by 774 observers to report on 670 human rights violations by the police and security forces during the Covid-19 outbreak. The App allows uploading of photographs and questionnaire data and can continue to be used. However, the response rate of police and security forces was disappointing with little evidence of actions being taken on the basis of alleged violations.

What Lessons Have Been Learnt?
- To make best use of synergies across strategic communication interventions, it is important to develop an overall theory of change and results framework at the outset. The Covid-19 response programme in Nigeria was set up extremely quickly but would have benefitted from more planned integration across projects from the beginning.
- An effective strategic response to emergencies requires a whole of government response. The Covid-19 response programme in Nigeria worked well at the Federal level but more could have been done to engage with states and to support stronger coordination of the response at a more decentralised level.
- Effective community messaging needs to be context specific and to focus in particular at countering fake news. The programme paid good attention to real-life issues emanating at the community level and feeding these back to support more effective Covid-19 messaging.
- The Covid-19 response programme encompassed a good mix of interventions, but more could have been done to engage with security agencies and police to support the follow-up of alleged human rights violations. If you increase the demand for police accountability you need to also build the capacity and will to address that demand.
- It is important to hold regular coordination meetings between programme partners so that synergies across interventions can be effectively harnessed. Having a single programme manager across the whole of the Nigeria Covid-19 response programme would have made this coordination easier.