Programme Completion Review (20/21 Ver.) - Summary Sheet

Programme Title	Nigeria Countering Organised Crime and Corruption
Programme ID	C-AFR-0013
Country and Region	Nigeria (Benin, Togo)
IATI Unique ID	CSSF-03-000006
HMG Partners	NCA (CPS, IEI, Border Force, Home Office)
Total Budget	ODA: 2020/21 = £2.274m	Non-ODA: 2020/21 = £0.694m
Total Spend	ODA: 2020/21 = £2.141m / Total 2015/21 = £20.82m	Non-ODA:2020/21 = £0.694m / Total 2015/21 = £0.694m
Time Frame	Start Date: 2015/16	End Date: 2021

Outputs					Scale of Delivery
Capacity of Joint Border Task Force (JBTF) is improved to conduct effective investigations into SOC which exploits Nigeria's border vulnerabilities and delivers criminal justice outcomes					4
Capacity of Operation OKRA is improved to deliver key SOC-related intelligence gathering and analysis in line with good practice					3
Capacity of Nigerian Police Force (NPF) and Department of State Services (DSS) dedicated anti kidnap units (AKCU) is improved to deliver kidnap response capacity in line with good practice					3
NB: These outputs reflect changes in the results framework agreed in 2021 as part of the final ‘extension’ year of the programme. Previous outputs (and outcomes) descriptions can be found in the 2019/20 Annual Review.
Final Overall Scale of Output Delivery					3
Outcome Assessment / The 2020/21 Programme was a continuation of Serious Organised Crime (SOC) activity led by the National Crime Agency, which began in 2015/16. The 2019/20 Annual Review was complementary regarding the progress made up to the end of the 2019/2020 financial year. Overall, it found that: / “Vetted units are now in place and functioning well. They have established leadership, recruitment and succession plans for maintaining capacity in the future. They are now located appropriately and continue to receive mentoring from experienced advisers who are trusted and valued by their counterparts. JBTF and Operation OKRA Units have played critical roles in the investigation and prosecution of corruption and trafficking cases. A combination of training, mentoring, procedural development and material provision has ensured that human rights compliance is high…”. / 2020/21 constituted a final year of support to embed progress and ensure the greatest chances of sustainability. Its intended outcomes were: / Improvements in target Units’ identification, detection, pursuit and disruption of priority Serious Organised Crime threats to UK, Nigerian, Benin and Togo and Partner/other country interests. / Expansion in target Units' relationships and collaboration activities with other units/agencies. / A new Results Framework was developed for 2020/21, reflecting the final year of CSSF funding. 2020/21 activity has been heavily affected by COVID-19, which led to the draw-down of most HMG project staff and reprioritisation by partners. IT challenges and uncertainty regarding the future of project activities following UK funding reductions created additional pressures. Subsequently, implementation has been affected. Overall, most milestones have been met and a contribution towards achieving outcomes has been made. The project leads and their Nigerian counterparts have demonstrated an impressive ability to adapt, either delivering existing commitments differently, or establishing new and more achievable priorities.
Final Overall Scale of Outcome Achievement:					3
Overall Risk Rating:					Medium
Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b			2019/20b		2020/21c
Programme Rating	A	A+	A+	A		A	A	A	3		3
Risk Rating	Medium	Medium		High			Medium		Medium
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
Three project leads each working with a small team comprised of UK and Nigerian colleagues led the implementation of capacity building programmes in Abuja, Lagos and in Benin and Togo in support of local law enforcement partners. This capacity building included comprehensive programmes of curricula development and training delivered by a combination of Nigerian and UK actors, with an emphasis on creating local capacities to deliver training; on the job mentoring and advice through the project teams and other specialists; limited amounts of equipment and support for the provision of facilities.

What Results Did the Programme Deliver? Will they be Sustained?
- Nigeria - Operation NODA, led by programme partners which investigated the trafficking of Nigerian women and girls to Russia for sexual exploitation, resulted in the conviction of three traffickers who were sentenced to a total of 58 years imprisonment.
- Nigeria – The initial failure to identify those responsible for the murder of a UK National during an attempted kidnap in 2019 led to the case being passed to the Nigerian Police Force Anti Kidnap Unit (AKCU). This Unit was supported through the programme, which identified those responsible, enabling the commencement of judicial process.
- Benin - In December 2020, the law enforcement unit supported by the programme seized the largest quantity of cocaine in Benin’s history – 754.5kg concealed in a shipment of wood imported from Brazil. The operation resulted in the arrest and conviction of six people involved, including the organiser, who was deported from Nigeria to stand trial. All six defendants were convicted and sentenced to 15 years imprisonment each in May 2020.
- The Units established in each of the three programme areas are now recognised as part of the architecture of their agencies, turnover of staff is largely predictable and manageable, and locally led capacity building will be sustainable with lower input levels in the future.
- As CSSF funding ends, alternative sources, both within HMG and involving other international actors including UNODC and Germany, have been identified, providing assurance that project support will be maintained in the future to further embed the benefits of the programme.
What Lessons Have Been Learnt?
- Experienced project officers working closely with partner agencies have been essential for building and maintaining trust, ensuring momentum and providing links to wider HMG interests.
- Hands-on support can have a significant effect in terms of enforcement outcomes and capacity building; but to achieve sustained strategic effect requires ongoing political engagement.
- This reinforces the importance of joined up effort across HMG with high-level political and diplomatic engagement, empowering and supporting ongoing operational activity.
- Expecting integration between agencies is challenging and progress should be expected to be gradual and may require high-level engagement to set the policy context requiring collaboration.
- Technical projects such as those supported by the Nigeria SOC programme rely to some extent on functioning technology, which may be outside the ability of the project to influence directly.