Programme Completion Review (20/21 Ver.) - Summary Sheet

Programme Title		Nigeria Women, Peace and Security Programme
Programme ID		C-AFR-0015
Country and Region		Nigeria, Africa
IATI Unique ID		CSSF-03-000035
HMG Partners / (Lead in bold)		Foreign & Commonwealth Office (FCO) / (Foreign, Commonwealth & Development Office (FCDO) from 2/9/2020)
Total Budget		ODA: £0.81m			Non-ODA: £0
Total Spend		ODA: £0.686m			Non-ODA: £0
Time Frame		Start Date: October 2020			End Date: 31 May 2021
Outputs							Score
The capacity, coordination and connectedness of women’s rights organisations, politicians and women peace actors is strengthened, including their ability to respond to COVID-19 priorities.							3
The application of evidence informed approaches to violence against women and girls (VAWG) prevention and response is strengthened through development of a model for the application of the Violence Against Persons (Prohibition) Act, targeted technical support, learning and political influencing.							4
Evidence and analysis is generated to inform the UK’s ongoing work on Women, Peace and Security (WPS) and influence that of other key actors in Nigeria.							4
Final Overall Scale of Output Delivery							4
Outcome Assessment: The first indicator on the satisfaction of Gender Based Violence (GBV) survivors with services received was exceeded in two states (98% achieved, 90% target) and was not measured in the third state, Niger. The second indicator for guidelines adopted by two state-level peace-building agencies was achieved in Plateau State but is still in progress for Kaduna.
Final Overall Scale of Outcome Achievement:				3
Overall Risk Rating:				High
Summary of Programme Performance
Year	2016/17a		2017/18b	2018/19b		2019/20b	2020/21c
Programme Rating	N/A		N/A	N/A		N/A	4	3
Risk Rating	N/A		N/A	N/A		N/A	High
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
- The Programme funded two projects: (1) Strengthening State Capacities and Women’s Participation in COVID-19 Response and Broader Peacebuilding Initiatives, implemented by UN Women; and (2) Women-Led Integrated Protection Action Against Gender-Based Violence (WIPe GBV), implemented by Action Aid Nigeria.
- The programme contributed to the UK National Action Plan (NAP) on WPS by focusing on Women’s Decision Making and Gender Based Violence. The programme was a key delivery mechanism for the UK-Nigeria G7 WPS Partnership Initiative and aligned with the 2020 Nigeria NSC Strategy.
- This programme built on the WPS Scoping Study (March 2020) and the NAP evaluation.

The programme was originally designed for three years. However, ODA allocations were reassigned after the first phase (FY 20/21). The premature closure of the programme diverted focus to closure activities, before substantive programme outputs were being delivered.

What Results Did the Programme Deliver? Will they be Sustained?
- Emergency funding to Women’s Rights Organisations (WROs) to deliver frontline protection services in response to Covid-19 related spikes in GBV in Niger, Edo and Adamawa states. These include psychosocial services, emergency health support, referrals to state services and livelihoods support.
- Support to develop and implement a collaboration framework between civil society and politicians on gender responsiveness of Nigeria’s Covid-19 response.
- Developing an action plan in response to the Violence Against Persons Prohibition Act (VAPP) in Bauchi state.
- Assessment of women’s roles in mediation in farmer-herder conflicts in Plateau and Kaduna states.
- Research on the risks to women human rights defenders and women peacebuilders in Nigeria.
- Reached 332 survivors of GBV with emergency support in 3 conflict affected states (Adamawa, Edo and Niger). Despite the short time period, financial and technical resources were quickly dispersed to women’s rights organisations (WROs). GBV reporting levels increased as WROs raised awareness of services and how to access them.
- WROs were able to provide quality services, including GBV response and livelihoods training, which positively changed lives. Without replacement funding, the WROs are concerned about whether they will be able to provide services to meet the increased demand created through the programme’s community sensitisation activities.
- In Bauchi state, a Costed Model Action Plan (CMAP) for the implementation of the VAPP was developed in partnership with government and civil society. An Advisory Committee and a Technical Committee for the implementation of the CMAP going forward were established, inaugurated by the government, and trained by the programme.
- A Coalition of women leaders from government, civil society and the private sector was established to strengthen women’s meaningful participation and leadership in the Kaduna State government’s COVID-19 response and recovery efforts. Through the programme, a collaborative framework and one-year costed action plan with activities to monitor government’s actions and policies on enhancing gender responsive recovery plans and intervention, was developed. A mapping of women with mediation capacity was also conducted in 18 states.
- Five knowledge products were created, including two learning briefs, and reports on human rights defenders, mediation in farmer-herder conflicts and women mediators.

What Lessons Have Been Learnt?
- The programme was very ambitious in the outcomes it hoped to achieve in a short period of time and was able to achieve strong results, despite the tight timeframe and capacity issues. In particular, it was possible to mobilise resources to WROs working on GBV and achieve results by reaching GBV survivors with quality services in a short period of time. Having the right partners and strong working relationships and partnerships between FCDO, delivery partners, sub-grantees, governments, and civil society was also important for fast mobilisation and results.
- The WROs working on GBV response are concerned about how services will be maintained after funding has been cut and the programme has ended. Stopping GBV response funding in the early-mid stages of implementation carries a high risk of causing harm in communities.
- A more structured process around programme design and implementation would have been beneficial. Whilst a board was not required for a programme of this size, more structure, support and engagement from CSSF management would have improved programme management and accountability.
- There was a strong focus on learning throughout the programme, despite the short duration of the programme. This was successful in generating evidence to fill gaps identified in the scoping study and ensured that the activities conducted would have influence on future programming despite the early closure.
- Strategic partnerships with government promoted ownership and political buy-in for the development of CMAP. Diverse actors from community level to the State Cabinet were engaged. As a result, the Ministry of Budget and Economic Planning issued a directive for Ministries, Departments and Agencies (MDAs) to include budgets for VAPP Act implementation from 2022.
- A holistic approach to GBV services was effective in meeting survivors’ needs, reflected in the high satisfaction rates (98% of survivors were satisfied with the GBV services received). Survivors were supported through access to evacuation and received livelihoods support, which provided alternate options to going back to situations of abuse due to financial dependency.
- The development of a national database of women engaged in mediation and dialogue holds significant prospects for enhancing women’s inclusion in formal processes. It would have been useful to have a greater focus on sustainability for the database, particularly who would maintain and use it in the longer-term. Without funding, it is unclear how the database will be managed going forward.
- Forming the Women’s Coalition, provided an opportunity to build the skills of members and engage with MDAs, while working with public facing media increased the need for MDAs to be more accountable.