Programme Completion Review (20/21 Ver.) - Summary Sheet

Programme Title		North East Nigeria (NEN) Security and Stabilisation Programme
Programme ID		C-AFR-0019
Country and Region		Nigeria, West Africa
IATI Unique ID		CSSF-03-000008
HMG Partners / (Lead in bold)		Foreign Commonwealth and Development Office (FCDO) / Ministry of Defence (MOD)
Total Budget		ODA: £13.92m				Non-ODA: £15.84m
Total Spend		ODA: £13.67m				Non-ODA: £15.97
Time Frame		Start Date: April 2019				End Date: March 2021
Outputs							Scale of Delivery
Defence Engagement: enhanced capabilities of Lake Chad Basin (LCB) Security Partners.							3
Stabilisation: Police and other security actors have increased capacity to deploy into target areas and are viewed as accountable to local citizens.							4
Community security: Increased capacity of target communities, including women, to participate in conflict resolution and support peacebuilding.							3
Rehabilitation and reintegration: Increased willingness of target communities to accept the reintegration of conflict-affected groups including women and children.							4
Cross cutting: Enhanced programme coherence and mainstreaming of Monitoring, Evaluation and Learning (MEL), gender and Value for Money (VfM).							3
Final Overall Scale of Output Delivery							3
Outcome Assessment / The NEN programme was required to deliver in a highly challenging policy and operational environment. Despite this, it made good progress in meeting the majority of its outcomes. Whilst a new 20/21 results framework with more realistic indicators and targets contributed, the review team noted increased political access and influence; improved coordination and coherence; and greater programmatic leverage of other donors to achieve policy and programme objectives. Investments made in staffing, research and planning are paying dividends, and provide a strong foundation for future regional programming.
Final Overall Scale of Outcome Achievement:					3
Overall Risk Rating:					High
Summary of Programme Performance
Year	2016/17a		2017/18b		2018/19b			2019/20b		2020/21c
Programme Rating	A		A	B	A		B	B	B	3		3
Risk Rating	High		High		High			High		High
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
- Training and capacity building for the Armed Forces of Nigeria to strengthen their ability to engage and defeat enemy combatants, comply with International Humanitarian Law (IHL) and law of armed conflict (LOAC), and positively engage with marginalised groups (delivered through British Defence Section (BDS), British Military Advisory and Training Team (BMATT) and Op TURUS).
- Senior Military Advisory (SMA) support to Cameroon to develop and deliver a programme of capacity building activity intended to help enhance the ability of the Cameroonian Security Forces to counter the threat posed by Boko Haram (BH)/Violent Extremist Organisations (VEOs) – including Islamic State West Africa (ISWA).
- Advice and support to ensure the relevant actors in the Nigerian MOD, Defence HQ and AFN leadership are empowered and encouraged to implement Defence Reform and influenced to focus on priority areas.
- Support to the United Nations Development Programme (UNDP)’s Nigeria and Cameroon national windows of the Regional Stabilisation Facility (RSF), which aims to address the needs of immediate stabilisation through a rapid response package of support that is time-bound, localised, and integrated.
- Support to the (IOM) implementation of the "Strengthening the Rehabilitation and Reintegration of Male and Female Low-Risk Former Non-State Armed Groups (NSAG) Associates through Nationally-owned Processes” project (Operation Safe Corridor).
- Help to the Nigerian police in Borno to (i) improve conditions of police stations and police barracks (ii) improve police communications capability through the provision of long-range communications equipment (iii) encouraging more effective deployment through individual pre-deployment training and ‘life support’ kits.
- The implementation of two International Alert projects: i) Hadin Kan Mu Karfin Mu (Our Unity, Our Strength) aimed at reinforcing the resilience and reintegration of conflict affected women and children and promoting community peacebuilding in North East Nigeria. ii) a Public Safety and Security project to build a system for targeted communities in Borno State to address emerging safety and security concerns through more inclusive, coordinated and accountable security management.
- Financed efforts to improve government security forces’ willingness and capabilities to better protect civilians in northeast Nigeria through the NGO CIVIC.
- Supported a Nigerian Strategy for Peace and Development in the North East through Inter Mediate.

What Results Did the Programme Deliver? Will they be Sustained?
- Improvements in partner cooperation on LCB regional stability concerns.
- Increased host nation political and military access and engagement on regional security matters.
- Commencement of Defence Transformation process through establishment of dedicated Committee and sharing of UK experience and expertise.
- Improved civil-military regional cooperation in countering extremist threats between Cameroon and NE Nigeria with the repelling of Boko Haram militants from Banki. The cross-border civil-military cooperation between Nigerian and Cameroonian security, government, and community actors was a particular success.
- Increasing numbers of targeted populations who feel safe and secure within their communities and who feel that security actors are becoming more effective and accountable. The Regional Stabilisation Facility (RSF) supported community stabilisation committees have made useful contributions managing herder/farmer disputes and cross-border Internally Displace Person (IDP) issues in Banki and Damboa.
- Successfully integrated women and girls previously rejected by their communities, who now feel less marginalised within their communities.
- Improved effectiveness of multilateral 4DR and Stabilisation mechanisms following UK advisory and programmatic support.

What Lessons Have Been Learnt?

- Policy direction needs to clear and consistent, that resources available match the level of policy ambition set, and results are achievable within the operating context. It is essential that future programmes are ambitious, but realistic within the resource and operational constraints imposed.
- Future programmes should recognise coordination and coherence challenges posed by large numbers of small projects, when resources for oversight are limited. The programme has streamlined significantly and become more coherent.
- As programme priorities and focus evolve, it is important to ensure that these changes are captured in the programme architecture and documentation. Monitoring, evaluation and learning (MEL) systems need to be in step with implementation.
- The programme has proved highly political, both in the UK and in Nigeria. Implementation thus requires a mix of thematic, programmatic and MEL skills to be complemented with political savvy and targeted key leader engagement. Blending these together needs senior leadership engagement and a collegiate working environment.
- A key lesson is ensuring that collaboration is based on clear understanding of what both parties want, need and are able to provide. The programme struggled to align the HMG ‘offer’ with Nigerian demands in 2019/20.
- Future programming should report on a fewer number of common indicators that are true barometers of intent and progress, rather than become distracted by the need for tactical progress on a quarterly basis.
- In environments with high turnover of personnel, investments need to be made in ensuring that lessons are captured and applied, and programmes built on evidence of what does and doesn’t work effectively in context.