Programme Completion Review Summary Sheet

Programme Title	Sahel - Defence and Security Programme
Programme ID	C-AFR-0022
Country and Region	Sahel: Mali, Niger, Chad, Burkina Faso and Mauritania
IATI Unique ID	CSSF-03-000023
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO); Ministry of Defence (MoD); National Crime Agency (NCA)
Total Budget	ODA: £7.6m	Non-ODA: £6.2m
Total Spend	ODA: £7.1m	Non-ODA: £5.8m
Time Frame	Start Date: April 2018	End Date: March 2021

Outputs	Scale of Delivery
1. G5 Sahel better equipped to undertake its role in stabilisation efforts, through the provision of communications advice, training, and the supply of operational equipment provided by the UK.	2
2. Capacity of Malian security forces increased through the provision of high quality strategic advice and IHL training by the UK through the EUTM.	4
3. Enhanced professional development of selected officers from Sahelian armed forces supported by the UK.	3
4. Increased UK support to promote gender mainstreaming in defence and security organisations in the Sahel.	3
5. Demonstrated efficiency of UK participation and coordination at strategic level in local, national and international D&S efforts in targeted areas of the Sahel - demonstrating good VFM (value for money).	3
6. Malian Security Forces better equipped to more effectively generate and act on intelligence, through high level training, mentoring and the supply of operational equipment provided by the UK.	4
Final Overall Scale of Output Delivery	3

Outcome Assessment / The programme performed well in challenging circumstances (declining security, a coup in Mali, COVID-19), with limited human resources. Some aspects of the programme performed better than others, and UK investment in the region remains modest relative to the scale of the challenge, but the programme has increased the UK’s influence with Sahelien Security & Defence organisations and international missions and has improved the ability of Malian intelligence actors to detect and tackle threats.
Final Overall Scale of Outcome Achievement:	3
Overall Risk Rating:	Medium-High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A	N/A	B	B	A	A	3	3
Risk Rating	N/A	N/A		High		Medium		Medium-High
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?

- Provided two military officers and a senior civilian advisor to the UN mission in Mali (MINUSMA) to support planning (ahead of the UK’s deployment to MINUSMA) and coordination.
- Provided six military and two civilian secondees to the EU Training Mission (EUTM), supporting training to the Malian military on infantry, medical, counter-IED (improvised explosive devices), and international humanitarian law.
- Supported the professional development of Sahelian military officers by sending selected officers on UK and regional command, strategic, leadership and operational courses, and by providing support to the École de Maintien de la Paix (Peacekeeping School) in Bamako.
- Provided training and mentoring to the Malian security service (DGSE) to tackle serious and organised crime and related threats. Some support was also provided in earlier years to the Senegalese Anti-Corruption Unit to tackle serious and organised transnational crime connected to the Sahel.
- Provided training and mentoring to the Malian Gendarmerie to support intelligence-led operations.
- Supported the G5 Sahel (Burkina Faso, Chad, Mali, Mauritania and Niger), first through direct financial support using the EU’s coordination mechanism, then through the provision of non-lethal equipment to the Nigerien battalion of the G5 Sahel Joint Force, and then through support on strategic communications to the G5 Sahel.
- Supported the UN Office for the Coordination of Humanitarian Affairs (OCHA) to hold workshops and training on civil-military coordination and the funding of critical civ-mil coordination personnel.

What Results Did the Programme Deliver? Will they be Sustained?

- UK deployees to MINUSMA and the EU Training Mission in Mali (EUTM) have been highly valued and influential in driving (incremental) improvements in the operations and delivery of these multilateral missions, including transforming the international humanitarian law (IHL) training curriculum at EUTM and influencing the design of the MINUSMA’s Mobile Task Force, which tasks the UK deployment of 300 personnel.
- Various operations targeting organised crime and corruption delivered by local partners who have improved capacity thanks to this programme.
- 1400 Malian personnel attended UK-delivered training on international humanitarian law, to promote a human security approach by the Malian defence and security forces.
- The programme enabled the UN Humanitarian Affairs Agency to design and deliver civil-military coordination activity which had previously been stalled due to lack of funding, leading to improvements in civ-mil coordination and bringing in wider donor interest.
- The UK is recognised as a valuable and well-informed partner on defence, security and stabilisation issues by both national and international partners.
- Foundations established for improved, insight-driven strategic communications by the G5 Sahel, to enable better community engagement and increased public trust. This will be informed by audience insight on opinions, attitudes and behaviours of Sahelien audiences toward the G5 on development and security issues, involving 5,917 interviews across all five G5 countries and 30 focus groups in the tri-border region.

What Lessons Have Been Learnt?

- Donors and partners need to be realistic about how quickly the capacity of Sahelien partner security and defence forces can improve; length of political and financial commitments should be taken into consideration when designing programming. There is (understandably) no expectation of full-scale security sector reform; yet capacity building alone will provide only incremental improvements and will not solve many of the underlying governance issues.
- Defence partners have limited absorption capacity and external actors must be clear about where they can genuinely add value – donor coordination on defence and security is not straightforward but is nonetheless essential.
- For a programme to truly be more than the sum of its parts, and corral implementing partners, including within HMG, together in line with the programme’s strategy, a substantial investment (of time and human resources) is required in the internal processes that underpin coherence and coordination. The programme did this successfully through briefing notes, pre-deployment training, and regular partner meetings, but could do more to bring partners together.
- Any defence and security engagement requires robust and continuous assessment of human rights context and potential impacts of programme activities; to address this, a Human Rights Compliance Board has been created for FY21/22.
- Gender mainstreaming and embedding monitoring evaluation and learning (MEL) both require dedicated capacity, including internally. This means not only advisory capacity, but also sufficient programme management capacity so that the programme team can implement advisory inputs effectively.