Programme Completion Review (20/21 Ver.) - Summary Sheet

Programme Title	Sahel Stabilisation Programme
Programme ID	C-AFR-0023
Country and Region	Sahel (Niger, Mali, and Burkina Faso)
IATI Unique ID	CSSF-03-000024
HMG Partners	FCDO
Total Budget	ODA: £11.25m	Non-ODA: £1.1m
Total Spend	ODA: £7.124m	Non-ODA: £2.056m
Time Frame	Start Date: April 2018	End Date: March 2021

Outputs	Scale of Delivery
1.1 Increased production and improved dissemination of data/findings about conflict dynamics, stabilisation interventions and approaches in the Sahel.	4
2.1 Increased UK support for conflict resolution to strengthen local level management of land and natural resources in targeted areas of the Sahel.	3
2.2 Increased UK support for conflict prevention to overcome economic, health, water access, environmental and governance-related drivers of human insecurity in targeted areas of the Sahel.	3
2.3 Increased UK support to address drivers of conflict and barriers to stability rooted in gender inequality and social exclusion in targeted areas of Sahel.	3
2.4 Demonstrated efficiency of UK participation and coordination at strategic level in local, national and international efforts in targeted areas of the Sahel.	4
Final Overall Scale of Output Delivery	3

Outcome Assessment / The programme has achieved some good successes at the outcome level. However, there have been significant problems with the monitoring, evaluation and learning (MEL) capacity of implementing partners (IPs). This has been flagged in the previous two Annual Reviews. The scoring reflects these challenges as for several indicators the quality of IP reporting did not enable an accurate assessment of progress against results framework (RF) targets. It is unclear the extent to which this reflects problems with under performance or is primarily a MEL issue. It has also been noted that the MEL system put in place was difficult to measure against, and this led to some inconsistent reporting by IPs.
Final Overall Scale of Outcome Achievement:	3
Overall Risk Rating:	Medium-high

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A		A	B	A	A	3	3
Risk Rating	N/A	N/A		Medium		Medium		Medium-high
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
- Direct contribution to stabilisation in conflict-afflicted areas of the Sahel (via the MINUSMA Trust Fund, High Authority for the Consolidation of Peace (HACP - Nigerien Government Stabilisation Agency), Redressement Économique et Social Inclusif du Lac Tchad (RESILAC - Inclusive Economic and Social Recovery around Lake Chad) and GEOAnalytic / Foundation Hirondelle).
- Stabilisation efforts in fragile but vulnerable areas of the Sahel (MercyCorps, AMSS / Alliance for Rebuilding Governance in Africa (ARGA), Adam Smith International (ASI) and North Ghana Border).
- Research and dissemination of research to ensure evidence based/adaptive / best practice stabilisation (Institute for Security Studies (ISS)).

What Results Did the Programme Deliver? Will they be Sustained?
- Building relationships at the local level between communities and local government (AMSS/ARGA). Evidence of this includes safer access for government officials and services, increased conflict resolution, and communities beginning to hold the government to account.
- Working bilaterally and multilaterally: particularly shaping the MINUSMA Trust Fund, leading the donor group to push for more integrated, focused stabilisation efforts.
- Demonstrating stabilisation best-practice, working to boost effectiveness of local authorities in conflict resolution: the ASI project on Land Governance introduced 132 village land commissions as a system of arbitration of land disputes at the local level.
- Where appropriate, the programme worked to support state stabilisation strategies: CSSF supported the Plan de Sécurisation Intégrée des Régions du Centre (PSIRC) as the national strategy for the centre in Mali and the HACP state stabilisation body in Niger.
- Working in conflict prevention areas (which have increasingly become hot spots): including with a consortium of local NGOs in 7 municipalities in Sikasso, reducing violent conflicts through participatory conflict mediation processes and capacity building activities.

What Lessons Have Been Learnt?
- Lots of IPs places significant strain on CSSF management capacity - Eight IPs was arguably too many for this programme, especially given that they each reported in parallel directly to the CSSF team. This made coherence hard to achieve.
- Invest in cross-programme learning - Bring IPs with thematic and/or geographical overlaps together to facilitate peer learning and to amplify impacts (for example, ASI and MercyCorps’ work overlaps and has now been integrated into one project).
- Ensure research influences practice. Take an action-research approach to research methods and products. Consider how research can be commissioned and utilised more strategically and proactively by HMG to influence policy and programmatic opportunities.
- Support IPs to help ensure that they have the MEL capacity and systems in place to measure the effectiveness of their programmes, and then focus on verifying the data that is produced.
- Women and youth having a seat at the table is not the same as meaningful participation. The inclusion of representatives of marginalised groups in village land commissions was not sufficient to enable their meaningful participation, this requires more targeted capacity-building.
- The centrality of land as a conflict driver varies in different locations. Land governance can provide a good entry point but need to integrate into a more comprehensive approach with other donors.