 ­Programme Completion Review (20/21 Ver.) - Summary Sheet

Programme Title	Somalia Security Sector Reform
Programme ID	C-AFR-0027
Country and Region	Somalia, Africa
IATI Unique ID	CSSF-03-000027
HMG Partners / (Lead in bold)	Foreign Commonwealth and Development Office (FCO and DFID), Ministry of Defence
Total Budget	ODA: £2.55m	Non-ODA: £14.2m
Total Spend	ODA: £1.818m	Non-ODA: £17.342m
Time Frame	Start Date: April 2015	End Date: March 2021

Outputs	Scale of Delivery
1) Strengthen federal government’s security architecture and civilian oversight of forces.	4
2) Strengthen planning/cooperation between member state and federal security institutions.	3
3) Support Somali National Army (SNA) fighting and planning/logistics capabilities.	3
4) Support African Union Mission in Somalia (AMISOM)/United Nations (UN) to fulfil obligations under the Somali Transition Plan (STP).	4
Final Overall Scale of Output Delivery	3

Outcome Assessment	Progress made across all four outcomes, with federal/member state security institutions both creating strategies, policies, oversight mechanisms, and improving their ways-of-working, while the training/mentoring and equipment provision to the SNA-AMISOM-UN was crucial in holding population centres
Final Overall Scale of Outcome Achievement:		3
Overall Risk Rating:		High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	B	B	C	A	B	A	B	3	3
Risk Rating	High	High		High		High		High
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
- Tailored military support to SNA, AMISOM, and UN to drive forward both the longer-term capacity building of the SNA, as well as immediate operational needs to ensure the SNA works effectively with AMISOM and the UN to implement the Somali Transition Plan.
- Civilian advisory support to federal and member state security institutions to bring coherence to the Somali security architecture and build mechanisms for civilian oversight of security actors.

What Results Did the Programme Deliver? Will they be sustained?
- Embedded UK military expertise across SNA, AMISOM, and UN helped ensure a joined-up approach to security threats, with notable success in contingency planning for election security scenarios, and improvements in SNA combat capabilities as evidenced by improved ability to hold territory.
- Embedded civilian expertise in security institutions helped drive forward implementation of key strategies and policies, including the STP which required cooperation across multiple departments with divergent interests.
- These interventions are not fully sustainable in themselves and are dependent on long term commitments and improvements in the political environment, including supportive leaders),

What Lessons Have Been Learnt?
- Capacity building of FGS and FMS security institutions is focused on disparate goals (without baselines to identify progress) and needs a clearer single strategy and stronger coordination.
- HMG’s long-term goals in Somalia need long term resourcing to be realised and CSSF’s approach can too often be reactive and short-term.
##