Programme Completion Review (20/21 Ver.) - Summary Sheet
Programme Title	CSSF Somalia Stabilisation Programme
Programme ID	C-AFR-0028
Country and Region	Somalia
IATI Unique ID	CSSF-03-000028
HMG Partners	Foreign and Commonwealth Office and Ministry of Defence.
Total Budget	ODA: £7.626m	Non-ODA: £0
Total Spend	ODA: £7.8m	Non-ODA: £0
Time Frame	Start Date: 01/04/2017	End Date: 31/03/2021
Note: PCR covers four years of programme implementation following Programme Refresh in May 2017.
Outputs			Scale of Delivery
Government finds favourable conditions for the establishment and continuation of effective formal district administrations, and provides underlying conditions for the formation of formal district councils			4
Gender and conflict sensitive approaches to grassroot reconciliation and political negotiations are developed, integrated and transitioned, by the programme, in collaboration with African Union Mission in Somalia (AMISOM), SNSF, FGS and other stabilisation actors.			4
Community driven activities identified and delivered through Inclusive participatory (community, AMISOM, Somali Security Forces, MoIFAR and Federal Member State) processes, supported with a combination of programme funds and assistance of other partners.			4
Final Overall Scale of Output Delivery			4

Outcome Assessment / Over four years, the Stabilisation Programme delivered community-led reconciliation in key contested and newly recovered areas (NRAs) in four targeted States, paving the way for the Federal Government of Somalia (FGS) and the Federal Member States (FMS) to establish presence in line with the Somalia Transition Plan. The programme has worked with and through the Somali government, thus building the ability of key FGS and FMS institutions to plan, coordinate and monitor early recovery and stabilisation work. An investment was made into improving the ability of the Somali National Security Forces (SNSF) to conduct themselves with respect for gender and human rights norms and to promote accountability within the SNSF and the Ministry of Defence (MoD). The programme continued to evolve and respond to needs identified on the ground throughout its duration, with components dedicated to hyperlocal communications and Women, Peace and Security (WPS) rolled out in the final two years.
Final Overall Scale of Outcome Achievement:	4
Overall Risk Rating:	Medium-High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	A	A	A	A	A	A	A	4	4
Risk Rating	High	Medium		Medium		Medium		Medium-High
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
- The Early Recovery Initiatives (ERI) project primarily provides advice and capacity building for the Somali authorities and AMISOM to plan and conduct stabilisation initiatives in areas recovered from, or contested by, al-Shabaab (aS). It enables establishment of inclusive local community platforms to facilitate ownership of FMS and FGS by providing dispute resolution mechanisms; and opportunities for improved relations between communities and the SNSF.
- The Building Confidence in Recovery (BCR) project is strategic communications at the local community level mainly around the concerns of communities, to build support for and confidence in a return to government control.
- Immediate stabilisation support in NRAs through projects delivering rehabilitation of critical infrastructure or support to community resilience and reconciliation.
- Provision of institutional support to FGS on stabilisation policy coordination by funding key workers to undertake research and planning in UNSOM CRESTA/A (United Nations Somalia, Community Recovery and Extension of State Authority/ Accountability) and the Ministry of Interior, Federal Affairs & Reconciliation (MOIFAR) to deliver the National Stabilisation Strategy and State Stabilisation Plans. Ongoing assistance to CSSF Somali trained trainers, to develop and deliver SNA pre-deployment training covering Gender & Human Rights, Civilian Military Cooperation (CIMIC) and Communications skills.
- Research on women’s access to justice in the NRAs and training for female powerbrokers and influencers, traditional elders and law enforcement with the goal of improving access to formal justice mechanisms.

What Results Did the Programme Deliver? Will they be Sustained?
- Selected communities located in the NRAs along the main supply routes (MSRs) in Jubaland and South-West State have made positive progress in community reconciliation and established and strengthened relations with security forces and local and State-level government.
- Contribution to mediation of larger-scale State and district level inter-clan conflicts in the four targeted States (Jubaland, South West State (SWS), Galmudug and Hirshabelle) and facilitation of pre-recovery dialogues between communities and the Security Forces (SF).
- Six rounds of Community Atmospherics Panels (CAPs) in the NRAs of Lower Shabelle that provided insight into security, governance, access to justice and other issues affecting the targeted communities. Public Service Announcements (PSAs), radio debates and other strategic communications products were used.
- The federal-level MoIFAR and state-level Ministries of Interior (MoIs) maintained ownership and expanded their involvement in stabilisation planning and delivery.
- State Stabilisation Plans are in use and integrated into local governance structures.
- The programme worked with UK Mission Support Team (UKMST) (Operation Tangham) to deliver CIMIC training to AMISOM and the SNSF.

What Lessons Have Been Learnt?
- It is key for the programme to maintain flexibility and take time to develop the right approach in each area, drawing on different tools in the Early Recovery ‘toolbox’. Local reconciliation was the main need in Jubaland and SWS, whereas the clearance operations in Lower Shabelle required focus on SNSF conduct and relationship building between community and local government.
- Grass roots, community liaison with Community Based Liaison Officers (CBLOs) has been essential to access and influence with partners.
- Gender diversification of the CBLO or Community Outreach Officers (COO) would be positive. One COO currently is female, with the intention to increase this number.
- Early planning, early engagement with SF, International Community (IC), State and community groups is an essential element of success.
- Media coverage of AMISOM/SNA operations reduces impunity and prevents abuse. CBLO use of local journalists to ‘accompany’ military operations and SNA media teams, trained in the threats of the battlefield are able to provide accountability and oversight.
- Small applications of funding, strategically used, can have significant impacts.
- The appetite for gender and human rights, as well as CIMIC training, is there and its successful impact is measurable.
- A well scoped, resourced and situationally aware strategic communications program can be very effective in combatting aS.
- Program flexibility to bring in highly regarded outside trainers such as the Roméo Dallaire Child Soldiers Initiative lends credibility to the program and quality to the learning.
- The ERI program has experienced significant success and many of its lessons identified would be of value in similar conflict environments.