Programme Completion Review (20/21 Ver.) - Summary Sheet
Programme Title		Sudan Transitional Programme
Programme ID		C-AFR-0034
Country and Region		Sudan, East Africa
IATI Unique ID		CSSF-03-000030
HMG Partners		Foreign, Commonwealth and Development Office (FCDO)
Total Budget		ODA: £2.623m		Non-ODA: £0.0m
Total Spend		ODA: £2.595m		Non-ODA: £0.0m
Time Frame		Start Date: June 2020		End Date: March 2021 (Planned end date March 2022).
Outputs							Scale of Delivery
Provision of mechanisms which are empowered to develop and follow through on an inclusive national strategy for peace.							3
Clear understanding through consultation on best/gender-sensitive approach for transitional justice.							3
Better understanding of emerging conflicts, threats and drivers including the impacts on girls and women.							2
Understanding of the need and potential of a Conflict Sensitivity Resource Facility (CSRF) in Sudan.							3
Final Overall Scale of Output Delivery							3
Outcome Assessment / The programme contributed to HMG’s efforts to support the peace process and create a more conducive context for future stability. Achievement of outcomes was affected by the decision to close the programme one year early, in March 2021. Overall, the programme met some of its outcome targets – although there were some challenges in assessing the outcomes.
Final Overall Scale of Outcome Achievement:				3
Overall Risk Rating:				High
Summary of Programme Performance
Year	2016/17a		2017/18b		2018/19b	2019/20b		2020/21c
Programme Rating	N/A		N/A		N/A	N/A		3	3
Risk Rating							High
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
- Support to the national peace process through the deployment of an experienced peace process advisor. Technical support and capacity building to assist peace negotiations. At the State level, the programme strengthen community level conflict resolution mechanisms and early recovery support. This included a contribution to UNITAMS (United Nations Integrated Transition Assistance Mission in Sudan) for the collection of early warning conflict indicators.
- Support to establish transitional justice processes and mechanisms, in collaboration with civil society groups, the Sovereign Council and the civilian wing of the government.
- Funding a Conflict Sensitivity Facility which sought to integrate conflict sensitive practices, develop the understanding of the context and promote future partner support to the peace process that ensures conflict sensitivity.

What Results Did the Programme Deliver? Will they be Sustained?
The decision to close the programme early severely limited the outcomes delivered and most effort was focussed on closing or transitioning project activity. However, the programme achieved the following results:
- Technical support and capacity building was delivered to peace process stakeholders on issues related to the negotiations, and UN Women which sought to address gaps in inclusivity in the peace process.
- A Partners in Development Services (PDS) project supported the peace process between ethnic groups in Kordofan and Blue Nile Regions. Of particular note was the “shuttle diplomacy” undertaken between the Sudan People’s Liberation Movement – North (SPLM-N), the Prime Minister’s (PM) office, and the office of Gen Al-Burhan which may act as a foundation for recommencing formal talks.
- The CSSF was utilised to demonstrate the UK’s foreign policy leadership and enabled the UK to be the first donor to support UNITAMS.
- Support provided to the Civilian led Transitional Government (CLTG) and interested stakeholders on the structure and formation of a number of relevant commissions (including the Transitional Justice Commission and the Darfur Truth and Reconciliation Committee). This included legal review and analyses of draft laws to establish the Transitional Justice related mandate of the Commissions, though drafting amendment where not accepted by the Government of Sudan. Insufficient attention by key stakeholders impacted delivery of the implementation and naming of institutional actors to carry forward transitional justice processes and mechanisms.
- Training on understanding of transitional justice concepts, mechanisms and procedures to key stakeholders. It is too soon to determine whether the training resulted in an improved understand of transition justice concepts, which were then operationalised.
- An assessment of the conditions in twelve prisons, and an additional assessment on female prisoners’ psychological and living needs. As a result of Penal Reform International’s (PRI) work, the Minister of Interior established a committee to re-draft the prison law in line of PRI’s legal analysis and findings. Additional donor funding would be required for recommendations to be taken forward.
- The launch of a Conflict Sensitivity Facility in Sudan. Activity conducted included development of website; a scoping assessment to identify needs, a first roundtable, in partnership with OCHA, and an analysis piece on the political economy. It is not yet possible to assess what impact this activity has had on the decisions or processes of aid actors.
- The CSSF funded peace process adviser drafted various analysis papers, shared with other donors. Formal assessment was not possible to assess impact on donors’ decision making.

What Lessons Have Been Learnt?
- Monitoring, Evaluation and Learning: The early closure of the programme has impacted delivery and assessment of results. However, the development of a comprehensive results framework with incorporated metrics adapted to the Sudan context would have assisted the assessment of what was achieved in the reduce programme lifespan.
- Staffing and Structures: The programme would have benefited from a more formalised team structure in which policy and advisory staff played a more consistent systematic role to help guide overall direction, relative priorities and coordination.