 Annual Review (20/21 Ver.) - Summary Sheet

Programme Title	CSSF Central Asia Programme
Programme ID	C-EEA-0001
Country and Region	Central Asia (Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan and Uzbekistan)
IATI Unique ID	CSSF-05-000001
HMG Partners / (Lead in bold)	Foreign & Commonwealth Office, Department for International Development (DFID) (Foreign, Commonwealth and Development Office formed on 01/09/2020), Ministry of Defence (MOD), National Crime Agency (NCA – managed from FCO/FCDO baseline in FY20/21)
Total Budget	ODA: £3.27m	Non-ODA: £0.30m
Budget this FY	ODA: £3.27m	Non-ODA: £0.30m
Spend this FY	ODA: £3.24m	Non-ODA: £0.31m
Time Frame	Start Date: 1 April 2020	End Date: 31 March 2021

OUTPUTS SCORE
Global Partners Governance Foundation / 1.1 Advice provided on the creation and operational matters of a parliamentary human rights committee; / 1.2 Capacity built of MPs and staff appointed to a parliamentary human rights committee (committee); / 1.3 Capacity built of committee staff on effective engagement through direct support and advice for committee oversight activities; / 1.4 Human rights committee communications and outreach plan document developed and approved for implementation; / 1.5 MPs/staff appointed to the new human rights committee are exposed to best practice through international forums with UK and international peers and experts; / 1.6 In-depth analysis of prevailing human rights issues in Uzbekistan is carried out and a report produced to inform potential future engagement on strengthening human rights in Uzbekistan.	4
UK Government Partnerships International (GPI) / 3.1. Responsive advisory services provided on an as-needed basis; / 3.2. Delivery of workshops targeted at counterpart institutions needing development; / 3.3. Delivery of quality, well-planned masterclasses targeted at counterpart institutions; / 3.4. Degree to which GPI programmes its activities in a holistic, gender-sensitive way.	3
4.1 Free initial legal advice provided to local citizens in Uzbekistan.	4
UK Defence engagement: / 5.1: Increased capabilities of Central Asian Republics (CARs) armed forces on non-lethal professional military skills such as: peacekeeping skills; engineering; medical; gender issues; and anti-corruption; / 5.2: Improved english language skills of Kazakhstan, Tajikistan and Kyrgyzstan troops to enable them to engage on United Nations peacekeeping operations and international military courses; / 5.3: Capacity built of Uzbek MOD and National Guard English language teachers on English language skills and teaching methods.	4
National Crime Agency: / 6.1. Capacity built of CARs law enforcement officials on specific UK priority areas relating to Serious Organised Crime (SOC).	3
Institute for War & Peace Reporting / 7.1: Capacity built of students and tutors of journalism departments on new media, including on skills to counter mis/disinformation and conflict & gender-sensitive reporting; / 7.2: Capacity built of media outlets in selected Central Asian (CA) countries on using new media digital platforms and producing new content to counter mis/disinformation and conflict and gender-sensitive reporting; / 7.3: Established informal network of media students and professionals in selected CA countries to create conflict and gender-sensitive collaborative content.	4
UNFPA / 8.1: Advice provided to relevant ministries on sectoral Standard Operating Procedures (SOPs) for a multi-sectoral response to Gender Based Violence (GBV); / 8.2: Capacity of Faith Based Organisations (FBOs) and religious leaders built on GBV and Reproductive Health (RH).	4
UNDP / 9.1: Increased government capacity of policymaking on climate change; / 9.2. Increased national and regional engagement in COP26; / 9.3. Increased public awareness and advocacy for locally appropriate, climate change actions.	3
Overall Scale of Output Delivery	4

OUTCOME ASSESSMENT
In the absence of an overarching results framework and Theory of Change (ToC) – both being agreed as part of new CA CSSF Strategy, the outcome assessment is based on the performance of individual projects. Despite FY20/21 having been a particularly challenging year due to the COVID-19 pandemic, projects have delivered most outputs and significant progress has been made on intended outcomes. In some projects, it is either too early to comment on outcome level change because of relevant evidence not being available yet (as a result of programming activity having shifted to quarters three and four), or available evidence presenting a level of uncertainty around whether outcomes will be fully met.
Amber - On track but some doubts about whether outcome targets will be fully met.
Risk: Low / Medium

SUMMARY OF PROGRAMME PERFORMANCE
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	B	A	B	A	B	A	B	4	Amber
Risk Rating	Low/Medium	Low/Medium		Low/Medium		Low/Medium		Low/Medium
Programme changes during this period		The programme has strengthened its strategic focus in line with four agreed thematic priorities, delivering against the “Conflict & Stability” and “Reform” pillars of the National Security Council (NSC) Central Asia 2020-25 strategy. The number of projects was reduced from 21 in FY19/20 to 11 in FY20/21, with continuing projects aligned to thematic priorities and assessed to be performing well. The ODA budget reduced by 27% compared to FY19/20, while the non-ODA budget remained the same.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY20/21?

The programme funded 11 projects which aimed to improve UK defence and security partnerships in CA, reduce threats from SOC, support good governance reforms in Uzbekistan, improve the capacity of media, support the prevention and responses to GBV, and enhance policy action for climate security in CA.

Key Results for FY20/21

- Uzbek Parliamentary Commission for Follow-Up and Compliance with International Human Rights Obligations established in November 2020. Increased MPs and committee staff awareness of the role of parliament in enhancing human rights adherence and of best practice in the UK and elsewhere.
- Uzbek civil servants in Ministry of Justice provided with the knowledge and skills to support more inclusive and citizen-focused service delivery.
- 42,161 females and 49,130 men in Uzbekistan received free and independent legal advice. 12 proposals for amendments to policy and legislation on citizens’ rights submitted to Ministry of Justice, of which one (so far) has been approved by the President and passed into law.
- Improved English language capabilities of 208 students and teachers, to enable engagement on UN peacekeeping operations and international military courses. Over 90 CA military personnel attended courses on anti-corruption, human rights, gender and crisis management.
- 46 law enforcement officials across CA countries with strengthened knowledge of UK SOC priority areas including cybercrime investigation.
- Over 3,328 students trained, to date, on new media and reporting techniques including on skills to counter mis/disinformation, conflict, gender-sensitive and emergency COVID19 reporting.
- Continued progress on implementation of a multi-sectoral response to GBV across the region. 500 specialists demonstrating increased knowledge of relevant SOPs and over 170 religious leaders and members of FBOs demonstrating increased knowledge of GBV and reproductive health.
- Kyrgyzstan, Tajikistan and Uzbekistan delegations trained on climate diplomacy and negotiation as preparation for participation in the COP26; National climate debate tournaments in Kyrgyzstan and Tajikistan helped raise youth public awareness for more robust climate action.

Key Lessons

- The programme has adapted well to challenges presented by the COVID19 pandemic, adjusting interventions to ensure greater relevance. CSSF and cross-Whitehall response processes at times posed a barrier to flexing the programme in response to COVID19.
- Regional projects with strong country components and bilateral engagement offer clear benefits in terms of efficiency, facilitating exchange and transfer of learning between countries, and visibility for the UK.
- Online delivery of activities enabled wider reach. Building rapport with participants and ensuring full and constructive interaction proved more difficult, with different approaches trialled during the year.
- The campaign-based approach supports programme and policy integration but should focus on specific issues and keep processes proportionate given the staffing profile in CA countries.
- The gender focal point structure, with support of the regional gender adviser, has helped to strengthen the programme’s focus on gender commitments.

Key Recommendations for FY21/22

- Finalise, as soon as possible, the design of the new programme.
- Design the Monitoring and Evaluation (ME) approach and results structure for the new programme and secure the ME support required to develop this.
- Develop a coherent approach to value for money and agree how it can be measured.
- A structured review of the programme Risk Register needs to be put in place at least every quarter. Implementing partners should be encouraged to do the same.
- Carry out a light-touch gender capacity assessment to help inform learning & development.