Annual Review (20/21) - Summary Sheet

Programme Title	Eastern Neighbourhood
Programme ID	C-EEA-0003
Country and Region	Armenia, Azerbaijan, Belarus, Georgia & Moldova, Eastern Europe and Central Asia (EECAD)
IATI Unique ID	CSSF-05-000002
HMG Partners / (Lead in bold)	Foreign and Commonwealth Office (FCO), (Foreign, Commonwealth and Development Office formed on 01/09/2020), Ministry of Defence (MOD)
Total Budget	ODA: £4.209 million	Non-ODA: N/A
Budget this FY	ODA: £4.209 million	Non-ODA: N/A
Spend this FY	ODA: £4.155 million	Non-ODA: N/A
Time Frame	Start Date: 1 April 2020	End Date: 31 March 2021

Outputs	Scale of Delivery
Revised Output 1.1 CSSF is able to continue to support existing programme beneficiaries in breakaways and conflict-affected areas and contribute to meeting immediate human security needs of the most vulnerable during the pandemic.	3
Revised Output 1.2 Short-term interventions to Covid-19 help to provide analysis and data on critical needs and improve the effectiveness of the wider international response.	4
Revised Output 2.1 International mechanisms, peacebuilding initiatives and Civil Society Organisations adapt to Covid-19 and continue to function, making more use of digital solutions to maintain engagement.	3
Revised Output 3.1 Advocacy on Women, Peace and Security (WPS) is maintained and strengthens government commitments to support greater gender equality.	3
Revised Output 3.2 CSSF responses to Covid-19 demonstrate a strong commitment to gender equality and contribute to evidence and analysis on the impacts on women.	4
Revised Output 3.3 and 3.4 The most vulnerable, conflict-affected groups (including women and young people) are protected, empowered and better able to access education and economic opportunities to strengthen community-level resilience during Covid-19 and in response to conflict.	3
Output 4.1, 4.2, 4.3, 5.1, 5.2, 5.3 (relating to outcomes on defence and security and hybrid threats).	Not Assessed
Overall Scale of Output Delivery	3

Outcome Assessment	Programme outcomes were challenged by the Covid-19 pandemic and further by the outbreak of the Nagorno-Karabakh conflict in September 2020 and political changes across the region, including in Belarus. In response to the uncertainty of the Covid-19 situation a central decision was taken to pause contracting of new programming, resulting in delays to contracting planned delivery. Despite these delivery challenges, some significant results were demonstrated at output level as the programme adapted to protect activity on gender equality, maintain existing outputs with state and non-state actors and enhance the protection of beneficiaries from vulnerable communities across the region.
Overall Outcome Progress Rating:		Amber/Red
Overall Risk Rating:		HIGH

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	A	A	A	A	A	A	A	3	Amber / Red
Risk Rating	Medium	Medium		Medium		Medium		High
Programme changes during this period		The programme adopted revised outcomes and outputs in early 2020 to adapt programme activity to the outbreak of Covid-19 ensuring it could deliver an effective contribution to the wider international response, manage immediate risk to beneficiaries and protect longer-term objectives.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

The Eastern Neighbourhood (EN) programme contributes to the delivery of the National Security Strategy Implementation Group’s 2020-2025 EN Strategy through projects that seek to enhance resilience to a range of external and internal threats that are faced by five countries of the region (Georgia, Armenia, Azerbaijan, Belarus, and Moldova).
It contributes to international efforts in peacebuilding and draws on UK expertise to deliver conflict management responses in the four conflicts of the region (Abkhazia, South Ossetia, Nagorno-Karabakh and Transnistria). In addition, the programme delivers projects that explore ways to support reform in Belarus (although this was ultimately limited by changes in the political context following elections in September), enhance the resilience of defence and security actors, particularly in Armenia and Georgia, and advance the WPS agenda.

The UK, as the third largest donor after the EU and US, has a strong reputation for peacebuilding and engagement in this region, including through the extensive experience of UK-based Non-Government Organisations and partnerships with multilateral organisations. In 2020, the programme aided a UK humanitarian and developmental response to the outbreak of conflict in and around Nagorno-Karabakh and adapted to the primary and secondary impacts of Covid-19.

Key Results for FY 20/21

The programme successfully adapted programming to respond to the immediate needs of Covid-19 and maintain outputs in breakaway and conflict affected regions despite the stalling of peace talks and international formats. Short-term activity supported vulnerable beneficiaries and included providing Personal Protective Equipment and maintaining gender-based violence services to the most vulnerable in Transnistria (Moldova) and re-purposing Halo Trust vehicles into ambulances in Abkhazia (Georgia). The programme ensured adaptation of existing outputs (from FY19/20) including transitioning English Language Learning networks (that support the development of critical thinking skills in vulnerable communities most affected by disinformation) to online learning modalities and to maintain outputs to advance progress on the WPS agenda. Defence and Security partnerships were maintained, advancing the rights of women in Georgia’s Ministry of Defence and establishing new contributions to Black Sea Security and advancing the National Security agenda. A new partnership with the United Nations Development Programme (UNDP) supported the design of a new mine action response that will be delivered in Azerbaijan and Armenia in FY21/22, following the Nagorno-Karabakh conflict which has left vast areas mined and inaccessible.

Key Lessons

The achievement of outcomes on peacebuilding and policy reform are more challenging in a pandemic. Priority should be given to addressing vulnerabilities and short-term needs which are expected to exacerbate risks to longer-term objectives. This requires a higher risk appetite and early clarity on objectives, matched with consistency of funding if programme teams are to be supported to adapt.

Key Recommendations for FY21/22

The programme should prioritise and streamline its interventions. Continuing to reduce the number of small projects and investing in fewer, more regionally focussed projects will improve Value for Money, opportunities to monitor and evaluate progress at scale and ensure the programme is delivering against National Security Council strategic objectives. At the same time, these partnerships must include and harness the expertise of local organisations and invest in strengthening their capacity. The programme should strengthen its approach to consistent monitoring and evaluation. Desired results should be articulated, despite the challenges to achieving outcomes in the current context and develop tools for maximising the influence and access that can be gained from interventions. The programme should continue to test different approaches and generate learning given the lack of an established methodology for achieving change in the region