Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Egypt Programme
Programme ID	C-MNA-0004
Country and Region	Egypt, Middle East and North Africa
IATI Unique ID	CSSF-06-000002
HMG Partners / (Lead in bold)	Foreign, Commonwealth Office (FCO) / Foreign, Commonwealth & Development Office (FCDO) from September 2020
Total Budget	ODA: £53.55m	Non-ODA: £0.75m
Budget this FY	ODA: £12m	Non-ODA: £0
Spend this FY	ODA: £10.58m	Non-ODA: £0.15m
Time Frame	Start Date: April 2018	End Date: March 2021

Outputs	Scale of Delivery
World Bank Trust Fund-supported reforms for disadvantaged groups, especially women and youth	4
World Bank Trust Fund - supported reforms to the legal and business environment	4
World Bank Trust Fund - supported reforms improving Government of Egypt (GoE) fiscal position	4
High quality Economic research conducted and disseminated	4
Entrepreneurship acceleration	4
Training and engagement on working conditions.	4
Training and engagement on Digital Financial Services	3
Schools are equipped to open and operate safely during and beyond COVID-19	2
Strengthened child protection and Gender Based Violence (GBV) services.	4
Developing a strategic plan for the national health authority	3
Supporting central preventative and rapid response functions	3
Increasing laboratory capacity (COVID-19 testing)	4
Improving infection prevention and control	3
Developing Monitoring, Evaluation and Learning framework for hospital emergency response plans	4
Provision of front-line support (cash and services) to vulnerable refugees, irregular migrants, and their communities	4
Identification of national institutions with appropriate resources and capacity to lead Women Peace and Security National Action Plan development	4
Engagement of civil society organisations	4
Engagement with government and academic stakeholders	4
Stakeholder input incorporated into National Action Plan	4
Communication of plans and policies with women across the country	4
Development of evidence base for drafting inclusive National Action Plan	4
Internal Open Societies response design	3
Overall Scale of Output Delivery	4

Outcome Assessment	Overall, the Egypt CSSF programme delivered effectively against its outcomes throughout Financial Year 2020/21 (FY 20/21), even in an environment of great change and considerable pressure on both resources and staff. The CSSF programme demonstrated an ability to adapt to new and rapidly changing circumstances, a strength acknowledged by the embassy leadership team, development partners and the FCDO board, while continuing to deliver concrete support underpinned by up to date research.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium-High

Summary of Programme
Year	2016/17a		2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	B		A	A	B	B	A	A	4	Green
Risk Rating	Medium/ High		Medium/High		Medium/High		Medium		Medium-High
Programme changes during this period		There were significant changes to the programme in FY20/21, resultant from the need to adapt to both the COVID-19 pandemic, and its impact on both the operating environment, and on UK ODA budgets. This included: / 1. Conducting an assessment of the stability impact of COVID-19; / 2. Adapting programmes in response to new priorities, setting up new health engagement and cutting areas of work that were deprioritised; / 3. Reducing activity in line with ODA cuts implemented in June 2020; / 4. Reducing activity ahead of a 2/3 reduction in budget for the future financial year.
Note: an output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
CSSF funding was provided for fifteen projects, with the objectives of:
1. Increasing public sector transparency, accountability and inclusivity;
2. Improving access to, and quality of, employment;
3. Reinforcing and improving education and health services in Sinai;
4. Supporting and improving the Egyptian pandemic response;
5. Increasing engagement with the Egyptian justice and security sector.

Key Results for FY 20/21:
Results of particular note include support to the Egyptian Government’s COVID-19 pandemic response, with 420 healthcare workers trained in infection prevention and control, health supplies provided to 151 schools, and support to vulnerable individuals suffering from the pandemic’s economic impact, including cash transfers to 59,868 households.
In addition, the programme provided front line psychosocial, medical and legal support to 16,982 migrants in Cairo and 2,742 children across Sinai and Ismailia. It provided outreach education to counter Female Genital Mutilation (FGM) which reached over three million people, and it continued to support the longer term economic reform which will allow the country to recover, with amendments to insolvency and tax legislation, strengthened local financial governance, 32 high quality economic research products, and 627 directly-created new jobs.

Key Lessons
1. It should be recognised that Egypt remains a challenging environment for understanding the impact of programming on stability and cohesion.
2. Increased access to beneficiaries might provide some qualitative data for testing assumptions, in addition to increased engagement with, and delivery through, civil society.
3. The CSSF programme is of modest financial scale. Initiatives need to be accompanied where possible with diplomatic engagement.

Key Recommendations for FY 21/22
1. Robust conflict analysis will be required, as the programme moves to focus on conflict reduction, and the security and justice fields.
2. It will be essential to ensure that sufficient advisory support is in place to ensure the safe and responsible closure of current projects and development of new areas of work.
3. Project managers should engage with beneficiaries and implementing partners, as close as possible to the final point of delivery (i.e. final beneficiaries and the services providers working directly with them).