Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Jordan: Political and Economic Resilience Programme (PERP)
Programme ID	C-MNA-0016
Country and Region	Jordan, Middle East and North Africa
IATI Unique ID	CSSF-06-000036
HMG Partners / (Lead in bold)	Department for International Development (DFID), Foreign and Commonwealth Office (FCO) / Foreign, Commonwealth & Development Office (FCDO) from 2 September 2020
Total Budget	ODA: £11m	Non-ODA: £0.1m
Budget this FY	ODA: £11m	Non-ODA: £0.1m
Spend this FY	ODA: £8.59m	Non-ODA: £0
Time Frame	Start Date: April 2020	End Date: March 2023

Outputs	Scale of Delivery
Target government institutions more effectively manage their finances and engage with the public	3
State capacity to deliver key services, improve systems and deliver change	3
Civil society and people's capacity is built to more effectively engage with Government of Jordan (GoJ)	3
Local capabilities for peace and conflict transformation enhanced	4
Overall Scale of Output Delivery	3

Outcome Assessment	The CSSF has contributed to some progress in making GoJ decision making and processes more transparent, accountable and participatory by supporting clearer and more focussed communication on GoJ decisions and greater local community participation in decision making, particularly through the Community Leader National Network. The CSSF has helped to improve citizen trust in municipalities and supported marginalised groups to contribute their views on the services and reforms that would better meet their needs. The key challenge remains the ability of projects to translate local citizen engagement to influencing national level decision making. / The combination of social cohesion and social contract approaches to achieve progress on ensuring that the effects of change are better absorbed at community level is a key success of PERP. There is evidence of success in mitigating conflict and supporting society through multiple locally led entry points.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium-High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A	N/A	*	*	*	*	3	Amber
Risk Rating	N/A	N/A		*		*		Medium-High
Programme changes during this period		This is the first year of the PERP, which combines two legacy programmes (the Political Stability Programme (PSP) and the UK-Jordan Partnership Facility (UKJPF) Programme). Two large projects planned to begin in year one did not go ahead for a variety of reasons.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating
*PERP combines two legacy programmes: / the FY 18/19 Annual Review of the Political Stability Programme (PSP) scored A at output and B at outcome. The FY19/20 Programme Completion Review (PCR) for PSP scored A at output and A at outcome. Risk Medium for both; / the FY19/20 PCR for the UK-Jordan Partnership Facility (UKJPF) Programme scored B at output and B at outcome. Risk Medium.

What Support Did the UK Provide in FY 20/21?
- Delivery of local-level, locally driven public service capacity including essential infrastructure in areas most at risk of rising tensions against the state, reducing the risks of instability and strengthening citizen-government dialogue.
- Strengthening of the Rule of Law by supporting Royal Court legal reform recommendations, the implementation of GoJ Judicial Sector Strategy and anti-corruption commitments.
- A number of small and targeted Partnership Facility interventions to support HMG in delivering the aims of the UK-Jordan Partnership, with a focus on catalysing reforms through technical assistance, research and peer-to-peer exchange.

Key Results for FY 20/21:
- GoJ’s COVID-19 (C19) response strengthened through CSSF funded medical equipment, furniture and supplies across the 12 governorates. Community Leaders also supported in the launch of a widely recognised & visible national communications campaign aimed at supporting local businesses & products to recover from the effects of C19.
- In response to rising youth unemployment, the Reducing Community Tension project helped 164 youth (out of 258 who enrolled and 243 who completed) find permanent employment.
- Increased opportunities for youth participation in governance processes (through Support Youth Voices Campaign) and enhanced State-Citizen dialogue (through municipal services social resilience project), with 55 infrastructure projects identified as community priorities.
- Support (through the partnership facility) to increase economic resilience through debt response mapping and delivery of digital strategy implementation, governance and operational products.
- UK support through the partnership facility also contributed to Independent Election Commission efforts to run inclusive, more accessible and safer parliamentary elections, and strengthened youth participation (50% of whom were female).
- The Rule of Law project has begun to increase the level of trust of the private sector in the Economic Chamber.

Key Lessons
- PERP demonstrated excellent C19 adaptability. Adaptive programming, working closely with implementing partners, can ensure programming remains relevant and fit for purpose.
- Projects, particularly newer ones, demonstrated a strong ability to build in gender, youth and safeguarding considerations from design and to deliver targeted activities.
- Working on community level women and youth empowerment has proven to be an effective programming tool. More could be done to elevate these types of interventions to the state/national level - should consider as part of the Inclusive and Accountable Governance Project design.
- Relationships should be built across multiple levels of the key stakeholder organisations to minimise disruption & buy-in issues when heads of institutions change.

Key Recommendations for FY 21/22
- The programme level Results Framework should be strengthened and adapted during the year.
- The Monitoring, Evaluation, Research and Learning plan should be implemented over the coming year and should include stronger evidence gathering on gender sensitivity.
- Future projects should ensure that they are capturing and implementing lessons from older projects, particularly around ensuring adaptive management and implementation and being realistic on timelines.
- Exit plans for projects should include early consideration of how projects might transfer from CSSF.
- The selection process and management of the partnership facility should be strengthened, including earlier selection of projects. Management could also be strengthened through greater clarity on appropriate roles and responsibilities and learning should also be better captured and shared with relevant colleagues.