Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Jordan: Security and Stability Programme (SaSP)
Programme ID	C-MNA-0018
Country and Region	Jordan, Middle East and North Africa
IATI Unique ID	CSSF-06-000037
HMG Partners / (Lead in bold)	Ministry of Defence (MoD), Foreign and Commonwealth Office (FCO) Foreign, Commonwealth & Development Office (FCDO) from 2/9/2020, Home Office (HO)
Total Budget	ODA: £8m	Non-ODA: £9.9m
Budget this FY	ODA: £8m	Non-ODA: £9.9m
Spend this FY	ODA: £4.35m	Non-ODA: £3.96m
Time Frame	Start Date: April 2020	End Date: March 2023

Outputs	Scale of Delivery
Output 1.1 / Delivery of infrastructure, equipment and training to the Jordanian Armed Forces (JAF) to achieve: / A properly structured, resourced, efficient and capable Quick Reaction Force (QRF) held at high readiness and able to deploy to Jordan's borders to defend against incursion and overseas in support of regional stability. / Highly trained and efficient specialised JAF units, fit for modern operations, able to deliver shared security strategic outcomes. / Enhanced border security, reinforcing Jordanian security.	1.6
Output 1.2 / Delivery of leadership development, training capacity support and police capability development training in Counter Terrorism (CT), public order management, protective security, public engagement and emergency lifesaving to the Public Security Directorate (PSD).	0.8
Output 1.3 / PSD and JAF adopt a Gender Mainstreaming Strategy for 2020-2025 based on the results of a Gender Impact Assessment. / PSD and JAF approve a Strategic Training Framework for Gender Advisers and Gender Focal Points.	0.6
Output 2.1 / Activities delivered to support women-led Civil Society Organisation (CSO) participation in national and global dialogues on the gendered dimensions of preventing violent extremism and counter terrorism responses.	0.4
Output 2.2 / Activities delivered (through the PSD, Family Protection Department (FPD), and national women’s organisations) to prevent and respond to Gender Based Violence (GBV).	1.6
Output 2.3 / Activities delivered focused on building at-risk youth's sense of identity, belonging and connections to their families and communities.	2
Output 2.4 / Community Engagement Forums	Paused until FY21/22
Overall Scale of Output Delivery	4

Outcome Assessment	The programme made good progress across the ambitious breadth of activity undertaken at project level, despite restrictions imposed on staff and activity due to the COVID-19 pandemic. There are early strategic signs of acceptance of the need for a greater gender balance within the security sector, with the adoption by the PSD and planned adoption by the JAF of a Gender Mainstreaming Strategy for 2020-2025. Additionally, in support of the JAF, there is emerging evidence that the QRF is better modernised at brigade level to respond to internal and external threats. Against a backdrop of previous similar activity, a project focussed on supporting youth at risk of high stress levels; initial results exceeded expectations, and contributed to the development of the Inclusive Security and Resilient Youth (ISRY) concept note.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium-High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A	N/A	N/A	N/A	N/A	N/A	4	Green
Risk Rating	N/A	N/A		N/A		N/A		Medium-High
Programme changes during this period		The programme reduced its initial funding allocation by about £9.5m in response to restrictions on activity imposed to manage COVID-19 in Jordan. The programme flexed with the planned concept papers on inclusive security and resilient youth merged into the ISRY concept note, following the identification of the need to bring together the results of multiple pilot projects into one paper.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
The programme has five projects in support of: the PSD (two projects) and JAF; increasing youth resilience in three communities, and the Jordan National Action Plan (JONAP) to advance the implementation of UN Security Council Resolution 1325 on Women, Peace, and Security (WPS).

Key Results for FY 20/21:
- JAF QRF Brigade achieved readiness for short notice deployment.
- PSD adopted a Gender Mainstreaming Strategy for 2020-2025.
- PSD and JAF approved a Strategic Training Framework for Gender Advisers and Gender Focal Points.
- The pilot project, Nubader II, focussed on youth at risk of high stress levels and informed the ISRY concept note.

Key Lessons
- Maintain key stakeholder engagement when activity is stopped or at low level e.g. with senior leadership in the PSD when PSD-related activity is paused during a COVID-19 lockdown.
- Delays in lesson learning need to be taken into account when planning future activity.
- MoD delivery of architecture works but concerns remain over Value for Money (VfM) e.g. infrastructure projects may be more expensive than initial allocation or take longer to deliver than planned.
- Framework agreements allow very rapid and flexible responses; faster than an individual tender process, in response to new and emerging issues, e.g. the JONAP framework agreement allowed a rapid pivot to anti-GBV programming at the start of the COVID-19 crisis.

Key Recommendations for FY 21/22
- Ensure all Overseas Security and Justice Assistance (OSJA) guidance related to the programme are up-to-date and accessible, including with Senior Responsible Owner (SRO) sign-off.
- Ensure the capture and retention of knowledge gained and lessons identified by individuals in the CSSF team before the individual changes role or leaves post, including MoD infrastructure projects, VfM opportunities, and commercial contracts.
- Establish a process that regularly checks and challenges the programme Results Framework (RF), including: a) milestones, targets, and disaggregation of appropriate data, and; b) the quality and quantity of the data used to inform progress.