Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Lebanon: Political Reform Programme
Programme ID	C-MNA-0020
Country and Region	Lebanon, Middle East and North Africa
IATI Unique ID	CSSF-06-000034
HMG Partners / (Lead in bold)	Foreign & Commonwealth Office (FCO) / Foreign, Commonwealth & Development Office (FCDO) from 2/9/2020
Total Budget	ODA: £4.69m	Non-ODA: £0
Budget this FY	ODA: £2.99m	Non-ODA: £0
Spend this FY	ODA: £2.03m	Non-ODA: £0
Time Frame	Start Date: April 2019	End Date: March 2022

Outputs	Scale of Delivery
Institutional capacity and systems built, incentives for constructive engagement and reform created in support of greater accountability and transparency, more responsive policy, and more equitable opportunities.	4
Diverse political actors supported to be credible future leaders (with a focus on women).	2
Demand and consensus increased in support of a new brand of politics (more diverse, inclusive and issue-based).	2
Overall Scale of Output Delivery	3

Outcome Assessment	Two prominent state institutions have been supported to be more transparent and engaged with the public and civil society. Wider benefits have included key ministries and municipalities making data-driven decisions, including around COVID-19 lockdowns; public engagement and trust have been built through the provision of a reliable digital platform to access certain services; and women from a diverse network of political affiliation have been engaged through a new project.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium-high

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A	N/A	N/A	N/A	A	A	3	Green
Risk Rating	N/A	N/A		N/A		Medium		Medium-high
Programme changes during this period		The programme has proactively adapted to multiple crises within the operating context in Lebanon (rapid political and economic decline, COVID-19, Beirut Port explosion) and taken the opportunities to utilise in-year uplifts where possible to ensure delivery towards impact remained ambitious.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
- Governance, Oversight and Accountability in Lebanon (GOAL) project supporting the Central Inspection Bureau to drive transparency, oversight and openness within national and sub-national institutions, delivered through Siren Associates.
- A parliamentary reform project which promoted better transparency and accountability in parliament; strengthened the role of women MPs; supported the parliamentary committees to become more open to the public and civil society; and facilitated the digitising of legislative processes, through Westminster Foundation for Democracy.
- Empowerment of women from emerging political parties, cross-sectarian dialogue between women in politics, gender analysis delivered through Global Partners Governance and UN Women.
- Media training for key institutions, delivered through UK’s Government Communications Service International.

Key Results for FY 20/21:
- The role and capacity of Central Inspection Bureau (an oversight and anti-corruption state body) was enhanced through training, media engagement, partnerships with civil society and a strengthened relationship with parliament.
- Rollout of a digital IMPACT platform provided real life data to national and municipal bodies, including decisions around Covid-19 lockdowns, which has changed the way citizens interact with state institutions. The application-based service has enabled the public to navigate national lockdowns and register for vaccinations.
- Parliamentary committees, including on Budget, Information Communication Technology, Human Rights, and Women and Children, became more open to inviting subject matter experts and civil society to legislative discussions. Key legislation was introduced including the Sexual Harassment Bill, which was passed in record time, ensuring justice for victims. Post-legislative scrutiny by public and civil society bodies has now started and the newly established parliamentary website has been developed. Scrutiny is set to further increase over the coming years, including closer collaboration with the IMPACT platform.
- An existing relationship with the UK’s Government Communications Service International (GCSI) was leveraged to provide short-term bespoke media training to key institutions and improve public trust.
- Women from diverse emerging political parties were brought together to formulate a joint plan around political transitions, paving the way for future partnerships in subsequent years.

Key Lessons
- There is a degree of parliamentary interest in public engagement and collaboration with civil society. Progress with the Digital Transformation Committee on post-legislative scrutiny processes and passing of key legislation shows that a collaborative approach amongst diverse actors produces strong results.
- Central Inspection Bureau is a strong institution, capable of delivering tangible progress towards transparency and openness demonstrating that efforts to reform from within the state administration can be effective as well as through civil society. Support for Central Inspection should continue, expanding beyond the currently already wide reach.
- Amongst a quickly deteriorating political and economic context in Lebanon, support for key state institutions to deliver against UK objectives of democracy and anti-corruption remains the right approach.

Key Recommendations for FY 21/22
- Agree a high-risk appetite for this politically sensitive programme and protect core elements from short-term reprioritisation and disruption in funding wherever possible. Results from this governance and reform work require commitment and long-term strategic investment if they are to come to fruition, despite a complex and volatile context. Multi-year CSSF funding would allow HMG and partners to strategically navigate the context, build the right relationships, and work towards addressing complex and deep-rooted drivers of conflict and instability that take time to change.
- Gather lessons on support for state institutions during the final year of programming. Assess whether the level of ambition and scope remains appropriate to inform future policy and programming.
- Conduct a broad gendered political economy analysis to inform understanding of power distribution in the political arena, set ambition for reform, and inform future policy and programming.
- Refresh the Theory of Change and results framework, noting the realities of the context in Lebanon, ensuring that gendered assumptions are properly considered, and ambition and indicators fit the ongoing activity.
- Continue building partnership between parliament and Central Inspection, applying digital learning to parliamentary systems and processes and to sub-national level institutions where possible.