Annual Review (20/21 Ver.) - Summary Sheet

Programme Title	Lebanon: Security Programme
Programme ID	C-MNA-0021
Country and Region	Lebanon, Middle East and North Africa
IATI Unique ID	CSSF-06-000005
HMG Partners / (Lead in bold)	Foreign & Commonwealth Office (FCO), Ministry of Defence (MOD) / Foreign, Commonwealth & Development Office (FCDO) from 2/9/2020
Total Budget	ODA: £33.43m	Non-ODA: £42.9m
Budget this FY	ODA: £8.18m	Non-ODA: £7.2m
Spend this FY	ODA: £12.78m	Non-ODA: £7.87m
Time Frame	Start Date: April 2019	End Date: March 2022

Outputs	Scale of Delivery
Lebanese Armed Forces (LAF) Land Border Regiments (LBRs) trained to plan and conduct land border operations that are conflict and gender sensitive and International Humanitarian Law (IHL) and Law of Armed Conflict (LOAC) compliant.	4
LAF officers and soldiers trained to plan and conduct urban operations that are conflict and gender sensitive and IHL and LOAC compliant.	4
Intelligence led policing capability enabling Internal Security Force (ISF) improved responsiveness to communities, aligned with community policing principles to prevent and combat crime and threats to community safety and security.	4
At-risk youth gain access to a safe haven - individualized, targeted and gender-sensitive services and assistance. Meeting pressing basic needs that otherwise act as obstacles to rehabilitation and reintegration.	3
Overall Scale of Output Delivery	4

Outcome Assessment	FY 20/21 witnessed an increasing intensity in the converging, constant crises facing Lebanon. The challenges of declining security, political uncertainty, growing public protest, and threats from transnational and non-state actors persisted, and worsened by the COVID-19 pandemic and August 4th Beirut blast. The Lebanon Security Programme (LSP) played a fundamental role in facilitating the Lebanese response. It is a well thought through and integrated programme, whose activities are mutually supportive. Given its limited scope, the LSP is unable to address the root causes of Lebanon’s political, economic and security woes, thus its targeting of building the capacity of the few security institutions deemed to be capable of affecting change is appropriate. The LSP also delivers, in a minor and limited way, against the UK’s national interests towards a more secure and stable Lebanon in the region. Performance against the LSP’s multi-year outcome targets is on track.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium-High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	A	A	B	A	A	B	B	4	Green
Risk Rating	High	High		High		High		Medium-High
Programme changes during this period		The programme has proactively adapted to multiple crises within the operating context in Lebanon (rapid political and economic decline, COVID-19, Beirut Port explosion) and taken the opportunities to utilise in-year uplifts, where possible, to maximise LSP impacts.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
The Lebanon Security Programme operated across three strands of work, contributing to improved security and a reduced threat to the UK:
- Improved border security via capacity building support to the Lebanese Armed Forces (LAF);
- Improved internal security, with greater human rights compliance, via capacity building support to the LAF and Internal Security Force (ISF), and refurbishment of ISF operations facilities;
- Reduced vulnerability to conflict and violence via targeted rehabilitation and communication activities with Lebanese and Palestinian communities.

Key Results for FY 20/21
Despite a multitude of crises facing Lebanon, with the potential to stall programme delivery during FY20/21, LSP has achieved significant results including:
- Improved capability of more than 2,500 Troops and Non-Commissioned Officers across LAF and ISF, through strategic and International Humanitarian Law training;
- 100% of evaluated Land Border Regiments of the LAF now meet expected standards;
- 22 refurbished control rooms have enabled enhanced command and control for ISF;
- Safer communities through Preventing Violent Extremism-related projects, where 84% of targeted vulnerable youth reject the use of violence for ideological or sectarian purposes.

Key Lessons

- The importance of relationship building as a way of understanding how to maximise the delivery of individual and organisational change. Examples include working within the ISF hierarchy, mentoring LAF commanders and officers, and supporting marginalised youth in Tripoli and Beirut.
- Long term engagement with beneficiaries at all levels of Lebanese society has been key to the programme’s success. More than a decade of support from the UK has enabled deep partnerships that go well beyond transactional relationships and provide influence for the UK.
- Results frameworks can be limiting and backwards-looking when tracking non-linear change within complex systems – although the CSSF does allow alternative approaches.

Key Recommendations for FY 21/22

- Despite the worsening situation in Lebanon, the UK’s support to reform the country’s security forces cannot be open-ended. We must develop a scenario planning document that will inform development of the next iteration of the LSP.
- The programme Results Framework (RF) does not capture all projects within the LSP at outcome level. Refresh the RF to include all elements of the UK’s support.
- Ahead of development of the next iteration of the LSP, deepen the programme’s Monitoring, Evaluation & Learning (MEL) plan for its final year. Assess whether to commission Third Party Monitoring, evaluations and / or a Stability Tracker.
- It is difficult to meet CSSF ambitions on gender mainstreaming in the absence of specialist resource at Post or in London. Ensure the right level of gender advisory support is available.