Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons, and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK
Programme Title	Libya Programme
Programme ID	C-MNA-0022
Country and Region	Libya, Middle East and North Africa
IATI Unique ID	CSSF-06-000006
HMG Partners / (Lead in bold)	Foreign Commonwealth & Office (FCO), Department for International Development (DFID) / Foreign, Commonwealth & Development Office (FCDO) from 2/9/2020
Total Budget	ODA: £50.7m	Non-ODA: £0.12m
Budget this FY	ODA: £12.4m	Non-ODA: £0.1m
Spend this FY	ODA: £9.14m	Non-ODA: £0.01m
Time Frame	Start Date: April 2018	End Date: March 2021

Outputs	Scale of Delivery
1.The threat of explosive remnants of war in target conflict-affected municipalities is decreased through clearance and increased awareness.	4
2. Basic services and economic assets in target areas are improved in increasingly more inclusive, participatory, and transparent ways, supported by better planned decentralisation.	3
3. Civil society (particularly women-led organisations) is more capable to engage in and shape civic life through access to more impartial media, free and fair local elections, and enhanced community action, including against COVID-19.	2
4. The UN political process is operationally and technically supported and complemented by more capable local level mediation mechanisms and peace-building initiatives.	3
5. Target Libyan entrepreneurs are provided with microfinance and/or business support, and key economic actors with technical assistance on reforms.	2
Overall Scale of Output Delivery	3

Outcome Assessment	The Libya CSSF Programme is a key tool for tackling the drivers of conflict and instability in Libya and to provide support for the political process. Despite the challenges of delivery in a volatile environment, the programme for FY 20/21 has demonstrated clear progress towards the four stated outcomes of “recovery”, “supporting inclusive change”, “social cohesion”, and “greater economic opportunity.”
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium-High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	A	A	B	A	A	A	A	3	Green
Risk Rating	High	Medium		Medium		Medium		Medium-High
Programme changes during this period		A challenging year for Libya as the programme coped with considerable uncertainty; political, security and social, and the impact of COVID-19, CSSF budget reductions, and delays in contracting. The programme has adapted in response to changing demands in the political and security landscape, and amended outcomes to support the UN-led peace process. The programme has taken action to incorporate the majority of recommendations from the previous annual review, in particular on strategic direction, programme management and coherence and conflict sensitivity.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

The UK continued to provide support to 14 projects designed to deliver the four programme outcomes centred on recovery, supporting inclusive change, improved social cohesion, and greater economic opportunity. The focus of each outcome had been revised this year to better support the Libyan peace process; the role of women and girls in shaping policy and service delivery; and the linkages between national and local provision of services.

Key Results for FY 20/21:

- Mine Clearance work has supported 148,000 people return to their homes. Our teams were the first to deploy when fighting ended - 1,714 explosive remnants of war were disposed of.
- Successfully influenced Libya’s decentralisation policy through our Sub-national governance project; local government has been more effective supporting communities via improved planning.
- Supported Civil Society Organisations (CSOs) across East, West and Southern Libya to respond to COVID-19, with a focus on women-led organisations. With a focus on a more open media environment through our El Kul project, tackling misinformation and myths around Covid-19.
- Successfully supported the UN mission in Libya via the United Nationals Development Programme (UNDP) and the United Nations Support Mission in Libya (UNSMIL). We helped the delivery of successful local elections in Libya through the UNDP Municipal Council elections.
- Supported communities to reach peaceful resolutions to local challenges through Social Peace Partnerships, creating community resilience to conflict, and developing social change projects and community resources.
- Supported Libya’s entrepreneurs through STREAM, including a business incubator and training programmes, creating 126 jobs. Working with Expertise France to support the Libyan Central Bank develop a microfinance regulatory framework to support future development of the sector. We also supported governance reforms for the Libyan Investment Authority (LIA).

Key Lessons

- Flexibility and Agility. As soon as fighting stopped in Tripoli the programme team was able to work quickly with mine action implementing partners to respond to the emergency situation and, thanks to CSSF flexibility, was able to reallocate unused funds towards southern Tripoli, to help with the response.
- Coordination and Synergy. The CSSF team facilitated meetings between implementers to discuss areas of potential collaboration, coordination and synergy with regards to gender-focused activities. The programme team was keen to avoid duplication and encourage knowledge sharing between the two implementing partners.
- Adaptability FY20-21 was especially demanding with open conflict; rapidly evolving political dynamics; Covid-related restrictions; and a significant delivery delay imposed by a 4-month central-CSSF contractual delay. The programme team and implementing partners flexed delivery with four new iterations of the work-plan in four months.

Key Recommendations for FY 21/22

- The CSSF Libya Programme should articulate better the objectives set out in the latest Libya Country Plan. The Theory of Change and Results Framework to be adjusted to reflect accordingly.
- Strategic Direction/Coherence - Collaboration between the Political & the Programme Teams to be increased in order to make best use of programme resources and outputs, both in terms of targeting and feeding outputs and outcomes into political planning.
- The current indicators are almost exclusively quantitative. They do not provide an effective or accurate picture of what is expected from each output, or what it has achieved – or enabled. Indicators should better reflect not only the numbers, but also the influence and impact on the programme more widely, in particular the connections to the political and security strands of activity.