Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Middle East Peace Process (MEPP) Programme
Programme ID	C-MNA-0023
Country and Region	Occupied Palestinian Territories (OPTs)/Israel, Middle East and North Africa
IATI Unique ID	CSSF-06-000023
HMG Partners / (Lead in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MoD), Department for International Development (DFID) Foreign, Commonwealth & Development Office (FCDO) from September 2020
Total Budget	ODA: £50.8m	Non-ODA: £3m
Budget this FY	ODA: £12.5m	Non-ODA: £0.5m
Spend this FY	ODA: £21.53m	Non-ODA: £0.38m
Time Frame	Start Date: April 2019	End Date: March 2022

Outputs	Scale of Delivery
Improved capability, accountability, sustainability and inclusivity of the Palestinian Authority Security Forces (PASF).	4
Effective legal assistance provided to Palestinians at risk of displacement in the West Bank and East Jerusalem.	3
Key infrastructure, particularly electricity provision, constructed in isolated parts of Area C, to facilitate continued Palestinian presence on their land.	4
Positive perceptions of, and strengthened support for, the 2SS and/or a mutually agreed peaceful solution to conflict amongst key religious and other relevant constituencies.	3
Palestinian women’s and people with disabilities’ ability to achieve leadership positions in Palestinian society enhanced.	3
Overall Scale of Output Delivery	4

Outcome Assessment	CSSF support has contributed towards making the PASF more capable, accountable, sustainable and inclusive, although the PASF has not made as much progress as hoped and concerns are growing about its accountability. As a result of CSSF projects, Palestinian presence in key areas of the West Bank is better protected, but long-term trends show a steady erosion of the physical viability of the 2SS. Little work has occurred on creating more favourable political conditions for peacebuilding this year.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium-High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	A	A	B	A	B	B	B	4	Amber
Risk Rating	Medium	Medium		Medium		Medium		Medium-High
Programme changes during this period		COVID-19 had an impact on some projects, cancellation, shifting of plans and priorities to respond to evolving needs and also the new restrictions (including lockdowns). The team was flexible and adjusted project budgets across the programme and also absorbed underspend to provide crucial funding to the UN Relief and Works Agency for Palestine Refugees (UNRWA) in March 2021.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
- Support the Palestinian Authority Security Sector (PASS) to improve its capability, accountability and sustainability.
- Support to vulnerable Palestinian communities in the West Bank (Area C and East Jerusalem) to help them stay on their land and to protect their property.
- Construction of infrastructure for electricity provision in isolated parts of Area C, to facilitate continued Palestinian presence on their land.
- Humanitarian protection, relief, infrastructure and advocacy work for Palestinians in the West Bank.
- Strengthening of Palestinian women’s and people with disabilities’ ability to achieve leadership positions in Palestinian society.
- Support to dialogue between Muslim and Jewish leaders and to promote understanding of, and support for, a two-state solution.

Key Results for FY 20/21
- PASS decision making and Central Joint Operations Command and Control Centre (CJOC3) capability has been strengthened, with staff trained, facilities and IT systems developed, and a legal framework approved by PASS chiefs and the Prime Minister
- The legal aid programme managed 1,565 cases on behalf of 1,475 Palestinians (1,203 male and 272 female) at imminent risk of displacement during the current year, helping 96% of them to remain on their land and their homes in the short-term as proceedings progressed.
- 85 additional households in the Jordan Valley (400 individuals) now have access to off-grid energy, bringing total number of communities served to 90 and about 8,000 individuals.
- 50,000 beneficiaries were reached with humanitarian aid during the current year, including 15,000 beneficiaries reached in COVID-19 responses. Responses focussed on demolitions, confiscations and settler violence.

Key Lessons
- Presence in key areas is crucial to providing good insights for political and programme work. Team and partner presence in the West Bank and Gaza provide crucial insights for both the UK and other donors. Local programme partners working on legal aid and humanitarian assistance provided helpful analysis and insights for the Consulate.
- The lack of understanding of, and interest, in the MEPP in Israeli society remains a key obstacle to progress. The general lack of interest harmed the project’s ability to engage publicly with issues. The leadership project found that young Israelis have low knowledge/access to information on the MEPP, yet high interest/enthusiasm.
- In-person events are crucial to the success of peacebuilding projects. Trust has been built through joint events pre-Covid and some of that was diminished when participants could not meet in person.

Key Recommendations for FY 21/22
- Use local procurement for all projects in the next phase of the programme.
- Extend at least two of the Outcome 3 projects until March 2023 in order for the projects to progress further and gather more evidence about the approach, and its effectiveness and impact.
- Extend independent evaluation’s role in Outcome 3 projects, and clarify/expand its role to cover Monitoring & Evaluation (M&E) capacity building for partners and longer-term assessment of (outcome-related) change.