Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	North Africa Technical Assistance Facility (TAF) Programme
Programme ID	C-MNA-0026
Country and Region	North Africa (Morocco, Egypt, Tunisia, Algeria and Libya), Middle East and North Africa
IATI Unique ID	CSSF-06-000022
HMG Partners / (Lead in bold)	Foreign and Commonwealth Office (FCO) Foreign, Commonwealth & Development Office (FCDO) from 2/9/2020
Total Budget	ODA: £14.1m	Non-ODA: £0
Budget this FY	ODA: £3.1m	Non-ODA: £0
Spend this FY	ODA: £5.05m	Non-ODA: £0
Time Frame	Start Date: June 2017	End Date: March 2022

Outputs	Scale of Delivery
High quality, relevant, demand-led, conflict and gender-sensitive technical assistance is delivered through the TAF.	4
The TAF generates learning on how technical assistance can bring about change and shares this across the North Africa Good Governance Fund (NAGGF) programme.	4
Overall Scale of Output Delivery	4

Outcome Assessment	COVID-19 presented an unparalleled challenge to both the region and to FCDO’s programming over the course of FY20/21. Despite this, the North Africa Technical Assistance Facility (NATAF) has delivered effectively against outcomes, meeting or exceeding all targets. NATAF has adopted different ways of working to minimise the disruption to planned technical assistance, and even adapt to new and emerging priorities. As the NATAF moves into its final year of programming, the review finds that NATAF’s theory of change remains valid and that a regional facility for medium-term technical assistance is an impactful, cost effective, flexible and strategic way to build partnerships and achieve HMG’s objectives in North Africa.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium-Low

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	C	A	A/B	A	B	A	A	4	Green
Risk Rating	Medium-High	Medium-Low		Moderate		Medium		Medium-Low
Programme changes during this period		A commitment to spend at least 15% of funds on GEM 2 classified work. / Beginning to track climate related spend for HMG International Climate Fund (ICF) targets, a first for CSSF. / A commitment to increase Technical Assistance (TA) in Libya, as an HMG priority country.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21? The UK funded 34 Technical Assistance (TA) projects across Morocco, Tunisia, Egypt, Libya and Algeria. These spanned governance, economic, climate, security and justice, and Preventing Violent Extremism (PVE); and have ranged from embedded technical assistance, provision of technical specialists and consultants, tailored training, peer to peer information exchanges, and a variety of research papers and studies.

Key Results for FY 20/21:

These include the establishment of, and contribution to, 48 new relationships between HMG and stakeholders, enabled via 32 separate projects; identification of 48 different instances where there has been a significant change in policy or practice; 12 instances where NATAF’s support has led to partner governments or other donors committing to wider reform; and six instances where HMG facing analysis delivered through the TAF has improved wider programmes. Of note are the following projects:

- NATAF’s contribution to key reforms in Libya.
- NATAF contributions to a critical new relationship in Morocco.
- NATAF support to HMG analysis and policy on North Africa.

Key Lessons

The role of technical assistance (TA) in delivering HMG’s objectives has been proven, as has NATAF as an effective mechanism for the UK to build relationships in the region. However, further political engagement from Embassies will enhance TA.

Designing TA with strategic and sustainable objectives in mind, and ensuring it sits within broader political discussions, can maximise its potential to contribute to long-term sustainable change. Good quality TA is also more likely to bring sustainable change if complemented with political dialogue, outreach and early policy-level engagement

There is a clear imbalance in demand across the region. The loss of advisory capacity across North Africa is the biggest risk factor to designing effective, impactful TA.

TA is critical for both the guidance and ownership of a particular project, articulation and refinement of a host government ask, and an assessment of likely reform, sustainability and value for money.

Multi-phase projects can be a good way to maximise the potential of TA to contribute to sustainable change. Longer term commitments are an effective way to build trust and credibility as well as obtaining partner government stakeholders to buy into reform. Short-term TA, such as scoping, can be strategic, but it must be designed with a longer-term strategy in mind.

Key Recommendations for FY 21/22

It will be essential to ensure that sufficient advisory support is in place to ensure the safe and responsible closure of current projects, and development of new areas of work.

As consideration is given to a successor programme, a scoping exercise should take place to understand demand across MENA. A lessons learnt report should also be captured as well as consideration as to what can be conducted in-house by HMG.

TAF projects should be considered as force multipliers to wider CSSF programming and political relationships. Formal ownership by Country Boards should be agreed, and an in-country SRO.

NATAF project managers and North Africa Department programme team should engage beneficiaries, implementers and political desks near project end to consider next steps, agree comms, and sustainability plans.

NAD and Tetra Tech should consider the utility of the current Results Framework in capturing qualitative change and impact. In the final year of the programme, the NAD team should consider introducing Output weightings, recognising the shifts in importance of Outcome 2&3 as NATAF draws to a close.