Programme Completion Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. As the final review for the programme, it should be read in conjunction with previous Annual Review Summary Sheets to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	North Africa Regional Cooperation Fund Programme
Programme ID	C-MNA-0024
Country and Region	North Africa (Morocco, Egypt, Tunisia, Algeria and Libya), Middle East and North Africa
IATI Unique ID	CSSF-06-000021
HMG Partners / (Lead in bold)	Foreign and Commonwealth Office (FCO) Foreign, Commonwealth & Development Office (FCDO) from 2/9/2020
Total Budget	ODA: £11.5m	Non-ODA: £0
Total Spend	ODA: £8.34m	Non-ODA: £0
Time Frame	Start Date: April 2018	End Date: March 2021

Outputs	Scale of Delivery
Output 1: Support for a diverse group of organisations (multilateral, regional and national) to bring together gender sensitive networks of Civil Society Organisations (CSOs), state actors and individuals, on regional issues.	3
Output 2: Support for organisations and institutions to build capacity of staff to engage on regional issues in North Africa.	4
Output 3: Support for political access & influencing by HMG. This includes political engagement, strategic communication, lesson learning, programme incubation & adaptations.	4
Final Overall Scale of Output Delivery	3

Outcome Assessment	FY20/21 was a difficult year for the Regional Cooperation Fund (RCF) given the impacts of COVID-19 and the budget reductions due to the ODA reprioritisation. This stemmed some of the early cooperation which RCF fostered in its first two years of operation and meant these could not be developed through a successor programme. Nevertheless, given the short implementation period for the RCF, some successful in-roads were made: HMG convened numerous regional networks and established the structures and capacities for fostering regional cooperation around various thematic priorities.
Final Overall Scale of Outcome Achievement:		3
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	C	A	B	A	A	A	A	3	3
Risk Rating	Medium/High	Medium		Medium		Medium		Medium
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide in FY 20/21?

Delivery of research, training and advocacy activities, network development and a region-wide monitoring and evaluation contract, to support regional cooperation on common and transnational challenges in North Africa. This included:

- United Nations Women – research, advocacy and network building on Gender Equality and Violent Extremism in North Africa (GENEVA).
- United Nations Office on Drugs and Crime (UNODC) – training, technical assistance and network building to judiciary, police, and prosecutors in Egypt, Algeria, Libya and Tunisia; to strengthen response to smuggling of migrants, trafficking and illicit finance.
- Centre for Mediterranean Integration (CMI) – research and network building on the water- migration nexus in North Africa.
- Chatham House - research and network building through the North Africa Dialogue Series.
- Carnegie Middle East Centre – promoting democratic governance of Arab militaries through the Civil Military Relations in Arab States programme.
- World Bank MENA Multi-Donor Trust Fund (MDTF) - contribution to the WB MDTF, underpinning the WB’s regional strategy for Middle East and North Africa (MENA).
- North Africa Monitoring Evaluation and Learning – funding ITAD to provide monitoring, evaluation and learning (MEL) support to CSSF programmes across North Africa.
- European Bank of Reconstruction and Development (EBRD) – funding to the EBRD regional MDTF to influence their regional strategy in MENA, later repurposed to support women’s small and medium enterprises (SMEs) in Egypt.
- NAMEL- funding to ITAD for North Africa Regional Monitoring, Learning and Evaluation

What Results Did the Programme Deliver? Will they be Sustained?

UN Women created the first regional platform of North African stakeholders for policy reform to tackle the gendered dimensions of violent extremism. The Platform is now co-chaired by the UN Counter Terrorism Directorate (Sub-Committee to the UN Security Council).

UNODC showed early success towards regional cooperation on trafficking in persons (TiP) and smuggling of migrants (SoM). This was achieved by bringing together high-level national criminal justice actors from across the region on cooperation in TiP and SoM cases.

Chatham House convened four dialogues on shared challenges in North Africa. Meetings focused on regional integration, security and extremism, informality in borderlands and trade and investment. with representation from each NA country, across civil society, the business community, academia, IFI’s and multilaterals.

Carnegie Middle East Centre established the Tawazun platform, an interactive platform containing information on the defence sectors of Tunisia, Egypt, Lebanon and Syria. This tool is a key source of information for civilians upskilling themselves on Arab militaries, supports civilians in holding their governments to account on the practices of militaries.

The Centre for Mediterranean Integration produced a first of its kind study to generate new national climate data sets for Morocco (temperature & rainfall under different climate scenarios).

The World Bank MENA MDTF falls under a broader effort of the RCF (along with support to the EBRD) to leverage the much greater multilateral funds of IFIs, and influence their reach, expertise, and influence across the region.

North Africa Monitoring, Evaluation and Learning (NAMEL) worked across the three years of the contract providing MEL to North Africa and the North Africa Good Governance Fund.

What Lessons Have Been Learnt?

While the value of regional cooperation in North Africa is clear, the process is a slow burn phenomenon and improvements towards integration will be small scale and incremental. Commitment to this agenda must recognise this and be content with small returns on investment, or otherwise consider other, longer term funding mechanisms (i.e. not CSSF).

Projects are most successful at delivering results where recipients are engaged and enthusiastic. Some projects were more successful with non-governmental partners who were keen to discuss and improve ways of cooperating regionally, and who often have stronger regional networks and audiences to influence policy.

Seeking cross departmental buy-in and ownership of regional programming remains crucial, as does senior engagement and approval at post to ensure regional projects re-enforce posts’ priority objectives.