Programme Completion Review (20/21 Ver.) - Summary Sheet

Programme Title	Syria: Civilian Protection and Community Resilience (CPCR) Programme
Programme ID	C-MNA-0028
Country and Region	Syria, Middle East and North Africa
IATI Unique ID	CSSF-06-000035
HMG Partners / (Lead in bold)	Foreign and Commonwealth Office (FCO) Foreign, Commonwealth & Development Office (FCDO) from 2/9/2020
Total Budget	ODA: £5.1m	Non-ODA: £0
Total Spend	ODA: £5.29m	Non-ODA: £0
Time Frame	Start Date: April 2020	End Date: March 2021

Outputs	Scale of Delivery
Output 1 Syria Civil Defence (SCD) organisational capacity is strengthened.	4
Output 2 Syria Civil Defence (SCD) maintains current operating capability in areas of operation and improves technical operational capacity.	4
Output 3 Sentry Early Warning System (EWS) is maintained and expanded.	4
Final Overall Scale of Output Delivery	4

Outcome Assessment	The CPCR programme makes an important contribution to enabling the stability of Northwest Syria and supporting the conditions for long-term political and social change, by continuing to provide essential lifesaving, healthcare and security services. A period of relative stability has reduced the immediate demand for SCD search and rescue services and EWS alerts, which has been substituted by work to clear the debris of previous attacks, equip civilian infrastructure with alarms for future attacks, and a focus on women’s centres. The positive impact of this work on communities is included/stated in FCDO commissioned third party monitoring and implementing partner survey data, [albeit non-sex-disaggregated]. There is a clear need for the continued availability of these emergency response and EWS services whilst the trajectory of the conflict remains unclear, and Northwest Syria continues to be subject to daily airstrikes, with a more pronounced spike in March 2021.
Final Overall Scale of Outcome Achievement:		4
Overall Risk Rating:		Medium-High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A	N/A	N/A	N/A	N/A	N/A	4	4
Risk Rating	N/A	N/A		N/A		N/A		Medium-High
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?

The CPCR Programme is the latest iteration of the UK’s adaptive support in Northwest Syria. It contributed to early recovery and service delivery activities; and filled crucial gaps in the humanitarian response in Northwest Syria by providing emergency civil protection, first response and service delivery activity. It met immediate civilian needs and made an important contribution to the resilience of communities. Within FY20/21 the UK provided:
- Support to civilian protection via the White Helmets/SCD (from late December 2020 to end March 2021)
- Increased security and accountability through the Sentry Early Warning System (throughout FY20/21)
What Results Did the Programme Deliver? Will they be Sustained?

Whilst levels of violence in Northwest Syria were at a lower level in FY20/21 compared with previous years, due to the March 2020 ceasefire brokered by Turkey and Russia, services from CPCR partners remained relevant in responding to the needs of Syrian communities. Results included:
- Early warning ahead of 80% of air strikes.
- Financial support for more than 2,300 White Helmets volunteers.
- Continue operation of 151 SCD Service Centres, including comprehensive access to women’s services.
- More than 8,000 White Helmets service delivery activities per week, on average.
- Strengthening of SCD organisational capacity.

What Lessons Have Been Learnt?

Implementing partner key lessons tend to focus on the practicalities of project implementation, including:

- Flexing the modality for financial support can reduce risks to service delivery. The lead implementing partner’s decision to pre-pay part of sub-awards to SCD from its own cashflow significantly improved the sub-awardee’s ability to deliver.
- Delegation and capacity building can have broader positive effects. Allowing Syrian in-country trainers to manage their own time increased their productivity and satisfaction; capacity building for women increased their assertiveness in all aspects of their working life