Title: Climate Resilient Cities for Shared Prosperity Programme (CReSP)[1]
Programme Value £ (full life): £6.98m / Review Period: August 2020 – March 2022	Review Date: 13 December 2022
Start Date: 17 June 2019	End Date: 31 March 2023
[1] Previously known as ‘Sustainable Cities for Shared Prosperity (SCSP)’

Summary of Programme Performance
Year	April 2017 – July 2019	August 2019 – July 2020	August 2020 – March 2022	April 2022 – March 2023
Programme Score	A[2]	A[3]	A
Risk Rating	Moderate	Moderate	Moderate
[2] The CReSP programme was reviewed as part of the portfolio-level annual review of the former India Economic Reform and Prosperity Programme and was scored accordingly.
[3] The CReSP programme was reviewed as part of the portfolio-level annual review of the former India Economic Reform and Prosperity Programme and was scored accordingly.

List of Acronyms
ABB	Activity Based Budgeting	ITP	Integrated Transport Platform
ACS	Additional Chief Secretary	ITT	Invitation to Tender
ADG	Additional Director General	KPI	Key Performance Indicators
BDHC	British Deputy High Commission	KRIDE	Karnataka Rail Infrastructure Development Company Limited
BIM	Building Information Modelling	MM	Mott MacDonald
BMLTA	Bengaluru Metropolitan Land Transport Authority	MMH	Multi Modal Hub
BSUP	Bengaluru Sub-Urban Project	MoEFCC	Ministry of Environment, Forest and Climate Change
BS	Billing Schedule	MoHUA	Ministry of Housing & Urban Affairs
CBID	Capacity Building Institutional Development	MoU	Memorandum of Understanding
COP26	26th session Conference of Parties	MREL	Monitoring, Reporting, Evaluation, Learning
CMWSSB	Chennai Metropolitan Water Supply & Sewerage Board	NAR	Need Assessment Report
CPWD	Central Public Works Department	NIUA	National Institute of Urban Affairs
CRESP	Climate Resilient Cities for Shared Prosperity	NGO	Non-Governmental Organisation
C&D	Construction and Demolition	ODA	Official Development Assistance
DFID	Department for International Development	PA	Prosperity Advisor
DHC	Deputy High Commissioner	PDSF	Project Delivery Skills Framework
DIT	Department for International Trade	PIDG	Private Infrastructure Development Group
DULT	Directorate of Urban Land Transport	PMC	Pune Municipal Corporation
EDP	Extended Design Phase	SB	Secondary Benefit
EV	Electric Vehicle	SLA	Service Level Agreement
FCDO	Foreign Commonwealth and Development Office	SLP	Service Level Performance
FGD	Focus Group Discussion	SMC	Surat Municipal Corporation
GESI	Gender Equality and Social Inclusion	SmUDI	Smart Urban Development in Indian States
GoI	Government of India	SRO	Senior Responsible Officer
GoTN	Government of Tamil Nadu	TA	Technical Assistance
G&I	Gender and Inclusion	TNSDMA	Tamil Nadu State Disaster Management Authority
G2G	Government-to-Government	TS	Technical Skills
HMG	Her Majesty’s Government	UK	United Kingdom
HVP	High Value Project	UKEF	UK Export Finance
ICF	International Climate Fund	VfM	Value for Money
ITA	Integrated Transport Authority	ToC	Theory of Change

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

This is the first annual review of the ‘Climate Resilient Cities for Shared Prosperity’ (CReSP) programme as a standalone programme. Earlier, it has been reviewed twice as part of the portfolio-level review of the former India Economic Reform and Prosperity Programme (or the India Prosperity Fund Programme). This review covers the period August’20 – March 2022. The initial draft by outgoing SRO in December 2021 was left as a handover task for the incoming team. Thus, the AR was updated and reviewed again in Q4 2021 since the new programme team was assigned. The programme’s objective being ‘Acting as a catalyst for transformational change in the way urbanisation is delivered in India through targeted technical assistance (TA) to promote climate resilience, low carbon development strategies and inclusive socioeconomic growth’. The programme focuses on three outputs:
1. Output 1 – Overcoming barriers to investment by supporting the development of at least five high-value (min. £100m each) urban interventions in the project preparation process which will ultimately culminate in publishing invitation to tenders (ITTs) worth £500m, at least, to the market.
2. Output 2 – Upskilling relevant urban stakeholders so they are better able to deliver urban interventions to international standards and promote quality infrastructure interventions, inclusivity, sustainability and widely-shared prosperity.
3. Output 3 – Improving collaboration between urban actors; disseminating lessons from both domestic and international experience in inclusive and sustainable urbanisation.
CReSP contributes to deliver UK’s climate commitment under the International Climate Fund (ICF) and demonstrates UK’s global expertise in enhancing climate and environmental benefits. The ICF contribution to the programme is benchmarked at 49% which was enhance during the FY 20-21 in agreement with ex-FCO prosperity fund programme SRO.
With the identification of interventions across the three Outputs at the end of the design phase in March 2020, the programme was ready to move into the implementation phase. However, with the outbreak of Covid-19 and ODA reprioritisation exercise CReSP was repurposed to deliver revised UK’s priorities on climate change and pandemic resilience with Indian cities. This exercise was completed after multiple level of consultations with CReSP cities and delivery partners, following which a contract variation order was signed in October’20 to commence the implementation phase of the programme. Hence, majority of the reporting (August’20 – July’21) in this Annual Review relates to the implementation phase period and some from the Extended Design Phase.
Thereafter, the key step of formalisation of engagement between the FCDO and the 5 Project Authorities (from five states and cities of India) / project implementing agencies was concluded by May 2021. However, the programme faced a major hurdle due to the second wave of Covid-19, which peaked in April-May 2021 and changed the priorities of the government agencies towards management of the pandemic. This was followed by a yet another round of ODA budget cut which resulted in a 77% reduction in the CReSP’s programme delivery budget available for the remainder of 2021-22.
The twin impact led to a further review of the programme to establish areas where programme objectives could be met within the revised funding envelope and remaining time available (up to March 2023):
- Output 1 was prioritised and team secured commitments to deliver the high value project led interventions identified with 5 partner cities.
- Interventions under Output 2 were significantly cut down to manage budgets. four capacity building thematic trainings were agreed.
- Under Output 3 activities supporting the setting up of an Integrated Transport Authority (ITA) in Bengaluru and establishing the framework and implementation of pilot initiatives as part of the Integrated Transport Platform (ITP) were prioritised to be continued as they appeared most relevant to deliveries under Output 1.
.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The CReSP programme has been rated ‘’A” (programme met expectation).

Given the challenges on significant reduced allocation and COVID-19 delays, the programme set a good example in adjusting to change and delivering the first set of technical validation studies for all the 5 high value projects with UK best practices comparable studies.

The programme has demonstrated flexibility to adjust to management and operational changes and ensured constant engagement with the implementing agencies and concerned State Departments to secure buy-in and conclude the validation of technical review reports . Based on positive engagements, some cities / government authorities sought additional TA support in select policy work beyond the targeted assistance to the design and delivery of the HVPs. One such example include the Building Information Modelling (BIM) policy adaptation work with NITI Aayog and policy support on setting up the Integrated Transport Authority (ITA) support to Directorate of Urban Land Transport (DULT),Bengaluru.

Major lessons and recommendations for the year ahead [1/2 page]

Lessons
- The programme has benefited from flexible and agile programme management to adjust to the significant changes in the operating environment. However, these changes require continued close monitoring (of both financial, delivery, and risk developments) to meet budget forecasts, timely mitigation of risks and ensure progress to programme outcomes.
- Overall, engagement with the state and city level agencies has been challenging and time consuming. Formalisation took substantially longer than expected and sharing of information and interactions continues to be very slow with certain project authorities. For example engagement on the Surat High Value Project (HVP) has been put on hold unilaterally by the Surat Municipal Corporation (SMC), the project authority, since June 2021 due to delays in securing requisite project approvals internally.
- Change of personnel at the project authority level has greatly impacted the programme. For example in Chennai, change of leadership / transfer of bureaucrats (who were managing the project) following the state assembly elections slowed down the progress.
- Close coordination with the Prosperity Advisors based out of the different British Deputy High Commission (BDHC) offices and in the HVP cities has been useful in engagements with the implementing agencies / project authorities and addressing operational challenges – and should be continued.
- Regular interactions with the wider ‘Infrastructure & Urban’ team at the FCDO and DIT team have proven to be beneficial in progressing activities during the lockdown periods and beyond, for e.g. in project prioritisation during the Design Phase through consultative workshops, exploring synergies with other X-HMG programmes e.g. SmUDI, showcasing of the 5 HVPs under CReSP at DIT’s roadshow events etc.

Recommendations
- The programme will need to be agile for future uncertainties in relation to the pandemic, changing priorities of HVP cities / states and reduced budget allocation scenarios for CReSP programme in FY 2022-23. It will therefore be critical to continue with flexible and agile programme management and maintain as close an engagement as possible with the implementing agencies with the support of BDHC offices to keep progressing, while ensuring effective financial management and mitigation of risks. Action: CReSP (SRO) + Mott MacDonald
- Efforts to limit further significant changes to the programme and devising a robust communication plan to showcase HVP’s and TA support to cities as this will be final years for implementation and cities will be tendering out the HVPs. Action: CReSP (SRO) + Mott MacDonald
- Opportunities to make available development capital though UK funding sources e.g. CDC, PIDG, UKEF, etc. facilitated by the FCDO need to be explored as they could stimulate beneficiary agencies to be more proactive and support delivery of outputs within the programme timelines. Action: FCDO Infrastructure & Urban team + Mott MacDonald
- Engagement with city authorities should continue to help identify short-term requirements that may be met through the CReSP agile budget. Action: Mott MacDonald + BDHCs + CReSP (SRO)
- Appropriate KPIs need to be finalised in alignment with the ICF requirements for reporting. Once finalised, report cumulative results against the agreed ICF KPIs. Action: Mott MacDonald + CReSP Task Team
- Programme to continue to work with suppliers to ensure GESI aspects are robustly monitored (ensuring disaggregated data) and managed. Action: Mott MacDonald
- Continue to document innovations, effective strategies, lessons learned and best practices case studies and disseminate in series of knowledge transfer webinars / learning modules with other cities via other BHC programmes teams. Action: Mott MacDonald and CReSP (SRO)
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The programme theory of change (ToC) was initially developed in March 2020. As detailed in Section A, the scope of the programme has since been updated and the ToC reviewed at two key points:
1. During the extended design phase (EDP) March-September 2020, in light of the Covid-19 outbreak, nationwide lockdowns, and shift in priorities of Governments and partner cities
2. In June/July 2021 in line with cuts to the CReSP programme budget following the budget review.
The core programme rationale and logic through the three workstreams remain broadly as was initially envisaged. However, as a result of the budget review a number of activities were scaled back or dropped, which in turn have impacted on the breadth and depth of programme outcomes as they were initially envisaged. The major resulting changes to the ToC are as below:
- Outcome 1: Cuts to programme activities limit the degree to which significant outcomes outside of the footprint of the programme (as was envisaged via the ‘first follower’ organisations) will be realised. References to ‘first followers’ are therefore no longer included in the ToC or logframe.
- Outcome 2: Institutional reform activities have been scaled back. The programme focuses on capacity building / institutionalisation of training (rather than policy change) as a route to reform.
- Outcome 3: Partnership building activities have been scaled back, with a reduced emphasis on formalised partnership development (i.e. through MoUs). Collaboration and sharing of international best practice (through less formalised routes) remain a key change pathway.
- Outcome 4 and 5: These outcomes captured expected Secondary Benefits of the programme explicitly (under separate benefit statements). Following the logframe and ToC review, (indirect) outcomes 4 & 5 were included under the existing outcomes 1-3, to improve the clarity of the ToC – and clearly demonstrate secondary benefit causal linkages within the 3 core workstreams.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]
Overall programme is broadly on track to contribute to the expected outcomes and impact (with limited budgets), despite major challenges in relation to Covid-19 and the budget review. In the year ahead, CRESP will work closely with partner cities in fast-tracking the detailed engineering and financial viability assessment studies to expedite the HVPs bidding strategy. CReSP will work closely with DIT and BDHC nodal teams to engage on exploring marketing strategies and UK businesses exposure to HVP opportunities in partner cities.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

The programme rationale as outlined in the ToC remains valid: there is still a significant needs gap in Indian Public Sector urban planning in relation to: a) Accessing public sector funding; b) skills/capabilities in public sector urban planning and procurement to international standards; and c) embedding and prioritising climate, environmental, GESI and pandemic resilience considerations into urban design etc.

The change pathways outlined through the process of bringing CReSP HVP to market remain valid and are expected to lead to achievement of the programme outcomes. The HVPs will showcase international best practice in project design, procurement, and across the infrastructure life cycle, and act as exemplars, providing CRESP partners with real examples of how to attract finance and use a citizen-centric and climate-and environmentally responsive approaches.

The programme continues to demonstrate good value for money and has also demonstrated significant flexibility and adaptability throughout a difficult and changeable implementing context – developing additional TA activities beyond the initial scope that further support the original programme rationale and progress towards outcomes. Implementation of the CReSP programme and associated commitments made also help cement relationships between HMG and a wide group of Indian urban sector stakeholders, which lay the foundations for future collaboration, partnerships, and trade opportunities. It will need to continue to do so and ensure a sustainable exit in its last year.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	A set of large scale, high-value, exemplar urban interventions (HVPs) with ITTs amounting to £500m are developed and brought to the market that exemplify climate resilience, and promote inclusive economic growth, poverty reduction.
Output number:	1	Output Score:	A
Impact weighting (%):	65%	Weighting revised since last AR?	Yes, up from 60% (following budget review/re-pivoting of the programme)

Briefly describe the output’s activities, and provide supporting narrative for the score.
[max 1/2 page]

Indicator(s)	Milestone(s) for this review	Progress (August’20-March’22)
Output Primary indicator 1e: / 'No. of International Best Practices (Finance and GESI) and GESI Safeguarding interventions for each of the HVPs that elaborate sustainability and inclusive construction practices	Total target = 13	Achieved Submitted and approved = 13 best practices shared / 5 Project Finance - Best Practices (All 5 HVPs) / 5 GESI and Safeguards – Best Practices (All 5 HVPs) / 3 Sustainable and Inclusive Construction Practices - Best Practices Reports (Chennai, Bengaluru, Surat).
Output Primary Indicator 1f: / 'No. of Technical Reviews prepared that elaborate application of best practices for identified project components, through conceptual design stage	Total target = 10 technical reviews	Submitted and approved = 5 total / 5 Technical Review – Best Practices Report for Inter-city Multi modal Hubs (Bengaluru) / Technical Review – Best Practices Report Toolkit for Intra-city Multi modal Hubs (Bengaluru). / The key findings of these reports will lead to good practice recommendations on the design of KR Market Multi-modal hub and the 3 inter-city hubs at Bengaluru.
Output Primary Indicator 1g: / Report on formalisation with Implementing Agency	Total target / By July’21 = 5	Submitted and approved = 5 total / 5 Reports on formalisation with Implementing Agency (one for each HVP) on receipt of Letters of Intent. / These document the entire process of obtaining confirmation of interest from implementing agencies to avail the TA towards delivering the high value projects.
Output Secondary Indicator 1k: / No. of market engagement and international trade events, conventions, or conferences at which CRESP HVPs are promoted/ showcased (to attract investors and service providers)	Total target = 4 events	Events participated in to showcase CReSP to international audience= 2 total / UK South Asia Virtual Roadshow - Why India Why Now – Role of Technology for Smart, Sustainable and Resilient cities (organised by the DIT on 11th Nov 2020) / Partners for growth: Unlocking sustainable and climate-resilient infrastructure opportunities between the UK and India (4th March 2021).

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

Actual spend has been aligned to allocation for Output-1 from June 2019-July 2021 (Table D1). Deliverables / reports were submitted and discussed with the partner cities and nodal persons , the good practices were compared with existing project design features and recommendations including the GESI and environmental safeguards were agreed for inclusion in the final tendering documents by the implementing agencies in Bengaluru, Pune,

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Due to a reduced funding envelope, a number of milestones under Output 1 have been rationalised/ combined (e.g. benefit assessments, business cases and project financing plans have been combined). This has reduced the total number of milestones / deliverables being produced under some indicators and corresponding modifications in milestones/targets have also been made.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Climate change and sustainability themes are being integrated as key elements in recommendations, in order to enhance potential climate outcomes of the HVPs and/or support HVP implementing agencies to access climate finance. The 5 HVPs are currently being reviewed for ICF alignment. GESI Action plans have been developed for each HVP, and disaggregation is applied where possible to logframe indicators to support robust monitoring and management of GESI aspects.

Output 2
Output Title	Officials, including women, upskilled to address capacity gaps and new approaches to access project delivery skills
Output number:	2	Output Score:	B
Impact weighting (%):	20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress (August’20-March’22)
Output Primary Indicator 2a: No. of curriculum modules drafted for the training programmes	Total target = 8 (till programme closure)	Submitted = 1 / BIM -Awareness curriculum module / BIM Awareness Workshops - 2 Workshops were delivered viz. / A workshop specifically for the officials of the Central Public Works Department (CPWD) from 3-4th Sept 2020 / An Industry wide workshop on BIM from 11th-14th Dec 2020 / Support the Central Public Works Department (CPWD), Government of India to better recover, recycle / treat and reuse / utilise the construction and demolition (C & D) waste generated in India, by drawing in international best practice, including from the UK, to effectively reduce environmental impact in terms of energy consumption, pollution, waste disposal and management. / A 2-day Knowledge Exchange (KE) Workshop was organized virtually on 4 & 5th November 2020 to bring together the relevant industry stakeholders, policy makers and national and international experts, (including those from the UK), to share their insights and experiences to improve the overall applicability and uptake of C&D waste recycling in the country.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

Total savings against cumulative financial spend for Output-2 programme delivery from June 2019-July 2021 is 38% (Table D1). The programme has been kept agile to flexibly plan deliverables (e.g. preparation of a single (Final) Need Assessment Report (NAR) that comprehensively addresses all CBID themes; surveys (for NAR) and workshops (for BIM) have also been conducted online which has led to efficiencies and savings.
The activities were largely delivered as planned. Capacity building needs were assessed amongst HVP implementing agencies and the findings were discussed with the wider FCDO team to prioritise and finalise themes and titles for training in this financial year. This entire process as well as the BIM roadmap have been evolved through a consultative process. Participants to the training sessions will now include a wider set of stakeholders, as these are proposed to be conducted online, enabling benefits to reach a wider group and leading to better impact.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Specific capacity building needs were identified through surveys and interactions with HVP implementing agencies. 23 topics have been identified for training based on the Need Assessment surveys. These have been prioritised through a workshop with the x-HMG team in Aug 2021. A CBID Action Plan has also been prepared for delivery, in accordance with which the training curriculum and schedule is being developed within the available budget, to be delivered in FY 2021-22 and beyond.

Given the major reduction in programme budget in 2021, the number of different capacity building themes has been limited to 4 priority areas and these will be delivered in virtual classroom mode..

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The identification and finalisation of themes for capacity building and BIM have been undertaken in a consultative manner to secure buy-in of stakeholders and beneficiaries. The trainings will be delivered using online tools, building upon the experience of effectively delivering workshops on BIM remotely across a wide audience.

Output 3

Output Title	International experience in inclusive, sustainable and climate-resilient transport and urbanisation is identified and disseminated via partnerships and collaboration between national and international actors
Output number:	3	Output Score:	A
Impact weighting (%):	14%	Weighting revised since last AR?	Yes, down from 20% (following budget review/re-pivoting of the programme)

Indicator(s)	Milestone(s) for this review	Progress (August’20-March’22)
Primary Indicator 3b: / 'No. of reports/manuals submitted encompassing innovations in ITA and ITP, including organisational options, that contribute towards the programme objectives	Total target = 2	Submitted and approved = 2 total / Identification of the integrated transport authority model suitable for Bengaluru (Draft Report) / Integrated Transport Platform (pilot for Urban Observatory) + Manual (Draft report) (Bengaluru) / These will support the operationalisation of the BMLTA, BMLTA organisation structure, Urban Transport Fund and the ITP. / The best practices for operationalisation of similar ITAs including TFL across the world. These form the basis for evolving recommendations in the Draft report.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

Total savings generated against cumulative financial spend for Output-3 programme delivery from June 2019-July 2021 is 23% (Table D1). The activities in Output 3 were largely delivered as planned. The milestones / deliverables and recommendations have been well received by the implementing agency DULT, and are being utilised as mentioned above.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

As per the recent contract variation, due to major reductions in the programme budgets, Output 3 deliveries will be limited to assisting DULT in operationalisation of the BMLTA (ITA) and in defining a framework and implementation plan for a pilot on ITP for setting up a centralised parking portal, and planning data sets which the city can use in future (as part of ITP). As a result of reductions in the programme budget, other output 3 indicators relating to the City Supply Chain platform, and formalised partnerships have been dropped from the delivery plan.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Additional support has been sought by city governments on (a) sustainability and access to green financing by Karnataka Railway Infrastructure Development Ltd. (KRIDE) (A Joint Venture between the Ministry of Railways and the Government of Karnataka) for their project ‘Bengaluru Sub-Urban Railway Project (BSUP)’ in Bengaluru and (b) support to the Pune Municipal Corporation (PMC) to develop climate and air action plans, Electric Vehicle (EV) policy for Pune city. These were under active consideration and have now been included under CReSP for delivery. Achievements on these activities will be reported in the next annual review 2021-22. These interventions will enhance the focus on climate change under the programme to a significant extent.

Along with CReSP, couple of short-term projects (duration of delivery < 6 months) were also delivered and concluded during the review period. Key achievements, highlights and lessons learnt for such projects have been captured below.

D: RISK [½ to 1 page]

Overview of risk management: MODERATE

The Risk Register in requisite template is populated periodically mapping risks in each of the six risk categories and is closely monitored. Out of all categories major addition of risks were in the context category due to direct or indirect impact of continued pandemic situation in India and the UK. The programme has been kept agile and mitigation measures as defined are being undertaken and regularly monitored by the project team. Following are the key risks which has upward movement in risk exposure from last AR. The key risks facing the programme and the mitigation measures are as below. Risks are being managed within appetite.

Key Risks and Residual Impact	Mitigating Actions
1/External – Low capacity of the HVP authorities to design and develop viable projects leading to low absorption of funds (Moderate)	Continued high quality technical support and engagement with city / HVP personnel. Establishing long term partnerships with technical institutions for continued professional support.
2/Delivery – Limited interest of the private sector to invest in the HVPs / (Moderate)	Programme focuses on strengthening governance and policies to attract investments. Continuously liaising with DIT and X-HMG to enhance interest of international investors in the HVPs.
3/ Delivery – Low / non-performance by Service Provider(s) / (Major)	Capacity managed through scheduled performance review on management and technical capacities. Seek feedback from beneficiaries / project authorities and provide timely and clear feedback on outputs to support improvement.
4/ Reputational – Implementation weaknesses / corruption and/or other scandals at national or state level adversely affect reputation (Moderate)	Work closely with MoHUA and State / city Governments to highlight any reputational issue and resolve in a timely manner. Proactive communication to highlight benefits of the programme.
5/ Delivery – / Frequent change in leadership at the State and City level may hamper the project progress and the ownership of the city / HVP implementation agency with regard to specific interventions may reduce (Moderate)	As the interventions involve close coordination with the city / project implementing authorities and are long term in nature, city authorities were apprised of a need to create steering Committee at City/State level to ensure that the project stays on track, coordination with different stakeholders is expedited and there is adequate ownership at city / HVP level.
6/ Operational – Reprioritisation of spending focus by the UK may reduce scope of activities / allocation of funds and may lead to scaling down of interventions. Budget constraints may impact on the realisation of / ambitious programme outcomes (Major)	Changes in operating context is observed closely for suitable decision making. Programme is kept agile so that programme activities can be restructured to suit the scope of activities / revised allocation of funds, as required.
7/ Operational – Continued uncertainties post 2nd Covid wave / anticipation of 3rd wave and consequent change in Government priorities / shift in deployment of resources / focus of cities towards Covid management / journey restrictions, are making planning process challenging.	Programme team has built in delays in the projected financial summary, established weekly validation call schedules with the supplier to review desk-based analysis while primary interactions are not possible. / Further, continuous engagement by team with stakeholders is helping in understanding factual ground conditions and deciding next steps based upon mutual consent.
8/ Context – The Covid situation may impact funding for capital-intensive urban infrastructure projects due to changes in economic condition in the country. / (Moderate)	All possible options are being explored as suggested in Project Finance report to secure funding for HVPs in coordination with Implementing agencies based upon rational analysis of available options. Preliminary dialogue with IFIs initiated to explore funding options.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

Date of last narrative financial report	28th July 2021	Date of last audited annual statement	26th January 2021

This reporting period has seen financial contributions made to the core technical assistance service provider, Mott MacDonald Ltd. The payments for the activities are based on clear outputs which allowed economy to be ensured in delivery; and that procurement of all downstream contracts followed as per the agreed procurement manual.
The overall commercial and financial performance during the Extended Design Phase (EDP) and Implementation Phase was as per the budget and timeline despite global pandemic and travel restrictions during the reporting period. Programme spends were in line with the agreed Activity Based Budget (ABB). Programme delivery has remained agile and adaptive throughout several scope changes. A virtual mode of delivery has generally been adopted in view of travel restrictions. This has been an effective approach to communication across the consortium, as well as with the FCDO and implementing agencies. Risks have been monitored and managed well through continuous consultation with the FCDO. This has resulted in higher efficiency, savings, and achievement of value for money.
The systems, processes and governance practices set up during the Design Phase were effectively carried forward and strengthened during the implementation phase, enabling priorities for maximising value and optimising expenditure in terms of all 4 Es to set the programme in year-1 of implementation for the achievement of VfM. There are no major concerns about declining VfM.
Variance between allocated budget and actual spend
An overall saving of 11% has been achieved in the programme. In addition to the narrative provided in Section C (Detailed Output Scoring), the variance shown below can be attributed to deployment of staffs from the delivery partners’ local offices in the HVP cities (minimising additional travel costs), as well as general savings in travel expenses due to pandemic and travel restriction, advance planning at economical rates, and use of digital tools - all without compromise to the quality of deliverables and milestones.
Table.1: Cumulative Financial spend from June 2019 - July 2021
Cost Heads	Allocation	Actual spend	£ Variance	% Variance
Staff costs (UK & local)	£1,395,460.48	£1,366,609.38	£28,851.10	2%
Expenses	£291,940.00	£144,202.78	£147,737.22	51%
Transition funding	-	-	-	0%
Platform charges	-	-	-	0%
Programme delivery	-	-	-	0%
Output 1	£866,559.68	£866,560.05	-£0.37	0%
Output 2	£346,010.48	£214,802.55	£131,207.93	38%
Output 3	£457,630.40	£350,438.02	£107,192.38	23%
Governance	£403,057.00	£402,817.00	£240.00	0%
TOTAL	£3,760,658.04	£3,345,429.79	£415,228.25	11%

Quality of financial management e.g., accuracy of forecasting
The service provider has been providing Monthly Finance reports with all relevant details of cost in terms of the Activity Based Budget (ABB) and the Billing Schedule (BS) in the approved format on the 28th day of every month for scrutiny to the programme team at FCDO. Internally, the service provider’s financial and commercial management systems have been used to monitor and control costs against the budget. A financial and commercial management plan has been prepared to monitor the costs vis-a-vis the budget for the entire duration of the programme. A budget management system has been established to keep track of the original budget in Activity Based Budget (ABB) agreed with the programme team at FCDO. The Budget Management System is updated with the result of any potential changes in discussion and consensus with FCDO’s programme team. The billing schedule is monitored. The expenses are captured in monthly finance reports.
After the submission and approval of milestone deliveries by the programme team, invoices are generated and raised, after multiple layers of checks. Supporting details of timesheet as well as expenses are submitted to the programme team (FCDO) along with the invoices every month. In accordance with the Service Level Performance (SLP) agreed between the service provider and the FCDO, the service provider has been submitting various reports at desired intervals to provide updates on the programme progress, deliveries, issues, and challenges, supports required, financial progress, etc. The forecasting of budget and spends has realistically factored the operating challenges.
Summarising monitoring activities and how these have informed risk management and programming decisions
Regular weekly progress review meetings are held between the FCDO programme team and the service provider on overall programme management and delivery, as well individual monitoring of each HVP and other outputs (weekly / biweekly). Financial progress and spend against planned activities are reviewed every fortnight. Tripartite meetings between the FCDO and PA, implementing agency and delivery partners are also held from time to time.

Weekly progress reports, monthly programme performance reports, quarterly progress reports, monthly finance reports, quarterly risk registers, quarterly G&I scorecards, annual review reports are submitted by the delivery partners as per the approved formats and within the timelines agreed as per the SLP calendar for programme team’s review and record. These practices have helped in continuous oversight, management of risks, prioritising activities and in taking proactive preventive actions against potential challenges.