## Future
Value stream map for Government Sourcing Process (Open Procedure)
Purpose: To have an agreed outcome focused contract in place at the best possible price from the chosen supplier
[7 empty] | SCOPE | [15 empty] | Date: 20 October 2011
Version 0.4
| Policy |  | Business Need, Baselining & Market Analysis |  |  | Sourcing Strategy |  |  |  | Supplier Identification |  |  |  |  | Execution of Sourcing Strategy |  | Finalise Contract |  |  |  |  | Managing the contract & Supplier
|  | Policy Decision - Perception of Need | [21 empty] | Contract Management
Harmonious Relationship
Delivery plan & governance
Date set for contract renewal
|  |  |  | 1) Business Need Identification, Baselining & Market Analysis |  |  |  | 3) Sourcing Strategy |  |  | 4) Supplier Notification (OJEU) |  |  |  | 6) Execution of Sourcing Strategy through Evaluation of Tenders |  | 7) Finalisation of Contract |  |  | 8) Contract Signature
|  |  |  | Purpose - To ensure identification & clear articulation of the business need |  |  |  | Purpose - To establish the procurement & identify sourcing strategy |  |  | Purpose - To publish requirements through a contract notice in the supplement to the Official Journal of the European Union |  |  |  | Purpose - The best solution established through evaluation of tenders |  | Purpose - Notify the supplier and finalise the contract |  |  | Purpose - Formal signature of contract |  |  | Handing off to contract & supplier management
|  |  |  | Activity: | Outputs: |  |  | Activity: | Outputs: |  | Activity: | Outputs: |  |  | Activity | Output: | Activity: | Output: |  | Activity | Outcome:
|  |  |  | Analyse business needs Run stakeholder bootcamp to identify business needs and identify risks & mitigation. (SOP 1.1) | Sound understanding of business outcomes required |  |  | Create procurement strategy (SOP 3.1) | Procurement strategy agreed including: ~ Requirement defined ~ Procurement procedure & plan ~ Standard T&Cs ~ Scale and Value |  | Publish OJEU Notice Issue the Invitation to Tender (ITT) (SOP 4.1) | OJEU notice is published Bidders pack (ITT) published via web / e-sourcing system ITT including: ~ Criteria for mandatory exclusion |  |  | Receive & sort tenders & create a tender summary Conduct compliance check & clarification (SOP 6.1) | Summary of tenders received Tenders are ready to be evaluated | Gain approval to award decision (SOP 7.1) Issue standstill letter (notify of standstill period) & debrief suppliers (SOP 7.2) | Approval to award Standstill letter issued. Suppliers receive feedback |  | Sign Contract Publish contract award notice on TED Publish contract on Contracts Finder (SOP 8.1) | Contract signed Contract published unredacted on e-sourcing system or stored in appropriate document management system Contract published on Contracts
|  | Operational Imperatives e.g. Expiring Contracts |  | Conduct pre-procurement market engagement (SOP 1.2) Benchmarking against current provision (SOP 1.3) Write project specific Prior Information Notice & check pipeline of sourcing projects has been updated & published (SOP 1.4) | Baseline of current provision and cost Updated pipeline of sourcing projects published on departmental website Project Specific Prior Information Notice (PIN) published |  |  | Create next iteration of Business Case - Outline Business Case (OBC) (business justification, cost, benefits etc) (SOP 3.2) | ~ Contract Management Strategy ~ Criteria for mandatory exclusion ~ Evaluation Strategy & Criteria Outline Business Case updated |  |  | ~ Statement of Requirement ~ Ts & Cs ~ Evaluation strategy & criteria ~ Timescales / Project Plan ~ Compliance Instructions |  |  | Evaluate tenders: Apply mandadatory & discretionary criteria first before qualitative evaluation. Write evaluation report (SOP 6.2) Write full business case (SOP 6.3) | Tenders are evaluated and a successful bidder(s) is identified. Evaluation report is completed. Full business case drafted. | Update Full Business Case (SOP 7.3) | Approved Full Business Case updated |  |  | Finder MI Updated
|  |  |  | Hold Industry boot camp to conduct Market Analysis to identify requirements and what is available, using market specialists if appropriate (SOP 1.5 & 1.6) | Statement of Requirement |  |  | Create Bidders Pack (ITT) (SOP 3.3) | Bidders Pack (ITT) agreed including: ~ Criteria for mandatory exclusion ~ Prospectus (inc. requirements) ~ Specification (output/outcome based) ~ Ts&Cs ~ Evaluation strategy & criteria ~ Timescales / Project Plan ~ Compliance Instructions |  |  |  | 5) Supplier Clarification
|  |  |  | Write 1st draft of the strategic outline business case (SOP 1.7) Internal decision to "make or buy" If 'Buy' then use decision tool to identify the most appropriate procurement route (SOP 1.8) | First draft Strategic Outline Business Case (SOBC) including resource plan and programme plan. |  |  | Write OJEU contract notice (SOP 3.4) Conduct internal assurance & seek legal approval (SOP 3.5) | OJEU Contract Notice Approval to proceed |  |  |  | Purpose - To respond to all questions & clarifications simultaneously
[13 empty] | Activity: | Outputs:
[13 empty] | Online / e-sourcing system portal based Q&A Facility (SOP 5.1) | Suppliers have increased understanding of requirement
Web pages recording all clarifications with suppliers
[13 empty] | Refine project plan | MI updated
[13 empty] | Revisit resource plan & chech evaluation team availability (SOP 5.2) | Evaluation team in place
[13 empty] | Brief evalution team on criteria & methodology. Consider practice scoring session (SOP 5.3) | Evaluation team members ready to proceed
2) Mobilisation
Purpose - Sourcing team is set up for success, all associated stakeholders are clear on requirements
|  |  |  | Activity: |  |  | Outputs:
|  |  |  | Select cross disciplined team including contract manager & policy representative (SOP 2.1) |  |  | Dedicated team in place
|  |  |  | Create project performance hub (SOP 2.2) |  |  | Room, plan, communication strategy etc in place
|  |  |  | Complete assurance of the team, are they ready to proceed (SOP 2.3) |  |  | MI updated
|  |  |  | Establish & brief Project Board (SOP 2.4) |  |  | Project Board in place & understand objectives, evaluation Strategy agreed with end participants
|  |  |  | Establish what approvals will be required and when (SOP 2.5) |  |  | Approvals Plan
10 calendar days
22-36 calendar days
System allowing potential bidders to access bidders pack (e-sourcing System )
Govt/Dept.
22-36 Days
22-36 days from issue of OJEU
10 Days
10 days from Contract Award to Contract signature
BIQ
BIQ
Phase
VSM
Supplier Funnel
Timeline
X
1
KEY
BIQ
= Built in quality
= Legal Approval
= Treasury / Financial Approval
Scope
E-sourcing tools OJEU compliant
System allowing department to evaluate returns from bidder (e-sourcing System )
E-soucing tools OJEU compliant
Log interest electronically in the sourcing opportunity
Receive invitation to tender
Sign contract
BIQ
System updated detailing the final details and contract published
E-sourcing tools OJEU compliant
What - the contents of the Inviation to Tender (ITT) are drafted and ready to publish at OJEU publication
ITT is available to all interested suppliers at the same time as the OJEU is published
What - The team are in place and ready to proceed
Approvals are mapped and planned for
Activity
Opportunity to refine delivery plan and finalise contract management plan
Identify areas for redaction in contract for publication on Contracts Finder
Database advertising all sourcing opportunities (Contracts Finder & Tenders Electronic Daily)
E-sourcing tools OJEU compliant
Timeline
The timeline is dependant upon the size, the complexity and the risk of the procurement.
Contributors
Luke Jarvis, DoH
James Doran, Defra
Mike Jones, RCUK
Wendy Burdon, DfE
Graham Hyndman, MOD
Ann Mackie, MOD
Pat Pattenden, CO
John Weston, HMT
Rob Holland, FCO
Dave Cliff, DfE
Alan Boyd, DFiD
A depiction of the supplier journey, the touch points with the department and the places where deselection occurs.
Supplier
Journey
What - web based Q&A allows supplier questionsto be answered & clarifications to be issued simultaneously
Evaluators are clear about their role and what is expected of them
BIQ
e-sourcing System
E-sourcing tools OJEU compliant
= Business Case
Database advertising sourcing opportunities (Contracts Finder & Tenders Electronic Daily)
Departmental website
E-sourcing tools OJEU compliant
Govt/Dept.
BIQ
Subject matter experts only evaluate tenders that pass the mandatory exclusion criteria
Govt/Dept.