## GRA
Generic risk assessment for standard rules set number SR2015 No36
Standard facility: |  |  |  | Installing and using site investigation boreholes and temporary trial pits within a main river floodplain for a period of up to 4 weeks
Location: |  |  |  | Applies to all potential locations (main river flood plain)
Location of environmentally sensitive sites (km / m): |  |  |  | See below
Risk assessment carried out by: |  |  |  | Environment Agency
Date: |  |  |  | 2019-06-04
The scope of the standard permit is defined by the following risk criteria:
| Parameter 1 | Permitted activities - The installation of site investigation boreholes and temporary trial pits within a main river floodplain.
| Parameter 2 | The works must not be made within 5 metres of the bank or within 8 metres of a flood defence, river control work or drainage work, or within 5 metres of a culvert or remote defence.
| Parameter 3 | The works must not be made within 100 metres of an EU designated nature conservation site, SSSI or National Nature Reserve.
| Parameter 4 | All excavated materials should be returned to the where they were taken or removed from the flood plain if not returned.
| Parameter 5 | Must not increase flood risk.
Data and information |  |  |  | Judgement |  |  | Action (by permitting)
Receptor | Source | Harm | Pathway | Probability of exposure | Consequence | Magnitude of risk | Justification for magnitude | Risk management | Residual risk
What is at risk? What do I wish to protect? | What is the agent or process with potential to cause harm? | What are the harmful consequences if things go wrong? | How might the receptor come into contact with the source? | How likely is this contact? | How severe will the consequences be if this occurs? | What is the overall magnitude of the risk? | On what did I base my judgement? | How can I best manage the risk to reduce the magnitude? | What is the magnitude of the risk after management? (This residual risk will be controlled by Compliance Assessment).
Local population | Increased flood risk | Impact on local population and businesses, damage to property | Out of channel flow | Medium | Medium | Medium | Working close to a structure may cause damage or increase flood risk. | Include a condition that works are not carried out within 8m of a flood risk management structure or works. | Low
Local population | Increased flood risk | Impact on local population and businesses, damage to property | Out of channel flow | Medium | Medium | Medium | Working close to the watercourse may increase flood risk. | Include a condition that works should be carried out a minimum of 5 metres from bank top, and excludes the channel. | Low
Local population | Increased flood risk | Impact on local population and businesses, damage to property | Out of channel flow | Low | High | Medium | Working close to a structure may cause damage or increase flood risk. | Include a condition that the works are not carried out within 5 metres of a culvert or remote defence. | Low
Local population | Increased flood risk | Impact on local population and businesses, damage to property | Out of channel flow | Low | High | Medium | Materials should be replaces so that the capacity of the floodplain is no affected. | Include a condition that excavated materials are returned to the where they were taken or removed from the flood plain. | Low
Habitat and species | Siltation and erosion | Loss of or damage to habitat or species | In-channel flow and sediment movement, especially during high flow events | Medium | Medium | Medium | Working in the channel can cause increased sedimentation and other damage, which may be large enough to adversely affect a conservation site or species. | Do not carry out activity within 100 metres of European designated nature conservation sites, SSSIs and National Nature Reserve. | Low
Habitat and species | Spread of non native invasive species and plant and animal diseases | Loss of or damage to habitat or species | Spread of species in the catchment caused by non-native species being disturbed and spread downstream or transported by machinery and equipment to another site | Medium | Medium | Medium | Use of biosecurity measures and good site management will reduce the spread of non-native invasive species | The operating techniques/management system should include a plan of biosecurity and site management measures to prevent the spread of invasive non-native species and plant and animal diseases. | Low
Habitat and species | Siltation and erosion | Loss of or damage to habitat or species | In-channel flow and sediment movement | Medium | Medium | Medium | Limiting the time that the structure is in place, reduces the risk to habitat and species. | The activity shall be limited to a maximum of 4 weeks | Low
Water quality | Increased siltation caused by working in the river, direct disturbance whilst undertaking construction works or footprint of the finished works. | Increase in sediment load. | Direct run-off from site, or in-channel flow from works within bank. | Medium | Medium | Medium | Will reduce risk due to limited mobilisation of sediment or pollutants. | Include a condition to ensure that risks to water quality and sediment control will be minimised. | Low
WFD biological quality elements | Changes in flow, water quality or to habitat | Deterioration of ecological status through loss or harm to biology | Changes in: quantity and dynamics of water flow; connection to groundwater bodies; river connectivity; river depth and width variation; structure and substrate of river bed; and structure of riparian zone. | Medium | Medium | Medium | Limiting the size of the activity reduces the impact on receptors | General conditions which limit size, scale and magnitude of loss. | Low
| Very low | Low | Medium | High
High | 4 | 8 | 12 | 16
Medium | 3 | 6 | 9 | 12
Low | 2 | 4 | 6 | 8
Very low | 1 | 2 | 3 | 4
|  |  |  | Very low |  | #REF! | #REF! | #REF! | #REF!
|  |  |  | Low |  | #REF! | #REF! | #REF! | #REF!
|  |  |  | Medium |  | #REF! | #REF! | #REF! | #REF!
|  |  |  | High |  | 2 | 4 | 8 | Medium
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | 2 | 4 | 8 | Medium
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | 3 | 3 | 9 | Medium
| Very low | Low | Medium | High |  | #REF! | #REF! | #REF! | #REF!
Very low | 1 | 2 | 3 | 4 |  | #REF! | #REF! | #REF! | #REF!
Low | 2 | 4 | 6 | 8 |  | #REF! | #REF! | #REF! | #REF!
Medium | 3 | 6 | 9 | 12 |  | #REF! | #REF! | #REF! | #REF!
High | 4 | 8 | 12 | 16 |  | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!