ODUG Action Log – 9th April 2013

All actions for next meeting unless otherwise stated

Secretariat
Circulate minutes and actions from twelfth meeting	New
Publish note and actions from eleventh meeting on data.gov.uk	Completed
Send BIS DSB team electronic invites to all scheduled ODUG meetings	Completed
Publish note and actions from twelfth meeting on data.gov.uk	New

Collaboration Space
Advise ODUG members when they need to log into the collaboration space to prioritise new tranches of data requests	Ongoing

ODUG Benefits Cases
General
Recast current Benefits Cases into the newly agreed format	Carried forward

National Address Dataset
Survey of ~20 SMEs on use of National Address Data and PAF	Carried forward
Provide feedback to Group on progress of DSB implementation report – waiting on draft from BIS	Completed

Historic Price Paid Information
Identify further cases studies to support Historic Price Paid Information benefits case	Completed
Set up meeting with Land Registry	Completed

Historic Weather Observations
Contact Met data-user SMEs for input to benefits case.	Carried forward
Set up meeting with Met Office, including other potential users of Met Office Historic Weather Observations	Completed

VAT Register
Strengthen and expand evidence base for benefits case	Completed
Paper to Transparency Board	Completed

OS Derived Data Licensing Restrictions – with River Networks and Rights of Way
Meet with the Environment Agency about flooding data	Carried forward
Set up meeting with OS	Carried forward
Redevelopment of benefits case for rights of way	New
Send letter to OS articulating ODUG asks on derived data licensing	New

Cadastral land polygons
Develop benefits case	Completed
Identify if Land Registry is a commercial PAF licensee	New
ODUG fact checking benefits case – by 11 April	Completed
Send ODUG checked paper to Land Registry and OS – 11 April	Completed

DVLA Bulk data
Develop benefits case	Carried forward

Local Government data
Develop benefits case	Completed
GS and JT to meet Transparency Team to identify data requests for quick resolution	New

Charity Commission Register
ODUG to follow up directly with Charity Commission	New

Energy Performance Certificates
Develop benefits case	Carried forward

CodePoint with Polygons
Develop benefits case	Carried forward
Transparency Team to share additional information regarding request	New

Open Data Licensing
ODUG and ODI to deliver joint paper on Open Data Licensing Issues	Carried forward

Data.gov.uk Workstream
Data.gov.uk to provide number of visits for each ODUG benefits case	Carried forward
Add display of progress on Open Data Strategy commitments to reporting tool	Carried forward
Include supportive data requests from legacy list into current work	Carried forward
ODUG to write to depts. about progress on data publication commitments in respective the Pipeline and their Open Data Strategy Commitments	Carried forward
Review of all legacy requests to make sure those appropriate to use for support of current ODUG benefits cases are taken into account	Completed
Transparency Team to provide update to ODUG on all data requests the team has taken forward	Completed
Transparency Team to provide tidied up version of spreadsheet supporting data requests to ODUG	Completed
ODUG to meet with DGU and Transparency Team on updates to ODUG pages on DGU	New

Communications Workstream
Set up facility for sentiment monitoring for ODUG and provide a baseline assessment	Carried forward
ODUG Branding	Carried forward
Draw up and share key points to make and slides on ODUG	Carried forward
ODUG schedule of comms events and stakeholder engagement plan	Carried forward
Draft ODUG 6-month review	New
Develop plan for an ODUG event – including location and timing	Carried forward

KPIs and Risk
Review for next meeting	Ongoing

Other
Transparency Team to undertake a gap analysis of ODUG membership for skills and sectors	New
Plan and launch recruitment campaign for new ODUG members at the end of April	New