ODUG Action Log – 19 February 2013

All actions for next meeting unless otherwise stated

Secretariat
Circulate minutes and actions from tenth meeting	New
Publish note and actions from tenth meeting on data.gov.uk	New
Schedule series of meetings with 6-8 weeks interval	Completed

Collaboration Space
Advise ODUG members when they need to log into the collaboration space to prioritise new tranches of data requests	Ongoing

ODUG Benefits Cases
National Address Dataset – Lead HS/BB
Write-up background assumptions to numbers in National Address Dataset Benefits paper	New
Draft ODUG response to Ofcom consultation on PAF licensing – deadline 21 March 2013	New
Survey of ~20 SMEs on use of National Address Data and PAF	New
Provide feedback to Group on progress of DSB implementation report	New

Historic Price Paid Information – Lead SH
Identify further cases studies to support Historic Price Paid Information benefits case	Carried forward

Historic Weather Observations – Lead JC
Contact Met data-user SMEs for input to benefits case. Cabinet Office to provide some new contacts	Carried forward

VAT Register – Lead PM
Strengthen and expand evidence base for benefits case	New

3rd party licensing – with River Networks and Rights of Way - Lead GS
Meet with the Environment Agency about flooding data	Carried forward

Cadastral land polygons – Lead BB
Develop benefits case	New

DVLA data – Lead ??
Nominate lead ODUG member for this benefits case	New

Local Government data – Lead ??
Nominate lead ODUG member for this benefits case	New

Charity Commission Register- Lead ??
Nominate lead ODUG member for this benefits case	New

Energy Performance Certificates – Lead ??
Nominate lead ODUG member for this benefits case	New

Data.gov.uk Workstream
Data.gov.uk to provide number of visits for each ODUG benefits case	New
Coordinate use and application of statuses externally on data.go.uk and internally on collaboration space	New
Add display of progress on Open Data Strategy commitments to reporting tool	New
Review privacy implications for the new reporting tool	New
Feedback on final version of proposed dataset reporting tool (when advised ready to review)	New
Work with data.gov.uk team on feasibility assessment of posting reporting tool on the data.gov.uk site	New
Propose comms plan for launching reporting tool	New

Open Data Roadmap Workstreams
ODUG and ODI to deliver joint paper on Open Data Licensing Issues	Carried forward
Include supportive data requests from legacy list into current work	New
ODUG to write to depts. about progress on data publication commitments in respective Open Data Strategies	New

Communications Workstream
Set up facility for sentiment monitoring for ODUG and provide a baseline assessment	Carried forward
ODUG Branding	Carried forward
Draw up and share key points to make and slides on ODUG	Carried forward
ODUG schedule of comms events and stakeholder engagement plan	Carried forward
Draft ODUG 6-month review	New
Develop plan for an ODUG event	Carried forward

KPIs and Risk
Review for next meeting	Ongoing

Other
Publish minutes of Code of Practise Workshop on data.gov	New