Improving the business environment in emerging economies

Prosperity Fund Business Case

Global Business Environment programme

Contents

# Executive Summary
The proposed programme aims to improve the business environment, initially focusing on six developing, middle income economies, at a cost of £30m over four years. This will help lift significant numbers of people out of poverty on a sustainable basis by stimulating growth and creating jobs. It will also improve opportunities for international business, including UK businesses, to contribute to and benefit from the economic growth in these countries.
Purpose
Middle-income countries account for around 70 per cent of the world’s population, 73 per cent of the world’s poor, and around a third of global GDP[1]. Although middle-income countries are widely recognised as engines of global growth – accounting for around 50 per cent of global growth[2], they often have inadequate regulations and weak institutions which constrain growth and exacerbate challenges such as: stagnating productivity growth, lack of competitiveness, and low participation in global value chains. Promoting a favourable business environment can unlock inclusive growth and lift people out of poverty by creating incentives that open up markets, attract investment and generate savings for firms. This enables firms to reinvest productively, create more and better paying jobs and to grow. Global growth is a strategic priority which is vital for UK prosperity.
[1] World Bank, Middle Income Countries, Overview: http://www.worldbank.org/en/country/mic/overview
[2] IMF World Economic Outlook, April 2017, Chapter 2
Nature of intervention
The programme will provide technical assistance to national and sub-national governments to support their reform efforts by improving capacity in the following areas:
- business regulation and practice
- developing linkages with local and global value chains
- greater market competition and transparency
- quality standards in markets and trade
- data gathering and sharing on the quality of the business environment.
The following six focal countries have been identified as providing the best value for money for this intervention: Brazil, Indonesia, Nigeria, Pakistan, South Africa and Turkey. The core elements of the programme will be delivered by the World Bank, drawing on its extensive global reach, expertise in investment climate reform, and experience of assessing the ease of doing business. The UK will have programme oversight and provide strategic direction from London and at posts through in-country steering boards and the joint FCO/WBG governing board for the programme. Prosperity funding is a key vehicle for engaging with middle income countries. In some lower middle income countries with extant DFID programmes, the approach is designed in collaboration with DFID to ensure complementarity. In Nigeria and Pakistan for example, while DFID focuses on the poorest areas and those with stronger UK presence and influence, this programme will seek to engage other regions with growth potential over the next 10 years and leverage World Bank influence to achieve UK objectives.

Impact
Primary purpose: World Bank experience of undertaking similar reforms in over 100 countries shows that a programme of this size could yield between 20 and 25 major reforms, resulting in savings to firms and additional investment across the focal countries. The potential impact on aggregate GDP of successfully enacting these reforms could be significant. A conservative estimate of only nine major reforms could still add up to £1.7bn to aggregate GDP in focal countries over ten years. In addition, the intervention could also contribute to unlocking World Bank lending to these countries worth over $1bn within the lifetime of the programme, and the additional benefits that accrue from such investment.
Secondary benefit: Improving the business environment in focal countries promotes investor confidence by opening up markets and removing barriers which deter international, including UK, investment. This ultimately leads to greater export and investment returns to the UK. The potential secondary benefits internationally from the programme are significant. Conservative estimates suggest that benefits to the UK alone could range from £50m to £170m over ten years.

# Strategic Case

Context
The Prosperity Fund Ministerial Board in September 2016 approved a proposal to support business environment reforms in partnership with multilateral expertise from the World Bank Group and OECD, and asked for a detailed case to be developed. This business case sets out the rationale, overall budget allocation; high-level design of the programme; and other arrangements to enable delivery of the programme in partnership with the World Bank Group.
### The World Bank Group will set up a single donor Trust Fund to manage programme resources as well as develop and implement programme activities. Governance arrangements are set out in more detail in the management and financial cases.
# What is meant by the business environment
Business environment can mean a range of procedural factors and wider conditions including security, law enforcement and availability of infrastructure with an impact on business activities. This broad definition[3] is also referred to as the investment climate. For the purposes of this proposal, focus is on the complex of institutional and policy arrangements that govern and can be obstacles to business activity. These include regulatory, tax, legal and other policy frameworks which are a sub-set of the broader investment climate (with factors such as rule of law, political and macroeconomic stability, infrastructure and human capital). All together, these determine how efficiently domestic and international firms can operate. The quality of an economy’s business environment is a crucial determinant of its growth potential.
[3] Informed by The Donor Committee for Enterprise Development (DCED) resources on the Business Environment, see http://www.enterprise-development.org/implementing-psd/business-environment-reform/
# How a favourable business environment drives growth
As illustrated in figure 1 below, a favourable business environment drives prosperity by creating the opportunities and incentives for firms to invest productively, generate jobs, and grow. Transparent and simple regulations, low costs of doing business and open markets give entrepreneurs confidence to start businesses, increase market shares and expand into new markets. With increased market entry and competition, firms also become more likely to innovate, adapt to new technologies, and, ultimately increase productivity.

Figure 1: Impact of a favourable business environment on growth and poverty reduction

Improve
business environment
Easier for companies to do business
More investment, trade and start-ups
Higher income, increased productivity
More jobs, higher wages
Economic development and poverty reduction
The link between inclusive growth and a favourable business environment is supported by extensive research.[4] A study based on World Bank Doing Business data finds robust evidence of a positive impact of regulatory reforms on economic growth, with each regulatory reform associated, on average, with a 0.114% increase in growth[5]. The OECD also estimates that regulation and competition policy reforms could boost GDP by 1 – 1.5 per cent in G20 countries[6].
[4] See DCED (www.businessenvironment.org) for a useful summary of the evidence. Also DFID’s Business Environment Reform Facility at www.businessenvironmentreform.co.uk
[5] Haidar, J. I., 2012, “The impact of business regulatory reforms on economic growth”, Journal of the Japanese and International Economies, 26: 285 – 307
[6] OECD, 2014, “How can competition contribute to the G20 commitment to raise GDP by at least 2%?”

Regulatory and administrative frameworks are increasingly under the control of sub-national authorities. As with national governments, local governments require strong capacity and efficient procedures if they are to regulate to a high standard. Poor sub-national regulation is particularly harmful, as it raises barriers to internal trade. Sub-national World Bank Doing Business reports for example show significant differences in the ease of doing business between sub-national regions in most emerging economies where comparisons have been done[7]. Targeted reforms of sub-national business environments are therefore an important opportunity to promote inclusive growth and development across regions and communities.
[7] World Bank Group, 2016, Doing Business Report 2017: Equal Opportunity For All, The World Bank, Washington DC
### Constraints to growth – the problem and consequences for emerging economies
Middle-income countries account for over 70 percent of the world’s population, a similar proportion of global poverty (about 73 percent of the world’s poor) and generate about a third of global GDP. While countries in this category are considered as engines of global growth, they typically face the challenge of stagnating productivity growth coupled with high levels of inequality and poverty. One of the factors behind disappointing global growth has been poor productivity growth in middle-income countries (MICs)[8]. The OECD (2014) finds that productivity growth has only had a marginal effect on economic growth in middle-income countries. For example, the productivity gap with advanced economies has widened in Brazil, Mexico, and Turkey in the last decade[9]. These challenges are exacerbated by often weak governance structures that are susceptible to instability. Increasing prosperity through sustainable growth, participation in the global economy, and a more even distribution of wealth remain significant challenges for middle-income countries.
[8] OECD, 2016, Economic Policy Reforms 2016: Going for Growth Interim Report, OECD Publishing, Paris
[9] Perspectives on Global Development 2014: Boosting productivity to meet the middle-income challenge

These countries also face a competitiveness challenge, mainly due to over-reliance on exports of abundant natural resources. Although the abundance of natural resources has recently fuelled high rates of growth in emerging economies, new sources of growth are needed if these economies are to have sustainable growth by fully participating in the globally competitive economy.

The World Bank (2015)[10] estimates that about 70 percent of global trade is now associated with global value chains (GVC), and that developing countries with high GVC participation have a median per capita growth rate almost five times higher than those with low participation. With the largest 200 transnational corporations accounting for 80 percent of global trade, global value chains are also shaping the role of private investment beyond a potential source of capital to new functions such as standard setting for economic activity[11]. If countries do not participate more fully in global value chains they risk a growing productivity gap and a drag on growth.
[10] http://www.worldbank.org/en/topic/trade/brief/global-value-chains
[11] Taglioni, D and Winkler, D. (2016) Making Global Value Chains Work for Development, The World Bank, Washington DC
### Tackling constraints to growth
There are significant opportunities to improve the business environment in middle-income countries, many of which remain in the lower rankings of the Doing Business Report and with persistently low scores[12].
[12] See section below on “Assessing the quality of the business environment” for an explanation of the Doing Business Report and the scores.
Although emerging economies have generally continued to grow fast, the average growth rate has decelerated in recent years and convergence with advanced economies has slowed[13]. Tackling these constraints to growth will unlock more sustainable growth and accelerate poverty alleviation. OECD economic surveys of middle-income countries identify specific constraints that can be addressed by improving the business environment. For example, Turkey’s rigid regulatory framework means that its relative high cost of doing business for formal firms impairs the growth of modern enterprises, and similarly, South Africa’s complex rules for licenses and permits hinder the creation of start-ups while shielding existing businesses from competition[14]. OECD findings are consistent with the World Bank’s assessment of market failure as well as the regulatory issues identified by the IMF in its most recent bilateral Article IV consultations[15] with the target countries.
[13] See IMF World Economic Outlook April 2017.
[14] Economic surveys of Turkey (2014) and South Africa (2015), all OECD Economic Surveys can be found here.
[15] Part of the IMF’s surveillance mandate to avoid instability is to undertake comprehensive consultations with individual member states on their economic and financial policies.

There is a strong body of evidence[16] linking improvements in the business environment with boosts in productivity and competitiveness. A better business environment:
[16] http://www.enterprise-development.org/implementing-psd/business-environment-reform/
- directly reduces the time and financial costs of complying with regulation
- Indirectly, improves productivity by promoting competition - A streamlined regulatory and administrative framework makes it easier for young, efficient firms to enter the market and displace those that are less efficient. This incentivises firms to increase innovation and investment in order to boost efficiency and maintain market share[17]
  [17] There is a large body of research examining the link between the business environment, competition, and productivity. For an overview of the link between competition and macro-economic outcomes, see this OECD factsheet.
- Reduces regulatory burdens and incentives to operate in the informal sector. This is of particular concern in MICs globally. For example, informality in many emerging economies is an overriding challenge which limits firm size, human capital development, innovation and financial deepening[18] as well as tax revenue.
  [18] IMF Article IV Consultation (Peru, 2015) - all Article IV consultations can be found at www.imf.org.
Addressing these constraints requires the capability and commitment to undertake a range of regulatory and institutional reforms. Studies by the OECD find that once countries reach middle-income, the development of competitive, innovative businesses is often constrained by an inadequate regulatory environment and that competitiveness increasingly hinges on the efficiency of institutions and mechanisms governing goods, labour and financial markets[19]. Proposed solutions are consistent World Bank and IMF recommendations for tackling these constraints, including:
[19] OECD, 2014, Perspectives on Global Development 2014: Boosting productivity to meet the middle-income challenge, OECD Publishing, Paris
- Increasing productivity by fostering competitive service sectors and by reforming product, labour and financial markets;
- Boosting productivity through product market liberalisation. Emerging economies tend to have relatively high barriers to competition, trade, and investment for both domestic and foreign firms;
- Opening up public procurement and increasing transparency to prevent regulatory capture and corruption; and
- Encouraging competition so that more efficient and productive new businesses enter the market as inefficient ones drop out;
### Assessing the quality of the business environment

The World Bank flagship publication on this topic is the annual Doing Business Report. It uses an aggregate score for the procedures, time and cost for a set of indicators to express regulatory efficiency and quality. The indicator set includes: starting a business (capturing the minimum capital requirement), dealing with construction permits, getting electricity, registering property, paying taxes, trading across borders, enforcing contracts and resolving insolvency as well as getting credit and protection for minority investors[20]. The methodology uses a “Distance To the Frontier’ (DTF) score as the quantified measure from which the country rankings are derived. The DTF shows the absolute “distance” to the best in class performing country in those criteria, as a benchmark.
[20] Doing Business Report 2017
In addition to doing business rankings, global surveys and reports on investment and competitiveness are also compiled by a range of institution including the World Economic Forum and UNCTAD. While this range of information paints a useful picture of the global situation, none is fully comprehensive. This programme will contribute further research and analysis to identify and plug gaps within the suite of available products for assessing the business environment. Doing so will enable better targeting of reforms to improve the business environment in developing countries, both for developing countries seeking to make changes and for the range of international donors operating in this space.

### How we plan to intervene

The programme will target some of the key development constraints already highlighted, through specific activities that are aligned with the priorities of selected countries and host governments.

 A cross-cutting work stream - the Global Influence Initiative - will use the World Bank’s global reach and analytical work to support the design and implementation of reforms in focal countries. Benefits of this experience and knowledge will also be extended to other reform-minded countries by supporting peer learning opportunities and making the latest reform tools and research more widely accessible. The focal country programmes are designed around the following thematic pillars:

1. Strengthening business regulations and practices
2. Enhancing business competitiveness
3. Support to subnational efforts and equity.

The programme components are summarised below and set out in figure 2. The specific country activities will be outlined in implementation plans once the proposal is approved, but overall, country-specific solutions will aim to:

1. Simplify and strengthen regulations and practices by tackling business regulatory inefficiency and compliance costs as well as leveraging the private sector as a partner in regulatory and sector-level standards delivery. For example, self-regulation and third-party audits are common practice in developed markets where the risk to brand reputation and revenue create strong incentives for consumer protection. These approaches will be explored and developed alongside better public sector regulatory oversight
2. Enhance competitiveness by promoting locally produced value added as local businesses increasingly supply both foreign and domestic firms at various levels of the supply and value chain. This firm-level intervention will connect local firms through a supplier database and target programmes as well as other behavioural incentives to encourage local sourcing, upgrading and equal business opportunities for women and disadvantaged groups
3. help deliver the benefits of inclusive growth more widely by intervening to improve the capacity of devolved authorities (including sub-national government) with often limited capability but important regulatory responsibilities. Domestic and foreign investors and firms increasingly face variations in regulations and practices across locations of the same economy. The programme will aim to clarify (not necessarily harmonise) local regulations and to support their transparent implementation.

Figure 2: Programme overview

WINDOWS/ THEMATIC PILLARS	OBJECTIVES/SOLUTION AREAS	BUDGET (£30m)	IMPACTS	RISKS
Global Influence Initiative	Analytics and diagnostics / Reform toolkits / Adaptive policy design / Biennial Business Competitive Report and Forum	30%	Advancing thought leadership and reinforced design and implementation of business environment reforms in MICs. / UK leadership and global knowledge exchange on business environment topics.	Low / Anticipated high-level Government and business community support / Deliverables under purview of WBG
Country Engagements: / I. Strengthening business regulations and practices	Simplifying and strengthening business regulations / Promoting good regulatory practices / Opening markets and competition for investment	70%	More open and predictable markets and improved business regulations in MICs facilitating firm savings, growth, investment, exports, productivity and jobs.	Low / Anticipated high-level Government support / Technical assistance delivery is a core competency of WBG global and country teams / Proven concepts and track records
II. Enhancing business competitiveness	Increasing local value addition and job creation / Supporting firms to meet standards to access investment and exports		Improved competitiveness of locally-operating firms creating jobs, upgrading products and expanding internationally. / Increased linkages with MICs for international and UK firms.	Medium / Cutting edge topics requiring dependence on Government capacity / Sophistication and absorption capacity of private sector unknown
III. Subnational support and equity	Improving subnational business regulations / Improving subnational firm incentives frameworks		More equitable and inclusive growth by engaging at subnational level. / Increased business confidence and opportunities for international and UK firms in MICs.	Low-Medium / Anticipated high-level Government support with known capacity limitations at subnational level / Technical assistance delivery is a core competency of T&C global and country teams

Where we plan to intervene
An initial list of 11 potential target countries[21] based on the distribution of global poverty coupled with considerations of potential market size was included in the Concept Note for this programme. This broadly reflected priority countries for the Prosperity Fund. To maximise the impact of available resources and avoid fragmentation, the list of prospective countries was filtered through a number of criteria, as set out below, to arrive at a smaller group of high impact focal countries.
[21] These were as follows: Pakistan; Malaysia; Philippines; Vietnam; Argentina; Brazil; Mexico; Nigeria; South Africa; Egypt; Turkey
Political commitment of focus governments and the potential for additional impact from wider reforms were considered alongside WBG assessments of the likelihood of successful delivery, based on its longstanding engagement with partner governments on reform issues. Most of the priority countries listed were judged to have relatively high levels of political commitment with appropriate reform actions included in national development plans. In the case of SE Asia countries listed, reform commitments are also part of the regional integration agenda following the establishment of the ASEAN Economic Community in 2015.
In general, most countries have demonstrated a degree of political will, but those that stood out have also set up or empowered credible institutions to spearhead and coordinate reform efforts. For example: the Brazilian Finance Ministry’s Secretariat for Economic Monitoring, and the Special Advisory for Macroeconomic Reforms; Indonesia’s Coordinating Ministry of Economic Affairs; the Enabling Business Environment Secretariat in Nigeria’s Vice Presidency; the Federal Board of Investment in Pakistan’s Office of the Prime Minister; South Africa’s National Treasury, DTI and National Competition Commission; and Turkey’s Coordination Council for the Improvement of the Investment Environment. Some of the countries not selected in the initial phase have shown commitment to undertaking some reforms but not necessarily those which this programme would be best placed to support. High level dialogue and engagement will continue in focal and other countries to encourage commitment to reform.
Ease of doing business global rankings were used as a filter to exclude the following countries in the top third of ease of doing business rankings: Colombia, Malaysia, Mexico and Peru. Expert judgement (from both HMG and the World Bank) was that this represents a reasonable cut off point, with countries above the line less likely to derive primary benefit from interventions as countries whose economic development is more hindered by their business environment. The final target countries are placed from 69th to 169th in the latest global rankings

Extant prosperity funding. Some countries/regions on the list already have indicative funding allocations for years 2 to 5 of the Prosperity Fund; these allocations are either being used to fund improvements to the business environment (e.g. Mexico) or have decided that focusing on other themes would be better value for money (e.g. Colombia). These countries were given lower ratings for additional funding requirements. For example, the main pillars of the ASEAN regional programme will tackle business environment and financial services issues in Malaysia, Philippines and Vietnam, while Brazil, Colombia, Mexico and Indonesia have country allocations

Ability to leverage WBG in-country resources or complementing other UK programmes for greater impact. Countries such as Brazil, Nigeria, Pakistan and Indonesia where either WBG reform-based policy lending plans or significant DFID investment climate programmes are under way, and where these additional resources would complement rather than duplicate the work of the programme, were given higher ratings for leveraging greater impact and additionality than other countries

Analysis of potential for benefits to international business, including UK companies was based on internal modelling of prospective UK exports and investment, as well as information on the greatest barriers to increasing market access for UK companies. The Structural Economic Reforms for Growth and Market Access methodology used was not exhaustive, but gave an indication of potential exports and investment outflows to some of the prospective target markets as well as a strong comparative reflection of the importance of this area relative to other themes when considering market access barriers for UK companies
On this basis, Brazil, Indonesia, Nigeria, Pakistan, South Africa and Turkey were identified as the initial focal countries, but given the programme’s flexible and adaptive design, there is scope to intervene in other countries as implementation rolls out. In addition, an even wider range of countries is expected to benefit from the analysis and tools developed under the Global Influencing component of the programme.
Figure 3 below shows the key Doing Business rankings and scores for the target countries, alongside New Zealand, Singapore and the UK (ranked first, second and 7th respectively) by way of context.
Figure 4: World Bank overall Ease of Doing Business Rankings 2017

Country	Ranking (Global 1-190 where 1 is best)	Score / (Distance to the Frontier (DTF) score, 0-100 where 100 is the highest scoring country	Change in DTF score (Since 2015)
Brazil	123	56.53	-
Indonesia	91	61.52	Improved
Nigeria	169	44.63	Improved
Pakistan	144	51.77	Improved
South Africa	74	65.20	-
Turkey	69	67.19	-
New Zealand	1	87.01	Improved
Singapore	2	85.05	Improved
United Kingdom	7	82.74	Improved

Poverty Analysis
The substantial reduction in extreme poverty[22] between 1990 and 2013 from 35 per cent to around 10 per cent has mainly been due to record levels of economic growth in middle income countries, particularly in Asia. But since 10 per cent of the world’s population still lives on under $1.90 a day, significant effort is still required to achieve Sustainable Development Goal number 1 of ending poverty in all its forms. This programme contributes to the achievement of this global goal by directly tackling Sustainable Development Goal number 8 – to promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all. The causal link already set out between an improved business environment and economic growth clearly demonstrates the intended impact of this programme on poverty. Evidence from Stallings and Peres (2010)[23] suggests an indirect link between business environment reform and poverty reduction. Changes in the business environment can lead to increased employment, investment, competition, and productivity. These in turn have an aggregate effect on GDP and poverty. Business environment reforms will therefore primarily affect the supply side of the economy, for example by supporting a more vibrant, competitive private sector which in turn: attracts both foreign and domestic investment; stimulates productivity growth with knock on effects on GDP; and ultimately leads to job creation and poverty reduction.
[22] See World Bank poverty data at: http://datatopics.worldbank.org/sdgatlas/SDG-01-no-poverty.html
[23] Stallings, B; and Peres, W. (2010) Growth, Employment, and Equity: The Impact of the Economic Reforms in Latin America and the Caribbean, Brookings Institution Press
In order to have sustained economic growth and poverty reduction, Acemoglu and Robinson (2012)[24] suggest that inclusive economic as well as political institutions are required, which emerge through practical interventions to stimulate institutional reform. This programme will help stimulate arrangements for implementing effective reforms in focal countries while also ensuring sustainability and knowledge transfer more widely through its Global Influence Initiative.
[24] Acemoglu, D. And Robinson, J. (2012), Why Nations Fail: The origin of Power, Prosperity and Poverty, Random House, Danvers, MA
In addition to driving economic growth, there is evidence that pro-competition reforms can also make an important contribution to reducing income and wealth inequality. Ennis and Kim (2017)[25] show that in the absence of competition, market power tends to drive up prices and increases everyone’s consumption expenditure. This redistributes the additional money spent towards business owners and financial asset holders, who are overwhelmingly concentrated at the top of the income distribution. Ennis and Kim show that in the short-run, on average, for each dollar of monopoly profits, a total of USD 0.37 is transferred from the 90 percent poorest to the 10 percent wealthiest. The overall effect in the long-run is to increase the income of the wealthiest while reducing consumption power and savings for the rest of the population.
[25] Ennis and Kim (2017), “Market Power and Wealth Distribution” in OECD/World Bank A Step Ahead: Competition Policy for Shared Prosperity and Inclusive Growth, Washington, DC: World Bank Publishing.
This programme helps to tackle the thread running across all of the Sustainable Development Goals, through helping to create the conditions for sustainable development. As the programme is delivered and its results framework is fully developed, it is expected that measurement will be possible of the number of people living in poverty that have been supported as a direct result of programme interventions. At this stage it is not possible to estimate what those final figures will be. However, the country-specific interventions in the sections below, highlight how the programme will support SMEs and benefit the poorest through, for example, enhanced supplier databases and quality standards to access investment and export markets. Primary benefit in the appraisal case is estimated in terms of economic growth and the conditions for poverty alleviation in the focal countries.
Figure 4 below shows World Bank data on population, poverty, income and inequality in the focus countries, which illustrates the large number of people that could potentially benefit from this programme.
Figure 4: Income and poverty data in the focus countries
Country	Total population / 2015 estimates	Poverty headcount (<$1.90/day) / 2015 estimates	GNI per capita (USD current, 2015)	Gini Index (0-100 where higher number indicates greater income inequality)
Brazil	209m	7.5m	$9,990	52 (2014)
Indonesia	258m	21m	$3,440	40 (2013)
Nigeria	182m	85m (2009 est.)	$2,790	43 (2009)
Pakistan	189m	11.2m	$1,440	31 (2013)
South Africa	55m	8.5m (2011)	$6,080	63 (2011)
Turkey	79m	0.3m	$9,950	40 (2013)
Total	972m	133.5m	-	-

Although the poverty headcount in Turkey is much lower than the other target countries, it remains a highly unequal society (Gini coefficient 40) with a lower GNI per capita than Brazil, for example. Turkey is a priority country which has experienced significant changes in recent years, including the flow of millions of refugees and migrants, many of whom are of working age and will need to be absorbed into the labour market. The other focal countries also show similarly high levels of income inequality, with resources and opportunities concentrated in small groups. The intended reforms will lead to increased competitiveness and distribute resources more widely, which will reduce poverty by creating jobs, improving access to capital and delivering inclusive growth.
Political economy overview
Reforms to improve the investment climate invariably take place in a political context and accounting for the particular risks this entails is essential for successful delivery. Typical political barriers to enacting reforms include weak governance, absence of political will and influence of powerful vested interests. Political risks are especially high in developing countries where political processes tend to be more personality driven, institutions tend to be less well established, and outcomes are generally more fluid. Given the diversity of experience in different countries, Hal Hill (2013)[26] finds that reform efforts should be context-specific and enjoy the political support of key leaders who understand the case for reform and are willing to actively promote it.
[26] Hill, Hal. 2013. “The Political Economy of Policy Reform: Insights from South East Asia” Asian Development Review 30(1):108-130
Perceptions of political risk are also key considerations for successful outcomes. The World Investment and Political Risk report (2013)[27] places the perception of political risk as second only to concerns of economic instability. Political risks of most concern to investors were potential breaches of contract and the imposition of adverse restrictions and regulations. However, other concerns including civil disturbance, expropriation and conflict continue to be cited. Nearly a third of surveyed national regulatory changes introduced in 2010 that pertained to foreign investment reflected increased regulation or imposed new restrictions compared to only two percent of regulatory changes in 2000.
[27] https://www.miga.org/Documents/WIPR13.pdf
The programme design takes account of the challenges of working on business environment reforms across a range of different contexts. A recent report for DFID[28] states that “investment climate reform is inherently political, seeking to engage with it as a purely technical issue, divorced from its political context, fails to deliver ‘real’ reform. Whilst a politically smart approach is not a panacea to solving complex investment climate problems, it does offer insights into what might be politically feasible, and how donor programming is most likely to support real reform.” The World Bank’s significant experience in this area will add value and increase the likelihood of successful delivery of the programme. As already set out, political commitment was a key factor in country selection, which firmly bases the programme on country ownership of proposed reforms.
[28] “Politically smart approaches to donor investment climate programming” LASER/KPMG for DFID Feb 2016. See www.laserdev.org
A key feature of this programme is its flexible and adaptive approach, which takes account of political challenges and risks, using regular review and evaluation to ensure that the highest impact interventions are prioritised. This approach will be:
- Problem focused: locally identified and defined problems provide the entry point;
- Small bets: solutions are developed iteratively and first tested through ‘small bets’, which can be adapted and either scaled or abandoned if unsuccessful;
- Context specific: solutions are not locked in but based on on-going political and contextual analysis of ‘best fit’, ensuring that they are feasible and realistic for the local context;
- Locally led: reforms are locally led and development partners/practitioners work as facilitators, not drivers of reforms;
- Learning and adapting: requires ongoing data collection and analysis in order to adapt - this is where the Global Influencing Initiative adds significant value;
- Flexible: including with log frames and work plans, and using procurement processes that allow for funds not to be linked to pre-defined outputs. (See Commercial, Financial and Management cases for conditions on this point)
Some political risks are considered alongside other country-specific constraints identified in the section below.

### Country-specific constraints[29] and political economy overviews
[29] Based on World Bank and IMF assessments of constraints to growth

Building on the general constraints and risks already set out, this section details some key constraints faced by individual focus countries along with examples of the types of interventions being developed in response.

Brazil:
In the decade to 2014 Brazil lifted 29 million people out of poverty and inequality fell (drop in the Gini coefficient from 58.1 to 51.5). The real income of the poorest 40 percent rose by an average of 7.1 percent in the same period, compared to a 4.4 percent income growth for the population as a whole. However, inequality remains high and with annual productivity growth staying at 1.6 percent between 2001 and 2013, the gains achieved may not be sustainable. In comparison, productivity in China and Russia rose by 9.6 percent and 3.5 percent, respectively. The rate of reduction of poverty and inequality has stagnated with growth rate decelerating steadily from 4.5 percent in 2010 to 2.1 percent by 2014. GDP contracted by 3.8 percent in 2015, and is expected to fall further as investor and consumer confidence are undermined by economic and political instability.

Political instability and uncertainty are key risks. The current government is seen as pro-business and continues to push through necessary reforms in areas such as public spending, labour and pensions; however there are challenges to ensuring these reforms are successful including parallel efforts (that need further support) on stimulation of the private sector and attracting private investment. It has also made appointments, for example, to the Special Advisory on Macroeconomic Reform which reflect a commitment to the reform agenda. Brazil is currently going through the largest anti-corruption operation in the history of the country; stimulation of further competition is seen domestically as a positive way to create and maintain a fairer and more positive business environment.
Lastly, undertaking development policy loans to support wide-ranging productivity growth-related reforms is also a good indicator of commitment to reforms. Continuous engagement at various levels is essential with key government departments responsible for delivering reforms.

Improving Brazil’s business environment is a significant challenge, since for example, starting a business takes over three times longer than in comparable countries. World Bank global doing business rankings place Brazil at 174th out of 189 countries in starting a business, and 169th in dealing with construction permits. On average, it takes: 11 procedures and 101.5 days to start a business (of which 90 days are allocated towards applying to municipalities for a permit); and 19 procedures and 400 days to get a construction permit. Trade openness is very low and most foreign direct investment is driven by profits from a captive domestic market rather than efficiencies from participating in global value chains. The resulting distortions in the business environment are exacerbated by inadequate business competitiveness.
Business competitiveness in Brazil will be enhanced for example by:
- helping firms meet standards that will open up access to investment and export opportunities through enhanced information databases and software to fully traceable value chains for exports, as well as effective export promotion bodies
- complementing ongoing UK efforts to support the Ministry of Finance and Brazilian Development Bank with reforming rules and processes that enable the participation of international investors in infrastructure projects and professional (engineering, legal and accounting) services.

Indonesia:
Over the past decade, high commodity prices tilted investment incentives in favour of the natural resource sector and non-tradable sectors in Indonesia. However since 2012, growth and job creation have slowed, exposing Indonesia’s dependence on natural resources for export and investment and, by extension, for job creation. Real GDP growth declined to 4.8 percent in 2015, down from its 6.4 percent peak in 2010. Higher productivity in non-commodity sectors in Indonesia is needed to push growth. Increasing productivity in these sectors will require an improvement in Indonesia’s business environment and functioning of markets.
Improving the business environment is a top priority for the President (targeting an improvement to number 40 on the Ease of Doing Business index). The Government is pro-reform and receptive of external support. Progress has already been made: 16 economic reform packages have launched over the past year. Regulations have been cut and the flow of new regulation slowed. As a result, Indonesia has jumped in rank from 109 in 2015 to 91 in 2016; and the World Bank placed it 5th in terms of biggest improvements to business regulations over the past year. However, there are still areas for improvement. While the various initiatives and announcements are positive, there is a need for a coherent approach to ensure implementation and sustained impact.
The Indonesian government plays an active role in controlling the economy. The 16 policy packages issued recently aim to stimulate investment, strengthen competitiveness and diversify the economy. Included in the packages are measures to reduce regulatory obstacles, secure the legal rights of investors, facilitate international trade and promote infrastructure investment. Among other improvements, the reforms have opened an additional 35 industries to foreign ownership and cut the time taken to secure business permits to 3 hours through a one-stop shop facility.
Although the President has shown a clear focus on economic reform, investment promotion and regulatory simplification, the complexity of Indonesia’s government machinery presents a risk. Empowering the Coordinating Ministry of Economic Affairs to ensure coherence across reform areas is a crucial step in the right direction, but high level dialogue and continuous engagement with various actors is essential as the programme rolls out. These risks can be in part mitigated by focusing on specific reform packages/regulations with broad political in-country support and a genuine chance of long-term impact. Close engagement with the teams at post will be necessary to achieve this.
Indonesia cannot raise growth above the five percentage level necessary to absorb new entrants into the labour force and to reverse the recent trend of slower poverty reduction if the high costs of doing business; regulatory uncertainty and lack of competition are not addressed. Firms have cited business licenses and permits as the fourth most frequently reported obstacle to their business. While most main licenses are regulated at the national level, sub-national governments have significant freedom to determine licensing procedures and requirements. Indonesia is highly decentralised with complex and unpredictable sub-national regulations given the lack of uniformity at lower levels of government. This leads to discrepancies in processing time, cost and requirements between national regulations and sub-national implementation.
Regulations and competiveness in Indonesia will be strengthened for example by:
- supporting the relevant government task force with reviews of regulatory delivery, development of an inventory of regulation, and improving the quality of the flow of regulation
- focusing on revising specific trade and investment regulations which stifle competition while actively promoting pro-competitive reforms and signalling Indonesia’s interest in joining new international trade agreements
- connecting local firms through a supplier database and targeted activities as well as leveraging behavioural incentives to encourage local sourcing and upgrading of products.

Nigeria:
External shocks, including lower commodity prices, tightening financing conditions, and increased risk aversion of international investors drove the economy into recession by June 2016, in the context of a challenging domestic environment. GDP growth fell from 6.3 percent in 2014 to 2.7 percent in 2015, before shrinking by 1.58 percent in 2016. Macroeconomic instability has been characterized by negative growth, inflation, and a weakening currency. Oil and gas have generally continued to comprise over 90 percent of Nigeria’s exports and more than 70 percent of consolidated budgetary revenue, even though the oil sector represents less than 10 percent of GDP. With oil prices projected to remain “lower-for-longer”, a new growth strategy for the post-oil economy will need to be adopted over the medium to long term. This will require decisive regulatory reforms to improve the business environment, and governance reforms to improve the efficiency of public expenditures.

The main political risks are around elements of protectionist policies that aim to boost domestic production but can also compromise investment opportunities. Corruption is also a significant issue in Nigeria. It will be crucial therefore to focus on specific reforms/interventions that do not carry vested interests that could exacerbate this problem.

The Nigerian government has committed itself to economic diversification to tackle Nigeria’s oil dependence, including through its 2017-2020 Economic Recovery and Growth Plan, which should encourage the pursuit of reforms aimed at increasing private investment. Successive Action Plans on the ease of doing business launched by the Vice President in February 2017 have recorded some successes, including for example, reducing certain registration processes by enhancing online portals, and introducing “visa on arrival” services for certain investment/business categories. These reforms helped Nigeria moved up 24 places in the World Bank’s Doing Business report.

It will be important to focus on barriers faced by smaller businesses in Nigeria in order to support the economic diversification agenda and to engage in the future engine of growth and job creation in country.
The business environment in Nigeria will be enhanced for example by:

- reviewing incentives and industry opportunities in reform-minded states to identify new potential sectors for attracting private investment
- supporting local SME with enhanced supplier databases and other efforts to meet the quality standards to access investment and export markets.
Pakistan:
With 1.7 million youths entering the job market annually, Pakistan’s increasing working-age population provides the country with a potential demographic dividend but also with the critical challenge of job creation. With only 3 percent of women engaged in formal economic activities, the prospect is even more challenging. At 24.3 percent, Pakistan’s female labour force participation rate is the lowest in South Asia, and compares poorly with the 81.1 percent of male participation. Investment climate weaknesses have seen total investment as a percentage of GDP decline from almost 19 percent in 2006-07 to around 15.21 percent in 2015-16 (as against the annual average of almost 33 percent of GDP for South Asia) and institutional capacity to attract and retain FDI remains weak.
Long entrenched rent seeking practices in government and more widely are significant barriers to effective reform in Pakistan. However, there is political interest in regulatory reform in the focal provinces for UK support (Sindh and Punjab).  Both the provinces contribute to the Doing Business Report ranking of Pakistan.  Though still in its nascent stages, an Investment Climate Reform Unit supported by the World Bank Group with DFID funding has been set up in Punjab and a similar approach is being developed for Sindh, which could potentially be supported by this programme. Given the significant barriers to change within the public sector in Pakistan, consistent technical support to the government is required to help it achieve some early benefits which should in turn encourage commitment to continuing reform efforts.
Furthermore, businesses in Pakistan face a multitude of barriers which mainly stem from a systemic failure of regulatory management. The IMF Staff Report for the 2015 Article IV Consultation highlights the need to reinforce recent gains in economic stability and generate sustainable growth momentum through key priorities including improving the business climate for higher and more inclusive growth. Federal and provincial governments in Pakistan therefore need drastic reform to improve the country’s investment climate and sustain economic growth and investment inflows so that employment opportunities and income are generated.
The ease of doing business in Pakistan will be enhanced for example by:

- Facilitating reforms of business licensing, company registration and FDI approvals, and encourage more reliance on risk-based approaches to regulation; and
- Improving institutional coordination across federal and provincial boundaries and introduce specific business-to-government feedback arrangements.

South Africa: The economy has been affected by external factors such as the slowdown of China and other emerging economies, which were major drivers of its investment and exports. Domestically, the slow pace of structural reforms and infrastructure bottlenecks (particularly energy) have also taken a toll on the economy. Private investment contracted by 4.9 percent in the first half of 2016 from a year earlier – after a 0.6 percent decline over 2015 – indicating reduced business confidence. Overall, South Africa remains a highly unequal society, with an unemployment rate in excess of 25 percent for the majority population. South Africa’s poor investment climate and business environment (ranked 74 in the 2017 Doing Business Report) obstruct the key role the private sector could play in addressing these challenges, especially in terms of boosting employment, investments, exports, and fiscal revenues.
Overall policy uncertainty tops the list of barriers to doing business in South Africa. Rhetoric about “radical economic transformation” and calls for reforms in land ownership tend to chill the investment and overall business climate.
More recently, policy uncertainty prompted by changes to the cabinet unsettled investors and prompted ratings agencies to downgrade South Africa’s sovereign debt to sub-investment grade, or junk status. However, there are indications of increasing need for reform to restore investment status (and electoral prospects in 2019) as business and consumers will face higher borrowing costs and lower growth.
Entrenched vested interests are also a notable barrier to an open and competitive business environment, particularly in terms of patronage in top political positions i.e. in Finance, Energy and State-Owned Enterprises. But overall, there’s likely to be appetite to implement targeted reforms in the wider business environment through relevant parts of national and provincial governments.
SMEs face complex and costly business regulations, poor infrastructure services, slow and expensive contract enforcement, and limited access to finance. These factors drive many firms into informality, and it is estimated that upwards of 2 million people in South Africa work in the informal economy (outside of agriculture) and account for up to one-third of total economic activity in some provinces.
Business competitiveness in South Africa will be improved for example by building on existing partnerships with competition authorities, to:

- remove policy and regulatory obstacles to competition in key sectors such as retail, energy, telecommunications
- enhance competition enforcement through anti-cartel policy and tools for cartel detection
- expand engagement with public procurement authorities and provincial governments on pro-competition actions.

Turkey: the reform process has slowed in recent years, and Turkey has yet to cross the barrier to high income. As indicated in the poverty analysis above, Turkey has faced significant challenges recently, including the flow of millions of refugees and other migrants, many of whom will need to be absorbed in the labour market. With per capita income at around US$9,177, it is 20 percent shy of the high income threshold defined by the World Bank. After a period of rapid deregulation during the early 2000s, Turkey has made little progress since 2007 and has seen many competitors close the gap or even surpass it in terms of quality of investment policy regime; degree of institutional coordination at both the national and sub-national levels; improvements in the business environment; and reforms of its private-sector related regulations. The refugee crisis also poses a challenge to growth and shared prosperity as Turkey hosts around 3 million refugees and strains to provide adequate social infrastructure and urgently needed education and employment opportunities.

Political instability and uncertainty due to repetitive election cycles are notable risks to investment in Turkey. However, a Fitch evaluation stating that the constitutional referendum held in April 2017 may facilitate a revival of credit-positive economic reforms[30]. The premise is that as political uncertainty diminishes, with extended presidential powers and elections only expected in late 2019, the government’s focus will shift towards economic growth and introduction of new structural reforms.   But the pace of reform could be impeded by Turkey’s immediate challenges, including security concerns, high inflation and unemployment.
[30] See https://www.fitchratings.com/site/pr/1022322
Turkey’s 10th Development Plan identifies competitiveness/ease of doing business as a priority area and sets out specific objectives of improving the investment climate in the country.  There has been some improvement in the ease of doing business in the last decade but there is still much to be done, especially around the rule of law, transparency and predictability.  Although challenges and obstacles to implement remain, simplification of rules and regulations aimed at improving the business environment and competitiveness are included in Ministerial Strategies and political commitment continues to be reiterated. The degree of commitment is also shown by the actions of bodies such as the Coordination Council for the Improvement of the Investment Environment (YOIKK), Investment Support and Promotion Agency of Turkey (ISPAT) alongside the Ministries of Economy and Development.
Ranked 69th on the World Bank Group’s overall Doing Business Index, Turkey’s business environment does not stand out among upper middle income countries—the obstacles have been outweighed by the opportunities presented as a result of Turkey’s dramatic structural transformation. For Turkey to move to high income status, growth will have to come from improvements at the economy-wide, sector-specific, and firm level. This will require the application of new technology, upgrading in productivity, better management, and a more efficient allocation of resources, which are best accomplished in a competitive, predictable business environment. Regulatory red tape, legal uncertainty, and a business climate that favours “know-who” over “know-how” continue to be issues. For instance, according to the World Bank’s Turkey Systematic Country Diagnostic, the low quality of regulatory and accountability institutions stands out as the most binding constraint to attracting capital and promoting innovation and growth. This is exacerbated at both the national and sub-national levels by overlapping institutional mandates and responsibilities for issues, such as investment support and promotion of FDI and domestic firms, including SMEs.

In Turkey, activities will complement the proposed priorities for the country programme and build on the Turkey Regional Enterprise Survey and other analytical work to focus on sub-national doing business reforms, regulatory impact assessment as well as investment policy and promotion to support, for example:

- the design and implementation of a strategy to link multinational firms and domestic enterprises both at the national and sub-national levels
- institutional arrangements and incentives to improve the capability of local firms and development of a supplier database.

## UK Business constraints and benefits
## Evidence from a range of sources[31] strongly confirms that the current state of the business environments in the target countries and sub-regions is a major deterrent to international including UK exports and investments in these markets. The programme has been designed to take into account these particular challenges. Summary outlines are given below.
[31] Including UK-ASEAN Business Council; British Chambers of Commerce and HMG posts.

In Indonesia, a 2015 British Chamber & European Chamber of Business Confidence survey[32] found the regulatory environment and red tape as the top two constraints to doing business in Indonesia. A 2016 UKTI survey of UK business on market access concerns showed similar results.
[32] See http://www.britcham.or.id/page/12/ease-of-doing-business
In South Africa, entry and growth of UK companies in the market is most commonly constrained by the following factors, and uncertainty about how the Government will address them in the short to medium term[33]:
[33] Information from post.
  1. inconsistent and inadequate investment incentives in certain sectors
  2. rules which require local partners to control 51% equity – and associated regulations (e.g. credits for skills transfer to local staff)
  3. difficulty identifying credible local partners (including SMEs)
  4. complex and opaque sector-specific regulation e.g. in telecommunications
  5. lack of transparency in public procurement.

In Nigeria, a report for the FCO by PWC[34] on the business environment at State-level finds that “limited access to finance, inadequate power supply and limited infrastructure remain major business constraints across the focus states and nationwide”. A UK agricultural investor in one state was quoted as follows: “The combination of a lack of US dollars, fluctuating and depreciating currency, high interest rates and inconsistent government policy does not give investors confidence to invest.” Furthermore, internal HMG analysis identifies inefficient/burdensome regulations as one of the key barriers to UK market access, alongside corruption, taxation issues and security.
[34] PWC “An analysis of state-level business environment in Nigeria” 2017 available at http://www.pwc.com/ng/en/pdf/promoting-economic-prosperity-fco-report.pdf

In Turkey[35], UK companies are put off by regulatory red tape, legal uncertainty and lack of transparency and predictability. They also sometimes face technical difficulties for foreign workers to get work permits. The latest Fitch rating[36] suggests that the recent Turkey referendum may facilitate a revival of credit-positive economic reforms. Political uncertainty is likely to diminish and the government is expected to shift its focus towards economic growth and introducing new structural reforms.  However, UK firms are also responding to immediate issues including insecurity and high inflation. Improving the capability of local firms will help UK businesses engage with Turkish companies in terms of language barriers, compliance and transparency issues and technological innovation. The more local companies are linked to multinational value chains the higher the UK businesses’ chances of doing business with them on a fair, level playing field.
[35] Views from post.
[36] See https://www.fitchratings.com/site/pr/1022322
In Brazil[37], setting up a company is a major barrier for foreign companies in general, with inefficient/burdensome regulations identified as the largest barrier to market access for UK firms. Processes are not streamlined, licenses usually take a long time and the tax system is extremely confusing, which can increase the cost of setting up the company and subsequent operations in Brazil. Companies typically need local experts to help them navigate the regulatory puzzle. Activities planned under this programme will therefore benefit UK companies along with other foreign firms.
[37] Assessment from Post

In Pakistan[38], foreign businesses need to comply with additional regulatory measures beyond those applicable for local businesses. These are costly and time consuming and include for example, obtaining No Objection Certificates for investments in specific sectors and geographic areas.  Work which is underway to better understand these barriers and propose recommendations for how business regulations for foreign investors can be rationalized could potentially be taken forward by this programme. These measures are expected to benefit UK and other foreign investors.
[38] ibid

## Fit with UK strategic priorities and compliance with legislation
National Security Objective no.3 is to promote UK prosperity. A strong economy provides the foundation to invest in security and global influence, which in turn provides more opportunities at home and overseas to increase prosperity, reduce poverty and build security for all.[39] The National Security Strategy specifically commits to doing more in emerging economies to encourage global economic growth. This proposal directly supports these priorities by tackling constraints to growth through improving the business climate, competitiveness, and operation of markets in partner countries.
[39] National Security Strategy and Strategic Defence and Security Review (2015)
Internal analysis and multilateral reports identify a range of middle-income countries with high potential for inclusive growth and consequent opportunities for exports and investment (including from the UK) once reforms take effect. Partnering with a multilateral institution, such as the World Bank, which has done extensive work on business environment reforms, increases the likelihood of successful delivery. The partnership will draw on lessons learned from: several successful partnerships; multilateral aid reviews; and crucially on ongoing relationships between the World Bank and countries with which the UK plans to fully engage on reform issues. A detailed assessment of the suitability and sustainability of this delivery option is included in the appraisal case.
This programme complies with the International Development Act 2002[40] by primarily focusing on generating investment and inclusive growth which will support poverty reduction by creating more and better paid jobs in focus countries. It directly contributes to the third objective of the UK Aid Strategy on using Official Development Assistance to promote economic development and prosperity in the developing world.[41] It also contributes to the Sustainable Development Goals[42], particularly Goal 1 (No poverty) and Goal 8 (Decent work and economic growth).
[40] http://www.legislation.gov.uk/ukpga/2002/1/contents
[41] UK AID: Tackling Global Challenges in the National Interest (2015)
[42] UN SDGs September 2015
### Added value and alignment with Prosperity Fund Theory of Change

The Prosperity Fund aims to promote higher rates of sustainable growth and greater investment and trade flows by improving conditions for growth in partner countries. This programme will focus on delivering three out of the five intermediate outcomes identified for the Prosperity Fund as shown in figure 6 below. The programme will directly contribute to improved conditions for growth in target countries by helping to strengthen: policy and regulatory environment; capacity to design and implement effective regulations; and government’s commitment to improve institutional and business practices.
A great deal of work to improve the business environment in many countries is already underway, but HMG prosperity funding provides clear value addition compared to other funding sources due to the following unique elements of the proposed programme:
- Focus on large middle-income countries which would otherwise not be prioritised for grant support, thereby benefitting large numbers of people and supporting inclusive growth[43]
  [43] DFID programmes focus on Fragile and Conflict Affected States (FCAS), whereas this programme focuses on Middle Income Countries that have large economies and large numbers of people in poverty.
- Key components on sub-national development and public procurement are major challenges shared by focal countries and other emerging economies[44]
  [44] See DCED “Support for Regional and Local Business Environment Reform” (2016) which reviews the significance and impact of sub-national reforms. www.enterprisedevelopment.org
- Adaptive programme design (which requires high data availability and strong counterpart capacity). This will also allow flexibility to consider potential activities in other countries on a reserve basis
- Global influence and knowledge sharing, drawing on World Bank’s global reach and expertise
- Opportunity for bespoke interventions focussed on strategic export markets where the UK has comparative advantage

Figure 5: programme alignment with overall prosperity fund objectives

The Business Environment programme will focus on delivering three out of the five intermediate outcomes identified for the Prosperity Fund
### What others are doing to address the need

Wider Prosperity Fund activity: this programme will ensure synergy with other prosperity funded thematic interventions including on trade, anti-corruption and infrastructure while supporting an enabling regulatory environment for potential sector programmes being developed. The programme is also designed to complement country and regional proposals with business environment or regulatory reform components. For example, Indonesia will focus some of the country programme resource on government to government support to improve central regulatory coordination and oversight while this programme will support specific regulatory reforms and practices across sectors and themes, including a focus on competition policy and sub-national regulation.
The Prosperity Fund allocation for monitoring and evaluation of the portfolio will also spend £2.5m in support of initial work by the World Bank: on new ways of measuring the impact of reforms; and to establish country benchmarks ahead of a new global investment competiveness survey and report. This intervention means that key measurement issues will have been considered by the time the global programme enters implementation. This strand of work will then be supported by this programme as part of the cross-cutting component (the Global Influence Initiative).
Although the Trade and Business environment programmes have complementary activities to strengthen regulations and improve standards, the Trade programme tackles a wider array of non-tariff barriers including customs procedures and intellectual property. While there are clear similarities between components of these programmes, different approaches are applied to different locations. The use of different approaches to tackle similar problems will build experience and understanding of solutions that work in different contexts. Similarly, by improving the capacity to develop sound infrastructure proposals, the infrastructure programme aims to generate investor confidence, which is underpinned by a favourable business environment. Overall, improving the business environment also removes some of the scope for rent-seeking activities, thereby directly supporting the objectives of the anti-corruption programme. Close engagement is expected to continue during the planning and delivery of these programmes with ongoing checks across programmes to ensure consistency. This will be facilitated by the in-country steering groups. (See Management Case).
DFID bilateral programming: The design of this global programme has been informed by DFID experience and consultation, in particular the recent Report on Business Environment Reform in Sub-Saharan Africa and South Asia[45]. DFID has significant investment climate interventions in Nigeria and Pakistan which will be complemented by the proposed interventions under the Prosperity Fund. In Nigeria, DFID’s key bilateral support to federal business environment reforms ended in 2017 while the rest of its current and future programming will focus on northern states. Work under the prosperity fund will pick up support to federal-level reforms as well as focusing on reform-minded states in the south, for example Lagos State or Ogun State. Similarly, DFID’s investment climate bilateral programming in Pakistan is concentrated in the Punjab, while this programme will focus on reforms in Sindh Province.
[45] See Business Environment Reform Facility at www.businessenvironmentreform.co.uk – paper on “What works in BER in SSA and S.Asia”, Feb 2017.
Other donors: The UK also contributes to the wider investment climate work supported by a range of donors and administered by the World Bank Group under the Facility for Investment Climate Advisory Services (FIAS) trust fund. However, interventions under FIAS focus mainly on improving the business environment and supporting sustainable growth through private sector development in low income and vulnerable economies around the world. The large middle-income countries targeted for prosperity funding are unlikely to be prioritised under FIAS so any duplication will be avoided. To ensure complementarity we will also engage with other donors supporting regulatory reforms. For example in South Africa and Indonesia, a coordinated approach is needed with reform efforts supported by Switzerland. This can either be based on location, sector or specific activity depending on the country context and potential for added value for all donors involved without the need for blended finance or incurring additional costs.
World Bank policy lending: Work on the business environment funded by the Prosperity Fund will also leverage the impact of World Bank policy lending plans in Brazil, Nigeria and Pakistan.

Other stakeholders
Recipient governments: based on extensive engagement with governments in target countries, the World Bank has found that four (Brazil, Indonesia, Nigeria and Pakistan) out of the six target countries demonstrate very high levels of commitment to reform while South Africa and Turkey show high levels of commitment. Detailed implementation plans for each country will take account of the degree of commitment and the role of UK political engagement.
UK posts in target countries: UK posts and World Bank staff will engage closely in focal countries to ensure coherence of UK activities in countries. The involvement of posts is foreseen in the governance arrangements for in-country programme activities. It is also crucial for DIT to follow the implementation of the programme closely so that UK companies are well positioned to compete for secondary benefits once reforms take effect. As already indicated, political engagement in some of the focal countries could usefully reinforce the technical support on offer and potentially strengthen governments’ commitments to enacting reforms.
UK business: continuous engagement with UK business bodies and representatives during implementation will provide a practical assessment of UK companies’ readiness to compete for secondary benefits in the form of market access, investment and exports. DIT in post will lead on this aspect through involvement in the country steering groups.
### Sustainability and political engagement
A multilateral approach has the benefit of well-established relationships with policymakers and other stakeholders in potential target countries. A coalition between HMG’s network and a multilateral partner creates a powerful platform for sustained, strategic, and coordinated engagement with national and sub-national governments.
Using adaptive policy design, the programme will tailor interventions to meet and complement the specific national development objectives of each partner country. Improving the business environment complements these countries’ development plans by spurring economic growth, contributing towards the SDGs and raising the scores and rankings in the highly visible annual Doing Business survey. The overseas network will help reinforce political relationships and maximise the impact and sustainability of reforms.
The programme will utilise the World Bank’s social and environmental safeguards[46] (as defined by the Environment and Social Framework). This risk and impact-based approach will boost protections for people and the environment through policies that serve to identify, avoid and minimise harm to people and the environment. This helps to ensure the sustainability of the programme, as well as linking tightly to relevant Sustainable Development Goals. The Environment and Social Framework will underpin programme-level key performance indicators used to measure sustainability.
[46] http://www.bankinformationcenter.org/wp-content/uploads/2016/10/the_esf_clean_final_for_public_disclosure_post_board_august_4.pdf
Gender impact
The OECD shows that women’s economic empowerment, specifically as entrepreneurs with access to growth markets, is a major contributor to pro-poor growth within a nation’s economy[47]. Similarly, the World Bank finds that greater gender equality could increase labour productivity by as much as 25 per cent in some countries[48]. Women are more likely to work in the informal sector and are typically disadvantaged by prevailing laws, regulations and customs. Laws, regulations, and customs restricting women’s ability to manage property and conduct business are crucial binding constraints to growth. Even where laws and regulations are gender-neutral in theory, they may still result in gender biased outcomes[49].
[47] OECD (2006) Promoting Pro-Poor Growth: Private Sector Development
[48] The World Bank (2012) World Development Report 2012, Gender Equality and Development
[49] See OECD Gender dimensions of investment climate reform, 2010

For example, in Pakistan married women are not able to register a business in the same way as men. In many countries[50] women face greater vulnerability to corruption in the process of registering a business, they often lack information more than men and are less aware about the procedures. In addition, they may be less likely to afford the procedures, have a lack of collateral or funds to contribute towards high start-up capital requirements, less time available for completing lengthy procedures in part due to the burden of domestic responsibilities, and greater difficulty accessing registration facilities. All of these barriers may negatively affect women contributing to their choice to not formalize their businesses.
[50] See DCED paper on Business Environment Reform and Gender, August 2016, for a detailed discussion and evidence.

There are also knock on implications. For example, the lack of formal business registration influences a woman’s credit history and ability to borrow and can restrict enterprise growth and legal responsibilities, rights and protections as employers, and access to business development services.
Countries with more cumbersome business environments have smaller shares of women entrepreneurs and vice versa. Accordingly, simplifying business processes can create more first-time female business owners at a rate 33% faster than that for their male counterparts[51].
[51] Chamlou 2008, The Environment for Women’s Entrepreneurship in the Middle East and North Africa Region. World Bank Report.

An ILO study[52] covering Nigeria and Rwanda, concluded that despite laws guaranteeing the rights of women to own property, prevailing customary practices and traditional laws do not recognize these rights. For example, matrimonial property is often held in the husband’s name. While a husband can pledge these assets as collateral for loans, the wife cannot do this without her husband’s authorization.
[52] ILO 2011, quoted in DCED paper on Business Environment and Gender, August 2016.

The same study notes that customary inheritance practices often prevail over equal inheritance rights for women and these rights are not enforced. As such, women are often unaware of their legal rights or do not have access to recourse mechanisms. The implication for women entrepreneurs is a lack of control over assets of the business and the inability to offer secure collateral for loans. Addressing these property ownership issues is imperative for the development of women’s enterprises.

Gender Equality Act compliance
In line with Gender Equality Act compliance, good practice development and smart economics, this programme will meaningfully consider and demonstrate how it will contribute to reducing gender equality and support women’s economic empowerment. This programme will contribute to unlocking inclusive growth and efficiency by:
1. assessing the gender impact of current practices and of the proposed interventions;
2. tackling gender-specific barriers to business and supporting gender-sensitive business environment reforms, including: legal and regulatory reform of discriminatory laws, regulations, and their implementation;
3. targeting sectors and linkages with the most potential to impact women’s employment, entrepreneurship and socio-economic situation;
4. sex-disaggregating the collection, tracking, and measurement of data, results and impact; and
5. ensuring interventions do no harm and do not worsen gender inequality and discrimination.

The World Bank’s Environment and Social Framework[53] will be utilised in line with World Bank policy to ensure the programme prioritises women and girls, and employs the right key performance indicators to demonstrate this.
[53] ibid

In practice this means that:
1. Gender and inclusion is integrated across programme diagnostics, design and implementation;
2. Programme management incentives, systems and processes are robust and in place to support gender and inclusion mainstreaming;
3. There is the required social development and gender technical expertise to support the team in quality delivery and institutional mainstreaming as well as sufficient capability and capacity to support gender and inclusion;
4. Procurement processes include gender and inclusion components and delivery partners are held to account for gender and inclusion capability and delivery;
5. Risk management processes monitor gender equality act compliance and identify, monitor and mitigate potential risks and unintended consequences of programme interventions;
6. Any communications strategy reflects awareness of gender and inclusion dimensions of business environment reform in policy dialogue and programme results’ reporting.
The programme will also be supported by and aligned to, the centrally run Prosperity Fund Monitoring Reporting, Evaluation and Learning system (MREL), where gender and inclusion are fully integrated.

Expected results
A favourable business environment is an underlying enabler of inclusive growth. Action to improve the business environment has a multiplier effect on programmes and interventions in other sectors. For example, reducing the cost of setting up new businesses will make skills and entrepreneurship programmes more effective. Figure 6 below shows the key outcomes and impacts at the programme level.
Figure 6: Expected impacts from each component
COMPONENT	OUTCOMES	IMPACT
Global Influence Initiative	Advancing thought leadership and reinforced design and implementation of business environment reforms in MICs. / UK leadership and global knowledge exchange on business environment topics.	Creation and growth of firms / More and better jobs (including for women and youth) / Greater aggregate productivity / Higher investment and trade flows / Increased international and UK exports and market access / Increased international and UK investments
Country activities: / I. Strengthening business regulations and practices	More open and predictable markets and improved business regulations in MICs facilitating firm savings, inclusive growth, investment, exports, productivity and jobs.
II. Enhancing business competitiveness	Improved competitiveness of locally-operating firms creating jobs, upgrading products and expanding internationally. / Increased linkages with MICs for international and UK firms.
III. Subnational support and equity	More equitable and by engaging at subnational level. / Increased business confidence and opportunities for international and UK firms in MICs.

Evidence from Haidar (2012)[54] shows that each business regulatory reform envisaged can be associated with boosting economic growth by 0.114 percentage points on average and potentially more depending on the number of reforms and extent of restrictions. Across the focal countries, expected outcomes of the programme include:
[54] HAIDAR, J.I (2012) ‘The impact of business regulatory reforms on economic Growth’ Journal of Japanese International Economies 26 (3) (2012) 285–307
- up to 25 major reforms which will enable businesses to grow;
- increased productivity and firm compliance-cost savings, including due to more open and accessible markets;
- increased competitiveness and scope for enhanced products and value addition; and
- more inclusive growth across national regions and population groups.
These outcomes will ultimately contribute to the creation of jobs, poverty reduction and economic growth. When reforms supported by this programme take effect, they could potentially contribute £1.7bn to additional GDP across the focal countries. The resulting scope for increased trade and investment flows will open up opportunities for UK exports and investments. The theory of change is set out below and estimates of the potential impact of the programme are quantified in the appraisal case.
Theory of Change
A key assumption underpinning successful delivery is that some of the political and institutional barriers to change are overcome during implementation. The main barriers including weak governance, political will, powerful vested interests as well as capacity and capability are discussed in the Strategic Case as well as the options analysis below. The programme aims to contribute to poverty reduction in focus countries by target key constraints to growth through specific activities to support business environment reforms. Implementation through the World Bank increases the likelihood of success by drawing on its capability and expertise in supporting investment climate reforms.
The theory of change, which is also illustrated in figure 7 below is described as follows: The provision of a range of inputs including global expertise, diagnostic reform toolkits, peer learning networks, behavioural economics research, technical advice on regulatory reform including production of evidence/analysis to create new approaches, and support for implementation of reforms will in the immediate term improve the capacity of target countries to:
- implement evidence-based business regulations;
- improve business data and government to business service platforms;
- foster open markets and global value chain participation;
- coordinate the implementation of regulations across agencies and devolved authorities more effectively; and
- better mitigate the effect of regulation on particular groups, including youth and women.
In the medium term this will help integrate the target countries into the global economy and foster sustainable growth, leading to outcomes such as:
- more transparent, predictable, accessible and efficient regulations and services;
- more open and competitive markets with higher investor confidence;
- government commitment to continuous improvement, including in doing business global rankings;
- increased job creation and value addition;
- opportunities for international including UK exports and investment;
An improved business environment enables: the creation and growth of firms and better jobs; diversification of investment and trade flows; and increased productivity. This ultimately lifts people out of poverty, which is the primary purpose for intervening.
An indicative results framework will be developed during the pre-implementation phase to reflect baseline data and country-specific plans.
## Figure 7

Appraisal Case
This section builds on the strategic rationale for intervening to support business environment reforms in emerging economies and the underpinning theory of change already set out in the Strategic Case. The Appraisal Case:
- qualitatively assesses the main options for delivering effective interventions;
- sets out the available evidence to support the expected impact of the programme; and
- provides estimates of the potential impact of the programme.
Qualitative Options Analysis
Delivery options and strategic decisions
Partnering with multilateral institutions such as the World Bank Group and/or OECD was initially proposed as the most effective way to maximise benefit from the extensive work of these organisations on regulatory reform to improve the investment climate in middle-income countries. This qualitative analysis tests this proposal against the following alternative options: a) doing nothing; and b) using commercial suppliers.
Each option is assessed against key implementation issues including: capability and capacity to deliver; cost of delivery; risk; and lead time to delivery. A summary of the assessment and scoring matrix is shown below.
Option (a) doing nothing: in the counterfactual scenario, national governments would continue their ongoing activities to improve regulations and practices. It is expected that some reforms would be implemented in the ‘do nothing’ scenario, which would have a degree of measurable impact on economic growth and development. However, given the capacity constraints and political context in the target countries, reforms are unlikely to be as comprehensive and sustainable without significant additional expert support and knowledge exchange.
Impact: national governments often lack the funds or capability to deliver reform. Developing a good business environment requires the right institutions, people and processes to design, implement, enforce, monitor, evaluate, review, and revise policies dynamically. Regulations need to keep abreast of new products and technological change. The absence of additional capability and the strength of political pressures in the ‘do nothing’ scenario could lead to measures that are the least challenging being implemented at the expense of the most appropriate reforms. The effect of this on secondary benefits to international business including UK companies, as illustrated by the scoring, is that any potential benefits beyond current market shares are unlikely to be realised.
Option (b): delivering the programme through commercial suppliers would entail a competitive process to identify the best placed private sector organisation to implement the programme.
Impact: since this approach would increase capacity in targeted countries and help focus on the most effective reforms, it is likely to have positive outcomes as shown in the scoring below. Particular focus on the inclusion of local firms in value chains including sectors of UK comparative advantage would further strengthen prospects for secondary benefits to the UK. However, overall impact could be undermined in some focal countries by the extent of engagement with the relevant authorities and perceived credibility of commercial suppliers. In addition to capability, business environment reforms require long-term commitment and sustained effort, which many commercial suppliers may struggle to demonstrate in some of the target countries.
Deliverability: political and institutional barriers are major risks to delivery. In addition to the institutional constraints already mentioned, government policy and reform plans are often subject to the influence of vested interests. Groups tend to lobby against key reforms or encourage more protection for sectors and businesses they represent.
Successful delivery is therefore contingent on continued commitment to reform, which requires effective engagement and credibility. Supported by UK lobbying efforts, commercial suppliers are expected to have a reasonable level of engagement, but this is unlikely to have the breadth and depth enjoyed by multilaterals such as the World Bank across the target countries. A commercial approach could work, but in some cases and contexts credibility may be an issue, which in turn could impair the delivery and sustainability of reforms.
Value for money: Commercial suppliers are likely to deliver the programme as efficiently as leading multilaterals, but typically command higher management fees.
Option (c): Partnership with the World Bank as the main delivery partner, and building on its track record, expertise, credibility and deep engagement with national governments. This approach takes account of the Independent Commission for Aid Impact (ICAI) reports[55] on the effectiveness of DFID engagement with the World Bank and more broadly how it works with multilateral agencies to achieve impact. ICAI found that the interventions reviewed performed well and met most of the criteria for effectiveness and value for money.
[55] ICAI Review, 2015, “How DFID works with multilateral agencies to achieve impact”; www.icai.independent.gov.uk/report/
The World Bank was given a positive rating in the UK Multilateral Aid Review[56], with both criteria of ‘match with UK priorities’ and ‘organisational strengths index’ receiving ratings of Very Good. The Multilateral Aid Review recognises that ‘the World Bank’s global reach, technical capacity, breadth of funding instruments, and convening and influencing role make it central to UK development objectives. The World Bank is good at delivery against challenging objectives. It manages risk well.’
[56] DFID,2016, “Raining the standard: the multilateral development review 2016”; www.gov.uk/government/publications/raising-the-standard-the-multilateral-development-review-2016
Impact: The World Bank has the expertise, record and global coverage to ensure credibility with recipient governments and scope for continued engagement which is essential for the delivery of sustainable reforms. An independent evaluation[57] of extensive investment climate reforms supported by the World Bank Group in 119 countries from 2007 to 2013 costing around $3.7 billion finds that up to 80 per cent of interventions are both relevant and effective.
[57] Independent Evaluation Group. 2015. Investment Climate Reforms: An Independent Evaluation of World Bank Group Support to Reforms of Business Regulations. Washington, DC: World Bank.
By partnering with a multilateral institution such as the World Bank, with a credible record of supporting reforms, the programme would be more responsive by drawing first hand lessons from recent reform efforts to develop more tailored interventions. The Independent Evaluation Group report (2015)[58] recommends the development of diagnostic tools to improve the country-specific relevance of World Bank interventions. This programme responds to this by including a cross-cutting component to improve diagnostic analysis and tools as set out in the Strategic Case. The likelihood of significant impact due to the factors above is reflected in the scoring below for primary impact. The programme will support reforms that are solely in the focal countries’ rather than the UK’s interest. However, by aligning the business environment with global standards, the programme will deliver benefits to focal countries resulting in further inclusion in global value chains including areas of UK comparative advantage.
[58] Ibid; https://ieg.worldbankgroup.org/evaluations/investment-climate-reforms
Deliverability: We judge multilateral partners with global reach and expertise as necessary for successful delivery given their credibility and depth of engagement in the selected focal countries. The choice of countries, reform strands and UK engagement in programme design and delivery will help generate opportunities aligned with UK interests.
Value for money: Although both commercial and multilateral options are likely to deliver the programme efficiently, there is a real opportunity in this case to leverage additional impact by partnering with the World Bank for example by supporting activities in focal countries which enable access to a pipeline of policy lending (amounting to over $1 billion), associated with regulatory reform. Option C is therefore expected to deliver better value for money than other options.
 It should be noted that different parts of the World Bank Group have separate arrangements for managing programmes and donor trust funds. An arrangement has been agreed in which the programme will gain from input and expertise from across the group.
Option C also allows the UK to share the delivery risk with an implementer with robust arrangements for managing funds as well as monitoring and evaluating delivery while retaining oversight through effective governance and by linking payments to implementation milestone.

Figure 8: assessment of options*
Criteria / Options	Primary impact (35%)	Secondary impact / (25%)	Deliverability / (20%)	Value for Money / (20%)	Total Weighted Score
A – Counterfactual	2	1	1	1	1.35
B – Delivery through commercial contracts	4	4	4	3	3.8
C – Delivery in partnership with World Bank Group	5	3	5	4	4.3

*Options are scored on a scale of 0-5, with each criterion weighted as shown to emphasize the primary purpose and the relative importance of the respective criteria in achieving the programme objectives. 0 indicates the absence of effect while 5 shows that an option fully meets the criteria.
Recommendation: on the basis of this assessment, delivery in partnership with the World Bank Group (option C) is the recommended option.

Evidence
As set out in the Strategic Case, a favourable business environment drives prosperity by giving entrepreneurs confidence to start businesses, increase market share and expand into new markets. Market entry and competition tend to boost innovation, leading to increased productivity. There is strong evidence that poor regulation and lack of competition tend to reduce growth and disproportionately harm specific groups (for example women). Evidence linking the business environment to growth prospects includes, for example:
- Jalilian et al (2003)[59], show a causal link between regulatory quality and economic performance in a cross-country analysis of the impact of regulation on economic growth in developing countries.
  [59] Jillian et al (2006) ‘The impact of regulation on economic growth in developing countries: a cross-country analysis’ Working Paper
- Studying the impact of business regulatory reforms on economic growth in 172 countries, Haidar (2012)[60] finds that each business regulatory reform could be associated, on average, with a 0.114 percentage point increase in economic growth after controlling for a broad range of factors, including political stability and corruption.
  [60] Haidar, J. (2012). The impact of business regulatory reforms on economic growth. Journal of the Japanese and International Economies, 26(3), pp.285-307
- The OECD (2016)[61] also estimates that regulatory and competition policy reforms could boost GDP by 1-1.5 percent in some G20 countries with larger gains in those with more restrictive rules.
  [61] OECD, 2016, Economic Policy Reforms 2016: Going for Growth Interim Report, OECD Publishing, Paris
- The OECD (2014)[62] and others estimate that joint action by the G20 could boost output, lower global risks and deliver more balanced and sustainable growth. Product and labour market regulation and infrastructure investment, all of which affect the business environment, were estimated to have the biggest effect.
  [62] OECD, 2014, “How can competition contribute to the G20 commitment to raise GDP by at least 2%?” OECD publishing, Paris
Overall, the business environment tends to be weaker in many developing economies, so there is significant scope to support business environment reforms and influence growth, as already set out in the Strategic Case. In an assessment for DFID, White and Fortune (2015)[63] find evidence that business environment reforms (BER) can contribute to reducing poverty by increasing investment and economic growth. The pro-poor impact of BER is greatest for integrated packages of reform, rather than narrow thematic reforms. It concludes that unlocking the potential for economic growth and investment ‘certainly requires BER’, although due to methodological problems it is difficult to isolate the effect of reform on growth, and other binding constraints, such as infrastructure, can limit the potential effect.
[63] White, S. and Fortune, P. (2015) Business Environment Reform and Poverty: Rapid Evidence Assessment. London: Coffey International Development
# Quantification Limitations
The estimation exercise in the sections below covers the potential impact of a range of policy reforms on the GDP of focal countries and on UK exports, but does not capture directly or quantify key benefits of reforms including poverty reduction, the impact on gender and potential outward investment. Qualitative analyses of these factors and evidence of their potential impact are set out in the strategic case (see pages 14-16 and 33-36).

GDP estimates carry significant uncertainty due to the difficulty set out below in accurately predicting the potential multiplier effect of an improved business environment and isolating the impact of the reforms given changes in many other factors that affect the supply side.

Extensive work by international financial institutions has consistently shown quantification of programme-specific impacts to be particularly unreliable[64]. This is mainly due to the range of factors, including for example, exchange rate fluctuations, commodity price shocks, global financial market volatility that are beyond scope but are interrelated so tend to materially influence key impact measures. Key issues highlighted by Stallings and Peres include: A failure, or inability, to disaggregate; failure to appreciate linkages between national economies and the international context; failure to appreciate how reforms in the package might interact with each other and; failure to articulate the effects on employment and global income distribution. The range of influencing factors along with a long results chain from programme activities to impact measures such as job creation, formation of firms and investment generation render any prediction of future investment or employment levels considerably uncertain.
[64] Stallings, B; and Peres, W. (2010) Growth, Employment, and Equity: The Impact of the Economic Reforms in Latin America and the Caribbean, Brookings Institution Press

Estimating primary impact

This section summarises the approach used to estimate the potential impact of the programme. The primary purpose of this programme is to generate economic benefits in focal countries from an investment of £30m aimed at improving the business environment. World Bank Group experience of supporting similar reforms in around 120 countries, suggests that this intervention could potentially result in up to 25 major reforms across the focal countries.

 Estimates of the potential impact of the programme are based on: IMF growth projections; analysis of the potential effect of reforms on GDP growth; and World Bank assessments of likely outcomes. The outcome of effective support to business environment reforms can be reflected in changes to relevant legislation, administration processes, and institutional arrangements.

Approach
The methodology used is based on evidence showing that an improved business environment unlocks GDP growth. Analysis by Haidar[65] further suggests that the impact on GDP growth of each additional business environment reform enacted, after adjustments to account for factors including political stability and corruption is, on average, 0.114 percentage points. Assumptions including the following are applied to the focal countries: a) other parallel efforts to improve the business environment are underway in each country; b) a one per cent contribution rule reflecting the contribution of this programme to the overall reform effort; and c) costs are disbursed evenly over 4 years (2017-21) and any impact will materialise with a time lag. Projected primary benefits are estimated to take effect from 2020.
[65] Haidar, J. (2012). The impact of business regulatory reforms on economic growth. Journal of the Japanese and International Economies, 26(3), pp.285-307.
Estimates based on this methodology and assumptions suggest a central net present value impact of approximately £1,740m. The range illustrated in figures 9 and 10 below shows the potential impact on the GDP of target countries over 10 years, with the central and lower estimates showing the effect of successfully enacting, for example, nine and three major reforms respectively. To tackle optimism bias and provide more conservative estimates, a high success scenario has not been included. In these scenarios, some countries, for example Nigeria, South Africa and Turkey are assumed to either be relatively less committed or able to enact reforms at the same pace as others, subject to the political economy context. The selection of countries with a slower pace of reform could change in the light of further political economy analysis.

Figure 9: Estimated potential overall impact on aggregate GDP of successfully enacted reforms
	Impact after 10 years
Medium success scenario (9 reforms)	£1,740m
Low success scenario (3 reforms)	£680m

Results

The primary benefits of a fully successful programme of around 25 major reforms could be significant over 10 years. Here we illustrate the medium and low success scenarios whose impact is estimated at approximately £1,740 and £680m, respectively.
The scale of quantified benefits may seem high relative to the size of the initial investment, but these estimates should be considered in the context of ease of doing business reforms affecting a large portion of the economy, leading to an increased growth rate and considerable gains over an extended period of time. The financial costs of providing support for the implementation of such reforms are relatively small by comparison. A quantitative analysis has not been carried out for the other delivery options; however, it is clear that the World Bank has greater capacity to successfully implement a higher number of reforms in the countries in scope than the private sector. Thus, delivery through the World Bank provides the greatest ratio of benefits to costs.
As indicated in the qualitative options analysis, we judge a partnership with International Financial Institutions as necessary for successful delivery given their credibility and depth of engagement in the selected focal countries. As such, while equally capable and efficient, a commercial approach is unlikely to gain as much traction, which would have a knock on effect on the successful delivery of sustainable reforms.
Figure 10: Estimated potential present value primary impact of programme on GDP of recipient countries after 10 years
Country	Medium success scenario (9 reforms)*	Low success scenario (3 reforms)*
Indonesia	$620m	$310m
Turkey**	$290m	$0m
Brazil	$1,020m	$510m
Pakistan	$140m	$70m
Nigeria**	$100m	$0m
South Africa**	$100m	$0m
Total	$2,270m	$890m

* Notes: Estimated figures have been rounded to the nearest 10m.
** Nigeria, South Africa and Turkey are assumed to have a relatively lower pace of reforms in the low and medium success scenarios, based on political economy assessments indicated in the strategic case. Further political economy analysis will be undertaken to update this assessment.

## Estimating Secondary Impact

The business environment is an integral part of the thread underpinning sustainable global economic growth. Better business environments give international business, including UK companies, not only confidence to do more business and invest productively, but also the opportunity to increase market access and market share. As set out in the Theory of Change, the impact of an improved business environment ultimately leads to greater export and investment returns including for the UK.
Barriers to competition, complex regulation, and closed procurement processes disrupt and deter international, including UK, investment overseas by reducing market access, damaging business confidence, and increasing compliance costs. UK businesses often cite[66] non-tariff regulatory barriers as key impediments to trade and investment.
[66] British Chambers of Commerce, 2017, “Exporting is good for Britain: Market barriers” London
Estimates of the impact on UK exports are based on the change in the demand for imports. Income growth has a varying impact on import growth depending on the nature of a specific country’s economy[67] (for example, the country’s baseline level of GDP and GDP growth; how open the country is to international trade; the country’s savings rate), alongside other key factors such as transport costs. A gain in GDP will increase incomes, and consequently, import demand is expected to rise.
[67] Senhadji, A. (1998). Time-Series Estimation of Structural Import Demand Equations: A Cross-Country Analysis. IMF Staff Papers, 45(2).
Approach
Secondary benefits are assessed by considering the increase in imports to the recipient country caused by the gain in income (GDP) resulting from the primary impact of the programme. This is then used to estimate the expected increase in UK export volumes based on the UK’s share of the recipient country’s imports. However, there is considerable uncertainty around quantifying the UK’s share of benefits and opportunities.
Estimates of secondary benefits are based on assumptions including that: a) successfully enacted reforms result in increased demand for imports in recipient economies; b) The UK’s share of total imports remains constant at current levels; c) costs are disbursed evenly over 4 years (2017-21) and benefits realised from 2020-27, following a time lag.
 Estimates based on this methodology and assumptions suggest a central net present value secondary benefit of approximately £170m as shown in figure 11.
Figure 11: Range of potential additional impacts in present value of successfully enacted reforms on UK exports
	Impact after 10 years
Medium success scenario (9 reforms)	£170m
Low success scenario (3 reforms)	£50m

Results
Based on the approach described above, estimates of secondary benefits to the UK, resulting from reforms supported by this programme, range from between approximately £50m and £170m once reforms take effect. Secondary benefits to the UK are not limited to investment outflows and additional exports. The quantified secondary benefits are likely an underestimate, as they do not look at investment or other, second round, effects. Increased competition in export markets provides incentives for UK firms to act more competitively, thus increasing productivity. However a causal relationship is difficult to quantify due to the indirect nature of this additional impact.

While these estimates assume that UK market share remains unchanged, it is expected that secondary benefits can be maximised through additional, separate, non-ODA, UK initiatives such as trade and investment promotion campaigns to ensure that UK firms are prepared to take advantage of any opportunities arising from outcomes of this programme.

Figure 12: Estimated range of potential additional UK exports to each country as a result of successfully enacted reforms
Country	UK Market share in Imports	Medium Success (9 reforms)*	Low Success (3 reforms)*
Indonesia	0.50%	$20m	$10m
Turkey**	2.45%	$20m	$0m
Brazil	1.42%	$30m	$20m
Pakistan	3.79%	$80m	$40m
Nigeria**	3.92%	$30m	$0m
South Africa**	3.28%	$30m	$0m
Total		$210m	$70m

* Notes: Estimated figures have been rounded to the nearest 10m
**Nigeria, South Africa and Turkey are assumed to have a relatively lower pace of reforms in the low and medium success scenarios, based on political economy assessments indicated in the strategic case. Further political economy analysis will be undertaken to update this assessment.

A range is presented in figure 12 to account for the prospect of not all intended major reforms being successfully implemented and to mitigate risks arising from difficulties in: determining the likelihood of reforms failing; political buy in and cooperation of recipient countries.

## Sensitivity Analysis
The primary and secondary estimates are based on Haidar’s analysis which suggests that each successfully enacted major reform could add 0.114 percentage points to GDP growth. Haidar found that without controlling for a range of different variables the impact increased to 0.150 percentage points. A sensitivity analysis applied to the estimate for this programme shows a broader range of potential gains if the expected impact on GDP growth is varied. For example, by setting the expected impact on GDP growth at either 0.075 or 0.150 percentage points, the overall value of potential primary benefits across scenarios could range from approximately £450m to £2,300m and the overall value of potential secondary benefits across scenarios could range from approximately £30m to £210m.

Figure 13: Estimated present value of programme benefits sensitivity analysis
	Primary Reform Impact*
Medium success (9 reforms)	£1,150m	£1,740m	£2,300m
Low success (3 reforms)	£450m	£680m	£900m
Secondary Reform Impact*
Medium success (9 reforms)	£110m	£170m	£210m
Low success (3 reforms)	£30m	£50m	£70m

* Notes: Estimated figures have been rounded to the nearest 10m

# Commercial Case
## Delivery mechanism and implementing partners
The programme is delivered by the World Bank Group (WBG), which has the proven capacity, capability and experience to deliver similar thematic programmes. The programme will benefit from the central assurance assessment of World Bank systems and any additional due diligence at the programme level will draw on existing risk frameworks and HMG guidance on due diligence on multilateral institutions.
The programme will run for four years starting in the autumn 2017, and will deliver the outputs and outcomes defined in the Theory of Change in the appraisal case. HMG funding is provided through an accountable grant to WBG which is managed as a single-donor trust fund. The arrangement is underpinned by an administrative agreement between the UK and WBG, with specific provisions, including on governance and implementation. The process undertaken in setting up this partnership with the World Bank is illustrated in figure 14 below. HMG will not directly procure goods or services. Where the WBG needs to procure goods or services, including equipment and external expertise, they will follow the provisions of the administrative agreement, which are consistent with HMG procurement principles and international best practice.
Figure 14: approach to partnering with the World Bank

Overview of trust funds: A trust fund is a financial instrument that supports World Bank Group partnerships with donors. WBG will typically receive, spend, and monitor funds for a specific purpose agreed with donors, who are usually government departments, multilateral agencies or charitable foundations. As trust fund administrator, and irrespective of the governance arrangement, WBG retains full responsibility for implementing World Bank-executed activities and appraisal and supervision of those activities executed by recipient governments. Although normal progress and financial reporting applicable to all trust funds administered by the WBG remain in place, a more frequent reporting cycle may be required[68]. A more flexible approach would for example enable short-notice responses to UK media or parliamentary scrutiny of issues such as value for money of the programme; type of activities; and benefits to the UK.
[68] See the Management Case for details of the MREL arrangements.
## Managing performance and value for money
To manage implementing partner performance, well-defined KPIs will be specified in the administrative agreement and its provisions, in relation to both the WBG’s management of the programme and the delivery of programme results. Cross-Whitehall expert advice will be used to ensure this is done effectively. Additional detail on the framework for monitoring and evaluating the programme is included in the management case.
Funding will be structured as output-based payments. The specific deliverables required for triggering disbursements are agreed in advance between FCO and WBG. In year one, an initial payment will be made upon signing the administrative agreement and subsequent payments issued annually once milestones, including the following, are met: diagnostics and constraints analyses conducted; programme design completed; baselines and results frameworks set up; global influence reports (global toolkits, diagnostics, knowledge notes behavioural economics research); impact evaluations initiated/progressed; global business/investor competitiveness survey and report; and high-level, multi-stakeholder, peer-to-peer learning and thought leadership event held. Delivery of these outputs will be included in reports to the partnership council / programme board, and if content with progress, the FCO will write to the World Bank confirming the disbursement of funds.
The programme’s operational emphasis will be on approaches, tools, and implementation models that ensure measurable development results. The Global Influence Initiative focuses on improving the analytical foundations, design, implementation and evaluation of business environment reforms will allow the programme to better target, design, and measure its own interventions, thus increasing the prospects of the programme delivering significant impacts. This cross-cutting component is also key to the programme’s flexibility, allowing solutions to be refined and adapted on the basis of the most relevant and up-to-date evidence. Country-level interventions will be based on assessments of individual countries’ needs, learning from past and current reform efforts, and tailored from the menu of options within the programme.
To ensure best value for money, an administration arrangement has been negotiated which draws expertise and input from both the International Finance Corporation and the International Bank for Reconstruction and Development parts of the World Bank Group. Working with the WBG through a trust fund arrangement allows them to deliver services in more innovative and flexible ways, thus increasing the impact of their activity. It also attracts a recently simplified and more transparent cost-recovery arrangement, designed to increase their internal efficiency in administering and governing the funds. The recent DFID-led multilateral aid review identified the WB as one of the most effective and efficient agencies. As a key strategic partner - one of the five largest shareholders, with a UK appointee on the Board of Directors and with UK contributions to WB Trust Funds totaling £540 million in FY2015/16, the UK has a prominent position in the governance of the Bank and is in a strong position to push for more efficiency and value for money, and work closely with WBG teams to shape and manage this fund for maximum impact and value..

In addition, progress and results will be robustly monitored and evaluated throughout implementation and to adapt the programme where necessary to ensure maximum impact. The WBG will provide semi-annual written progress reports, reviewing delivery against the agreed results framework. Within six months of the End Disbursement Date the WBG will also provide a final narrative progress report, which will feed into FCO’s final programme evaluation. The administrative agreement will contain a provision to ensure that we can review or evaluate funded activities at any time up to closure of the Trust Fund.
## Financial reporting
The WBG will maintain separate records and ledger accounts in respect of this funding. Current financial information relating to receipts, disbursements and fund balance will be made available quarterly, with a final update within six months of commitments and liabilities being satisfied and the fund closed. Within six months of the WBG financial year, the WBG will make available an annual single audit report, comprising (i) a management assertion together with an attestation from the WBG’s external auditors concerning the adequacy of internal control over cash-based financial reporting for all cash-based trust funds as a whole; and (ii) a combined financial statement for all cash-based trust funds together with the external auditor’s opinion thereon.

## Potential risk transfer
This arrangement has significant risk sharing potential as illustrated in figure 15 below.
Figure 15: scope for risk transfer
Risk Category	Potential allocation
	FCO	WBG	Shared
Design risks			X
Implementation risks		X
Performance risks		X
Control risks			X
Financing risks			X
Technology risks		X
Termination risks			X
Legislative risks			X
Commercial risks		X
Political risks	X

## Potential delivery risks
The chosen delivery route carries low commercial risk. The table below shows potential risks and how they might be mitigated.

Figure 16: Typical implementation risks and how they could be mitigated

Risk	Mitigating Actions
Poorly defined KPIs and required outcomes	Draw on best practice across HMG programmes where this approach is common / Ensure sufficient flexibility in the administrative agreement and programming approach to enable review and refinement of future years’ KPIs and required outcomes
Inadequate WBG monitoring, reporting, evaluation and learning (MREL)	Clearly define expected standards in the administrative agreement / Maintain regular dialogue with WBG about MREL outputs / Establish close liaison between WBG and UK in-country teams to allow verification by direct observation.
WBG effectiveness	Close partnership on developing the programme and designing interventions to ensure there is realistic ambition and understanding of UK expectations / Ensure well-defined KPIs and quality standards/expectations in administrative agreement
WBG reliability	Close working with WBG team / Monitor wider WBG developments for early signs of change that might give rise to withdrawal / Maintain knowledge of potential alternative partners
Programme design failure	Set strong and clear objectives and requirements / Ensure that the quality and effectiveness of design proposals are well scrutinised and challenged / Output based payment structure incentivises quality of design
Programme delivery failure	Output based payment structure linked to KPIs. / Effective programme management / Robust and continuous MREL practices
Insufficient flexibility in administrative agreement	Define requirements as accurately as possible and be disciplined about changes / Align expectations of what adaptive programming means in practice / Have an agreed mechanism for managing changes to requirements

Financial Case
## Type of agreement – contract length, cost and method of payments
The legal basis for the partnership with the World Bank to deliver a £30m programme over four years from October 2017, is in the form of an Administrative Agreement. The Agreement and its provisions set out the terms and activities to be managed through a trust fund, including: the activities to be financed; eligible expenditure; the results framework; and budget. The arrangement will also outline the management and administration of the payments; the type and frequency of progress reporting by the World Bank; and if needed the ability to withhold and cancel payments. Indicative costs by country and programme component are shown in figure 16 below.
Figure 16: indicative costs by country and programme component
Global/country theme	I. Strengthening business regulations and practices	II. Enhancing business competitiveness	III. Subnational support and equity	Budget estimate
Global influence initiative	✓	✓	✓	£8m
Brazil	£2m	£1m	£1m	£4m
Indonesia	£2m	£1m	-	£3m
Nigeria	£1.5m	£1m	£1m	£3.5m
Pakistan	£0.5m	£1m	£1m	£2.5m
South Africa	£1.5m	£1.5m	£1m	£4m
Turkey	£1m	£1m	-	£2m
Trust Fund management				£1.5m
Sub-total				£28.5m
FCO resource				£1.5m
Total				£30m

Reporting
In addition to formal reporting on financial activities to the partnership council as set out in the Administrative Agreement, the World Bank will also maintain records and ledger accounts of funds deposited in the Trust Fund and will update all financial activity including receipts, payments and fund balance on its Development Partner Centre website. The FCO programme team in London with oversight of all Prosperity Fund programmes will work with WBG to capture and baseline data. They will also ensure close engagement on data quality and consistency with monitoring and reporting resource contracted to cover the Prosperity Fund portfolio. Once all the commitments and liabilities under the Trust Fund have been met and the Trust Fund is closed, the final financial information will be made available to the FCO which, in agreement with the World Bank, can also request an exceptional financial audit to be carried out.
Accountability
The World Bank will provide a semi-annual progress report to the FCO with reference to agreed outputs and the overall results framework. For FCO monitoring purposes more frequent reviews of progress are foreseen between FCO and WBG as set out in the governance section of the management case.
The FCO can request a more formal review at any time, the scope of which would be agreed beforehand with WBG. Any costs of additional reporting or conducting reviews will be met by the Prosperity Fund central MREL budget within agreed limits for each programme. In mitigating fiduciary risk, the World Bank is expected to take all appropriate measures to prevent fraud and corruption as set out in the administrative agreement with the FCO. The risk of fraud on World Bank executed support is minimal and the FCO takes a zero tolerance approach to corruption and fraud. Where there are allegations of misconduct, timely and appropriate action will include: sharing information on an active investigation, where appropriate, informing the FCO of progress and the outcome of an investigation; and taking the necessary action to recover funds. In the case of an active investigation, HMG fraud processes will be followed.
Disbursement and cancellation
Payments will be linked to indicators and disbursed regularly following a written request from WBG. By giving three months’ notice the FCO can cancel its contribution to the Trust Fund with no penalty and the World Bank will return the balance to the FCO. If the FCO believes the World Bank has failed to meet any of the conditions of the Agreement, the World Bank and FCO will meet to resolve the matter. If this fails, the FCO can with thirty days’ notice withhold all, or a portion, of the next instalment.
Proposed payments (see also ‘disbursement’ in management case)
The FCO will make regular payments or contributions to the Trust Fund which are linked to the achievement of agreed outputs. To allow for flexibility, the size of the payments and instalments can be changed if agreed by both parties beforehand. Through internal processes, the WBG will allocate funds to support in-country delivery as well as cross-cutting activities. A draft delivery matrix with prospective payment-linked indicators and an indicative profile of disbursements is shown in figure 17 below.
Figure 17: Delivery matrix with indicative disbursement profile
Country activity	By 10/2017	2017/18	2018/19	2019/20	2020/21
FCO/WBG Administration agreement signed	x
Diagnostics and constraints analyses conducted		x
Program design completed		x
Baselines and results frameworks set up		x
Country-specific reports (assessments, guidelines, surveys, manuals, training materials, etc.)			x	x
Institutional / strategic changes recommended			x	x	x
New laws / regulations / amendments / government policies / procedures / practices / standards drafted/proposed for reform			x	x	x
Recommended institutional / strategic changes adopted				x	x
Recommended laws / regulations / amendments / procedures / practices / standards reformed or government policies adopted				x	x
Workshops, training events, seminars, conferences held		x	x	x	x
Global influence
Global influence reports (global toolkits, diagnostics, knowledge notes behavioural economics research, etc.)		x	x	x	x
Impact evaluations initiated/progressed		x	x	x
Global Business/Investor survey questionnaire and report concept note	x
Global Business/Investor Competitiveness Survey and Report		x		x
High-level, multi-stakeholder, peer-to-peer learning and thought leadership event		x		x
Indicative disbursement profile	£6.5m	£5.5m	£5.5m	£5.5m	£5.5m

Cost of UK programme resource
The programme will be managed by the WBG and any use of specialist advisors, third party organisations or any other type of external consultants will be undertaken by WBG within the limits of funds allocated to planned activities. However, in addition to the London programme team, a proportion of full time equivalent staffing will be needed in focal posts to support delivery as indicated in the management case. Figure 18 below provides an indication of FCO resource costs.
Figure 18: indicative FCO resource costs
Grade	Responsibilities	Annual cost
FCO pay band D	Programme oversight and strategic direction; lead on World Bank engagement; wider representation and engagement with key partners and stakeholders; mitigation of key risks.	£ 108,109
FCO pay band C	Programme management; financial and progress reporting; liaison with UK posts.	£ 73,754
FCO pay bands B and C / (FTE) x 6 locations*	In-country liaison with World Bank teams/missions; progress reporting; coherence of programme with wider prosperity work.	£ 168,116
Subtotal		£ 349,980
Admin/T&S/training/contingency		£ 66,300
Total		£416,279

*Costs in different locations will vary. Figures are based on 2016/17 full economic staff costs.
Assessment of financial risk and fraud
 Fiduciary risk is also covered in the ‘Reporting’ and ‘Accountability’ sections. The programme will seek to mitigate potential risks of fraud and corruption by ensuring that:
- funds are only channelled through the agreed process;
- posts work closely with the WBG in-country team to ensure that outputs linked to disbursements in financial reporting accurately reflect the actual progress of delivery; and
- the consultative committee (see ‘Governance’ section) provides additional assurance as required, by undertaking periodic scrutiny of financial activity.
Management Case
The programme will be delivered by WBG regional/country teams and managed centrally in Washington DC. HMG programme management resource will comprise FCO staff in London and at posts as set out in figure 18 above, with the overall accountability of the FCO Director of Economic Diplomacy serving as Senior Responsible Owner (SRO). DFID will participate on the Partnership Council with WBG while other HMG departments will have working level advisory input to the programme. DFID, HMT, DIT and BEIS will also have more strategic oversight on portfolio and ministerial boards.
The respective sizes of the WBG in-country teams focusing on macroeconomics, trade and investment activities including the implementation of this programme are shown below. The delivery teams will: liaise closely with UK staff at posts; be supported by a range of specialists on regular missions to each focal country; and benefit from a central resource in Washington DC, responsible for oversight and management of country programmes under the trust fund.
Given the governance model outlined below, particularly the role of in-country sounding boards, there will be some demand on FCO overseas resource of a proportion of FTE of a programme manager at each focal post (FCO Bands B or C). World Bank staff responsible for developing and implementing activities will closely liaise with the programme manager at post to ensure synergy with other UK activities. The programme lead will also provide strategic input as a member of the country sounding board.
Figure 19: Indicative WBG in-country staffing covering the relevant thematic area
Country	WBG Macroeconomics Trade & Investment in country staff
Brazil	2
Indonesia	6
Nigeria	4
Pakistan	4
South Africa	6
Turkey	1

Governance
This programme will be governed at two levels through: 1) a partnership council and 2) country sounding boards.
The Partnership Council will comprise representatives from the FCO, WBG and DFID. At the discretion of the Council, representatives from post, WBG country teams, development partners and the private sector may be invited to provide input.
The Council will meet at twice a year to review the annual report, indicative work plans and budget allocations as well as agreeing payments linked to the achievement of agreed milestones. Semi-annual reports will include outputs, outcomes, impact as well as any measures taken to ensure the sustainability of the programme objectives. The FCO and WBG global programme leads will also meet at least quarterly for updates on progress including input from respective country teams. The Council will be co-chaired by the FCO.

Figure 20: Programme governance

Country sounding boards will comprise WBG regional and country teams, UK representatives at post as well as representatives of host governments. While the majority of business is expected to be carried out by in-country teams, FCO and WBG global leads will participate in some of the sounding board meetings. The country boards will report to FCO/WBG global programme leads on in-country activities including:
1. Ensuring the design of country work plans have buy-in from host governments;
2. Avoiding duplication between the UK and WBG teams in-country;
3. Sharing information and align expectations on reforms.

As a minimum, country boards will:
- meet at least twice a year to discuss the programme process and progress while sharing relevant documents as these become ready/available;
- share forward looks with indicative timings for relevant missions to focal country and provide briefings on kick off and wrap-up of missions;
- ensure coherence by providing input and support as necessary (e.g. UK missions providing views of UK businesses to the WBG’s private sector/investor consultation/survey and vice versa where World Bank views can inform wider UK prosperity work)
- coordinate relevant high level engagement with host governments to ensure more effective engagement.
Implementation progress will also be regularly reviewed by a cross-Government advisory group. These arrangements allow for the coordinated engagement necessary for effective delivery as illustrated in figure 21 below.
Figure 21: Potential for coordinated delivery

Monitoring and evaluation
Governance arrangements including the partnership council and country steering groups will ensure comprehensive and regular monitoring of the programme, taking into account a wide range of views from the private sector, host governments and other development partners undertaking related interventions. In addition to the standard monitoring and evaluation included in the administration of trust funds, some independent assessment will also be undertaken as part of the wider Prosperity Fund process. The programme team will ensure close engagement between WBG and the Prosperity Fund Evaluation and Learning teams developing the overarching evaluation methodology for the Prosperity Fund as detailed below.
Results framework
The monitoring, reporting, evaluation and learning (MREL) for this programme will be consistent with the Prosperity Fund-level approach to MREL. We will work with the Fund contractors to develop critical indicators for Fund and programme level reporting, identifying aggregatable indicators for regular reporting and management indicators to allow programme managers to assess progress and impacts. The programme MREL will be consistent with the programme theory of change and the log-frame analysis that flows from this. We will report expenditure monthly and impacts (results) quarterly in line with Prosperity Fund reporting rhythms.
Reporting frequency and costs
Consistent with Prosperity Fund requirements a quarterly results reporting system will be in place and consistent with overall Fund processes and systems – particularly around data quality and consistency. Programme data capture and baselining will be the responsibility of the programme and its implementers but costs of this will be charged to the central MREL budget. This element of the programme is capped at 1% of programme allocation.

Evaluation and Learning
If this programme is selected as one of the sample for Fund level evaluation, the strategic questions required for both the fund evaluation and to provide feedback to programmes on routes to impact will be developed. The overarching evaluation methodology will be decided by the Fund level evaluators and we will work to deliver the required coordination between the various contractors at programme level.
If the programme is not selected for Fund level evaluation we will work with the programme level Evaluation and Learning contractor to develop a set of strategic questions that we will want to answer through the process. These questions may include Fund level questions if appropriate.
We further note that not all programmes are evaluable and as part of the coordination with the Prosperity Fund evaluation contractors we will assess this and decide on a way forward with the PFMO.
Monitoring and Reporting
Responsibility for data capture, baselining and reporting sits with the programmes and their implementers. Indicators will need to be agreed with the Fund level monitoring and reporting contractor, the evaluators and the programme implementers. The monitoring and reporting contractor will identify the data requirement in terms of format and quality. We will work with our stakeholders to ensure that reporting is done in a timely and useful manner.
Flexible programming
Applying flexibility will vary between components and from country to country. The programme has also designed an in-built flexibility to intervene and support the dissemination of expertise across a wider set of countries. Flexibility increases the likelihood of successful delivery and ensuring the most effective use of HMG resources in countries where the political climate tends to change frequently for example Nigeria or Brazil.
Risks
Risks around impact assessment, evaluation and flexible programming are listed above. In working with a large global institution such as the World Bank Group sufficient time needs to be factored in for budget monitoring and reporting to adhere to FCO requirements and adequately support any Ministerial, media and parliamentary scrutiny. Wider risks are covered in the commercial case.
Communication
Consistent with the wider Prosperity Fund communications strategy, the programme will actively engage stakeholders from business, partner governments and other sectors to promote programme activities including in forums and events such as conferences. The FCO team at post will lead on in-country engagement, working with Economic Diplomacy and Communications directorates in London. Communication will include messaging within FCO on internal tools and platforms as well as external promotion through the use of social media, local and national press/online coverage and video messages for post websites or Facebook pages. A communication strategy for the programme will be finalised during inception.