November 2019

Briefing Pack for
Senior Responsible Owners (SROs) of GMPP programmes and projects and HMRC Major Change.

Table of Contents

# Introduction

This Briefing Pack contains important information that supplements the IPA’s ‘Your role as a senior responsible officer’ document and your Letter of Appointment as Senior Responsible Owner for a programme or project within the Government Major Projects Portfolio (GMPP) and/or HMRC’s Major Change Portfolio.

You should familiarise yourself with the content of the IPA’s ‘Your role as a senior responsible officer’ document in advance of this document and in conjunction with the and your Letter of Appointment and apply the guidance and principles as appropriate to support the successful delivery of your specific programme or project within both the HMRC and GMPP contexts.

In addition you will need to understand the accountabilities of other key HMRC change governance roles set out an Annex A (2), and work collaboratively with them to ensure the integrity of these accountabilities in support of successful delivery.

This document will also be of value to:

- ExCom Senior Business Sponsors of transformation programmes
- HMRC Programme Directors and their teams
- Assurance Review Team leaders and members

# What is a Senior Responsible Owner (SRO)

The SRO is the most senior role in HMRC’s programme and project governance arrangements and is the individual accountable for ensuring that a change programme or project meets its objectives and delivers the required outcomes to ensure that the business can realise the benefits stated in the business case.

# What is the Infrastructure and Projects Authority (IPA)?

IPA (formerly known as the Major Projects Authority or MPA) provides expertise in infrastructure and the financing, delivery and assurance of major projects, to support more effective management and delivery across government. IPA sits at the heart of government, reporting to the Cabinet Office and HM Treasury. You should also make yourself aware of the IPA guidance on management of major projects, especially the role they play in assuring your programme and the interventions they can make.

# What is the Government Major Projects Portfolio (GMPP)?

The GMPP includes the largest, most complex and highest risk projects across government.

Programmes or projects meeting one or more of the following characteristics should be referred to the IPA for inclusion on the GMPP:

- above the delegated authority limit for the organisation;
- could create pressures leading to a breach in departmental expenditure limits, administration cost limits, or estimates provision;
- would entail contractual commitments to significant levels of spending in future years for which plans have not been set;
- could set a potentially expensive precedent;
- is novel and contentious; or could cause significant repercussions, posing risks to the public sector;
- requires primary legislation or where HM Treasury consent is a statutory requirement.

This normally happens as part of the review process on the Risk Potential Assessment document.

Programmes and projects not meeting the above criteria may be added to the GMPP with the agreement of IPA and HM Treasury spending team.
# What are HMRC’s Project Delivery Standards?
The IPA has published a Project Delivery Standard to be used across all government departments and sets out best practice guidance for any government portfolio, programme or project at a very high level. It has been created to set expectations for the management of portfolios, programmes and projects ensuring value for money and successful, timely and cost-effective delivery of government policy and business objectives.

The Standards work with our HMRC Change Governance (formerly the Change Framework), which ensure HMRC has a consistent set of programme documentation, tools and processes in order to create a coherent portfolio of change, and already follows the best practice the Standard is based on.
# Your role as SRO

You are personally accountable for ensuring the ongoing delivery of the programme or project as set out in your Letter of Appointment.

You are responsible for securing the resources necessary for success and for the ensuring that the related implementation and transition activities realise the agreed objectives and benefits.

You will be personally accountable to Parliamentary Select Committees and be expected to explain the decisions and actions you have taken. This could include where a Minister has intervened to change the project during the implementation phase in a way which has implications for the cost and/or timeline of implementation. You will be able to disclose your advice about any such changes.

You must ensure the effectiveness of the governance, assurance and project management arrangements and maintain them throughout the life of the programme or project. You should adopt best practice and be prepared to justify any deviation from it, in line with guidance published by the Cabinet Office.

The HMRC Portfolio Team are on hand to help you during your tenure as SRO. They can be contacted through the Portfolio Director.

# Characteristics of an SRO

An SRO will:

- Be a visible, engaged and active leader, not a figurehead;
- Deliver the agreed outcomes and benefits;
- Create an open, honest and positive culture committed to delivering at pace;
- Challenge senior officers and Ministers when appropriate and escalate quickly;
- Ensure that appropriate governance is applied within the programme
- Provide appropriate support, steer and strategic focus to the Programme / Project Director and ensure that they have a clear and current letter of appointment; and
- Have sufficient time, experience and the right skills to carry the full responsibilities of the role.
# Specific SRO accountabilities
## Ensure that the programme or project is set up for success

- Ensure that the programme or project is set-up to make an unambiguous and demonstrable link to strategic policy;
- Translate this policy intent into clear deliverables which are established and agreed with senior stakeholders;
- Carry out a robust and commercially viable options appraisal, which balances risk with opportunity, as part of initial project feasibility;
- Establish a firm business case during the initiation/definition phase and ensure that any planned change continues to be aligned with the business and is formally recorded and approved;
- This business case should align with the SRO’s delegated authority;
- Identify and secure the necessary investment for the business case (this includes both budget and operational resource);
- Adhere to appropriate and transparent project governance in line with HMRC Project Delivery Standards;
- Build strong and effective relationships with key stakeholders, justifying their trust and retaining their confidence, and obtain their commitment to benefits realisation.

## Ensure that the programme or project meets its objectives and delivers the projected benefits

- Gain agreement to the stated objectives and benefits amongst stakeholders, including Ministers where appropriate;
- Understand the broader government perspective and its impact on the project;
- Ensure the strategic fit of the stated objectives and benefits;
- Agree a clear and simple approach to performance management and monitor delivery of the objectives and benefits, taking appropriate action where necessary to ensure their successful delivery.

## Develop the organisation structure and plan

- Ensure that there is a coherent organisation structure and appropriately detailed plans;
- Build the right team, securing necessary resources and skills and providing clear lines of accountability;
- Provide appropriate support, steer and strategic focus to the Programme or Project Director.

## Monitor and take control of progress

- Monitor and control the progress at a strategic level, being honest and frank about progress, risks and issues;
- Ensure that any changes to agreed benefits are flagged appropriately within programme / project governance and that the business case is updated accordingly (throughout the delivery lifecycle);
- Ensure that you maintain appropriate change control in line with HMRC’s governance process.
- Ensure that the integrity of the programme / project is maintained and speak truth to power – including to Parliamentary Select Committees;
- Communicate effectively with senior stakeholders regarding progress and provide clear, appropriate and delivery-focused decisions and advice to the Programme or Project Director.

## Ensure problem resolution and referral processes are appropriate and effective

- Identify, understand and drive the successful mitigation of project risks;
- Escalate serious issues quickly and with confidence to senior management and/or Ministers;
- Develop strong and effective engagement between the project team and its stakeholders and sponsors;
- Ensure that communication processes are effective and that the project’s objectives and
deliverables continue to be consistent with the organisation’s strategic direction.

## Ensure that the project or programme is subject to review at appropriate stages

- Recognise the value of robust project review and ensure it occurs at key points in the project lifecycle, particularly at the pre-initiation (feasibility) and initiation stages;
- Make certain that any recommendations or concerns from reviews are met or addressed in a timely manner;
- In the event of a “red” or “amber-red” review or a red or amber-red quarterly GMPP review rating, ensure that the Chief Executive has been made aware of the situation and has been briefed accordingly. 	Ensure that your project or programme is conducting regular evaluation and “lessons learned” exercises, both in their delivery and in respect of outcomes achieved. Lessons should be recorded and shared across the Department.

## Manage formal closure

- Ensure that a plan is in place to formally close the programme or project and ensure that the lessons learned are documented within the final evaluation report and disseminated to key stakeholders;
- Ensure that the post implementation review takes place and that the output is communicated to the appropriate stakeholders;
- Ensure a plan for both long term benefits realisation and on-going sustainability is agreed with key stakeholders as part of the process of moving the project to “business as usual”;
- Ensure a Post Implementation Review is undertaken, typically 6-18 months following closure of the programme or project.
# Strategic Accountabilities
HMRC has a clear Strategy and Vision which sets out our current strategic position and future direction of travel. A number of Strategic Decisions have been taken to help HMRC become a world class organisation. HMRC has developed a model to align all its change activity to the agreed Strategic Decisions.

## How the Model works

HMRC have established Strategic Capabilities which will deliver the Outcomes the organisation needs for the future:

For example “To be a world class IT organisation using transformed, cloud based technology”.

Impact Assessments have been completed for each project within your Programme. These highlight alignment to the HMRC Strategic Decisions, links to existing change portfolio projects and programmes and identify any gaps, questions or challenges.

For more information please contact the Portfolio Design Team (Gary Downes).

## Your Accountability

Detailed in Appendix B of your SRO accountability letter you will see details of your contribution to the delivery of HMRC’s Strategic Capabilities. You are responsible for iterating this Appendix and presenting an updated signed version alongside any change control request or business case.

# Giving evidence to Select Committees

The Civil Service Reform agenda included proposals for Senior Civil Servants to be directly accountable to Parliament for delivering major projects.

The ‘Osmotherly Rules’ which set out how departments interact with select committees, have been reviewed. As a result, in addition to their internal accountabilities, SROs for programmes and projects will now be held personally accountable to Parliamentary Select Committees. Guidance can be found here.

# Managing Public Money

You should operate at all times within the rules set out in Managing Public Money. Public servants have a demanding fiduciary duty to use public money responsibly. Much of what managing public money requires is just good common sense, sound financial management.

There are also some specific rules and conventions about how certain things are handled, which ensure that policies, programmes and projects work smoothly and serve their intended purposes.

# HM Treasury delegated limits and Cabinet Office Controls

You must be mindful of, and act in accordance with, the specific Treasury delegated limits for and Cabinet office controls relevant to HMRC.

HMRC has delegated authority to commit expenditure up to a total of £75M. This limit applies to any programme or any project that is part of a larger programme. It applies to the total spending on programme or project costs.

Programmes with expenditure above this amount, or which are “novel or contentious”, will require formal HMT approval. To enable this to be done in a timely and effective basis, HMT should be consulted at an early stage and involved on an ongoing basis in the development of the business case and in monitoring implementation, probably through the Programme Board.

HMT will also require sight of any programme or project where the lifecycle costs are over £25m.

Approval “in principle” should be sought at an early stage in the development of the project with formal approval being sought at sign-off of the full business case. Key programme documentation such as Strategic Outline Case etc. should be shared with HMT as part of this consultation.

The Cabinet Office Controls are part of the UK government’s approach to tackling its budget deficit while supporting growth, ensuring public money is used as efficiently and effectively as possible. Guidance on how the controls work and how expenditure will be approved can be found here.

Additional information can be found in External Approvals (HMT & Cabinet Office) and Treasury approvals process for programmes and projects.

Before approaching HM Treasury or IPA you should contact the HMRC External Controls Team within Change Assurance and Investment at “Mailbox, Investment Appraisal”.

# Developing your personal delivery leadership capability

You should liaise with the HMRC PPM Head of Profession to discuss maintaining and enhancing your personal programme and project delivery skills.

If you are undertaking the SRO role alongside your Director General or Deputy Chief Executive responsibilities, you will not be required to enrol on Major Projects Leadership Academy (MPLA). However, your Programme Director or equivalent SCS level role will be expected to have completed, or enrol for, MPLA and you should support and oversee the ongoing professional development of MPLA graduates in your team, and encourage them to take an active part in MPLA alumni activities.

Examples of the types of courses available to enhance your programme and project skills include:

- Orchestrating Major Programmes (OMP)
- Major Projects Leadership Academy MPLA)
- Project leadership Programmes (PLP)
- 1 day leading as an SRO programme
- EU Exit Programme for Project Leaders (PPL)
- Policy to Delivery

# The 7 Lenses of Transformation
## Overview

In 2016 IPA created a cross-government community of practitioners to share experience of transformation. They wanted to learn from successful work across government to identify areas we collectively need to tackle and improve our chances of delivery.

The 7 Lenses emerged from discussions with change leaders across government to develop a common language about what successful transformation programmes have in common. All of these programmes are very different, but they were able to identify common themes that you need to get right. IPA have distilled this mass of learning experience into a tool that is straightforward to apply in your environment.

Using the lenses will give you confidence and reassurance that you are focussing on the right priorities, and will help you to identify which areas need more attention.

This tool was developed and reviewed by experienced practitioners from within and outside government from a variety of roles, including programme directors, senior responsible owners and chief digital officers. The IPA and Government Digital Service (GDS) have been using the 7 Lenses in their ongoing work to support delivery, for example through the IPA’s independent assurance of major projects and GDS’ digital and technology spend controls. Though IPA know there is no single recipe for success, they’ve found that using this common language is helpful for teams delivering transformation across government.

## Using the 7 Lenses

The 7 Lenses are helpful when applied at different stages in your transformation journey. They’re intended as a common language, which can help you find useful materials from other parts of government, as well as to develop your own materials and tools.

This tool is primarily aimed at departmental change leaders, including SROs, programme directors, chief digital officers and chief information officers. It has proven to be equally applicable to any size organisation (including agencies, small departments, parts of a big department and big departments).

## How the 7 Lenses can help

The 7 Lenses are particularly useful to give teams a common language and consistent framework for talking about transformation. They are useful throughout the lifecycle of the transformation.

When setting up your transformation, the 7 Lenses can help you:

- structure your work and get started
- define success
- secure commitment and support from senior leaders
- make sure you have considered all of the things you will need to do to be successful

The 7 Lenses can be used at any time as a healthcheck to establish:

- how are you doing?
- what’s the next most important thing you should focus on? (prioritisation and planning) 	will you get there? (reality check) 	are you missing anything?

People who support and assure projects have found the 7 Lenses helpful to:

- educate on transformation programme management
- provide methodology
- talk the same language
- reduce the time required to become productive

The 7 Lenses can be used as part of delivery assurance at different stages of the project, and especially at major project review points. Familiarising yourself with the 7 Lenses and where you are will enable you to have better conversations at these review points.

Together this helps to ensure the transformation is delivered in the best possible way.

## The 7 Lenses

The 7 Lenses are available to view here on GOV.UK.

# NAO/Cabinet Office - Common Causes of Project Failure
The list below has been developed by National Audit Office and Cabinet Office to highlight the common causes of project failure.

Lack of clear link between the project and the organisation’s key strategic priorities, including agreed measures of success.

Lack of clear senior management and Ministerial ownership and leadership.

Lack of effective engagement with stakeholders.

Lack of skills and proven approach to project management and risk management.

Too little attention to breaking development and implementation into manageable steps.

Evaluation of proposals driven by initial price rather than long-term value for money (especially securing delivery of business benefits).

Lack of understanding of and contact with the supply industry at senior levels in the organisation.

Lack of effective project team integration between clients, the supplier team and the supply chain.
# Key principles of Programme and Project Management
Key principles are outlined in the IPA Project Delivery Standards.

HMRC programmes and projects operate in the context of the HMRC Portfolio and the Change Governance (formerly the Change Framework). HMRC operates good practice Portfolio Management principles through the Transformation Portfolio Management Group and the Change Assurance and Investment function.
# Vision
All those who will be affected by a programme or project need to have a clear picture or vision of what the future looks like. There should be a vision statement which describes, at a high level, the sort of new services, business processes, organisational structure or culture to be introduced. This can be a useful tool in gaining commitment to the proposed changes from those who will be involved.
# Blueprint
The Blueprint builds on the vision statement and gives a more detailed description of the change to the business area and will help to identify the full costs and impacts of the planned changes. It is developed alongside the business case and the work done on benefits management. This work cannot be developed in isolation and should be done in conjunction with business representatives.
# The Business Case
The Business Case is the justification for an investment based on the overall value for money and achievability of the proposed changes.

The Business Case balances costs and benefits against strategic objectives and brings together information such as timing and risks so that a measured judgment can be made on whether or not to commit resources.

Elements of a sound investment case include:

- Rationale for the investment including the background on why it is needed e.g. ministerial/legislative obligations and its fit with HMRC’s strategic plan;
- Clear options appraisal and justification of recommended option, including comparative discounted cash flows;
- Identification and quantification of all costs and benefits (and highlighting any unquantifiable costs and benefits) including monitoring and evaluation costs;
- Evidence that the proposal is commercially feasible/deliverable;
- Identification of any dis-benefits and whether the programme should still be delivered;
- Risk assessment (risk identified, managed and allocated)
- Sensitivity analysis, and adjustment for optimism bias;
- Affordability, and clear acceptance by the relevant directorates of the costs and savings attributed to them

Each case needs to be clear about:

- The source of costing information (often it should be CDIO);
- Due sign-off for costs and benefits, including as necessary; confidence levels and relevant dependencies that could affect either;
- The Sign On: Sign Off process;
- The sources of funding e.g. Transformation or CDIO run costs/business as usual in other lines of business;
- The link from costs to deliverables and benefits;
- Optimism bias, tolerances and assumptions aligned to the Treasury Green Book.

Business Cases must comply with HM Treasury Green Book requirements and HMRC Investment Appraisal policy and guidance.

You are responsible for ensuring that any changes to the scope, costs, benefits or planned delivery milestones are managed and approved in accordance with HMRC change control. Agreed tolerances stated within the original Business Case will apply.

Change Assurance and Investment (CAI) have suggested four areas of focus to improve business cases:

  - Engage early - engage CAI and Transformation Finance and Benefits early, as you prepare to draft the business case and during its evolution. This will avoid a burst of hurried activity that can delay the governance and/or mean poor quality business cases or papers. A range of keyholders also examine business cases and papers ahead of them going through the formal governance; you will want to ensure an early engagement with them too, to smooth the path.

  - Linking cost to outcomes including benefits - there is the need for some granularity in business cases, to get underneath the headline figures. So, for example, instead of setting out a range of activities and top level benefits, a layer underneath that eg the five key deliverables, their costs and their benefits would help the decision making.

  - Surfacing tensions - this is not in an emotive sense, rather it is the clarity around choices that need to be made. Those choices may well be hard choices, and a focus on those will help give visibility to the decisions that are needed and provide the information to enable those decisions.

  - Ranges and precision - historically, insufficient weight has sometimes been put on: optimism bias, tolerances and clarity on assumptions. More clarity on those aspects will assist the understanding of the risks and linkages that are inevitable parts of transformation delivery. The tolerances aspect is increasingly important as any deviation from agreed tolerances in GMPP programmes will lead to a review by the Chief Executive with a summary published, as required by new IPA guidance – ill thought through tolerances will increase that work and public exposure.
# Benefits Management
In simple terms, a benefit can be defined as ‘a measurable improvement from change’. The fundamental reason HMRC invests in programmes and projects is to realise benefits through change.

Using a structured approach to benefits management helps ensure the benefits from HMRC’s investment are not only identified in the business case but are planned for, monitored and actually realised in practice. Fundamental to this is collaborative working with business areas to agree the level and value of benefits and who will be responsible for their realisation.

Further on benefits management is available here on the intranet.
# Managing risks and issues
## Risks

All programmes and projects are subject to uncertainty and therefore are exposed to potential risks. Risks are events or scenarios which, should they occur, can threaten the progress and success of the programme or project. They can present a positive opportunity as well as a negative threat.

The purpose of risk management is to identify risk as early as possible and keep the level of exposure at an acceptable level. Risk Management must therefore be an integral part of the way a programme or project is planned and managed. Risks should be actively managed and appropriate controls put in place to both reduce its probability, but also to mitigate the impact of any negative event should it arise.

## Issues
An issue differs from a risk in that it is something happening now, or known to be imminent. An issue needs immediate action to prevent it adversely affecting the ability of the programme or project to meet its objectives. Should a risk materialise it becomes an issue and should be managed as such.
# Stakeholder management and communications
Without an effective approach to managing and communicating with their stakeholders programmes and projects are more likely to fail.

Getting stakeholder management and communications right ensures:

- high awareness and commitment to the proposed changes
- consistent messages are relayed inside and outside the programme
- stakeholder expectations about what the programme/project will deliver are effectively managed

A Communication Plan should be prepared and implemented as soon as possible and then maintained throughout the programme lifecycle. It should be updated at each key stage to ensure appropriate stakeholders have been identified and are engaged at the appropriate time.
# Business Readiness
As SRO, you are responsible for ensuring that the Programme Readiness for Change Lead role is resourced to effectively collaborate with business stakeholders and those responsible in the business for benefits management to manage the landing of change.

The Readiness for Change Lead will work with the business areas throughout the lifecycle of programmes and projects to ensure both delivery of a specific change and to understand and work with the impact of specific delivery on the cumulative picture of change and the ability of HMRC to absorb all planned change.
# Quality Management
Quality covers many aspects of what a programme or project does. This can range from ensuring alignment with departmental standards, to ensuring that what is delivered meets the agreed requirements of business users.

The Programme Manager will take day-to-day responsibility for quality management on your behalf and through the Programme Management Office (PMO) will ensure necessary activities including audit, assurance and review processes are carried out.
# Assurance of programme or project delivery
The purpose of assurance is to give confidence to the SRO and Board that the programme or project is being managed effectively and is on track to deliver the desired outcomes and the expected benefits.

Assurance activities should be undertaken by those independent of the programme or project, although the
SRO and Board may commission internal ‘health checks’ at key points in the lifecycle to inform or complement external assurance activities.

It is mandatory for all programme / projects to have an Integrated Assurance and Approval Plan (IAAP). Integrated assurance and approval is the planning, coordination and provision of assurance activities and HMT and departmental approval points throughout the lifecycle.

Departments are required to submit a draft IAAP for each Major Project for validation by both the IPA and HMT. Further guidance is available on the IPA site.

As SRO you have ultimate accountability for ensuring your programme or project is subject to commensurate, appropriate and timely assurance across the lifecycle, including post closure.
# Learning from Experience
The structured reporting of ‘lessons learned’ and the identification and sharing of good practice is a recognised approach in programme and project management.

A critical part of this involves capturing and sharing lessons and successes so others can learn from this, saving HMRC time, effort and money.

After action reviews and lessons learned should be carried out throughout the lifecycle of
project/programme, with copies of the findings being forwarded to HMRC’s Portfolio Centre of Excellence team for wider sharing once complete.
# Managed Closure
All programmes and projects, whether they run to plan or stop prematurely, must be closed in a managed and controlled way, through an agreed and planned set of activities.

All HMRC programmes and projects will be required to formally close in accordance with HMRC’s Change Governance (formerly Change Framework).

Consideration should be given by the SRO and Programme or Project Board throughout the programme/project lifecycle as the value add of completing a Post Implementation Review (PIR). The SRO and Programme or Project Board will ensure where appropriate details of the PIR terms of reference are included in the closure documentation/activity.

The PIR is typically carried out between 6 to 18 months following formal closure and among other things will evaluate the extent to which the benefits and business outcomes stipulated in the Business Case have been realised, and compare planned and actual costs and benefits to enable an overall assessment of value for money to be made.

GMPP programmes and projects will be subject to an IPA exit review.

# Annex A: Governance principles for the HMRC Change Portfolio
## 1) Key change governance bodies

### ExCom

The Executive Committee is the executive decision making body for HMRC Transformation. Its role:

- Has ultimate accountability for the HMRC change portfolio and delivery of the stated outcomes and benefits
- Takes decisions on prioritisation across the portfolio and the resolution of issues escalated from supporting Boards and Committees.

In fulfilling this role it will be supported by:

- Strategic Performance and Resources Committee
- Strategy and Design Committee
- Organisational Capabilities Committee

### Strategic Performance and Resources Committee

Provides strategic oversight of the resources available to HMRC and their connection to strategic performance against the 5 year Business Plan. Provides oversight of key corporate performance, efficiency, and productivity, highlighting opportunities, strategic gaps and issues, managing the relevant strategic risks and deciding on the prioritisation of investment of resources accordingly.

### Strategy and Design Committee

Provides high level oversight and direction of HMRC’s agreed corporate and functional strategies and their implementation across the HMRC Business Framework.

### Organisational Capabilities Committee

Leads on the identification, definition and development of the Organisational Capabilities (human, tangible and intangible) relevant to Business and Operating models required to fulfil HMRC’s strategic ambitions.

This Committee also ensures that vulnerabilities in organisational capability are identified and invested in as appropriate

### Programme Boards

Each of the transformation programmes will be required to set up a Programme Board. This group will support the SRO and the Programme Director to deliver the programme. The primary purpose is to drive the programme forward to deliver the intended outcomes and benefits.

## 2) Key change governance roles

### ExCom Senior Business Sponsors

- ensure availability of relevant business side Subject Matter Expertise
- defining business requirements, in conjunction with platforms and programmes, and signing them off 	agreeing benefits in business cases
- ensuring change meets business and customers’ needs
- ensuring that the full impact of the change is understood and can be accepted into BAU
- assuring the delivery of cumulative change into BAU supported by the Business Change Managers that report to the senior business owner
- successful exploitation of new capabilities by the business to realise the intended benefits
- will be held accountable for ensuring the realisation of the intended outcomes and benefits

### Programme Directors

- holding the end-to-end plan for the programme, aligning programme deliverables to +5 Business Plan / SR Commitments, and to the platform plans
- the Business Case and the budget for the programme, including assurance and approvals
- implementing and/or commissioning the change required;
- benefits realisation (supported by readiness for change teams, who support the planning of change and manages the relationship between change and the business)
- stakeholder engagement
- business readiness
- ensuring that policy, business and IT change are delivered and work in concert 	reporting
- risks, issues and dependency management
- championing HMRC’s Change Governance

Transformation Portfolio Management

Briefing Pack for Senior Responsible Owners (SROs) of GMPP programmes and projects

and HMRC Major Change