Terms of Reference
Women in Finance Charter for Brazil
1. OBJECTIVE

As part of UK Government’s Prosperity Fund Green Finance Programme, the British Embassy in Brazil is commissioning a study with the following objectives:
1. Strategic support for the design of a ‘Women in Finance Charter in Brazil’. The Charter will support gender balance across all seniority levels in financial services firms in particular.
  1. The contracted partner will present an assessment of current gender inclusivity within financial services bodies in Brazil and provide recommendations on whether the charter would help achieve gender parity within the sector.
  2. The contracted partner will develop a charter, which resembles the Women in Finance Charter produced by HM Treasury in the UK. The partner will use this as a basis, but will adapt and produce a similar charter, which would be taken up by Brazilian firms/bodies.
2. Strategic support for the launch of the ‘Women in Finance Charter in Brazil’ in 2019.
- The selected partner would be expected to engage with media and press outlets in preparation for the launch.
- The selected partner would present recommendations on how firms could implement policy/structural changes to comply with the charter.

2. CONTEXT

The Prosperity Fund in Brazil is developing a programme that aims to increase productivity, reduce poverty and improve economic growth, by reducing transaction costs and stimulating competition and innovation. Gender inclusivity is promoted throughout the different initiatives included within the Prosperity Fund’s Green Finance programme wherever possible.

The Green Finance programme aims to catalyse and mobilise private finance and support effective allocation of government resources to leverage private investment into sustainable infrastructure. It will contribute to build the path to a low carbon economy through investments in sustainable infrastructure in Brazil.

Gender barriers in the financial services industry are significant. According to a KPMG empirical study, only 36% of total 223 companies listed at Brazil’s Stock Exchange have at least one woman at their Board of Directors, while these represent only 6% of the total[1]. Women are nearly twice as likely as men to make sustainable investments are, as such, increased women’s participation in the overall investment scenario in Brazil is likely to boost a greener economy.[2] The programme will seek to improve gender equality in financial services by seeking to mobilize female talent into financing mechanisms, striving for a “critical mass” of women in top jobs, promoting female fund managers and woman-centred portfolios. It will adhere to the principles of HM Treasury’s Women in Finance Charter, driving Brazil towards a more balanced and fair financial services industry.[3]
[1] KPMG - A governanca corporativa e o mercado de capitais, 2016
[2] Morgan Stanley - Sustainable Signals, 2015
[3] HMT Women in Finance charter
Brazil ranks 79th out of 144 countries in the World Economic Forum Gender Gap Report.[4] Brazilian women have close parity to men on educational attainment and health. However, in terms of economic participation and political empowerment, there is significant disparity. Brazil has the largest gender gap in annual salaries in Latin America – 29.7%[5] – and the lowest percentage of seats held by women in parliament in the region – 9.9%.[6] Global evidence confirms a correlation between gender equality and GDP per capita, the level of competitiveness and human development.[7] A 2013 World Bank study estimated up to a 0.2 percentage point reduction in the country’s annual gross domestic product (GDP) growth rate from unequal pay.[8] This means that there is a proportional positive variation between gender inequality GDP growth. Barriers to women’s economic participation are an important binding constraint to growth in Brazil and could be addressed in the design of the reforms the UK-Brazil Prosperity partnership will achieve. The UK government, through Prosperity Fund, will seek to create opportunities for women’s economic empowerment and access to job opportunities and ensure that gender inequality in Brazil is not worsened.
[4] Global Gender Gap Report 2016. World Economic Forum
[5] IADB, New Century, Old Disparities – Gender and Ethnic Wage Gaps in Latin America IDB Working Paper Series 109. Note: The gap increases to 31.4% when there are children on the household, much greater than in Chile [18.6%], Mexico [10.5%] or Colombia [6.3%]).
[6] World Bank - Gender Data Portal.
[7] World Economic Forum - The Case for Gender Equality
[8] World Bank - Gender E quality Pays Off in Brazil

Furthermore, all initiatives using UK technical assistance have to comply with the Gender Equality Act 2014, and should support IDA compliance. GEA states ‘All UK ODA has to meaningfully consider the impact of how it will contribute to reducing gender inequality and demonstrate that it has done so’. For further information, please refer to the Prosperity Fund Gender Policy and Guidance note. Bidders should demonstrate that they have the requisite expertise to ensure gender equality is mainstreamed into the work they are commissioned to do.

3. DELIVERABLES

The British Embassy in Brazil is seeking for a specialist to undertake this project and provide the information requested as below:

1. Gather evidence-based data about the situation of women currently working in the Finance sector in Brazil
  1. Understand where Brazil is in terms of gender equity in the financial services’ market – comparing women’s participation in different grades, wage disparity, level of study, among other factors
  2. Understand the causes of inequality in the Finance market – comparing it to other sectors
  3. Define recommendations that should be followed by the industry, in order to progress on gender gap issue in this market
2. Define and respond to the ‘appetite’ of firms in the sector on commitments included within the charter. The project should answer the following questions in order to demonstrate this:
  1. How many companies/bodies would sign up to the Charter before the launch?
  2. Would companies commit to long-term structure changes following commitments to the Charter? What is the best time to launch the Charter, with what stakeholders and what already committed companies Understand the possible challenges for companies to join the charter and how to mitigate these risks
3. Design the Charter Structure
  1. Set out the commitments that companies will likely adhere to as part of the Charter, which promote gender parity within organisations;
  2. Set out regular publications by the companies to measure changes and impact. Define the content and frequency of the updates.
  3. Set out targets for the number of companies that will likely sign up to the charter per year and the future trajectory for membership of the charter;
  4. Define the communication plan / media coverage that the Charter will need to reach its objectives;
  5. Recommend a governance structure for the charter, which includes Brazilian government institutions.
  6. Set out the selection process, the monitoring process, the annual report elaboration
  7. identify key stakeholders ( government, public/private institutions, NGO, academic) who should be associated to lead on the Charter development;
  8. Through the evidence data gathered, develop comprehensive KPIs and success metrics to monitor market’s adherence to the Charter

4. RESPONSIBILITIES
The awarded Contractor will report to the Embassy’s Green Finance Programme Manager.
The Contractor will be responsible for all the research, including data collection, processing, analysing and reporting. In case of receiving information from the British Embassy, the awarded Contractor must agree with the confidentiality of the information as requested.
The contractor should agree to hold an introductory meeting, a final meeting (management presentation) and monthly meetings to share progress, and agree decisions pertinent to the success of the deliverables of the project.
The British Embassy can request possible adjustments in the products (reports) to be delivered and agreed by both parties. The objective is to ensure clarity and a clear understanding of the expectations of both parties.
The Contractor is responsible to deliver the products mentioned in item 3 in compliance with the Timeline and Payment method described in item 5.

5. TIMETABLE AND PAYMENT SCHEME
The study should be carried out during the period of November 2018 to January 2019. The details about initial, final and monthly meetings dates are displayed the table below.
The payment scheme contemplates payment by results and deliverables. The first payment will consist of 50% of the total amount of the proposal and will be executed face to the Guideline delivery meeting. The second payment, which will consist of the remaining 50% of the total amount, will be granted after the delivery of the recommendation report. All payments will only be processed once deliverables have been received and fully approved by the Green Finance Team at the British Embassy.

Steps	Timeline	Payment
Proposal open to application	Oct 1st 2018
Applications end	Oct 26th 2018
Selection Board	Oct 31th 2018
Contract Award	Nov 5th 2018
Kick off meeting	Second week of Nov 2018
Diagnosis Analysis Report	Week of 17 Dec 2018	First payment (50%)
Delivery of Charter Design and Appetite	Week of 25 Feb 2019	Second payment (50%)

The proposal should be up to £25,000. Any proposals outside this range will be disregarded.
A Selection Board will analyse all proposals received and select the award Contractor. The Board is composed by at least 4 (four) people from diverse backgrounds such as programme, political and commercial from the British Embassy. The awarded contractor will be notified shortly. The candidates not selected will receive an automatic response.

6. SENDING THE PROPOSALS
The proposals must include:
- All elements which will be considered for tender evaluation (more information in Evaluation criteria doc), such as names and curriculum of the technical team of consultant(s) who will undertake the study and suggested methodology and sources to be applied in the research;
- Financial proposal of the study considering all charges and fees, in the range presented in item 5 (more information in Schedule of Prices and rates doc).

The parties interested to apply for this work should submit their proposals to BrazilGreen.FinanceTeam@fco.gov.uk by 12:00pm October 26th. For any queries during the application time, please forward an email to BrazilGreen.FinanceTeam@fco.gov.uk