Terms of Reference
Strategy Development and Capacity Building for Development Finance Institutions

1. OBJECTIVE

As part of the UK Government’s Prosperity Fund Green Finance Programme, the British Embassy in Brazil is commissioning a project that aims to assist the development of a Strategy within ABDE in support of Brazil’s COP 21 goals, and deliver Capacity building within two Development Finance Institutions affiliated with ABDE. The overall objectives are to:
- Increase and leverage resources to finance projects that promote sustainable development and support UN Sustainability Goals and delivery towards Brazil’s Paris NDC commitments.
- Strengthen the adoption of international standards in the Development Finance Institutions aligning these standards with Brazilian legislation, and increasing the attractiveness of those institutions in the international market.
- Accelerate the development of the green finance market in Brazil, including through the role of Development Finance Institutions as role models.

2. CONTEXT

United Kingdom and Brazil have a strong partnership in the Green Finance Sector, highlighted during the most recent Brazil and UK EFD - Economic Financial Dialogue which took place in London in August 2018. At the EFD both Finance Ministers reiterated their commitment to work together including through building capacity within Brazilian institutions to build a green and sustainable finance market.

The Brazilian Association of Development (ABDE - Associação Brasileira de Desenvolvimento) is a key stakeholder in the green finance market. The Association is composed of Brazilian Development Finance Institutions (Instituições Financeiras de Desenvolvimento - IFDs), such as federal public banks, development banks controlled by states, cooperative banks, state public commercial banks with development portfolio and development agencies, FINEP and SEBRAE. All those institutions together form the National System of Development (Sistema Nacional de Fomento - SNF). ABDE is responsible to define the SNF strategy and to execute actions to enhance SNF presence.

One main goal of ABDE is to work to strengthen Brazilian Development Finance Institutions, by promoting the exchange of information, creating proposals to enhance the financial market and disseminate and implement best practice. One of the most important roles of IFDs is to support new market creation and access to credit to actors who would otherwise not be supported by the private finance sector. IFDs believe that the consolidation of this market will result in an increased amount of resources available to fund projects that promote sustainable development, and help Brazil reach UN sustainability Goals and commitments in COP 21. The activities as outlined in this Terms of Reference are in line with the ABDE priorities to finance sustainable projects. The ABDE priorities aim to:

- Generate and add value to Brazil financial market using economic models of sustainable development.
- Provide an opportunity to act in new markets increasing productivity standards and competitiveness of companies.
- Further develop a consumer market interested in responsible and sustainable products.
- Increase the application of sustainability standards applied in development projects by Brazilian institutions.

The structure under development by ABDE affiliates aims to build programmes, which allow the issuance of bonds in the local and international market, with the objective of re-financing existing green/sustainable portfolios as well as new projects aligned with the Green Bonds Principles and Climate Bond Initiative concepts.

3. DELIVERIES AND RESULTS

The successful delivery partner will be expected to deliver the following activities:

Design recommendations aligned with Climate Finance Strategy to reach Paris NDC agreements for ABDE:
- Perform a national and international benchmark (including with the UK) with the objective to understand how development banks have an important role to play in the Climate Finance Strategy to reach Paris NDC agreements.
- Propose recommendations on how ABDE should to act in the Climate Finance Strategy to reach Paris NDC agreements, considering particularities of their members and geographic areas.

Capacity building with two affiliate members of ABDE on Green Portfolio Management: BDMG (Banco de Desenvolvimento de Minas Gerais) e BRDE (Banco Regional de Desenvolvimento do Extremo Sul):
- Create appropriate indicators to measure the contribution of their investment portfolio to mitigate climate changes.
- Create appropriate indicators to measure the contribution of their investment projects to mitigate climate changes.
- Apply monitoring and evaluation tools of the Climate Finance Strategy to reach Paris NDC agreements for the two selected banks BDMG and BRDE.
- Long-term strategy and recommendations to Climate Finance Strategy to reach Paris NDC agreements for both selected banks BDMG and BRDE.

Workshop to disseminate the results of the above interventions with all ABDE members:
- Share the results and lessons learned from the interventions to all ABDE members in a face-to-face workshop.
- Produce a management report (both Portuguese and English version) including the premise, methodology and results from the project, considering all the interventions as described above.

4. RESPONSIBILITIES
The awarded Contractor will report to the Embassy’s Green Finance Head of Programme.
The Contractor will be responsible for all the research, including data collection, processing, analysing and reporting. In case of receiving information from the British Embassy, the awarded Contractor must agree with the confidentiality of the information as requested.
The contractor should agree to hold an introductory meeting, a final meeting (Management presentation) and monthly meetings to share progress, and agree decisions pertinent to the success of the deliverables of the project. More details in the schedule session.
The British Embassy can request possible adjustments in the products (reports) to be delivered and agreed by both parties. The objective is to ensure maximum success of the project and management of new products during the project.
The Contractor is responsible to deliver the products mentioned in item 3 in compliance with the Timeline and Payment method described in item 5.

5. PAYMENT AND SCHEDULE
The study should be carried out during the period of November 2018 to February 2019. The details about meetings dates are displayed the table below.
The payment scheme contemplates payment by results and deliverables. The first payment will consist of 50% of the total amount of the proposal and will be executed face to the second meeting and the report of delivery 1 (under session 3). The second payment, which will consist of the remaining 50% of the total amount, will be granted after the delivery of the final deliveries 2 and 3 report (under session 3), including comments and the discussion held in the Presentation of final result meeting.
All payments will only be processed once deliverables have been received and fully approved by the Green Finance Team at the British Embassy.

Steps	Timeline	Payment
Proposal open to application	10 10 2018
Applications end	31 10 2018
Selection Board	05 11 2018
Contract Award/Announcement	07 11 2018
Kick off meeting	12 11 2018
First follow up meeting	04 12 2018
Second follow up meeting and delivery 1 report	15 01 2019	Payment 1 (50%)
Final meeting – presentation of final results	12 02 2019
Submission of deliveries 2 and 3 reports	26 02 2019	Payment 2 (50%)

The proposal should be up to £25,000. Any proposals outside this range will be disregarded.
A Selection Board will analyse all proposals received and select the award Contractor. The Board is composed by at least 3 (three) people from diverse backgrounds such as programme, political and commercial from the British Embassy.
The awarded contractor will be notified shortly. The candidates not selected will receive an automatic response.

6. PROPOSAL SUBMISSION
The proposals must include:
- All elements which will be considered for tender evaluation (more information in Evaluation criteria doc), such as names and curriculum of the technical team of consultant(s) who will undertake the study and suggested methodology and sources to be applied in the research;
- Financial proposal of the study considering all charges and fees, in the range presented in item 5;
- All proposals must comply with Gender Equality Act 2014 published by UK Govern with the objective to address gender equality.

The parties interested to apply for this work should submit their proposals to BrazilGreen.FinanceTeam@fco.gov.uk by 12:00pm October 31st. For any queries during the application time, please forward an email to BrazilGreen.FinanceTeam@fco.gov.uk