Annual Review - Summary Sheet

PROGRAMME TITLE: Iraq CSSF Governance Programme
Country/Region:	Iraq (Middle East and North Africa - MENA)
HMG Partners (LEAD in bold)	Department for International Development (DFID), Foreign and Commonwealth Office (FCO)
Total Spend:	ODA: £11,434,921[1]			Non-ODA: £0
Start Date: April 2017		End Date: March 2018
Outputs					Score
Public works & light infrastructure rehabilitation projects undertaken.					A+
People, including households, in liberated areas served by temporary jobs opportunities & livelihood enhancement efforts					A+
People, including households, in liberated areas served by livelihood enhancement efforts and small business grants.					A+
Stabilisation support provided through technical assistance and Government of Iraq (GoI) capacity built					C
Local governorate, security & community dialogue facilitation mechanisms developed					A
Decentralised governance support mechanisms developed					A
Knowledge products are developed to inform stabilisation support					A
Overall output score					A
Outcome Assessment: Outcomes met expectation.
Outcome Score: A			Risk: Moderate
[1] The difference between the final annual expenditure (£11.4m) and the amount indicated in the Programme Document (£10.6m) is accounted for by ‘in year’ reallocations and uplifts of funding to the UNDP Funding Facility for Stabilisation and the Aktis project on sub-national governance.

Summary of Programme Performance[2]
[2] Although the CSSF Governance Pillar in its current configuration began in 2016-17, previous configurations extend back to 2015-16, which explains the inclusion of previous Annual Review scores.
Year	2015/16	2016/17	2017/18*
Programme Score	A	A	A
Risk Rating	Med	Med	Moderate

*output/outcome scores
What support is the UK providing?
In 2017-18, the UK spent £11.4m in grant aid to deliver the CSSF Iraq (Governance & Resilience) programme. The desired outcome for the reporting year was the reduction of Da’esh influence, increased community cohesion, and more representative, responsive and accountable GoI institutions. The desired impact of the programme was a more secure and stable Iraq.
The programme focussed its efforts on newly liberated areas of western Iraq (Anbar, Salah al-din, Nineveh) and Basra in southern Iraq. Core activities in Anbar, Nineveh and Salah al-din included rehabilitation of damaged infrastructure in a way that generated jobs, and the establishment of state/society dialogue mechanisms. In Basra (not directly impacted by the fight against Da’esh), only governance programming was pursued. All projects aimed to strengthen the GoI’s legitimacy in the face of the ongoing threat from Da’esh.
Summary of progress and lessons learnt/actions taken since last review
CSSF Iraq has supported the GoI in making a compelling offer to its people. During the reporting period, UNDP’s Funding Facility for Stabilisation (FFS), supported by CSSF, identified over 1,900 projects for the restoration of services and essential infrastructure in liberated areas. Of these, 880 had been completed by the end of March 2018. By the same date, approximately3.2 million Iraqis had moved back to their places of origin, thanks in part to FFS projects generating the conditions for safe return. Projects included the (UK funded) rehabilitation of a water plant serving 300,000 people. Over 19,000 residents earned a wage from rehabilitation and restoration of services in their neighbourhoods. The UK’s focus on gender inclusion was critical to the stabilisation effort. Women were recruited as engineers, social workers and in local councils. In total, more than 7,000 small cash grants were distributed to businesses or households, of which more than 4,700 reached female-headed households. The UK also facilitated the embedding of stabilisation advisers in 10 municipalities to support local government planning capabilities.
The Danish Refugee Council (DRC) implemented reconstruction and rehabilitation activities and livelihoods provision initiatives in the liberated provinces of Nineveh and Salah al-din, on the basis of priorities identified by community groups. Thirteen effective local governorate, security and community dialogue mechanisms were established to enable citizens to articulate their needs and concerns to GoI authorities.
Aktis’s Sub-National Governance project delivered a series of capacity-building activities to local authorities in Basra, Nineveh and Anbar. These were designed to improve these authorities’ ability to internally plan and coordinate, implement devolved powers, consult with citizens, and interact with central government. Four forums facilitating face-to-face meetings between civil society representatives and local government were established, alongside five provincial plans or strategies.
High quality knowledge projects were delivered that strengthened the evidence base for programming and policy. These included a Joint Analysis of Conflict & Stability (JACS), a first round of nationally-representative polling by National Democracy Institute (NDI) to get citizens perceptions across a wide range of issues, and a study on Iraqi migration outflows to Europe. The NDI polling activity was a highlight, with Embassy-wide input into its design, and the outputs delivered to the Embassy in a way that helped with both measuring of programme effectiveness and generating political intelligence ahead of the elections.
A group of six recommendations were made for 2016-17, aiming to (i) strengthen programme monitoring and evaluation; (ii) interrogate the performance of projects run by the DRC, the UN Development Programme (UNDP), and the UN Mine Action Service (UNMAS); (iii) refresh the programme results framework; (iv) boost the value for money of UNDP programming; (v) strengthen the programme’s overall approach to conflict sensitivity, gender sensitivity, and human rights; and (vi) reinforce the risk management mechanisms around the programme.
Significant progress has been made against the bulk of these recommendations. A suite of Monitoring and Evaluation (M&E) instruments was introduced during the course of the year, improving the UK’s ability to monitor the performance of specific projects, and evaluate impact across the portfolio. A further improved approach to M&E, Research and Learning is now in place for FY18/19. DRC project performance was assessed thoroughly, and a decision taken to extend UK funding for their activities until a closure date of March 2019. UNDP’s stabilisation project is now underpinned by a convincing plan for evaluating impact and capturing lessons, and by provisions to improve the capacity of implementing partners to apply conflict sensitivity and gender inclusion principles.
UK support to mine clearance activities will now be provided through DFID centrally-managed funds from FY18/19 (rather than through CSSF). The results framework was refreshed for 2017-18, and a much improved version is in place for the multi-year governance programme FY18/19-20/21. Notable advances have been made on conflict sensitivity and gender sensitivity. Risk management mechanisms for the programme are now considered adequate.
Summary of recommendations for the next year
At portfolio level, recommendations refer principally to the importance of continuing to use informed analysis to ensure that the CSSF responds to the most important conflict and stability risks faced by Iraq. Other recommendations reiterated the value of existing plans to review the CSSF Iraq Value for Money approach; to formalise the already increased scrutiny of partner’s evidence of spend; and to update the results framework to include secondary/indirect benefits e.g. improved political analysis, access and influence.
Programme level recommendations focus on the enduring importance of high quality programme management. The Governance & Resilience programme is already responding to the many compliance demands and the team should now shore up its ability to capture, read, understand and learn from the numerous informational outputs (notably partner reporting) associated with these compliance demands. This will ensure that high-quality programme management actively informs strategic decision-making.
At a project level, only minor course corrections are required. A suggestion was made to increase the initial allocation for the UNDP FFS project, whilst encouraging GoI ownership of reconstruction thereafter.