Annual Review - Summary Sheet

PROGRAMME TITLE: Iraq CSSF Security and Justice Programme
Country/Region:	Iraq (Middle East and North Africa (MENA)
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MoD)
Total Spend:	ODA: £6.5m[1]			Non-ODA:£1.2m
Start Date: April 2017		End Date: March 2018
Outputs					Score
Efforts undertaken to reduce the threat of Explosive Ordnance Devices.					A+
Support the development of mechanisms and tools to enhance Iraq’s security sector institutions’ capability					A
Tools developed to support transitional justice & reconciliation					C
Overall output score					B
Outcome Assessment: Outcomes partially did not meet expectation
Outcome Score: B			Risk: Major (AR team assessment)
[1] The difference between the final annual expenditure (£6.5m ODA, £1.2m non-ODA) and the amount indicated in the Programme Document Summary (£7.485m ODA, £1.6m Non-ODA) is accounted for by a stop to contributions towards the United Nations Integrated Reconciliation Programme (IRP).

Summary of Programme Performance
Year	2015/16[2]	2016/17	2017/18
Programme Score	A	A	B	B
Risk Rating	High	Medium-High	High
[2] Although the CSSF Security and Justice programme in its current configuration began in 2017-18, previous configurations extend back to 2015-16, which explains the inclusion of previous Annual Review scores.

*output/outcome scores

What support is the UK providing?

In 2017-18 the UK spent £7.7m to deliver the Security and Justice programme. The desired outcome was Da’esh influence diminished, increased community cohesion & Government of Iraq (GoI) institutions representative, responsive and accountable. The programme focused its efforts on: £4m to support Explosive Threat Management (ETM) to enable safe return of Internally Displaced People (IDPs) in liberated areas through risk education, surveys, clearance, capacity building/training and coordination; £2.25m to help build stronger and more accountable security institutions at the central level and in the liberated province of Anbar, including technical assistance to support security sector and police reform; £1.85m for transitional justice and reconciliation programming and advisory support; £75k to support design, monitoring and evaluation of the Security and Justice Programme.

Summary of progress and lessons learnt/actions taken since last review

Explosive threat management through United Nations Mine Action Service (UNMAS) saw a step change in effort resulting in unprecedented levels of clearance and public awareness activities: 1,500 devices were removed in Q2, and 533,529 in Q4. Support was increased from £4m to £5m in year, and will transfer out of CSSF to DFID for FY 18/19.
Proposals on Iraq security sector architecture and reform were put forward for consideration by the government, albeit without any decisions, and strong relationships were built with the Ministry of Peshmerga Affairs (MoPA), to support future reform initiatives. “Proof of concept” support was provided to United Nations Development Programme (UNDP) pilot policing project which takes forward a Ministry of Interior (MoI) road map to develop police capacity, and translate it into operational and tactical effect, with a focus on building community partnerships locally. Judicial diplomacy (delivered through CSSF advisory support) built new links between UK and Iraqi judges and the creation of the Iraq Higher Judicial Council was supported, including support to women judges. Tools to support transitional justice and reconciliation didn’t achieve the progress expected and the UNDP Integrated Reconciliation Project (IRP) project was closed as a result.

Recommendations made in the last review focused on the UNDP Integrated Reconciliation Programme, which was closed in year. The review also recommended that the team strengthen the approach to monitoring the delivery of technical advisors. Quarterly objectives for advisors were put in place in late 17/18 for advisors to deliver and be assessed against. There are plans to develop and use tools to monitor political access and influence in 18/19.

Lessons identified throughout the year include: IRP: these were distilled and shared across the UK Government. They focused on the need to ensure that partners have strong contextual knowledge before programmes are designed.

Delivery models: need to consider the trade-offs between different models of intervention – e.g. between a multilateral approach through the UN and a bilateral technical assistance approach, based on changing considerations related to risks and security implications of the activity; duty of care requirements; Value for Money (VFM); ensuring effective UK Government political engagement and appropriate levels of strategic direction and support.

Summary of recommendations for the next year

Programme level recommendations focused on monitoring and evaluation, risk and gender. Namely to: further develop the outline theories of change for transitional justice/reconciliation and Security Sector Reform (SSR) to better underpin the results framework, and develop a more robust set of indicators for advisory support and on gender and conflict sensitivity; consider resourcing full time gender capacity; consider how risk management can be further strengthened including assignment of risk rating to Security and Justice (S&J) programme outputs, and a clear process for managing risk at output/project level. Update the Transitional Justice and Reconciliation Overseas Security and Justice Assessment (OSJA) which should reflect new initiatives, including the S&J programme engagement with the judiciary.

Project level recommendations were:
Transitional Justice & Reconciliation: reassess and explore options to support the National Reconciliation Commission in the Prime Minister’s office to develop a vision of reconciliation based on what is currently working in Iraq, and work with them to better identify and coordinate reconciliation activities including those supported by international actors;
- SSR: reassess the political economy of SSR reform in the 2018 post-election context, and where the UK can best add value, to clarify policy objectives on SSR (and defence education) and re-assess how the CSSF can best support these, with appropriate delivery models.
- Oversight of technical advisers: ensure clear roles, objectives and responsibilities for management of technical advisers, including oversight and decision-making, and enhance the feedback loop to inform UK policy/diplomacy on security sector reform issues.
- UNMAS: To DFID/FCO: Ensure continued and greater diplomatic engagement in support of UNMAS advocacy towards the government, notably to licence operators to use explosives and key equipment in threat removal. In concert with this, encourage UNMAS to develop an exit strategy for its work over a multi-year time period, planning for a full handover to the Iraqi security forces.